## Sheet1
Weekly Progress Report
Zone:-
Work at Tendring State
S.No | Activities | Time Lines | Weekly progress as on... | Cumulative progress as on….
1 | Road Strengthening | 2 months after sanction
2 | Patch Repair works including emergency works | Tender call-01.03.2025 Works start-07.04.2025
3 | Pot Hole Repair, Maintenance vans, thermoplastic road marking, repair of signages, kerg stone paintings. | Tender call-15.03.2025 Works start-15.04.2025
4 | Deselting, Pump Houses | Tender call-01.03.2025 Works start-07.04.2025
5 | Hiring of Dewatering Pumps | Tender call-15.04.2025 Works start-15.05.2025
6 | Construction of footpaths and drains | 2 months after sanction
7 | Foothpath repair and drain repair | Tender call-31.03.2025 Works start-15.05.2025
8 | Horticulture works | 58 works in progress Balance 4 tenders -31.03.2025
9 | FOB/Subway maintenance | Tender call-31.03.2025 Works start-15.05.2025
10 | Road new Signages | Tender call-31.03.2025 Works start-15.05.2025
Works in Progress
1 | Road Strengthening | As per running agreements
2 | Patch Repair works including emergency works | As per running agreements
3 | Pot Hole Repair, Maintenance vans, thermoplastic road marking, repair of signages, kerg stone paintings. | As per running agreements
4 | Deselting, Pump Houses | As per running agreements
5 | Hiring of Dewatering Pumps | As per running agreements
6 | Construction of footpaths and drains | As per running agreements
7 | Foothpath repair and drain repair | As per running agreements
8 | Horticulture works | As per 58 running agreements
9 | FOB/Subway maintenance | As per running agreements
10 | Road new Signages | As per running agreements