## Sheet1
Target Date for Start of Repair Work on Bituminous Roads
(As on 21/02/2017)
S. No. | Name of Work | Road Stretch |  | Length of Road (In KM) | Duration of Work |  | Scope of Work
|  | From | To |  | From | To
Strengthening:
1 | Mehrauli Mahipal Pur Road (Massod pur to NH-8) | Massod Pur | NH-8 | 3.8 | In progress |  | 50 mm DBM and 40 mm DBC
2 | Guru Ravi Dass Marg (MB Road to SA Road) | MB Road | SA Road | 4.75 | 16.03.2017 | 31.03.2017 | 50 mm DBM and 40 mm DBC
3 | Anuvart Marg (August Kranti Marg to MG Road) | August Kranti Marg | MG Road | 2.5 | 06.03.2017 | 31.03.2017 | 50 mm DBM and 40 mm DBC
4 | Press Enclave Road | Aurobindo Marg | BRT | 3.78 | 10.03.2017 | 28.03.2017 | 50 mm DBM and 40 mm DBC
5 | M.B.Road | Mathura Road | NH-2 | 8 | 06.03.2017 | 31.03.2017 | 50 mm DBM and 40 mm DBC
6 | M.M Road from Andheria More to Fortis Hospital | Andheria More | Fortis Hospital | 3.1 | In progress |  | 50 mm DBM and 40 mm DBC
7 | M.B Road | Lado Sarai | Batra Hospital | 5.6 | 03.03.2017 | 31.03.2017 | 50 mm DBM and 40 mm DBC
8 | Ch. Jhandu Sing Marg | Raj Nagar Flyover | Africa Avenue Road | 1.53 | 03.03.2017 | 31.03.2017 | 50 mm DBM and 40 mm DBC
9 | Outer Ring Road | I.I.T. Flyover | Chirag Delhi | 3.7 | 20.03.2017 | 31.03.2017 | 50 mm DBM and 40 mm DBC
| Total |  |  | 39.51
Resurfacing:
1 | Savitri Cinema Road | Outer Ring Road | Junction | 1.2 | 15.03.2017 | - | PCC and 40 mm DBC
2 | Baba Balak Nath Marg | BJ Marg | RTR Marg | 1.1 | 22.02.2017/ 23.02.2017 | 31.03.2017 | PCC and 40 mm DBC
3 | AIIMS Flyover Ring Road | Only Flyover Complete |  | 3.5 | 07.03.2017 | 28.03.2017 | 40 mm SMA
4 | Girdhari Lal Goswami Marg (Road No. 89) | Naraina Road | Rajender Nagar | 3.65 | 07.03.2017 | 31.03.2017 | PCC and 40 mm DBC
5 | Sri Aurobindo Marg (AIIMS to Mehrauli) | AIIMS | Mehrauli | 5 | 15.03.2017 | 31.03.2017 | PCC and 40 mm DBC
| Total |  |  | 14.45
Microsurfacing:
NIL

## Sheet2
LIST OF PROPOSED WORKS FOR INSPECTION
S. No. | Name of Work | Road Stretch |  | Length of Road (In KM) | Duration of Work |  | Scope of Work
|  | From | To |  | From | To
Strengthening:
1 | M.B Road | Lado Sarai | Batra Hospital | 5.6 | 03.03.2017 | 31.03.2017 | 50 mm DBM and 40 mm DBC
2 | Ch. Jhandu Sing Marg | Raj Nagar Flyover | Africa Avenue Road | 1.53 | 03.03.2017 | 31.03.2017 | 50 mm DBM and 40 mm DBC
Resurfacing:
2 | Baba Balak Nath Marg | BJ Marg | RTR Marg | 1.1 | 22.02.2017/ 23.02.2017 | 31.03.2017 | PCC and 40 mm DBC