## Sheet1 (6)
ACTION PLAN FOR DESILTING UNDER PWD MAINTENANCE ZONE NORTH AS ON 16.05.2016
Sl. No. | Name of Roads | Length in km | Date of start | Traget date of one time cleaning (Pre monsoon) | % Progress for one time cleaning (Pre monsoon) as on 16.05.16 | Date of Completion | JE in charge / Mobile No. | AE in charge / Mobile No. | EE in charge / Mobile No.
CIRCLE NORTH
Name of Division : EE North-Roads
Name of MLA :- Sh. Pawan Kumar Sharma
Name of Constituency :- Adarsh Nagar
1 | Kushal Cinema Road Starting from Raseela Paint Shop to T Point Pryas Road in Jahangirpuri-I, W.No. 16 Civil Line Zone | 1.102 | 21-12-15 | 07-06-16 | 80% | 2016-06-17 | Sh. Anmol Kumar 8742957738 | Sh. S.K. Bali 9717322310 | Sh. Bishamber Dass 9873245771
2 | Dhobhi Ghat Road Starting from Kushal Cinema Chowk to Shah Alam Bandh Road | 0.45 | 21-12-15 | 07-06-16 | 80% | 2016-06-17 | Sh. Anmol Kumar 8742957738 | Sh. S.K. Bali 9717322310 | Sh. Bishamber Dass 9873245771
3 | Malik Ram Tandon Marg from Road No. 51 to Shah Alam Bandh Road | 0.89 | 21-12-15 | 07-06-16 | 80% | 2016-06-17 | Sh. Anmol Kumar 8742957738 | Sh. S.K. Bali 9717322310 | Sh. Bishamber Dass 9873245771
4 | Shah Alam Bandh Road from Burari Road to 80" Road (ROW) at Malik Ram Tondon Road upto Road No. 51 | 1.55 | 21-12-15 | 07-06-16 | 80% | 2016-06-17 | Sh. Anmol Kumar 8742957738 | Sh. S.K. Bali 9717322310 | Sh. Bishamber Dass 9873245771
5 | Shah Alam Bandh Road from Main G.T. Road to Malik Ram Tandon Marg | 1.4 | 21-12-15 | 07-06-16 | 80% | 2016-06-17 | Sh. Anmol Kumar 8742957738 | Sh. S.K. Bali 9717322310 | Sh. Bishamber Dass 9873245771
6 | Mangal Bazar Road starting from Kushal Road Green Belt to Shah Alam Bandh Road | 0.4 | 21-12-15 | 07-06-16 | 80% | 2016-06-17 | Sh. Anmol Kumar 8742957738 | Sh. S.K. Bali 9717322310 | Sh. Bishamber Dass 9873245771
7 | Prayas Road (from Shah Alam Bandh Road to Dhalao, Jahangirpuri) | 0.7 | 21-12-15 | 07-06-16 | 80% | 2016-06-17 | Sh. Anmol Kumar 8742957738 | Sh. S.K. Bali 9717322310 | Sh. Bishamber Dass 9873245771
8 | Fire Station to Pump House | 0.55 | 21-12-15 | 07-06-16 | 80% | 2016-06-17 | Sh. Anmol Kumar 8742957738 | Sh. S.K. Bali 9717322310 | Sh. Bishamber Dass 9873245771
9 | Mall Road Extension from Azadpur Flyover to Mukarba Chowk | 3.35 | 27-03-16 | 07-06-16 | 35% | 2016-09-22 | Sh. Sachin Choudhary 9560134704 | Sh. R.P Verma 9868704799 | Sh. Bishamber Dass 9873245771
10 | Model Town-III Road from Mall Road to Arya Samaj Mandir | 0.727 | 20-05-16 | 07-06-16 | --- | 2016-11-15 | Sh. Sachin Choudhary 9560134704 | Sh. R.P Verma 9868704799 | Sh. Bishamber Dass 9873245771
11 | Indra Park Road | 0.38 | 20-05-16 | 07-06-16 | --- | 2016-11-15 | Sh. Sachin Choudhary 9560134704 | Sh. R.P Verma 9868704799 | Sh. Bishamber Dass 9873245771
12 | Princess Road from Mall road to Road No.51 | 3.1 | 20-05-16 | 07-06-16 | --- | 2016-11-15 | Sh. Sachin Choudhary 9560134704 | Sh. R.P Verma 9868704799 | Sh. Bishamber Dass 9873245771
13 | Road No. 51 from Azadpur Flyover to Outer Ring Road | 2.5 | 20-05-16 | 07-06-16 | --- | 2016-11-15 | Sh. Sachin Choudhary 9560134704 | Sh. R.P Verma 9868704799 | Sh. Bishamber Dass 9873245771
Name of ML :- Sh. Akhilesh pati Tripati
Name of Constituency :- Model Town
14 | Mahatma Gandhi road (Ring Road) from Camp Chowk to Azadpur Flyover | 3.5 | 10-05-16 | 07-06-16 | 5% | 2016-11-05 | Sh. Sachin Choudhary 9560134704 | Sh. R.P Verma 9868704799 | Sh. Bishamber Dass 9873245771
15 | Lala Auchint Ram Road from Stadium Road to Pambari Road | 0.95 | 20-05-16 | 07-06-16 | --- | 2016-11-15 | Sh. Sachin Choudhary 9560134704 | Sh. R.P Verma 9868704799 | Sh. Bishamber Dass 9873245771
16 | Stadium Road from Chattrashal Stadium Mall Road to GT Road | 0.68 | 20-05-16 | 07-06-16 | --- | 2016-11-15 | Sh. Sachin Choudhary 9560134704 | Sh. R.P Verma 9868704799 | Sh. Bishamber Dass 9873245771
17 | Brahamkumari Marg from Mall Road to G.T. Road | 0.65 | 20-05-16 | 07-06-16 | --- | 2016-11-15 | Sh. Sachin Choudhary 9560134704 | Sh. R.P Verma 9868704799 | Sh. Bishamber Dass 9873245771
18 | Model Town II Road from Mall Road to F-14/56 Model Town | 0.495 | 20-05-16 | 07-06-16 | --- | 2016-11-15 | Sh. Sachin Choudhary 9560134704 | Sh. R.P Verma 9868704799 | Sh. Bishamber Dass 9873245771
19 | G.T Road from Gurudwara Nanakpiao to Azadpur Round about | 2 | 10-05-16 | 07-06-16 | 5% | 2016-11-05 | Sh. Sachin Choudhary 9560134704 | Sh. R.P Verma 9868704799 | Sh. Bishamber Dass 9873245771
Name of MLA:- Sh. Sharad Chauhan
Name of Constituency :- Narela
20 | Old G.T. Karnal Road | 3 | 20-05-16 | 07-06-16 | --- | 2016-11-15 | Sh. Suresh Chand Bairwa 8826718940 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
21 | Narela Alipur Road from Shahpur Grahi to Old GTK Road Alipur | 5.02 | 20-05-16 | 07-06-16 | --- | 2016-11-15 | Sh. Suresh Chand Bairwa 8826718940 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
22 | New GT Road to Old GT Road (via PHC Alipur) from New GTk Road to Old GTK Road | 0.38 | 20-05-16 | 07-06-16 | --- | 2016-11-15 | Sh. Suresh Chand Bairwa 8826718940 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
23 | Holambi Khurd Crossing to Shahpur Garhi turn | 1.9 | 20-05-16 | 07-06-16 | --- | 2016-11-15 | Sh. Suresh Chand Bairwa 8826718940 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
24 | Railway Crossing to Holambi Khurd | 0.7 | 20-05-16 | 07-06-16 | --- | 2016-11-15 | Sh. Suresh Chand Bairwa 8826718940 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
25 | NH-44 from Mukarba Chowk Flyover to Palla Mor | 7.4 | 20-05-16 | 07-06-16 | --- | 2016-11-15 | Sh. Suresh Chand Bairwa 8826718940 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
26 | NH-44 (Service Road) L.H.S | 4.5 | 20-05-16 | 07-06-16 | --- | 2016-11-15 | Sh. Suresh Chand Bairwa 8826718940 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
27 | NH-44 (Service Road) R.H.S | 4.5 | 20-05-16 | 07-06-16 | --- | 2016-11-15 | Sh. Suresh Chand Bairwa 8826718940 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
28 | Ramdev Chowk Narela to Kanya Gurukul | 1.9 | 16-05-16 | 07-06-16 | Work just awarded | 2016-11-11 | Sh. Suresh Chand Bairwa 8826718940 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
29 | Narela Alipur Road from Narela Y section to Shahpur Garhi | 3.4 | 16-05-16 | 07-06-16 | Work just awarded | 2016-11-11 | Sh. Suresh Chand Bairwa 8826718940 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
30 | Narela Safiabad Road from Narela to Safiabad Border | 2.9 | 16-05-16 | 07-06-16 | Work just awarded | 2016-11-11 | Sh. Suresh Chand Bairwa 8826718940 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
31 | Narela Lampur Road from Narela to Lampur Border | 3.8 | 16-05-16 | 07-06-16 | Work just awarded | 2016-11-11 | Sh. Suresh Chand Bairwa 8826718940 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
32 | New GT Road to Old GT Road (via PHC Alipur) from New GTk Road to Old GTK Road | 0.38 | 20-05-16 | 07-06-16 | --- | 2016-11-15 | Sh. Suresh Chand Bairwa 8826718940 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
33 | Nangli Puna Underpass to Khera Kalan Railway X-ing. | 3 | 20-05-16 | 07-06-16 | --- | 2016-11-15 | Sh. Suresh Chand Bairwa 8826718940 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
34 | Khera Kalan to Holambi Kalan via Naya bans | 7 | 26-05-16 | 07-06-16 | --- | 2016-11-21 | Sh. Suresh Chand Bairwa 8826718940 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
35 | NH-44 to Bakhtawar Pur | 3.5 | 26-05-16 | 07-06-16 | --- | 2016-11-21 | Sh. Suresh Chand Bairwa 8826718940 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
36 | Subhash Chowk Bhakhtawar Pur to Palla | 3.2 | 26-05-16 | 07-06-16 | --- | 2016-11-21 | Sh. Suresh Chand Bairwa 8826718940 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
37 | Subhash Chowk Bhakhtawar Pur to Hiranki Bandh | 4.2 | 26-05-16 | 07-06-16 | --- | 2016-11-21 | Sh. Suresh Chand Bairwa 8826718940 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
38 | NH-44 from Palla More (Shani Mandir) to Singhu Border | 5.4 | 26-05-16 | 07-06-16 | --- | 2016-11-21 | Sh. Suresh Chand Bairwa 8826718940 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
Name of MLA :- Sh. Ajesh Yadav
Name of Constituency :- Badli
39 | ITI Road from Main Jahangirpuri Road to Metro App. | 0.324 | 21-12-15 | 07-06-16 | 60% | 2016-06-17 | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
40 | Back side K Block Road from Metro App. to dividing road K Block | 0.17 | 21-12-15 | 07-06-16 | 60% | 2016-06-17 | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
41 | Lucky Park Road from J-51 to J-1951 | 0.5 | 21-12-15 | 07-06-16 | 60% | 2016-06-17 | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
42 | Lucky Park Road to I-2000 (Back Side Road) | 0.35 | 21-12-15 | 07-06-16 | 60% | 2016-06-17 | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
43 | Mangal Bazar Road B Block | 0.55 | 21-12-15 | 07-06-16 | 60% | 2016-06-17 | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
44 | Zonal Park Road C Block | 0.55 | 21-12-15 | 07-06-16 | 60% | 2016-06-17 | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
45 | Jahangirpuri Main Road from G.T. Road Red Light to Fire Station | 1.395 | 21-12-15 | 07-06-16 | 60% | 2016-06-17 | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
46 | Bhalswa Dairy Road from Flood Road to C Block along Bhalswa Lake via Shani Bazar | 1.83 | 21-12-15 | 07-06-16 | 60% | 2016-06-17 | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
47 | Railway Road from NH-44 to Badli Railway Station | 1.25 | 16-05-16 | 07-06-16 | Work just awarded | 2016-11-11 | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
48 | Swaroop Nagar Road | 2 | 20-05-16 | 07-06-16 | --- | 2016-11-15 | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
49 | ORR Mukarba Chowk Flyover | 6.8 | 20-05-16 | 07-06-16 | --- | 2016-11-15 | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
50 | G.T. Karnal Road to Libaspur Road | 1.6 | 16-05-16 | 07-06-16 | Work just awarded | 2016-11-11 | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
51 | 66 Ft. Road Libaspur to Gurudwara Road | 1.7 | 16-05-16 | 07-06-16 | Work just awarded | 2016-11-11 | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
52 | G.T. Karnal Road to Siraspur Village | 2 | 16-05-16 | 07-06-16 | Work just awarded | 2016-11-11 | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
53 | Libaspur to Siraspur Road | 0.5 | 16-05-16 | 07-06-16 | Work just awarded | 2016-11-11 | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
54 | Mam Chand Dhania Marg | 2.7 | 16-05-16 | 07-06-16 | Work just awarded | 2016-11-11 | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
Name of MLA :- Shri Ved Prakash
Name of Constituency :- Bawana
55 | From Western Yamuna Canal to Auchandi Border | 18.5 | 26-02-16 | 07-06-16 | 20% | 2016-08-23 | Sh. Suresh Chand Bairwa 8826718940 | Sh. K.S. Dahiya 9810654956 | Sh. Bishamber Dass 9873245771
56 | Auchandi Border to Tatesar Village | 9.3 | 26-02-16 | 07-06-16 | 20% | 2016-08-23 | Sh. Suresh Chand Bairwa 8826718940 | Sh. K.S. Dahiya 9810654956 | Sh. Bishamber Dass 9873245771
57 | Majra Dabbas to Sannoth Mor | 8 | 26-02-16 | 07-06-16 | 20% | 2016-08-23 | Sh. Suresh Chand Bairwa 8826718940 | Sh. K.S. Dahiya 9810654956 | Sh. Bishamber Dass 9873245771
CIRCLE NORTH-WEST
Name of Division : EE NWR-I
Name of MLA :- Sh. Som Dutt Sharma
Name of Constituency :- Sadar Bazar
1 | Road No. 40 (Bir Bandha Bairagi Marg) | 3.45 | 25.04.16 | 20-6-2016 | 15% | 24.08.16 | Er. Sheikh Nizam / 9899248998 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
2 | Swamy Narayan Marg | 2.94 | 25.04.16 | 20-6-2016 | 10% | 24.08.16 | Er. Sheikh Nizam / 9899248998 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
3 | Old Rohtak Road | 3 | 25.04.16 | 20-6-2016 | 25% | 24.08.16 | Er. Sheikh Nizam / 9899248998 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
4 | Kalidass marg (sarai rohilla flyover) | 0.7 | 25.04.16 | 20-6-2016 | 15% | 24.08.16 | Er. Sheikh Nizam / 9899248998 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
5 | Nand Lal Marg | 1.11 | 25.04.16 | 20-6-2016 | 25% | 24.08.16 | Er. Sheikh Nizam / 9899248998 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
6 | Azad Road | 1.485 | 25.04.16 | 20-6-2016 | 11% | 24.08.16 | Er. Sheikh Nizam / 9899248998 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
7 | Haji Abdul Salam Quareshi Marg | 0.48 | 25.04.16 | 20-6-2016 | 25% | 24.08.16 | Er. Sheikh Nizam / 9899248998 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
8 | Patap Nagar Road | 0.75 | 25.04.16 | 20-6-2016 | 40% | 24.08.16 | Er. Sheikh Nizam / 9899248998 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
9 | Bhagat Singh Road | 0.31 | 25.04.16 | 20-6-2016 | 13% | 24.08.16 | Er. Sheikh Nizam / 9899248998 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
10 | Link Road (east Moti Bagh) | 0.165 | 25.04.16 | 20-6-2016 | 14% | 24.08.16 | Er. Sheikh Nizam / 9899248998 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
11 | Rampura main road | 1.2 | 25.04.16 | 20-6-2016 | 16% | 24.08.16 | Er. Sheikh Nizam / 9899248998 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
12 | Link Road | 0.207 | 25.04.16 | 20-6-2016 | 12% | 24.08.16 | Er. Sheikh Nizam / 9899248998 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
Name of MLA :- Sh. Jitender Singh Tomar
Name of Constituency :- Tri Nagar
13 | Road No.37 Ext. | 0.32 | 25.04.16 | 20-6-2016 | 12% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
14 | Shyamji Krishan Verma Marg (Road No. 44) | 2 | 25.04.16 | 20-6-2016 | 5% | 24.08.16 | Er. Devender Prasad / 9899894912 | Er. M.L. Garg / 9868383698 | Er. Praveen Kumar Kathuria / 9971669344
15 | Kabir Das Road | 1.59 | 25.04.16 | 20-6-2016 | 12% | 24.08.16 | Er. Devender Prasad / 9899894912 | Er. M.L. Garg / 9868383698 | Er. Praveen Kumar Kathuria / 9971669344
16 | Railway Road (Sardar Balbir Singh Sandhu Marg) Road No.43 to URB Shakurbasti | 0.99 | 25.04.16 | 20-6-2016 | 11% | 24.08.16 | Er. Devender Prasad / 9899894912 | Er. M.L. Garg / 9868383698 | Er. Praveen Kumar Kathuria / 9971669344
17 | Eklavya Marg | 0.37 | 25.04.16 | 20-6-2016 | 14% | 24.08.16 | Er. Devender Prasad / 9899894912 | Er. M.L. Garg / 9868383698 | Er. Praveen Kumar Kathuria / 9971669344
18 | Veer Hemu Marg | 1.085 | 25.04.16 | 20-6-2016 | 16% | 24.08.16 | Er. Devender Prasad / 9899894912 | Er. M.L. Garg / 9868383698 | Er. Praveen Kumar Kathuria / 9971669344
19 | Maharishi Parshu Ram Marg | 0.75 | 25.04.16 | 20-6-2016 | 13% | 24.08.16 | Er. Devender Prasad / 9899894912 | Er. M.L. Garg / 9868383698 | Er. Praveen Kumar Kathuria / 9971669344
20 | Triwalubar Marg | 0.29 | 25.04.16 | 20-6-2016 | 14% | 24.08.16 | Er. Devender Prasad / 9899894912 | Er. M.L. Garg / 9868383698 | Er. Praveen Kumar Kathuria / 9971669344
21 | Main Road of G-Block & H-Block | 0.325 | 25.04.16 | 20-6-2016 | 16% | 24.08.16 | Er. Devender Prasad / 9899894912 | Er. M.L. Garg / 9868383698 | Er. Praveen Kumar Kathuria / 9971669344
22 | Valmiki Road | 0.6 | 25.04.16 | 20-6-2016 | 12% | 24.08.16 | Er. Devender Prasad / 9899894912 | Er. M.L. Garg / 9868383698 | Er. Praveen Kumar Kathuria / 9971669344
23 | Abdul Hamid Marg | 0.78 | 25.04.16 | 20-6-2016 | 14% | 24.08.16 | Er. Devender Prasad / 9899894912 | Er. M.L. Garg / 9868383698 | Er. Praveen Kumar Kathuria / 9971669344
Name of MLA :- Smt. Bandana Kumari
Name of Constituency :- Shalimar Bagh
24 | Outer Ring Road | 2.8 | 25.04.16 | 20-6-2016 | 15% | 24.08.16 | Er. Sheikh Nizam / 9899248998 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
25 | Outer Ring Road | 2.8 | 25.04.16 | 20-6-2016 | 10% | 24.08.16 | Er. Sheikh Nizam / 9899248998 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
26 | RUB Shalimar Bagh Road | 0.6 | 25.04.16 | 20-6-2016 | 15% | 24.08.16 | Er. Sheikh Nizam / 9899248998 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
27 | Jhule Lal Mandir Marg Shalimar Bagh | 1.25 | 25.04.16 | 20-6-2016 | 12% | 24.08.16 | Er. Sheikh Nizam / 9899248998 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
28 | Dividing Road | 0.26 | 25.04.16 | 20-6-2016 | 11% | 24.08.16 | Er. Sheikh Nizam / 9899248998 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
29 | Abhinav model School | 0.4 | 25.04.16 | 20-6-2016 | 14% | 24.08.16 | Er. Subhash Tomar / 9958138151 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
30 | Ahinsa path Road | 0.4 | 25.04.16 | 20-6-2016 | 16% | 24.08.16 | Er. Subhash Tomar / 9958138151 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
31 | NP - MP Road | 0.46 | 25.04.16 | 20-6-2016 | 13% | 24.08.16 | Er. Subhash Tomar / 9958138151 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
32 | SP School Road | 0.65 | 25.04.16 | 20-6-2016 | 14% | 24.08.16 | Er. Subhash Tomar / 9958138151 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
33 | BDFD Road | 0.54 | 25.04.16 | 20-6-2016 | 16% | 24.08.16 | Er. Subhash Tomar / 9958138151 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
34 | Shaheed Udham Singh Marg | 1.6 | 25.04.16 | 20-6-2016 | 12% | 24.08.16 | Er. Sheikh Nizam / 9899248998 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
35 | Swami Shardanand Saraswati Marg | 1.2 | 25.04.16 | 20-6-2016 | 14% | 24.08.16 | Er. Sheikh Nizam / 9899248998 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
36 | T.V Tower Road | 0.66 | 25.04.16 | 20-6-2016 | 9% | 24.08.16 | Er. Subhash Tomar / 9958138151 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
37 | Maharaja Agarsen Road | 2.84 | 25.04.16 | 20-6-2016 | 10% | 24.08.16 | Er. Subhash Tomar / 9958138151 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
38 | Power House Road | 1.03 | 25.04.16 | 20-6-2016 | 10% | 24.08.16 | Er. Subhash Tomar / 9958138151 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
39 | Gopal Mandir Road | 1.105 | 25.04.16 | 20-6-2016 | 10% | 24.08.16 | Er. Subhash Tomar / 9958138151 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
40 | Muni Maya Ram Road | 1.738 | 25.04.16 | 20-6-2016 | 12% | 24.08.16 | Er. Subhash Tomar / 9958138151 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
41 | Gurudwara Road | 0.6 | 25.04.16 | 20-6-2016 | 15% | 24.08.16 | Er. Sheikh Nizam / 9899248998 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
42 | Gyan Shakti Mandir Marg | 1.25 | 25.04.16 | 20-6-2016 | 12% | 24.08.16 | Er. Sheikh Nizam / 9899248998 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
43 | Maharishi Dayanand Marg | 0.4 | 25.04.16 | 20-6-2016 | 11% | 24.08.16 | Er. Subhash Tomar / 9958138151 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
44 | Bhagwan Mahavir Marg | 0.54 | 25.04.16 | 20-6-2016 | 10% | 24.08.16 | Er. Subhash Tomar / 9958138151 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
45 | Club Road | 0.6 | 25.04.16 | 20-6-2016 | 12% | 24.08.16 | Er. Sheikh Nizam / 9899248998 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
46 | K.L. Bagga Marg | 0.6 | 25.04.16 | 20-6-2016 | 15% | 24.08.16 | Er. Sheikh Nizam / 9899248998 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
47 | Haiderpur Main Road | 0.9 | 25.04.16 | 20-6-2016 | 12% | 24.08.16 | Er. Sheikh Nizam / 9899248998 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
48 | Canal Road | 0.88 | 25.04.16 | 20-6-2016 | 11% | 24.08.16 | Er. Sheikh Nizam / 9899248998 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
49 | Ram Leela Ground Road | 0.88 | 25.04.16 | 20-6-2016 | 14% | 24.08.16 | Er. Subhash Tomar / 9958138151 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
50 | Ring Road | 3.2 | 25.04.16 | 20-6-2016 | 10% | 24.08.16 | Er. Sheikh Nizam / 9899248998 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
51 | Road No. 41 | 3 | 25.04.16 | 20-6-2016 | 15% | 24.08.16 | Er. Subhash Tomar / 9958138151 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
Name of MLA :- Sh. Rajesh Gupta
Name of Constituency :- Wazirpur
52 | Gulab Singh Marg from G.T. Road to Road No. 37 Prerna Chowk | 3.1 | 25.04.16 | 20-6-2016 | 10% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
53 | Pardeshwar Dham Mandir Marg | 1.1 | 25.04.16 | 20-6-2016 | 30% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
54 | Ch. Mange Ram Marg | 0.37 | 25.04.16 | 20-6-2016 | 15% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
55 | Madhav Marg | 1.6 | 25.04.16 | 20-6-2016 | 30% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
56 | Sh. Guru Nanak Dev Ji Marg | 0.482 | 25.04.16 | 20-6-2016 | 11% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
57 | Front of Keshavpuram Police station | 0.45 | 25.04.16 | 20-6-2016 | 30% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
58 | K.C.Goel Marg | 0.756 | 25.04.16 | 20-6-2016 | 10% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
59 | Maharishi Dayanand Saraswati Marg | 0.455 | 25.04.16 | 20-6-2016 | 12% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
60 | Shri Ram Kishan Mandir Marg | 0.551 | 25.04.16 | 20-6-2016 | 15% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
61 | Kulachi Hans Raj School Marg | 0.23 | 25.04.16 | 20-6-2016 | 12% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
62 | F-Block Market | 0.38 | 25.04.16 | 20-6-2016 | 11% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
63 | B-Block Market | 0.27 | 25.04.16 | 20-6-2016 | 14% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
64 | Deep Chand Central Market | 1 | 25.04.16 | 20-6-2016 | 10% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
65 | Road No. 37 (Maharaja Nahar Singh Marg) | 3 | 25.04.16 | 20-6-2016 | 12% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
66 | Road No. 38 | 1.45 | 25.04.16 | 20-6-2016 | 15% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
67 | Jhule Lal Marg | 0.363 | 25.04.16 | 20-6-2016 | 12% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
68 | Shiv Ram Mandir Marg | 0.3 | 25.04.16 | 20-6-2016 | 11% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
69 | Lala Lajpat Rai Marg | 0.327 | 25.04.16 | 20-6-2016 | 14% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
70 | Mata Jai Kaur Road | 0.29 | 25.04.16 | 20-6-2016 | 10% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
71 | Sunder Lal Jain Road | 0.55 | 25.04.16 | 20-6-2016 | 12% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
72 | Bunkar Colony Road | 0.224 | 25.04.16 | 20-6-2016 | 15% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
73 | Kakaji Lane | 0.328 | 25.04.16 | 20-6-2016 | 12% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
74 | Laxmi Bai College Road | 0.385 | 25.04.16 | 20-6-2016 | 11% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
75 | Main GT Road | 1.08 | 25.04.16 | 20-6-2016 | 14% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
76 | Bharat Nagar Road | 2.09 | 25.04.16 | 20-6-2016 | 10% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
77 | Nimri Colony Road | 3.4 | 25.04.16 | 20-6-2016 | 12% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
78 | Tawetia Marg | 1.03 | 25.04.16 | 20-6-2016 | 15% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
79 | K.C Goel Marg upto Underpass | 0.65 | 25.04.16 | 20-6-2016 | 12% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
80 | Lawrence Road | 0.87 | 25.04.16 | 20-6-2016 | 11% | 24.08.16 | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
CIRCLE NORTH-WEST
Name of Division : EE NWR-II
Name of MLA :- Sh. Satyender Jain
Name of Constituency :- Shakur Basti
82 | Ch Balbir Singh Marg from Road No. 30 to Rohtk Road (NH-10) | 1.06 | 12.03.2016 | 30.06.2016 | 80% | 09.07.2016 | Sh. Rajesh Mewada 9873754012 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
83 | Bhao Rao Dev Ras Marg | 1.4 | 12.03.2016 | 30.06.2016 | 5% | 09.07.2016 | Sh. Rajesh Mewada 9873754012 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
84 | Deen Dayal Upadhyay Marg | 0.6 | 12.03.2016 | 30.06.2016 | 5% | 09.07.2016 | Sh. Rajesh Mewada 9873754012 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
85 | Major Ashwani Marg | 1 | 12.03.2016 | 30.06.2016 | 80% | 09.07.2016 | Sh. Rajesh Mewada 9873754012 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
86 | Road between B4 and B5 Block Paschim Vihar | 0.35 | 12.03.2016 | 30.06.2016 | 70% | 09.07.2016 | Sh. Rajesh Mewada 9873754012 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
87 | NH-10 (Delhi Rohtak Road) | 4.5 | 12.03.2016 | 30.06.2016 | 5% | 09.07.2016 | Sh. Rajesh Mewada 9873754012 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
88 | Guru Harkishan Marg (road No. 43) | 1.8 | 08.03.2016 | 30.06.2016 | 5% | 05.07.2016 | Sh. Sunit Singh 9971230165 | Sh. L.K. Tripathi 9891192952 | Sh. Praveen Kathuria 9971669344
89 | Chandra Shekhar Azad Marg (Road No. 42) | 1.23 | 12.03.2016 | 30.06.2016 | 5% | 09.07.2016 | Sh. Narender Singh 9868004850 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
90 | Guru Harkishan Marg (road No. 43) | 1.7 | 12.03.2016 | 30.06.2016 | 5% | 09.07.2016 | Sh. Narender Singh 9868004850 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
91 | Mahatma Hans Raj Marg | 1.4 | 12.03.2016 | 30.06.2016 | 35% | 09.07.2016 | Sh. Narender Singh 9868004850 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
92 | Guru Birja Nand Marg | 1.4 | 12.03.2016 | 30.06.2016 | 5% | 09.07.2016 | Sh. Narender Singh 9868004850 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
93 | Sant Nagar M2K Road | 0.47 | 12.03.2016 | 30.06.2016 | 5% | 09.07.2016 | Sh. Narender Singh 9868004850 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
94 | Amar Shaheed Bismil Marg | 0.94 | 12.03.2016 | 30.06.2016 | 5% | 09.07.2016 | Sh. Narender Singh 9868004850 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
95 | Police Line Road | 0.62 | 12.03.2016 | 30.06.2016 | 5% | 09.07.2016 | Sh. Narender Singh 9868004850 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
96 | Parwana Road, Saraswati Vihar | 2.8 | 12.03.2016 | 30.06.2016 | 40% | 09.07.2016 | Sh. Narender Singh 9868004850 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
97 | Road No.30 | 2 | 12.03.2016 | 30.06.2016 | 25% | 09.07.2016 | Sh. Rajesh Mewada 9873754012 | Er. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
Name of MLA :- Sh. Jitender Singh Tomar
Name of Constituency :- Tri Nagar
98 | Phirni Road | 0.53 | 12.03.2016 | 30.06.2016 | 5% | 09.07.2016 | Sh. Narender Singh 9868004850 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
Name of MLA :- Ms Rakhi Birla
Name of Constituency :- Mangolpuri
99 | Guru Govalkar Marg (Outer ring road Xing Mangolpuri Marble Market to Rajeev Nagar) | 5.8 | 26.02.2016 | 30.06.2016 | 35% | 25.02.2017 |  | Sh. Raj Kishore Raj, AE, 9971409602 | Sh. Praveen Kathuria 9971669344
100 | Road No. 316 | 1.4 | 08.03.2016 | 30.06.2016 | 30% | 05.07.2016 | Sh. Sunit Singh 9971230165 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
101 | Road No. 317 | 0.35 | 08.03.2016 | 30.06.2016 | 30% | 05.07.2016 | Sh. Sunit Singh 9971230165 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
102 | Road No. 318 | 0.85 | 08.03.2016 | 30.06.2016 | 30% | 05.07.2016 | Sh. Sunit Singh 9971230165 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
103 | Road No. 319 | 0.35 | 08.03.2016 | 30.06.2016 | 30% | 05.07.2016 | Sh. Sunit Singh 9971230165 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
104 | S.N. Hardiker Marg (Road No. A-1) | 1.19 | 08.03.2016 | 30.06.2016 | 30% | 05.07.2016 | Sh. Sunit Singh 9971230165 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
105 | Sir Chotu Ram Marg (road No. A-3) | 1 | 08.03.2016 | 30.06.2016 | 30% | 05.07.2016 | Sh. Sunit Singh 9971230165 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
106 | Kanjhawala Link road | 0.4 | 08.03.2016 | 30.06.2016 | 30% | 05.07.2016 | Sh. Sunit Singh 9971230165 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
107 | Outer Ring Road No. 26 | 0.3 | 08.03.2016 | 30.06.2016 | 30% | 05.07.2016 | Sh. Sunit Singh 9971230165 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
108 | Sanjay Gandhi Hospital Road from Road No.316 to J Block Survodya Vidhyalya to Kanjhawla Road. | 1.6 | 08.03.2016 | 30.06.2016 | 50% | 05.07.2016 | Sh. Sunit Singh 9971230165 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
109 | Police Station Road from Road No.3 i.e. Kanjhawla Road to Sanjay Gandhi Hospital Road. | 1.3 | 08.03.2016 | 30.06.2016 | 80% | 05.07.2016 | Sh. Sunit Singh 9971230165 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
110 | Kala Mandir Cinema Road in Mangolpuri | 0.8 | 08.03.2016 | 30.06.2016 | 50% | 05.07.2016 | Sh. Sunit Singh 9971230165 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
111 | LP Road (Tank Road) Mangolpuri | 1.2 | 08.03.2016 | 30.06.2016 | 30% | 05.07.2016 | Sh. Sunit Singh 9971230165 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
112 | B-Block Road Mangolpuri | 1.4 | 08.03.2016 | 30.06.2016 | 30% | 05.07.2016 | Sh. Sunit Singh 9971230165 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
113 | Road No.A-2 From Pole Star to CSC-II, Sec.1/2, Rohini. | 0.54 | 08.03.2016 | 30.06.2016 | 30% | 05.07.2016 | Sh. Sunit Singh 9971230165 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
114 | Road from New Bal Bharti Public School to Road No.3 Sec.2 | 0.4 | 08.03.2016 | 30.06.2016 | 30% | 05.07.2016 | Sh. Sunit Singh 9971230165 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
115 | Road from CSC Market Pkt.4 to Mangolpur Kalan Phirni Road Sec.2 | 0.3 | 08.03.2016 | 30.06.2016 | 30% | 05.07.2016 | Sh. Sunit Singh 9971230165 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
116 | Roadfrom PocketA-1 to Pocket A-2 in Sec.4 Rohini | 0.225 | 08.03.2016 | 30.06.2016 | 30% | 05.07.2016 | Sh. Sunit Singh 9971230165 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
117 | Roadfrom Pocket B-5to Pocket B-9 in Sec.4 Rohini MC Pry. School | 0.31 | 08.03.2016 | 30.06.2016 | 30% | 05.07.2016 | Sh. Sunit Singh 9971230165 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
118 | Road From Pocket A-2 to Pkt.C-13 in Sec.3 Rohini | 1 | Tender opened & under process | 30.06.2016 |  |  | Sh. Jai Singh 9312101073 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
119 | Road from Pocket F-22 to Pocket H-34 in Sec-3 Rohini | 1 | Tender opened & under process | 30.06.2016 |  |  | Sh. Jai Singh 9312101073 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
120 | Road from MC Pry. School 3A to Sarvodaya School in Sec.3, Rohini | 0.325 | Tender opened & under process | 30.06.2016 |  |  | Sh. Jai Singh 9312101073 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
121 | Road from DDA Shopping Centre to Kendriya Vidyalaya in Sec.3, Rohini. | 0.325 | Tender opened & under process | 30.06.2016 |  |  | Sh. Jai Singh 9312101073 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
122 | Jaipur Golden Hospital Road Sec.3 | 1 | Tender opened & under process | 30.06.2016 |  |  | Sh. Jai Singh 9312101073 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
Name of MLA :- Sh. Sandeep Kumar
Name of Constituency :- Sultanpur Majra
123 | Nangloi Rly.Stn to Sultanpuri Bus Terminal via Jalebi Chowk | 2.1 | 08.03.2016 | 30.06.2016 | 50% | 05.07.2016 | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
124 | Sultanpuri Bus Terminal to Flood Control Drain. | 1 | 08.03.2016 | 30.06.2016 | 80% | 05.07.2016 | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
125 | Sultanpuri Main Road | 0.6 | 08.03.2016 | 30.06.2016 | 30% | 05.07.2016 | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
126 | Shani Bazar Road | 0.6 | 08.03.2016 | 30.06.2016 | 75% | 05.07.2016 | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
127 | H Block Road | 0.32 | 08.03.2016 | 30.06.2016 | 30% | 05.07.2016 | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
128 | Jagdamba Road | 0.38 | 08.03.2016 | 30.06.2016 | 30% | 05.07.2016 | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
129 | Bhalla Factory road | 0.38 | 08.03.2016 | 30.06.2016 | 50% | 05.07.2016 | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
130 | G-Block Road | 0.15 | 08.03.2016 | 30.06.2016 | 30% | 05.07.2016 | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
Name of MLA :- Sh. Ritu Raj Jha
Name of Constituency :- Kirari
131 | 70 ft Road Kirari | 1.25 | 08.03.2016 | 30.06.2016 | 30% | 05.07.2016 | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
Name of MLA :- Vijender Gupta
Name of Constituency :- Rohini
132 | Road No. B-8 | 1.18 | Tender opened & under process | 30.06.2016 |  |  | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
133 | PWD Road to DJB Booster Pump (Length 0.270 KM) | 0.27 | Tender opened & under process | 30.06.2016 |  |  | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
134 | PWD Road to Baba wala Park (Corner of Booster Pump) (Length 0.590 KM) | 0.59 | Tender opened & under process | 30.06.2016 |  |  | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
135 | Dr. K.N. Katju Marg(45m wide road) | 3.77 | Tender opened & under process | 30.06.2016 |  |  | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
136 | Road No. B-4 | 1.4 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
137 | Road No. B-5 | 1.64 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
138 | Road No. B-7 | 1.25 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
139 | Col. Sarna Marg Sec.9 & 13 | 1.02 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
140 | Internal Road of Sec.9 Rohini | 0.325 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
141 | Internal Road of Sec.9 Rohini | 0.33 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
142 | R.N. Gujral Marg Sec.9 | 0.265 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
143 | Chetak Apartment to New Modern Apartment Sec.9 | 0.319 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
144 | Vidhya Vihar to Neelgiri Apt. Sec.9 | 0.33 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
145 | Captain Dahiya Marg Sec.9 & 13 | 1.68 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
146 | Ahinsha Marg Sec.9 & 13 | 1.68 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
147 | Sunrise Appartment (K. N. Katzu Marg) to Neelkanth Appartment (K. N. Katzu Marg) | 0.975 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
148 | Kawal Kunj Soceity to K.N. Katzu Marg (Length 0.265 KM) | 0.265 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
149 | Fire Station to CRPF School Corner Sec.14 Rohini (Ram Prasad Bismil Marg) | 0.72 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
150 | Babosa Chowk to Tulsi Apartment Sec.14, Rohini. | 0.55 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
151 | PWD Ring Road to Maheswari Apt. Sec.14 toward Sec.13. | 0.845 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
152 | Rukmani Devi Institute to Rohini Court Sec.14 | 0.45 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
153 | Connecting road from ORR to Road No.B-5 passing through CRPF School, Sec.14, Rohini | 0.86 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
154 | Maharaja Aggarsen Marg (Road No. 42-A) | 2.3 | 12.03.2016 | 30.06.2016 | 5% | 09.07.2016 | Sh. Narender Singh 9868004850 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
155 | A-1/1 to G-18/1 (Length 0.600 KM) | 0.6 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
156 | Western Yamuna Canal to Badli Chowk (Length 0.310 KM) | 0.31 | Tender opened & under process | 30.06.2016 |  |  | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
157 | G-17/1 to Western Yamuna Canal (Length 0.750 KM) | 0.75 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
158 | Western Yamuna Canal to Arya Appartment (Length 0.590 KM) | 0.59 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
159 | Western Yamuna Canal to A-11/87 (Length 0.300 KM) | 0.3 | Tender opened & under process | 30.06.2016 |  |  | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
160 | Pradeep Bhatia Marg (Road No. A-5) | 1 | Tender opened & under process | 30.06.2016 |  |  | Sh. Sunit Singh 9971230165 | Sh.Amar Singh 9891192952 | Sh. Praveen Kathuria 9971669344
161 | Road No. 41-A Bhagwan mahavir Marg. | 3.995 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
162 | Road No. B-3 | 1.55 | Tender opened & under process | 30.06.2016 |  |  | Sh. Jai Singh 9312101073 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
163 | G-23/30 to E4/15 Sec.7 | 0.396 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
164 | B-6/159 to Naharpur DAV School back side Sec.7 | 0.296 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
165 | B-22/279 to G-21/222 Sec.7 | 0.321 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
166 | B-4/30 to CGHS Dispensary Sec.7 | 0.172 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
167 | H18 to F-25 Sec.6 & 7 dividing road | 1.3 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
168 | Rama Road Sec.8, Rohini | 0.73 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
169 | Road from Road No. 41-A to Rama Road in Sec.8, Rohini | 1.05 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
170 | Road from Road No. 42-A to Rama Road in Sec.8, Rohini | 0.55 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
171 | Sawran Jayanti Park Road, Sec.9 &13 | 1.68 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
172 | PWD Road (B-7) to Corner of E-II Ashtha Kunj (Length 0.245 KM) | 0.245 | Tender opened & under process | 30.06.2016 |  |  | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
173 | Corner of Data Ram Society to CEPT (Length 0.390 KM) | 0.39 | Tender opened & under process | 30.06.2016 |  |  | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
174 | Behind Data Ram Society to Corner of Mt. Abu School (Length 0.390 KM) | 0.39 | Tender opened & under process | 30.06.2016 |  |  | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
175 | PWD Road (B-7) to CEPT (Length 0.580 KM) | 0.58 | Tender opened & under process | 30.06.2016 |  |  | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
176 | H-3/53 to DDA Park (Length 0.145 KM) | 0.145 | Tender opened & under process | 30.06.2016 |  |  | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
Name of MLA :- Mohinder Goyal
Name of Constituency :- Rithala
177 | Deen Bandhu Sir Chotu Ram Marg (Road No. A-4) | 1 | Tender opened & under process | 30.06.2016 |  |  | Sh. Jai Singh 9312101073 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
178 | Road No. B-1 | 0.96 | Tender opened & under process | 30.06.2016 |  |  | Sh. Jai Singh 9312101073 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
179 | Road No. B-6 | 1 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
180 | MTNL Godown to C6/137 Sec.5, Rohini | 0.533 | Tender opened & under process | 30.06.2016 |  |  | Sh. Jai Singh 9312101073 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
181 | Som Bazar Road, Sec.5, Rohini | 0.71 | Tender opened & under process | 30.06.2016 |  |  | Sh. Jai Singh 9312101073 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
182 | Shiva Road from Ring Road to Dividing Road of Sec.5 & 6, Rohini. | 2.217 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
183 | Vidya Jain Public School, Se.6, Rohini | 0.477 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
184 | C-4/253 to C5/253, Sec.6, Rohini | 0.33 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
185 | D-6 and A-1 Road sec.6,Rohini | 0.33 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
186 | Road from F-3 block to H-4 in Sec.11, Rohini | 0.7 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
187 | From A-1 to F-3 Block near NDPL office Sec.11, Rohini. | 1.5 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
188 | From Block H-1 to H-5 Block Sec.11, Rohini | 0.65 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
189 | From F-1 to H-2 Block near NDPL office Sec.11, Rohini. | 0.65 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
190 | From C-4 to A-3 Block near NDPL office Sec.11, Rohini. | 0.65 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
191 | From F-1 to F-3 Block near NDPL office Sec.11, Rohini. | 0.375 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
192 | From A-1 to A-3 Block near NDPL office Sec.11, Rohini. | 0.375 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
193 | From C-1 to C-5 Block near NDPL office Sec.11, Rohini. | 0.375 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
194 | From Community Centre to NDMC Colony, Sec.11, Rohini. | 0.69 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
195 | D-1 TO I-3 (Length 0.463 KM) | 0.463 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
196 | G-1 TO E-5 (Length 0.650 KM) | 0.65 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
197 | G-7 TO G-1 (Length 1.000 KM) | 1 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
198 | H-3 TO H-1 (Length 0.400 KM) | 0.4 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
199 | A-2 TO E-3 (Length 0.650 KM) | 0.65 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
200 | C-1 TO I-11 (Length 0.600 KM) | 0.6 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
201 | District Park TO C-1 (Length 0.438 KM) | 0.438 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
202 | F-2 TO F-6 (Length 0.338 KM) | 0.338 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
203 | A-6 TO A-8 (Length 0.263 KM) | 0.263 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
204 | F-3 TO F-5 (Length 0.338 KM) | 0.338 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
205 | I-1 TO Police Station (Length 0.538 KM) | 0.538 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
206 | B-2 TO B-6 (Length 0.210 KM) | 0.21 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
207 | A-8 TO B-6 (Length 0.600 KM) | 0.6 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
208 | B-1 TO C-1 (Length 0.475 KM) | 0.475 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
209 | A-8 TO B-1 ROAD (Length 0.445 KM) | 0.445 | Tender opened & under process | 30.06.2016 |  |  | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
210 | Road No. B-2 (Ram murthi Passi Marg) | 1.652 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
Name of MLA :- Sh. Ved Prakash
Name of Constituency :- Bawana
211 | Road from Pkt-10 to Pkt-D-4, Sec-20,Rohini | 0.505 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
212 | Road from Pkt-14 to Pkt-C-1,Sec-20,Rohini | 1 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
213 | Road from Pkt-8 to Pkt.-9,Sec-21, Rohini | 0.505 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
214 | Road from Pkt-B to Park, Sec-21, Rohini | 0.187 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
215 | Road from Pkt-13 to Pkt-9,Sec-21, Rohini | 0.448 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
216 | Road from Pkt-5 to Pkt-6, Sec-21, Rohini | 0.115 | 15.05.2016 | 30.06.2016 |  | 11.09.2016 | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
Name of Division :- West Road-1
Name of MLA :- Sh. Jagdeep Singh
Name of Constituency :- Hari Nagar (28)
1 | Goswami Tulsi Dass Marg i.e. Road No. 32 | 1.6 | 05.05.2016 | 25.05.2016 | 5% | 04.11.2016 | Ankur Goswami 9950265713 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
2 | Dr. Kundan Lal Marg | 0.42 | 05.05.2016 | 25.05.2016 |  | 04.11.2016 | Ankur Goswami 9950265713 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
3 | Rajouri Appartment Road | 3 | 05.05.2016 | 25.05.2016 | 15% | 04.11.2016 | Ankur Goswami 9950265713 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
4 | H.No. 14/35 to 13/101 Subash Nagar (Near Shandley School) | 0.454 | 05.05.2016 | 05.06.2016 |  | 04.11.2016 | Ankur Goswami 9950265713 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
5 | Shanti Devi Marg | 0.375 | 05.05.2016 | 10.06.2016 |  | 04.11.2016 | Ankur Goswami 9950265713 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
6 | Ashok Nagar Road | 0.318 | 05.05.2016 | 05.06.2016 |  | 04.11.2016 | Ankur Goswami 9950265713 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
7 | Ayodhya Prasad Chopra Marg | 0.45 | 05.05.2016 | 05.06.2016 |  | 04.11.2016 | Ankur Goswami 9950265713 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
8 | Road No. 32 to 17/117 Subash Nagar | 0.35 | 05.05.2016 | 05.06.2016 |  | 04.11.2016 | Ankur Goswami 9950265713 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
9 | H.No. 6/1 to 3/200 Subhash Nagar | 0.68 | 05.05.2016 | 05.06.2016 |  | 04.11.2016 | Ankur Goswami 9950265713 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
10 | Vedic Marg | 1.35 | 05.05.2016 | 10.06.2016 |  | 04.11.2016 | Ankur Goswami 9950265713 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
11 | H.No. 11/76 to 11/85 Subhash Nagar | 0.05 | 05.05.2016 | 05.06.2016 |  | 04.11.2016 | Ankur Goswami 9950265713 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
12 | H.No. 8/1 to 14/149 Subhash Nagar | 0.35 | 05.05.2016 | 05.06.2016 |  | 04.11.2016 | Ankur Goswami 9950265713 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
13 | H.No. 10/1 to 14/97 Subhash Nagar | 0.292 | 05.05.2016 | 05.06.2016 |  | 04.11.2016 | Ankur Goswami 9950265713 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
14 | Sardar Kulwant Singh Sethi Marg | 1.046 | 05.05.2016 | 10.06.2016 |  | 04.11.2016 | Ankur Goswami 9950265713 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
15 | DA-1, Hari Nagar to DB-1 Hari Nagar | 0.423 | 05.05.2016 | 10.06.2016 |  | 04.11.2016 | Ankur Goswami 9950265713 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
16 | Shaheed Bhagat Singh Mrg. (Jail Rd) | 2.28 | 05.05.2016 | 05.06.2016 |  | 04.11.2016 | Ajay Vishraj 8800146761 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
17 | Shaheed Bhagat Singh Mrg. (Jail Rd) | 1.4 | 05.05.2016 | 05.06.2016 |  | 04.11.2016 | Ajay Vishraj 8800146761 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
18 | B-2/Dharam Marg | 1.38 | 05.05.2016 | 31.05.2016 |  | 04.11.2016 | Ajay Vishraj 8800146761 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
19 | Capt. Anuj Nayyar Marg. | 0.67 | 05.05.2016 | 31.05.2016 |  | 04.11.2016 | Ajay Vishraj 8800146761 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
20 | B1- B2 Connecting Road. | 0.59 | 05.05.2016 | 31.05.2016 |  | 04.11.2016 | Ajay Vishraj 8800146761 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
21 | Gurudwara Road | 0.63 | 05.05.2016 | 31.05.2016 |  | 04.11.2016 | Ajay Vishraj 8800146761 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
22 | BA-BB Block Road | 0.38 | 05.05.2016 | 31.05.2016 |  | 04.11.2016 | Ajay Vishraj 8800146761 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
23 | B2 Block Sabzi Mandi Road | 0.4 | 05.05.2016 | 31.05.2016 |  | 04.11.2016 | Ajay Vishraj 8800146761 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
24 | Prem Nagar Gurudwara Rd. | 0.52 | 05.05.2016 | 31.05.2016 |  | 04.11.2016 | Ajay Vishraj 8800146761 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
25 | Major Rajeev Laul Marg | 0.88 | 05.05.2016 | 10.06.2016 |  | 04.11.2016 | Ajay Vishraj 8800146761 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
26 | Shaheed Mangal Pandey Marg | 0.74 | 05.05.2016 | 15.06.2016 |  | 04.11.2016 | Ajay Vishraj 8800146761 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
27 | Bhai Kanheya Ji Marg (ITI Road) | 0.67 | 05.05.2016 | 15.06.2016 |  | 04.11.2016 | Ajay Vishraj 8800146761 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
28 | Mangal Pandey Marg (Hari Nagar Clock Tower to Maya Puri) | 0.85 | 05.05.2016 | 15.06.2016 |  | 04.11.2016 | Ajay Vishraj 8800146761 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
Name of Division :- West Road-2
Name of MLA :- Sh. Rajesh Rishi
Name of Constituency :- Janak Puri (30)
29 | Prof. Joginder Singh Marg (In front of Janakpuri Distt. Centre) | 1.18 | 05.05.2016 | 10.06.2016 | 2% | 04.11.2016 | Ranjeet Srivastva 9821691159 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
30 | Authority Road (Janak Puri) | 0.65 | 05.05.2016 | 10.06.2016 |  | 04.11.2016 | Ranjeet Srivastva 9821691159 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
31 | Mota Singh Road | 0.98 | 05.05.2016 | 10.06.2016 |  | 04.11.2016 | Ranjeet Srivastva 9821691159 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
32 | Possangi Pur Road | 0.4 | 05.05.2016 | 10.06.2016 |  | 04.11.2016 | Ranjeet Srivastva 9821691159 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
33 | Major Deepak Tyagi Marg | 0.97 | 05.05.2016 | 10.06.2016 |  | 04.11.2016 | Vishal Seth 9650167976 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
34 | A-1 Block Main Road | 0.62 | 05.05.2016 | 10.06.2016 |  | 04.11.2016 | Vishal Seth 9650167976 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
35 | Road Opp. A1B Block Janak Puri | 0.28 | 05.05.2016 | 10.06.2016 |  | 04.11.2016 | Vishal Seth 9650167976 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
36 | Asalatpur Road | 0.16 | 05.05.2016 | 10.06.2016 |  | 04.11.2016 | Vishal Seth 9650167976 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
37 | Asalatpur Road-II | 0.79 | 05.05.2016 | 10.06.2016 |  | 04.11.2016 | Vishal Seth 9650167976 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
Name of MLA :- Jarnal Singh
Name of Constituency :- Rajouri Garden (27)
38 | 100' Road (Patel Chowk to Subhash Nagar Drain (Patel Chowk Road) | 0.8 | 07.05.2016 | 15.06.2016 |  | 06.08.2016 | Yogesh Joshi 9795313669 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
39 | 100' Road New Khayala Road | 0.7 | To be opened on 16.05.16 | 15.06.2016 |  |  | Yogesh Joshi 9795313669 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
40 | 80' Road Chowkhandi Road | 1 | To be opened on 16.05.16 | 15.06.2016 |  |  | Yogesh Joshi 9795313669 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
41 | Ring road to A-31 rajori garden | 0.045 | To be opened on 16.05.16 | 15.06.2016 |  |  | Yogesh Joshi 9795313669 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
42 | Najafgarh Road to A-71 Rajouri Garden | 0.04 | To be opened on 16.05.16 | 15.06.2016 |  |  | Yogesh Joshi 9795313669 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
43 | Sakti Mandir Marg | 0.2 | To be opened on 16.05.16 | 15.06.2016 |  |  | Yogesh Joshi 9795313669 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
44 | Najafgarh Road | 1.95 | To be opened on 16.05.16 | 15.06.2016 |  |  | Yogesh Joshi 9795313669 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
45 | Arya Samaj Marg | 0.12 | To be opened on 16.05.16 | 15.06.2016 |  |  | Yogesh Joshi 9795313669 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
46 | J.Krishnatrey Marg | 0.11 | To be opened on 16.05.16 | 15.06.2016 |  |  | Yogesh Joshi 9795313669 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
47 | AD-1 to BF- 31 (Tagore Garden) | 0.6 | To be opened on 16.05.16 | 15.06.2016 |  |  | Yogesh Joshi 9795313669 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
48 | DE-131 to Community Hall | 0.22 | To be opened on 16.05.16 | 15.06.2016 |  |  | Yogesh Joshi 9795313669 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
49 | Devki Nandan Marg | 0.78 | To be opened on 16.05.16 | 15.06.2016 |  |  | Yogesh Joshi 9795313669 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
50 | Tanki Wala Marg | 0.2 | To be opened on 16.05.16 | 15.06.2016 |  |  | Yogesh Joshi 9795313669 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
51 | Sant Berwa Marg with Titar Pur drain | 0.6 | To be opened on 16.05.16 | 15.06.2016 |  |  | Yogesh Joshi 9795313669 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
52 | Road No. 28 | 0.5 | To be opened on 16.05.16 | 15.06.2016 |  |  | Yogesh Joshi 9795313669 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
53 | Major Sudesh Gadok Marg (J 12/1 to NG Road) | 0.62 | To be opened on 16.05.16 | 15.06.2016 |  |  | Yogesh Joshi 9795313669 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
54 | Major Sudesh Marg (NG Road to Ring Road) | 1.9 | To be opened on 16.05.16 | 15.06.2016 |  |  | Yogesh Joshi 9795313669 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
Name of MLA :- Jarnal Singh
Name of Constituency :- Tilak Nagar (29)
55 | Lala Ganesh Dass Marg | 1.27 | 07.05.2016 | 15.06.2016 |  | 06.08.2016 | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
56 | Road between Two Blocks of G- Block Vikas Puri | 0.24 | 07.05.2016 | 15.06.2016 |  | 06.08.2016 | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
57 | From G-1 Block Vikas Puri to Palican Road VikasPuri | 0.52 | 07.05.2016 | 15.06.2016 |  | 06.08.2016 | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
58 | Keshopur Sabzi Mandi Red Light (Outer Ring Road) to Subhash Nagar Drain | 0.386 | 07.05.2016 | 15.06.2016 |  | 06.08.2016 | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
59 | Road No. 235 | 0.35 | 07.05.2016 | 15.06.2016 |  | 06.08.2016 | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
60 | Road No. 235 extension | 0.76 | 07.05.2016 | 15.06.2016 |  | 06.08.2016 | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
61 | Chowkhandi Road | 0.22 | 07.05.2016 | 15.06.2016 |  | 06.08.2016 | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
62 | Najafgarh road from Subhash Nagar Crossing to Dhauli Piao | 4.2 | To be opened on 16.05.16 | 15.06.2016 |  |  | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
63 | Tilak Nagar To 20 Block Tilak Vihar | 0.5 | 07.05.2016 | 15.06.2016 |  | 06.08.2016 | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
64 | Road from H-Block To H-3 Block | 0.54 | 07.05.2016 | 15.06.2016 |  | 06.08.2016 | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
65 | Road from Guruvirjanand Marg to Distt. Park,Vikas Puri | 0.14 | 07.05.2016 | 15.06.2016 |  | 06.08.2016 | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
66 | Shaheed Raj Guru Marg Vikas Puri | 1.28 | 07.05.2016 | 15.06.2016 |  | 06.08.2016 | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
67 | Tilak Vihar Main Road | 0.54 | 07.05.2016 | 15.06.2016 |  | 06.08.2016 | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
68 | Road Adjcent to PVR Complex Vikas Puri | 0.15 | 07.05.2016 | 15.06.2016 |  | 06.08.2016 | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
69 | Pelicon Road from Guru Virzanand Marg to Road No. 235 Extension | 0.91 | 07.05.2016 | 15.06.2016 |  | 06.08.2016 | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
70 | Tilak Nagar Main Market Road | 0.07 | 07.05.2016 | 15.06.2016 |  | 06.08.2016 | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
71 | Outer Ring Road | 2.5 | To be opened on 16.05.16 | 15.06.2016 |  |  | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
72 | Brain Public School Road | 0.75 | 07.05.2016 | 15.06.2016 |  | 06.08.2016 | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
73 | K. R. Manglam | 0.54 | 07.05.2016 | 15.06.2016 |  | 06.08.2016 | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
74 | H- Block to Vikas Puri | 0.194 | 07.05.2016 | 15.06.2016 |  | 06.08.2016 | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
75 | 70 Block Park Ashok Nagar to Tihar No. 2 School | 0.52 | 07.05.2016 | 15.06.2016 |  | 06.08.2016 | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
76 | 2/1 to 2/10 Ashok Nagar | 0.6 | 07.05.2016 | 15.06.2016 |  | 06.08.2016 | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
Name of MLA :- Sh. Mahender Yadav
Name of Constituency :- Vikas Puri (31)
77 | Road No. 236 | 1.8 | To be opened on 19.05.16 | 15.06.2016 |  |  | Rajat 9868014576 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
78 | Road No. 237 | 0.45 | To be opened on 19.05.16 | 15.06.2016 |  |  | Rajat 9868014576 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
79 | Road between Krishi Appt. to DAV school (PWD Road) | 0.295 | To be opened on 19.05.16 | 15.06.2016 |  |  | Rajat 9868014576 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
80 | Road between Devdoot Appt. to Parmarth Appt. PWD Road Vikas Puri | 0.28 | To be opened on 19.05.16 | 15.06.2016 |  |  | Rajat 9868014576 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
81 | Road between Jupiter Appt. to Priya Appt. PWD Road Vikas Puri | 0.39 | To be opened on 19.05.16 | 15.06.2016 |  |  | Rajat 9868014576 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
82 | Road Between Nalanda Appt. To Nightingale Appt. Vikas Puri | 0.54 | To be opened on 19.05.16 | 15.06.2016 |  |  | Rajat 9868014576 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
83 | Road Sunrise Appt. to DAV School (PWD Road) Vikas Puri | 0.435 | To be opened on 19.05.16 | 15.06.2016 |  |  | Rajat 9868014576 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
84 | Road from F-234 to IFC drain (Over head tank) Vikas Puri | 0.25 | To be opened on 19.05.16 | 15.06.2016 |  |  | Rajat 9868014576 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
85 | Road from ITI Corner (Flat No. 58) to Central School Corner (Flat No. 391) LIG Flat Hastsal | 0.24 | To be opened on 19.05.16 | 15.06.2016 |  |  | Rajat 9868014576 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
86 | Road from Navyug Appt. to IFC drain (Brotherhood Appt.) Vikas Puri | 0.38 | To be opened on 19.05.16 | 15.06.2016 |  |  | Rajat 9868014576 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
87 | Guruvirja Nanad Marg | 2.7 | To be opened on 19.05.16 | 15.06.2016 |  |  | Jai Raghuvinder 9868053348 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
88 | Road starting from Oxford School to Airport Appt. (PWD Road) Vikas Puri | 0.88 | To be opened on 19.05.16 | 15.06.2016 |  |  | Jai Raghuvinder 9868053348 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
89 | Road between Lok Vihar Appt. (PWD Road) to Fblock Market Vikas Puri | 0.675 | To be opened on 19.05.16 | 15.06.2016 |  |  | Jai Raghuvinder 9868053348 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
90 | Nangloi - Najafgarh Road | 5.5 | To be opened on 16.05.16 | 15.06.2016 |  |  | Karam Veer 9654402679 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
Name of MLA :- Sh. Naresh Balyan
Name of Constituency :- Uttam Nagar (32)
91 | Najafgarh Road (Shivaji Marg) (Pankha Road Red Light to Kakrolla Mor) | 3 | To be opened on 19.05.16 | 15.06.2016 |  |  | Karam Veer 9654402679 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
Name of MLA :- Sh. Rajesh Rishi
Name of Constituency :- Janak Puri (30)
92 | Najafgarh Road (Shivaji Marg) (Dhauli Piao to Pankha Road Red Light) | 1.25 | To be opened on 19.05.16 | 15.06.2016 |  |  | Karam Veer 9654402679 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
Name of MLA:-Sh. Sukhbir Singh Dalal
Name of Constituency:- Mundka
1 | Delhi Rohtak Road (NH-10) from Metro Pillar No. 415 to Hiran Kudna more | 4.000 | 05/02/2016 | 30/06/2016 | 58% | 02/08/2016 | Sh. Amandeep Kamboj 9911558786 | Sh. R.B.Nehra (Additonal Charge) 9355666768 | Sh. D.V.S. Kansal 9873601920
2 | Guru Golwalkar Marg (Kanjhawala Road) | 9.800 | 26/02/2016 | 15/06/2016 | 27% | 25/02/2017 | …..do…… | …..do…… | …..do……
3 | Najafgarh- Nangloi Road from NH-10 | 3.750 | 27/02/2016 | 15/06/2016 | 67% | 25/06/2016 | …..do…… | …..do…… | …..do……
4 | Road from Ghevra More to Chand Pur More | 7.900 | 22/02/2016 | 15/06/2016 | 25% | 02/10/2016 | …..do…… | …..do…… | …..do……
5 | Delhi Rohtak Road (NH-10) from Hiran Kudna more to Tikri Boader | 7.000 | 10/03/2016 | 30/06/2016 | 67% | 15/07/2016 | …..do…… | …..do…… | …..do……
Name of MLA:-Sh. Raghuvinder Shokeen
Name of Constituency:-Nangloi
6 | Delhi Rohtak Road (NH-10) | 2.500 | 05/05/2016 | 15/06/2016 | 5% | 22/09/2016 | Sh. Balbir Singh 9899751635 | Sh. R.B.Nehra 9355666768 | Sh. D.V.S. Kansal 9873601920
|  | 2.700 | 06/04/2016 | 15/06/2016 | 30% | 22/09/2016 | …..do…… | …..do…… | …..do……
7 | Outer Ring Road No. 26 | 2.800 | 30/04/2016 | 15/06/2016 | 15% | 22/09/2016 | …..do…… | …..do…… | …..do……
8 | Road from Outer Ring Road Meera Bagh to GH-8 Fire station Paschim Vihar | 1.251 | 20/05/2016 | 15/06/2016 | - | 22/09/2016 | …..do…… | …..do…… | …..do……
9 | Road from GH-6 Chowk to GH-5 and 7 Paschim Vihar | 0.292 | 20/05/2016 | 15/06/2016 | - | 22/09/2016 | …..do…… | …..do…… | …..do……
10 | Road from Garg Plaza to L.I.C. Colony Paschim Vihar | 1.322 | 20/05/2016 | 15/06/2016 | - | 22/09/2016 | …..do…… | …..do…… | …..do……
11 | Road from Sai Baba Mandir GH-12 to GH-8 Fire station Paschim Vihar | 0.963 | 06/04/2016 | 15/06/2016 | 50% | 22/09/2016 | …..do…… | …..do…… | …..do……
12 | Road from Outer Ring Road Bhera Enclave to Sai Baba Mandir Paschim Vihar | 1.251 | 06/04/2016 | 15/06/2016 | 50% | 22/09/2016 | …..do…… | …..do…… | …..do……
13 | Road from GH-13 to Sayed Nangloi Village Chowk Paschim Vihar | 0.902 | 20/05/2016 | 15/06/2016 | - | 22/09/2016 | …..do…… | …..do…… | …..do……
14 | Road from Sant Mar'ks School to DDA Mkt. GH-5&7 Paschim Vihar | 0.435 | 20/05/2016 | 15/06/2016 | - | 22/09/2016 | …..do…… | …..do…… | …..do……
15 | Laxmi Narain Marg (N.S. Road) | 0.700 | 06/04/2016 | 15/06/2016 | 90% | 22/09/2016 | …..do…… | …..do…… | …..do……
16 | Ch. Prem Sukh Road | 1.292 | 06/04/2016 | 15/06/2016 | 65% | 22/09/2016 | …..do…… | …..do…… | …..do……
17 | 60' road in Jawala Puri | 1.150 | 06/04/2016 | 15/06/2016 | 60% | 22/09/2016 | …..do…… | …..do…… | …..do……
18 | Road from Capital Plaza Market to Jhaj Aptt. Mianwali Nagar | 0.350 | 20/05/016 | 15/06/2016 | - | 22/09/2016 | …..do…… | …..do…… | …..do……
19 | Road from Vindhachal Aptt. To Viral Co. Op. Society Mianwali Nagar | 0.350 | 20/05/016 | 15/06/2016 | - | 22/09/2016 | Sh. Balbir Singh 9899751635 | Sh. R.B.Nehra 9355666768 | Sh. D.V.S. Kansal 9873601920
20 | Road from Rblock jwalapuri to Sai mandir Guru Harkishan Nagar | 0.360 | 20/05/016 | 15/06/2016 | - | 22/09/2016 | …..do…… | …..do…… | …..do……
21 | Road from Durbal Nath Vatica to NH-10 | 0.600 | 20/05/016 | 15/06/2016 | - | 22/09/2016 | …..do…… | …..do…… | …..do……
Name of MLA:-Sh. Garish Soni
Name of Constituency:-Madi Pur
22 | Road from 48 NWA Ch. Balbir Singh Marg to Road No. 32 | 0.390 | 25/05/2016 | 15/06/2016 | - | 22/09/2016 | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. D.V.S. Kansal 9873601920
23 | Vashisth Kumar Gulla Marg | 1.390 | 09/05/2016 | 15/06/2016 | 25% | 22/09/2016 | …..do…… | …..do…… | …..do……
24 | N.A. Road | 1.000 | 01/06/2016 | 30/06/2016 | - | 22/09/2016 | …..do…… | …..do…… | …..do……
25 | Ch. Balbir Singh Marg (Club Road) | 0.390 | 09/05/2016 | 15/06/2016 | 50% | 22/09/2016 | …..do…… | …..do…… | …..do……
26 | Road from Paschim Puri Chowk to New Slum Qtrs. | 0.450 | 10/06/2016 | 30/06/2016 | - | 22/09/2016 | …..do…… | …..do…… | …..do……
27 | Road from Shiv Mndir Road (Rohtak Road) to shiv Mandir Madipur Village | 0.700 | 03/05/2016 | 15/06/2016 | 60% | 22/09/2016 | …..do…… | …..do…… | …..do……
28 | Road from Madipur Main Road from Rohtak Road to Paschim Puri Chowk | 1.000 | 15/06/2016 | 30/06/2016 | - | 22/09/2016 | …..do…… | …..do…… | …..do……
29 | Road No. 32 (Hans Raj Model School )to Road No. 33 | 1.510 | 28/04/2016 | 15/06/2016 | 50% | 22/09/2016 | …..do…… | …..do…… | …..do……
30 | Road from H.No. A-250 to Shiv Mandir Road in C-103 Punjabi Bagh | 0.480 | 23/04/2016 | 15/06/2016 | 50% | 22/09/2016 | …..do…… | …..do…… | …..do……
31 | Road No. 77 (Punjabi Bagh) | 1.410 | 23/04/2016 | 15/06/2016 | 40% | 22/09/2016 | …..do…… | …..do…… | …..do……
32 | Road No. 28 | 1.930 | 20/05/2016 | 30/06/2016 | - | 05/07/2016 | …..do…… | …..do…… | …..do……
33 | Road No. 29 | 2.800 | 20/05/2016 | 30/06/2016 | - | 05/07/2016 | …..do…… | …..do…… | …..do……
34 | Road from Road No. 41 from H.No. 1 to 81 in West Punjabi Bagh | 1.715 | 20/05/2016 | 30/06/2016 | - | 05/07/2016 | …..do…… | …..do…… | …..do……
35 | Road from Najafgarh Road to WZ-494, Basai Darapur (Sheo Nath Tyagi Marg) | 0.675 | 20/05/2016 | 20/06/2016 | - | 28/07/2016 | …..do…… | …..do…… | …..do……
36 | Road from H-1 Bali Nagar (NG Road) to ESI Hospital (Ring Road) [ Major Sunil Bakshi Marg) | 0.520 | 20/05/2016 | 20/06/2016 | - | 28/07/2016 | …..do…… | …..do…… | …..do……
Name of MLA:-Sh.Shiv Charan Goel
Name of Constituency:-Moti Nagar
37 | Punjab Garden Road | 0.210 | 06/04/2016 | 15/06/2016 | 20% | 05/07/2016 | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. D.V.S. Kansal 9873601920
38 | Smt. Ginni Devi Road | 0.750 | 06/04/2016 | 15/06/2016 | 20% | 05/07/2016 | …..do…… | …..do…… | …..do……
39 | Bhagwan Dass Marg (K.C. Garg Marg) | 0.300 | 06/04/2016 | 15/06/2016 | 20% | 05/07/2016 | …..do…… | …..do…… | …..do……
40 | Ring Road | 3.000 | 06/04/2016 | 30/06/2016 | 20% | 05/07/2016 | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. D.V.S. Kansal 9873601920
41 | Najafgarh Road from Zakhira Round about to Moti Nagar | 2.240 | 20/05/2016 | 30/06/2016 | - | 28/07/2016 | …..do…… | …..do…… | …..do……
42 | Shivdass Puri Marg | 2.000 | 20/05/2016 | 20/06/2016 | - | 28/07/2016 | …..do…… | …..do…… | …..do……
43 | Road from Milan Cinema to H. No. 19/289 | 0.420 | 20/05/2016 | 20/06/2016 | - | 28/07/2016 | …..do…… | …..do…… | …..do……
44 | Road from HIL to Bus Terminal of 234, Karampura | 0.412 | 20/05/2016 | 20/06/2016 | - | 28/07/2016 | …..do…… | …..do…… | …..do……
45 | Rohtak Road from Zakhira to Punjabi Bagh | 2.100 | 30/04/2016 | 20/06/2016 | 15% | 28/07/2016 | …..do…… | …..do…… | …..do……
46 | Rama Road (Satguru Ram Singh Marg) | 1.695 | 30/04/2016 | 20/06/2016 | 30% | 28/07/2016 | …..do…… | …..do…… | …..do……
47 | Road from Road No. 36 (Sat Guru Ram Singh Marg (Maya Puri Chowk to SD Public School) | 2.000 | 31/05/2016 | 30/06/2016 | - | 04/08/2016 | …..do…… | …..do…… | …..do……
48 | Rama Road (Satguru Ram Singh Marg) | 1.200 | 20/05/2016 | 20/06/2016 | - | 04/08/2016 | …..do…… | …..do…… | …..do……
49 | Mahatma Gandhi Marg (Ring road) | 1.750 | 31/05/2016 | 30/06/2016 | - | 04/08/2016 | …..do…… | …..do…… | …..do……
50 | Road from Bus Route B-14 Tagore Market to G-82 Kirti Nagar | 0.910 | 31/05/2016 | 30/06/2016 | - | 04/08/2016 | …..do…… | …..do…… | …..do……
51 | Major Rajive Bhasin Marg D/Story | 0.325 | 07/05/2016 | 15/06/2016 | 10% | 04/08/2016 | …..do…… | …..do…… | …..do……
52 | Pankaj Batra Marg | 0.770 | 07/05/2016 | 15/06/2016 | 10% | 04/08/2016 | …..do…… | …..do…… | …..do……
53 | Lai Sai Mandir Marg D/Story | 0.325 | 20/05/2016 | 15/06/2016 | - | 04/08/2016 | …..do…… | …..do…… | …..do……
54 | 80' wide Road MS Garden Road | 2.490 | 07/05/2016 | 15/06/2016 | 10% | 04/08/2016 | …..do…… | …..do…… | …..do……
Name of MLA:-Sh.Hazari Lal Chauhan
Name of Constituency:-Patel Nagar
55 | Patel Road | 2.930 | 31/05/2016 | 30/06/2016 | - | 04/08/2016 | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. D.V.S. Kansal 9873601920
56 | Vishwakarma Marg | 1.000 | 07/05/2016 | 15/06/2016 | 10% | 04/08/2016 | …..do…… | …..do…… | …..do……
57 | T-Sohan Lal Marg | 0.900 | 07/05/2016 | 15/06/2016 | 10% | 04/08/2016 | …..do…… | …..do…… | …..do……
58 | G.L. Sikka Marg | 0.800 | 07/05/2016 | 15/06/2016 | 10% | 04/08/2016 | …..do…… | …..do…… | …..do……
59 | Suman Lata Badola Marg | 0.243 | 07/05/2016 | 15/06/2016 | 10% | 04/08/2016 | …..do…… | …..do…… | …..do……