## All Zone (South, East & North)
PWD Desilting Report (Preparedness for Monsoon)
DESILTING UNDER PWD MAINTENANCE ZONE SOUTH (M) AS ON 27.05.2016
Sl.No. | Name of Road | Length of Road | Date of Start of De-silting | Date of completion of De-silting | % Progress | JE in charge / Mobile No. | AE in charge / Mobile No. | EE in charge / Mobile No.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
CIRCLE SOUTH WEST (M)
EE/SWR-I
Name of MLA :- Smt. Pramila Tokas
1 | B.J. Marg | 1.3 | 21.05.2016 | 15.06.2015 | - | Sh. K Meena Mob.:- 8800762599 | Sh. Udai Meena Mob:- 9958268343 | Sh. Gulshan Sharma Mob.:-981134465
2 | Rao Tula Ram Marg (RTR Marg) | 1.7 | 15.05.2016 | 25.05.2016 | 50%
3 | Zonal road No. 2 (Baba Balak Nath Marg) | 1.1 | 21.05.2016 | 15.06.2016 | -
4 | Zonal Road No. 6 (Hare Krishna Mehto Marg) | 0.7 | 21.05.2016 | 15.06.2016 | -
5 | Nelson Mandela Marg | 4.04 | 25.05.2016 | 15.06.2016 | -
6 | Baba Gang Nath marg | 1.17 | 25.05.2016 | 15.06.2015 | -
7 | Outer Ring Road | 5.8 | 25.05.2016 | 15.06.2015 | -
8 | Vatika Road (DPS Vasant Kunj to MM road) | 0.7 | 25.05.2016 | 15.06.2015 | - | Sh. Ravindra Kumar Mob.:- 9818026779 | Sh. Sh. G.P. Khanna Mob.:- 9717284189 | Sh. Gulshan Sharma Mob.:-981134465
9 | Africa Avenue (Road No.9) | 2.2 | 25.05.2016 | 15.06.2015 | -
10 | Tamil Sangam Marg | 1.1 | 25.05.2016 | 15.06.2015 | -
11 | Major Som nath marg | 1.6 | 25.05.2016 | 15.06.2015 | -
12 | Kafi Azami Marg | 0.9 | 25.05.2016 | 15.06.2015 | -
13 | Church Road, R.K.Puram | 0.85 | 25.05.2016 | 15.06.2015 | -
14 | Babu Genu Marg, R.K.Puram | 0.6 | 25.05.2016 | 15.06.2015 | -
15 | Prem nath Dogra marg, R.K.Puram | 0.85 | 10.05.2016 | 21.05.2016 | 90%
16 | Kama Koti Marg | 0.85 | 25.05.2016 | 15.06.2016 | -
17 | Vivekanand Marg | 1.75 | 25.05.2016 | 15.06.2016 | -
18 | Venketeshwar Marg | 1.1 | 25.05.2016 | 15.06.2016 | -
19 | Ring Road | 3.5 | 25.05.2016 | 15.06.2016 | -
20 | Basant marg-I | 0.9 | 21.05.2016 | 15.06.2016 | -
21 | Basant Marg-II | 0.5 | 21.05.2016 | 15.06.2016 | -
22 | Poorvi Marg | 1.65 | 21.05.2016 | 15.06.2016 | - | Sh. Ravindra Kumar Mob.:- 9818026779 | Sh. Sh. G.P. Khanna Mob.:- 9717284189 | Sh. Gulshan Sharma Mob.:-981134465
23 | Paschimi Magar | 1.25 | 21.05.2016 | 15.06.2016 | -
24 | Munirka marg | 0.9 | 21.05.2016 | 15.06.2016 | -
25 | A-9 Street Road | 0.65 | 25.5.2016 | 15.06.2016 | -
Name of MLA :- Naresh Yadav
26 | M.M.Road | 8.1 | 21.05.2016 | 15.06.2016 | - | Sh. K Meena Mob.:- 8800762599 | Sh. Udai Meena Mob:- 9958268343 | Sh. Gulshan Sharma Mob.:-981134465
Name of MLA :- Comm. Surender Singh
27 | Ullan Buttor Marg | 0.7 | 21.05.2016 | 15.06.2016 | - | Sh. K Meena Mob.:- 8800762599 | Sh. Udai Meena Mob:- 9958268343 | Sh. Gulshan Sharma Mob.:-981134465
28 | Mahatma gandhi Marg (Ring Road) | 8.6 | 15.05.2016 | 15.06.2016 | - | Sh. C.M Meena Mob.:-9560929860 | Sh. Yad Ram Meena Mob.:-9999109979 | Sh. Gulshan Sharma Mob.:-981134465
29 | NH-8 | 2.9 | 25.5.2016 | 15.06.2016 | -
30 | Upper Ridge Road (Vande Martram Marg) | 5.5 | 25.5.2016 | 15.06.2016 | -
Name of MLA :- Sh. Jagdeep Singh
31 | Road No. 36(Sat Guru Ram Singh Marg) | 3.05 | 25.5.2016 | 15.06.2016 | - | Sh. C.M Meena Mob.:-9560929860 | Sh. Yad Ram Meena Mob.:-9999109979 | Sh. Gulshan Sharma Mob.:-981134465
Name of MLA :- Vijender Garg
32 | Ganga Ram Hospital Road | 1.08 | 25.5.2016 | 15.06.2016 | - | Sh. Rukuvi Thio Mob.:- 8800645513 | Sh. Naurati Ram Mob.:- 8130659730 | Sh. Gulshan Sharma Mob.:-981134465
33 | PUSA Road | 1.50 Actual 2.00 KM | 25.5.2016 | 15.06.2016 | - | Sh. Rukuvi Thio Mob.:- 8800645513 | Sh. Naurati Ram Mob.:- 8130659730 | Sh. Gulshan Sharma Mob.:-981134465
34 | Shankar Road | 1.64 | 21.05.2016 | 15.06.2016 | 10%
35 | Dr. K.S. Krishanan Marg | 0.915 | 21.05.2016 | 15.06.2016 | -
36 | PUSA Institute (IARI) Internal Road | 0.7 | 21.05.2016 | 15.06.2016 | -
37 | Suman Lata Badola Marg | 0.243 | 21.05.2016 | 15.06.2016 | -
38 | Madhav Setu Marg | 0.605 | 21.05.2016 | 15.06.2016 | -
39 | Dev Prakash Shastri marg (Road No. 25) | 4.45 | 21.05.2016 | 15.06.2016 | -
40 | Girdhari Lal Goswami Marg (Road No. 89) | 3.05 | 21.05.2016 | 15.06.2016 | -
41 | Ram Nath Vij Marg | 1.19 | 21.05.2016 | 15.06.2016 | -
42 | O.P. Bharti Marg 1 | 0.535 | 21.05.2016 | 15.06.2016 | -
43 | O.P. Bharti Marg 2 | 0.762 | 21.05.2016 | 15.06.2016 | -
44 | O.P. Bharti Marg 3 | 0.181 | 21.05.2016 | 15.06.2016 | -
45 | O.P. Bharti Marg 4 | 0.42 | 21.05.2016 | 15.06.2016 | -
46 | Dr. Girdhari Lal Goswami Marg | 0.6 | 25.05.2016 | 15.06.2016 | -
47 | Upper Ridge Road (Vande Martram Marg) | 1.5 | 25.05.2016 | 15.06.2016 | - | Sh. Rukuvi Thio Mob.:- 8800645513 | Sh. Naurati Ram Mob.:- 8130659730 | Sh. Gulshan Sharma Mob.:-981134465
EE/SWR-II
Name of MLA :- Sh. Rajesh Rishi (West) Name of Constituency :- Janak Puri (30)
1 | Pankha Road | 5.05 | 17.05.2016 | 30.06.2016 | 10% | Sh. Mithun Kumar Mob.8252079657 | Sh. S.K. Varshney M- 9212006584 | Sh. J.P. Vasisht M-9971396164
2 | Lal Sai Road | 2.525 | 17.05.2016 | 30.06.2016 | 10% | Sh. Rohtash Singh M- 9911476066
3 | Vidya Marg Road | 1.54 | 17.05.2016 | 30.06.2016 | 15%
4 | Dabri Road | 0.9 | 17.05.2016 | 30.06.2016 | 15%
5 | Mall Road | 0.612 | 17.05.2016 | 30.06.2016 | 10%
6 | Ram Mandir Marg | 0.861 | 17.05.2016 | 30.06.2016 | 10%
7 | Shani Bazr Road | 0.647 | 17.05.2016 | 30.06.2016 | 10%
8 | Fire Station Road | 0.5 | 17.05.2016 | 30.06.2016 | 15%
9 | Connecting Road 1 | 0.35 | 17.05.2016 | 30.06.2016 | 15%
10 | Connecting Road 2 | 0.45 | 17.05.2016 | 30.06.2016 | 15%
11 | Lal Sai to Pankha Road | 0.633 | 17.05.2016 | 30.06.2016 | 5%
12 | C2/22 to C2/274 | 0.762 | 17.05.2016 | 30.06.2016 | Nil | Sh. Rohtash Singh M- 9911476066 | Sh. S.K. Varshney M- 9212006584 | Sh. J.P. Vasisht M-9971396164
13 | Central School Road | 0.29 | 17.05.2016 | 30.06.2016 | Nil
Name of MLA :- Sh. Adarsh Shastri Name of Constituency :- Dwarka (33)
14 | Sagar Pur Road | 3 | - | - | 10% | Sh. Anuj Mishra M- 9868419032 | Sh. S.K. Varshney M- 9212006584 | Sh. J.P. Vasisht M-9971396164
15 | Nasirpur Road | 2.3 | - | - | 10%
16 | Palam Dabri Road | 2.6 | - | - | 10%
17 | Peer Baba Road | 0.647 | - | - | Nil
Name of MLA :- Sh. Jagdeep Singh (West) Name of Constituency :- Hari Nagar(28)
18 | Pandit Vishnu datt Marg | 0.85 | - | - | 10% | Sh. Mithun Kumar Mob.8252079657 | Sh. S.K. Varshney M- 9212006584 | Sh. J.P. Vasisht M-9971396164
19 | Satguru Ram Singh Marg | 0.85 | - | - | Nil
20 | Connecting Road | 1.77 | - | - | Nil
Name of MLA :- Sh. Naresh Balyan (SW) Name of Constituency :- Uttam Nagar
21 | Police Station Road | 0.3 | - | - | 10% | Sh. Mithun Kumar Mob.8252079657 | Sh. S.K. Varshney M- 9212006584 | Sh. J.P. Vasisht M-9971396164
22 | A Block Road | 0.4 | - | - | 15%
Name of MLA :- Sh. Kailash Gahlot(SW) Name of Constituency :- Najafgarh (35)
23 | Najafgarh Phirni | 2.2 | 26.04.2016 | 30.06.2016 | 60% | Sh. Navin Mob. 8285959206 | Sh.Munna Lal Mob. 7503926625 | Sh. J.P. Vasisht M-9971396164
24 | NajafgarhDechaun Road | 4.55 | - | - | 0%
25 | Najafgarh Nangloi Road | 2.6 | 13.05.2016 | 30.06.2016 | 40%
`26 | Najafgarh Jharoda Road | 7.2 | 26.04.2016 | 30.06.2016 | 40% | Sh. A.C. Meena Mob. 8802169763 | Sh. N.K. Sharma Mob. 9868768945 | Sh. J.P. Vasisht M-9971396164
Name of MLA :- Sh. Gulab Singh (SW) Name of Constituency :- Matiala (34)
27 | Najafgarh Dhansa Road | 16.25 | 19.03.2016 | 30.06.2016 | 40% | Sh. A.C. Meena Mob. 8802169763 | Sh. N.K. Sharma Mob. 9868768945 | Sh. J.P. Vasisht M-9971396164
28 | Najafgarh Bijwasan Road | 11.25 | 19.03.2016 | 30.06.2016 | 15%
29 | Laxmi Chand Marg | 11.3 | 19.03.2016 | 30.06.2016 | 20%
30 | Prithivi Singh Dagar Marg | 11.2 | 18.04.2016 | 30.06.2016 | 20%
31 | Jhatikara Morh to Jhatikara | 8.55 | - | - | -
32 | Goyla Deen Pur Road | 4.2 | 18.04.2016 | 30.06.2016 | 10% | Sh. Rohtash Singh M- 9911476066
Name of MLA :- Col Devinder Sehrawat (SW) Name of Constituency :- Bijwasan
33 | Old DG Road | 2.5 | - | - | - | Sh. Rohtash Singh M- 9911476066 | Sh. S.K. Varshney M- 9212006584 | Sh. J.P. Vasisht M-9971396164
34 | Link Road | 1.7 | - | - | - | Sh. Rohtash Singh M- 9911476066 | Sh. S.K. Varshney M- 9212006584 | Sh. J.P. Vasisht M-9971396164
35 | Kapashera Bijwasan Road | 3.8 | - | - | -
36 | Bhartal Road | 3.48 | - | - | -
CIRCLE SOUTH (M)
DIVISION SOUTH ROAD-I
1 | M.B. Road | 7 | 25.05.2016 | 10.06.2016 | 3% | Sh. Suresh Kumar 9899542920 | Sh. Sandeep Gupta 9560293030 | Sh. Narender Mahajan 9933331859
2 | Devli Road | 2 | 25.05.2016 | 10.06.2016 | 2%
3 | IGNOU Road | 2.9 | 25.05.2016 | 10.06.2016 | 10%
4 | Maharishi Balmiki Marg | 1.8 | 25.05.2016 | 10.06.2016 | 5%
5 | Durbal Nath Marg | 1.09 | 25.05.2016 | 10.06.2016 | 10%
6 | Raja Ram Marg | 0.89 | 25.05.2016 | 09.06.2016 | 2%
7 | H Block Dakshin Puri Road | 0.4 | 25.05.2016 | 09.06.2016 | 5%
8 | Firni Road | 1 | 25.05.2016 | 09.06.2016 | 2%
9 | West End Marg | 0.8 | 25.05.2016 | 09.06.2016 | 5%
10 | J Block Saket | 0.89 | 25.05.2016 | 09.06.2016 | 5%
11 | Old MB Road | 1 | 25.05.2016 | 10.06.2016 | 10% | Sh. Suresh Kumar 9899542920 | Sh. Sandeep Gupta 9560293030 | Sh. Narender Mahajan 9933331859
12 | Apeejay School Road (Gurudwara to J Block Road). | 0.3 | 25.05.2016 | 09.06.2016 | 5%
13 | 100 Foota Road Chattarpur | 1.4 | 25.05.2016 | 10.06.2016 | 2% | Dinesh Chandra 9654626313 | Sh. Mahendra Kumar Singh 9716312175 | Sh. Narender Mahajan 9933331859
14 | 60 Foota Road | 0.9 | 25.05.2016 | 09.06.2016 | 3%
15 | SSN Marg | 10.5 | 25.05.2016 | 10.06.2016 | 25%
16 | Gadai Pur Band Road | 3 | 25.05.2016 | 10.06.2016 | 10%
17 | Mandi Road | 8 | 10.05.2016 | 10.06.2016 | 70%
18 | Dera Bhati Road | 5.76 | 25.05.2016 | 10.06.2016 | 10%
19 | M.G. Road | 7.5 | 25.05.2016 | 10.06.2016 | 10%
20 | Aya Nagr Road | 0.6 | 25.05.2016 | 09.06.2016 | 2%
21 | Press Enclave (BRT to Saket Court) | 4 | 25.05.2016 | 10.06.2016 | 2% | Sh. Suresh Kumar 9899542920 | Sh. A.K. Sharma 9810576706 | Sh. Narender Mahajan 9933331859
22 | Family Court Road | 0.9 | 25.05.2016 | 09.06.2016 | 2%
23 | Pushp Vihar (Internal Road) | 4 | 25.05.2016 | 10.06.2016 | 2%
24 | H. Block Road | 1 | 25.05.2016 | 10.06.2016 | 2%
25 | Road in front of H.No. C-11 to C-20 Malviya Nagar | 0.11 | 25.05.2016 | 09.06.2016 | 25%
26 | Appjay School Road | 1.3 | 25.05.2016 | 10.06.2016 | 2% | Sh. Suresh Kumar 9899542920 | Sh. A.K. Sharma 9810576706 | Sh. Narender Mahajan 9933331859
27 | Shekh Sarai Phase-1 | 0.3 | 25.05.2016 | 09.06.2016 | 2%
28 | Khirki Road | 0.85 | 25.05.2016 | 09.06.2016 | 2%
29 | NBCC Plaza Road | 1.1 | 25.05.2016 | 10.06.2016 | 3%
30 | Birla Vidya Niketan | 1 | 25.05.2016 | 10.06.2016 | 2%
31 | Mandir Marg | 1.2 | 25.05.2016 | 10.06.2016 | 3%
32 | Pramod Mahajan Marg | 0.89 | 25.05.2016 | 09.06.2016 | 2%
33 | Main Road Sector-1, Pushp Vihar | 0.75 | 25.05.2016 | 09.06.2016 | 3%
34 | Pankaj Jewel Marg, Pushp Vihar | 1.1 | 25.05.2016 | 10.06.2016 | 5%
35 | Asian Market Road in Pushp Vihar | 0.45 | 25.05.2016 | 09.06.2016 | 2%
36 | Metro Enclave Road in Pushp Vihar | 0.45 | 25.05.2016 | 09.06.2016 | 4%
37 | Road between DDA Flat Masjid Moth Ph-II and Jahapanah Forest | 0.5 | 25.05.2016 | 09.06.2016 | 3%
38 | Road in front of Mother International School | 0.54 | 25.05.2016 | 10.06.2016 | 5%
DIVISION SOUTH ROAD-II
39 | August Kranti Marg. | 2.9 | 17.05.16 | 10.06.16 | 2% | Sh. Sanjeev Kumar 9873761123 | Sh. O.P. Rai 9868126611 | Sh. Jagdish Prasad 9560207879
40 | Balbir Saxena Marg | 0.8 | 17.05.16 | 09.06.2016 | 2%
41 | Ch. Dilip Singh Marg, P.S Hauz Khas | 0.6 | 17.05.16 | 09.06.2016 | 3%
42 | Mahinder Singh Jain Marg Road / Gautam Nagar Road | 1.2 | 17.05.16 | 10.06.16 | 3% | Sh. Sanjeev Kumar 9873761123 | Sh. O.P. Rai 9868126611 | Sh. Jagdish Prasad 9560207879
43 | P-Block Road from August Kranti Marg via jain Mandir & Dustbin to August Kranti Marg. | 0.34 | 17.05.16 | 09.06.2016 | 50%
44 | D-Block Road from H.No.D-27 to C-1, Ring Road ,NDSE-II | 0.3 | 17.05.16 | 09.06.2016 | 50%
45 | Sudarshan Cinema Road. | 0.72 | 17.05.16 | 09.06.2016 | 30%
46 | Gautam Nagar Road | 0.5 | 17.05.16 | 09.06.2016 | 30%
47 | August Kranti Marg to N-15 Panchsheel | 0.08 | 17.05.16 | 09.06.2016 | 2%
48 | Shivalik Road (Basant Kaur Marg) | 1.86 | 17.05.16 | 10.06.16 | 2%
49 | Guru Govind Singh Marg | 1.2 | 17.05.16 | 10.06.16 | 2%
50 | Siri Fort Road | 1.2 | 17.05.16 | 10.06.16 | 5%
51 | Road form Balbir Sxsena Marg to Ch. Dalip SinghMarg (NIFT Road), Hauz Khas | 0.6 | 17.05.16 | 09.06.2016 | 2%
52 | Road form August Kranti marg to Aurobindo Marg (Subash Chopra Road), Hauz Khas | 0.79 | 17.05.16 | 09.06.2016 | 2%
53 | Asiad Village peripheral road | 3 | 17.05.16 | 10.06.16 | 2%
54 | Sri Aurobindo Marg | 5 | 20.05.2016 | 10.06.16 | 5% | Sh. Shivendra Singh (7428188709) | Sh. R.K. Joshi 9868958324 | Sh. Jagdish Prasad 9560207879
55 | Outer Ring Road ( IIT Flyover to Jia Sarai) | 1.5 | 20.05.2016 | 10.06.16 | 3%
56 | Ch. Jhandu Singh Marg | 1.53 | 20.05.2016 | 10.06.16 | 3% | Sh. P.K. Meena (9013673061) | Sh. R.K. Joshi 9868958324 | Sh. Jagdish Prasad 9560207879
57 | Ch. Harsukh Marg | 1.83 | 20.05.2016 | 10.06.16 | 3%
58 | Ch. Hukum Chand Marg | 0.6 | 20.05.2016 | 10.06.16 | 3%
59 | Green Park Market Road | 1 | 20.05.2016 | 10.06.16 | 3%
60 | Shaheed Jeet Singh | 2.1 | 20.05.2016 | 10.06.16 | 3% | Sh. Shivendra Singh (7428188709) | Sh. R.K. Joshi 9868958324 | Sh. Jagdish Prasad 9560207879
61 | Road from B 15/7 to BSES Office,Q.I.A. | 0.3 | 20.05.2016 | 10.06.16 | 3% | Sh. Shivendra Singh (7428188709) | Sh. R.K. Joshi 9868958324 | Sh. Jagdish Prasad 9560207879
62 | Road from B 12 to IIM Qutub Institutional Area. | 0.1 | 20.05.2016 | 10.06.16 | 3%
63 | Peripheral Road of A Block of Q.I.A. | 0.41 | 20.05.2016 | 10.06.16 | 3%
64 | Road from USO House to FAI House Q.I.A. | 0.2 | 20.05.2016 | 10.06.16 | 3%
65 | Peripheral Road of C and B Block of Q.I.A. | 1.57 | 20.05.2016 | 10.06.16 | 3%
66 | Narender Kumar Pandey Marg | 1.16 | 20.05.2016 | 10.06.16 | 3% | Sh. P.K. Meena (9013673061) | Sh. R.K. Joshi 9868958324 | Sh. Jagdish Prasad 9560207879
67 | Hauz Khas Village | 0.9 | 20.05.2016 | 10.06.16 | 3%
68 | Ring Road | 2.1 | 20.05.2016 | 10.06.16 | 3%
69 | Anuvart Marg | 2.5 | 17.05.16 | 10.06.16 | 20% | Sh. Shivendra Singh (7428188709) | Sh. J. R. Meena 9910965798 | Sh. Jagdish Prasad 9560207879
70 | Aruna Asaf Ali Road | 3.5 | 17.05.16 | 10.06.16 | 5%
71 | Vedant Deshika Marg | 0.7 | 17.05.16 | 09.06.2016 | 2%
72 | Qutub Minar Round About | 1 | 17.05.16 | 10.06.16 | 5%
73 | B-1 Telephone Exchange Road,Vasant Kunj (Mahipalpur Road to B-5 & B-6 Road) | 0.6 | 17.05.16 | 09.06.2016 | 5%
74 | B-2 & B-3 Road, (Shiv Mandir to B-5 & B-6 Road) | 0.3 | 17.05.16 | 09.06.2016 | 5%
75 | Shiv Mandir to B-5 & B-6 Road) | 0.3 | 17.05.16 | 09.06.2016 | 5%
76 | D-1 & D-2 Road, Vasant Kunj | 0.24 | 17.05.16 | 09.06.2016 | 90%
77 | Sports Complex Road D-2,Vasant Kunj | 0.7 | 17.05.16 | 09.06.2016 | 90%
78 | Outer Ring Road (Chirag Delhi to IIT Gate) | 3.7 | 14.05.16 | 10.06.16 | 10% | --- | Sh. Surendra Kumar 9968227376 | Sh. Jagdish Prasad 9560207879
79 | S-Bend Road (Maharishi Dayanand Marg) | 1.8 | 14.05.16 | 10.06.16 | 5% | ---
80 | A-1 Block, Panchsheel Enclave Road | 0.5 | 14.05.16 | 09.06.2016 | 5% | ---
81 | B,C & D Block Panchsheel Enclave Road | 0.5 | 14.05.16 | 09.06.2016 | 5% | --- | Sh. Surendra Kumar 9968227376 | Sh. Jagdish Prasad 9560207879
CIRCLE SOUTH EAST (M)
EE/SER-I
1 | S. N. Puri Main Road From Cambridge School To CTC | 1.2 | 10.05.2016 | 10.06.2016 | 17% | Sh. K. Shree Dhar Mob. 9643839634 | Sh. Daulat Ram Mob. 9953116700 | Sh. Virendar Singh Mob. 9862284746
2 | Banglow Road To Gidwani Marg, Lajpat Nagar-4 | 0.12 | 10.05.2016 | 10.06.2016 | 20%
3 | S. N. Puri Internal Road Post Office to CPWD Via Jal Board Office | 0.15 | 10.05.2016 | 10.06.2016 | 18%
4 | S.N. Puri Internal Road Opp Police Post S.N. Puri | 0.12 | 10.05.2016 | 10.06.2016 | 15%
5 | S. N. Puri Internal Road MCD Store to round about Via Maternity Home | 0.63 | 10.05.2016 | 10.06.2016 | 20%
6 | Theka Road Sri Niwas Puri | 0.25 | 10.05.2016 | 10.06.2016 | 20%
7 | Dr. Moti Lal Jotwani Road, Lajpat Nagar-IV | 0.47 | 10.05.2016 | 10.06.2016 | 18%
8 | Central Road to Back of Ring Road, Lajpat Nagar-IV | 0.35 | 10.05.2016 | 10.06.2016 | 20%
9 | Kalka Devi Marg | 1.12 | 10.05.2016 | 10.06.2016 | 15%
10 | Kalka Devi Marg to Banglow Road, Lajpat Nagar-IV | 0.49 | 10.05.2016 | 10.06.2016 | 20%
11 | Road No. 4 Andrews Ganj | 0.4 | 10.05.2016 | 10.06.2016 | 20%
12 | Road No. 5 Andrews Ganj | 0.13 | 10.05.2016 | 10.06.2016 | 20%
13 | Road No. 7 Andrews Ganj | 0.24 | 10.05.2016 | 10.06.2016 | 16%
14 | Road No. 3 Andrews Ganj | 0.75 | 10.05.2016 | 10.06.2016 | 17%
15 | Raja Dheer Sain Marg EOK from Sant Nagar to East of Kailash | 0.57 | 10.05.2016 | 10.06.2016 | 20%
16 | Garhi Village to National Heart Hospital | 0.41 | 10.05.2016 | 10.06.2016 | 18%
17 | Raja Dheer Sain Marg | 0.14 | 10.05.2016 | 10.06.2016 | 15%
18 | Captain Gaur Marg | 2.15 | 10.05.2016 | 10.06.2016 | 20%
19 | Mathura Road (NH2) | 5.8 | 10.05.2016 | 10.06.2016 | 20% | Sh. Deepak Mob. 9968266846 | Sh. Sudarshan Kumar Mob. 9654097881 | Sh. Virendar Singh Mob. 9862284746
20 | C.V. Raman Marg | 2 | 10.05.2016 | 10.06.2016 | 18%
21 | Mata Mandir Road | 0.55 | 10.05.2016 | 10.06.2016 | 16%
22 | MMA Road | 3 | 10.05.2016 | 10.06.2016 | 20%
23 | M.P. Road | 1.35 | 10.05.2016 | 10.06.2016 | 20%
24 | Gurudwara Road | 1.8 | 10.05.2016 | 10.06.2016 | 17%
25 | Sukhdev Vihar Road | 1 | 10.05.2016 | 10.06.2016 | 20%
26 | Sujjan Mahendra Road | 0.66 | 10.05.2016 | 10.06.2016 | 18%
27 | Bhishma Pitamah Road | 2.3 | 10.05.2016 | 10.06.2016 | 15% | Sh. S.K. Singh Mob. 8882956012 | Sh. G.A.Khan Mob.7042417545 | Sh. Virendar Singh Mob. 9862284746
28 | Road from B.P.Marg to Round About Defence Colony | 0.156 | 10.05.2016 | 10.06.2016 | 20%
29 | Feroz Gandhi Road Lajpat Nagar | 1.05 | 10.05.2016 | 10.06.2016 | 20%
30 | Vir Savarkar Marg, Lajapat Nagar | 1.05 | 10.05.2016 | 10.06.2016 | 18%
31 | Shiv Mandir Marg from Zonal Office to Ring Road | 0.85 | 10.05.2016 | 10.06.2016 | 20%
32 | Josif Broz Tito Marg (B.R.T.) | 1.05 | 10.05.2016 | 10.06.2016 | 18%
33 | AIIMS to Bhairon Road 'T' Jn | 2.5 | 10.05.2016 | 10.06.2016 | 18%
34 | 2 nd Enty Road | 0.6 | 10.05.2016 | 10.06.2016 | 18%
35 | Bhairon Road | 0.98 | 10.05.2016 | 10.06.2016 | 18%
36 | Mathura Road | 3.25 | 10.05.2016 | 10.06.2016 | 18% | Sh. Greesh Sharma Mob. 9643347312 | Sh. V.K. Sani Mob. 9968876462 | Sh. Virendar Singh Mob. 9862284746
37 | F-1 Lodhi colony to BP Flyover | 0.35 | 10.05.2016 | 10.06.2016 | 16%
38 | East Nizamuddin Peripheral road | 0.7 | 10.05.2016 | 10.06.2016 | 17%
39 | BP Marg to Coffee House, Lodhi colony | 0.35 | 10.05.2016 | 10.06.2016 | 19%
40 | Hanuman Mandir to Seva Nagar flyover | 0.46 | 10.05.2016 | 10.06.2016 | 19%
41 | Hospital Road | 0.56 | 10.05.2016 | 10.06.2016 | 16%
42 | Kushak Nallah to CPWD Enquiry | 0.7 | 10.05.2016 | 10.06.2016 | 18%
43 | IV Avenue Road | 1.22 | 10.05.2016 | 10.06.2016 | 20%
44 | Kushak Nallah to Seva nagar flyover | 0.7 | 10.05.2016 | 10.06.2016 | 20%
45 | Neela gumbad to Lodhi flyover, Nazamuddin basti | 0.2 | 10.05.2016 | 10.06.2016 | 15% | Sh. Greesh Sharma Mob. 9643347312 | Sh. V.K. Sani Mob. 9968876462 | Sh. Virendar Singh Mob. 9862284746
46 | Railway phatak to subhash bazar | 0.258 | 10.05.2016 | 10.06.2016 | 18%
47 | Preet place to Nizmuddin railway station | 0.7 | 10.05.2016 | 10.06.2016 | 16%
48 | Rajdoot Hotel to Preet palace | 0.2 | 10.05.2016 | 10.06.2016 | 16%
49 | Ratan Lal Sahdev Marg | 0.978 | 10.05.2016 | 10.06.2016 | 16%
50 | School Road | 0.38 | 10.05.2016 | 10.06.2016 | 20%
51 | Sunder Nagar peripheral Road | 1.1 | 10.05.2016 | 10.06.2016 | 18%
52 | V Avenue Road | 1 | 10.05.2016 | 10.06.2016 | 18%
53 | Vardhman Marg | 0.35 | 10.05.2016 | 10.06.2016 | 16%
54 | X-Road between Block no-18 & 15 Lodhi colony | 0.16 | 10.05.2016 | 10.06.2016 | 20%
55 | X-Road between C-2(176) &C-2(177)Lodhi Colony | 0.16 | 10.05.2016 | 10.06.2016 | 20%
56 | X-Road between D-1 & C-2 Lodhi Colony | 0.16 | 10.05.2016 | 10.06.2016 | 16%
57 | Lodhi Road | 1.22 | 10.05.2016 | 10.06.2016 | 15%
EE/SER-II
1 | SA Road (including service road) | 5.4 | 10.05.2016 | 09.06.16 | 12% | Abhishek Kumar 9971547245 | N.R.Meena 880364667 | Sh. R.S. Garg Mob. 9818656184
2 | Road No. 13 | 1.35 | 10.05.2016 | 10.06.16 | 12%
3 | EPDP | 1.7 | 10.05.2016 | 10.06.16 | 14%
4 | Maharaja Agarsain Marg | 0.8 | 10.05.2016 | 10.06.16 | 12%
5 | Baba Fateh Singh |  | 10.05.2016 | 08.06.16 | 18%
6 | Hans Raj Sethi Marg | 1.7 | 10.05.2016 | 08.06.16 | 12%
7 | A Block Double Storey (EPDP to Hans Raj Sethi Marg) | 1.7 | 10.05.2016 | 09.06.16 | 14%
8 | Jaitpur Road (Shaheed Bijender Singh Gurjar Marg) | 1.25 | 10.05.2016 | 10.06.16 | 12% | Harbir Singh 9718139610 | Shiv Kumar 9650747902 | Sh. R.S. Garg Mob. 9818656184
9 | Jaitpur Road - Meethapur Chowk to Gurudwara | 1.21 | 10.05.2016 | 08.06.16 | 18%
10 | Higher Secondary School Road - Meethapur | 0.87 | 10.05.2016 | 08.06.16 | 16%
11 | Maharaja Agarsain Marg | 0.8 | 10.05.2016 | 10.06.16 | 14% | Harbir Singh 9718139610 | Shiv Kumar 9650747902 | Sh. R.S. Garg Mob. 9818656184
12 | Madanpur Khadar Road | 1.2 | 10.05.2016 | 08.06.16 | 12%
13 | Sarita Vihar Road | 1.35 | 10.05.2016 | 10.06.16 | 14%
14 | Road No.13A | 3.2 | 10.05.2016 | 30.05.16 | 16%
15 | NH-2 Mathura Road | 5.8 | 10.05.2016 | 08.06.16 | 15%
16 | Guru Nanak Market to Lala Lajpat Rai Marg | 0.57 | 10.05.2016 | 09.06.16 | 15% | Sachin Singhal 9650315678 | Ram Kirti 9873775445 | Sh. R.S. Garg Mob. 9818656184
17 | Nandi Vithi Marg | 0.73 | 10.05.2016 | 10.06.16 | 15%
18 | Link Road | 0.58 | 10.05.2016 | 10.06.16 | 16%
19 | Road From BRT to Hansraj Gupta Marg. | 0.34 | 10.05.2016 | 05.06.16 | 18%
20 | Hans Raj Gupta Marg | 0.33 | New Drain
21 | Lala Lajpat Rai Marg | 0.57 | 10.05.2016 | 10.06.16 | 12%
22 | Guru Harkishan Public School to Nehru Place | 0.27 | 10.05.2016 | 07.06.16 | 12%
23 | R-Block GK-1, Signal to Outer Ring Road | 0.58 | 10.05.2016 | 10.06.16 | 14%
24 | Outer Ring Road | 3.8 | 10.05.2016 | 30.05.16 | 15%
25 | Road From B-76 to B-111 (G.K-I) | 0.33 | 10.05.2016 | 08.06.16 | 14%
26 | Police Station CR Park to Vipin Chander Pal | 0.12 | No Drain
27 | Kal Mandir Road | 1.12 | New Drain |  | 16%
28 | Savitri Cinema Road | 3.14 | 10.05.2016 | 09.06.16 | 16%
29 | Gurudwara Road G.K.II | 1.8 | 10.05.2016 | 09.06.16 | 15%
30 | Surya Sen Marg | 0.6 | 10.05.2016 | 10.06.16 | 16%
31 | Market No.2 Desh Bandhu Apartment. | 0.37 | No Drain
32 | Vipin Chander Pal Marg | 0.75 | 10.05.2016 | 09.06.16 | 18%
33 | MB Road | 5.4 | 10.05.2016 | 10.06.16 | 14% | Pranay Rathor 9968923572 | Rakesh Kumar 9711772289 | Sh. R.S. Garg Mob. 9818656184
34 | Ravi Das Marg | 3.8 | 10.05.2016 | 08.06.16 | 16%
35 | DDA Market | 0.5 | 10.05.2016 | 10.06.16 | 15%
36 | KPS Marg | 0.5 | 10.05.2016 | 10.06.16 | 14%
37 | Suraj Kund Road | 0.6 | 10.05.2016 | 10.06.16 | 15% | Pranay Rathor 9968923572 | Rakesh Kumar 9711772289 | Sh. R.S. Garg Mob. 9818656184
DESILTING UNDER PWD MAINTENANCE ZONE EAST AS ON 27.05.2016
Circle/Div. :- (North East) Road M/ Division M-213
Sl. No. | Name of Roads | Length (inKm) | Date of Start | Date of Completion | % Progress | JE in charge / Mobile No. | AE in charge / Mobile No. | EE in charge / Mobile No.
1 | Road No. 66 | 3.8 | 31.01.2016 | 30.05.2016 | 90% | Sh. G.S. Mishra 9871530741 | Sh. Virender Kumar 9205135595 | Sh. K.P.Singh 9810438957
2 | Road No. 59 (Rd 3450m to 6450m) | 3 | Not Required
3 | Garhi Mendu Road | 4.685 | Not Required
4 | Gamri Road | 1.05 | 07.011.2015 | 30.05.2016 | 85%
5 | Main Road Maujpur | 0.999 | 07.011.2015 | 30.05.2016 | 40%
6 | Main Brahmpuri Road | 1.62 | 07.011.2015 | 15.06.2016 | 80%
7 | Loni Road Wazirabad Road to U.P. Border | 0.5 | 01.03.2016 | 29.04.2016 | 100% | Sh. Sanjeev Kumar 9716311561 | Sh. Virender Kumar 9205135595 | Sh. K.P.Singh 9810438957
8 | Road No. 59 ( Rd 0m to 3450m) | 3.45 | 28.04.2016 | 15.06.2016 | 55%
9 | Dividing road from Wazirabad Road red light to DTC Depot near H. No. B-5/18, Yamuna Vihar, Delhi | 0.5 | 28.04.2016 | 15.06.2016 | 100%
10 | Gokulpuri Main Road | 0.246 | Newly Contructed Drain
11 | Main Road Noor –E-Illahi Road | 0.98 | 28.04.2016 | 15.06.2016 | 100%
12 | Yamuna Vihar Road (C-1 To C-4) | 1.1 | 28.04.2016 | 15.06.2016 | 50%
13 | Tanki road to Mobin Chowk | 0.3 | 07.01.2015 | 04.05.2016 | 100%
14 | Road No. 63 | 3.18 | 19.02.2016 | 30.06.2016 | 90%
15 | Sewadham Road | 2.45 | 19.02.2016 | 30.06.2016 | 80%
16 | Bank Colony Road along western Side of Mandoli Jail Complex | 0.337 | Newly Contructed Drain
17 | Road No. 62 (Road No. 70 to Apsara Border) | 1200 | 28.01.2016 | 30.05.2016 | 90% | Sh. N.K Gupta 9810239349 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
18 | Road No. 70 (Seemapuri to Tahir Pur T-Point) | 1200 | 24.02.2016 | 22.06.2016 | 35%
19 | GTB Road (From Road No. 64 to Road No. 68) | 910 | 24.02.2016 | 22.06.2016 | 65%
20 | Seemapuri Road from Road No. 62 to 64 | 1065 | 24.02.2016 | 22.06.2016 | 55%
21 | LIC Road (from Malaria office MCD to GT Road) | 330 | 24.02.2016 | 22.06.2016 | 65%
22 | Road along Divider road to pummy sweet at Gurudwara road) | 360 | 24.02.2016 | 22.06.2016 | 65%
23 | Gurudwara Road from DTC bus depot Road No. 70 to GTB Hospital road | 1750 | 24.02.2016 | 22.06.2016 | 35%
24 | Road infront of Hans Raj Public School (Divider Road to Gurudwara road) | 365 | 24.02.2016 | 22.06.2016 | 45%
25 | Road from T-point, L-pocket to R Block small rotary | 860 | 24.02.2016 | 22.06.2016 | 35%
26 | GTB Hospital Road (From GT Road to Aggarwal Sweet Dilshad Garden) | 600 | 24.02.2016 | 22.06.2016 | 75%
27 | R-Block Road (From Divider road Agarwal sweet to GT Road) | 500 | 24.02.2016 | 22.06.2016 | 65%
28 | Road No. 62 (J & K pocket) to petrol pump GT Road (infront of Red Crosss society). | 330 | 24.02.2016 | 22.06.2016 | 65%
29 | Road from Gurudwara road (T-point of Kalander Colony) to Gauri Shankar Mandir | 310 | 24.02.2016 | 22.06.2016 | 45%
30 | Road from Divider Road (Mukherjee Public School to Sant Ram Public School at Gurudwara road) | 360 | 24.02.2016 | 22.06.2016 | 65%
31 | New Seemapuri Road from Road No. 64 (Mother Dairy) to Road No. 62 near maszid | 1160 | 24.02.2016 | 22.06.2016 | 65% | Sh. N.K Gupta 9810239349 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
32 | Road from LIC Colony (T-Point to rotary at Telephone Exchange) | 935 | 24.02.2016 | 22.06.2016 | 45%
33 | Road No. 64 Swami Dayanand Hospital to DLF More (U.P. Border) | 3000 | 24.02.2016 | 22.06.2016 | 75% | Sh. Deepak Kumar Shrivastava 9899601254 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
34 | Mandoli Road (From Loni Road to Nand Nagri Railway crossing) | 1942 | 24.02.2016 | 22.06.2016 | 75%
35 | Divider Road from Seemapuri road to Road No. 64 (near SDN Hospital) | 2400 | 24.02.2016 | 22.06.2016 | 65%
36 | CNG Petrol Pump to deer park (Divider road) west side | 200 | 24.02.2016 | 22.06.2016 | 25%
37 | CNG Petrol Pump to deer park (Divider road) east side | 197 | 24.02.2016 | 22.06.2016 | 55%
38 | From Rajiv Gandhi super hospital specialty hospital to GTB hospital road | 950 | 24.02.2016 | 22.06.2016 | 45%
39 | GTB Hospital road from Red light to Agarwal sweet (Divider road) | 195 | 24.02.2016 | 22.06.2016 | 90%
40 | Road from GT Road to Road No. 64 via Telephone exchange | 415 | 24.02.2016 | 22.06.2016 | 65%
41 | From Road No. 68 (petrol pump) to E-pocket GTB enclave police booth near Nutan Vidya Mandir public school | 375 | 24.02.2016 | 22.06.2016 | 70%
42 | From Road No. 69 MIG Flat to GTB Hospital Road Via Nutan Vidya Mandir public school | 900 | 24.02.2016 | 22.06.2016 | 90%
43 | Road along khel parisor from NVM school to Green field public school. | 250 | 24.02.2016 | 22.06.2016 | 55%
44 | Road from General Hospital (Road No. 64 to Shahdara Flyover) | 260 | 24.02.2016 | 22.06.2016 | 45%
45 | Road No. 68 (Road No. 69 to Road No. 66) | 3.4 | 17.02.2016 | 14.08.2016 | 35% | Sh. Rahul Vashistha 9560599842 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
46 | Loni Road G.T. Road to Loni Gole Chakkar | 2.894 | 22.01.2016 | 22.06.2016 | 35% | Sh. Rahul Vashistha 9560599842 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
47 | Road No. 65 | 1.2 | 22.01.2016 | 22.06.2016 | 25%
48 | Road No. 69 | 1.25 | 20.02.2016 | 18.08.2016 | 50%
49 | Tanga Stand Road from road no. 68 to Wazirabad Road. | 1.35 | 20.02.2016 | 18.08.2016 | 70%
50 | Babarpur Road (From Road No.66 to G.T. Road) | 2 | 15.05.2016 | 18.08.2016 | 0%
51 | Main Road LIG Flats, East of Loni Road from Loni Road to community centre Ashok Nagar. | 0.375 | 20.02.2016 | 18.08.2016 | 15%
52 | Main Road LIG flats, Loni Road to Govt. S.S. School Ashok Nagar. | 0.275 | 15.05.2016 | 18.08.2016 | 0%
53 | Captain javed Ali Marg |  | 15.05.2016 | 18.08.2016 | 0%
54 | Shastri Park To Khajuri Chowk | 3.75 | 01.03.2016 | 30.06.2016 | 55% | Sh. Hanuman Prasad Meena 9810309474 | Sh. Pawan Kumar Agarwal 9911230121 | Sh. K.P.Singh 9810438957
55 | E.A. Road | 4.2 | 01.03.2016 | 30.06.2016 | 45% | Sh. Manoj Kasana 9650094555 | Sh. Pawan Kumar Agarwal 9911230121 | Sh. K.P.Singh 9810438957
56 | Seelmapur Road from Road No. 66 to Dhalav. | 0.517 | 29.03.2016 | 30.05.2016 | 85%
57 | G.T. Road Old Yamuna bridge to Y Point | 0.9 | 29.03.2016 | 30.05.2016 | 85%
58 | Zero Pusta to Bharampuri culvert | 0.99 | 29.03.2016 | 15.06.2016 | 80%
Desilting Report (Preparedness for Monsoon) of Div. EE (SHAHDARA) ROADS/M-211
1 | Road No.56 | 5.6 | 01.02.2016 | 29.06.2016 | 50% | ShriAmarjeet Solin 9555268645 | Shri A.S. Yadav 9350677427 | Shri S.K. Modi 9868207966
2 | Road No.71 | 1.6 | 01.02.2016 | 29.06.2016 | 45%
3 | Road No. 71 A | 0.6 | 01.02.2016 | 29.06.2016 | 45%
4 | Road No. 72 | 0.91 | 01.02.2016 | 29.06.2016 | 45% | Shri Jitendra kirad 9818961231 | Shri Suresh Chand 9868700938 | Shri S.K. Modi 9868207966
5 | Road No. 72 Extension | 1 | 01.02.2016 | 29.06.2016 | 45%
6 | Road No.58 | 2.84 | 01.02.2016 | 29.06.2016 | 45%
7 | Road No.58 A | 1.6 | 01.02.2016 | 29.06.2016 | 45%
8 | Zonal office Road | 1.03 | 01.02.2016 | 29.06.2016 | 45%
9 | Surajmal Vihar Road | 1.2 | 01.02.2016 | 29.06.2016 | 45%
10 | Shrestha Vihar Road | 1.25 | 01.02.2016 | 29.06.2016 | 45%
11 | Shiva Khand Road | 0.9 | 01.02.2016 | 29.06.2016 | 45%
12 | ITI Vivek Vihar Road | 1.4 | 01.02.2016 | 29.06.2016 | 45%
13 | Ram Mnadir Road Via ITI Vivek Vihar | 1.35 | 01.02.2016 | 29.06.2016 | 45%
14 | Link Road from G.T. Road ITI Vivek Viahr | 0.6 | 01.02.2016 | 29.06.2016 | 45%
15 | Road No. 57 | 5.52 | 01.02.2016 | 29.06.2016 | 45% | Shri A.K. Singh 98102550998 | Shri Vinod Kumar Goyal 9868355695 | Shri S.K. Modi 9868207966
16 | Road No. 75 B Extn. | 2.13 | 01.02.2016 | 29.06.2016 | 45%
17 | Vishwas Nagar Road | 1.17 | 01.02.2016 | 29.06.2016 | 45%
18 | Shahdara Road | 0.6 | 01.02.2016 | 29.06.2016 | 35%
19 | Bhola Nath Nagar Road | 0.6 | 01.02.2016 | 29.06.2016 | 45%
20 | G.T. Road | 6.35 | 01.02.2016 | 29.06.2016 | 35%
21 | Gandhi Nagar Road | 1.5 | 01.02.2016 | 29.06.2016 | 40%
Desilting Report (Preparedness for Monsoon) for Zone East-M (M-212)
Name of MLA :- Sh. Manoj Kumar
Name of Constituency :- Kondli AC (56)
Circle/Div. :- East-M/East Road (M-212)
1 | Road from Live stock market to Gali No. 7 Block - C in Ghazipur Dairy Farm. | 0.8 | 15.05.16 | 29.06.16 | 0% | Mohd. Mustaqueem/ 9560834310 | Sh. S.K.Gupta/ 8447748410 | Sh. Iqbal Singh 9910925748
2 | Road from NH-24 to Hindon cut near Ghazipur Slaughter House. | 0.5 | 16.05.16 | 30.06.16 | 0%
3 | NH-24 Ghazipur to Kondli Bridge. | 1.5 | 14.05.16 | 29.06.16 | 0%
4 | Dharamshilla Road | 0.6 | 15.05.16 | 29.06.16 | 0% | Sh. P.K. Singh/ 9968334248 Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. Y.P. Singh/ 9910554287 | Sh. Iqbal Singh/ 9910925748
5 | Saheed Budh Singh Marg | 0.28 | 16.05.16 | 30.06.16 | 0%
6 | Dallupura Road | 1.25 | 16.05.16 | 30.06.16 | 0%
7 | M.P. Road No. 102 | 2.2 | 16.05.16 | 30.06.16 | 0%
8 | M.P Road No. 108 | 1.33 | 15.05.16 | 29.06.16 | 0%
9 | M.P Road 109 | 0.81 | 15.05.16 | 29.06.16 | 0%
10 | Road from Kondli Village up Gharoli Village X-ing. | 0.75 | 15.05.16 | 29.06.16 | 0%
11 | Road along Shiv Mandir in Gharoli Dairy Farm 'B' Block. | 0.66 | 15.05.16 | 29.06.16 | 0%
12 | EWS Flats to DDA Market Mayur Vihar Ph.-III X-ing upto Agarwal Sweet Shop. | 0.66 | 15.05.16 | 29.06.16 | 0%
13 | Main road between A & B Block New Kondli. | 0.35 | 15.05.16 | 29.06.16 | 0%
14 | Road from High land Apptt. To Soochna Apptt. In Vasundhara Enclave. | 0.4 | 15.05.16 | 29.06.16 | 0%
15 | Road from Manav Ashray Apptt. To Hindon Apptt. In Vasundhara Enclave | 0.48 | 14.05.16 | 29.06.16 | 0%
16 | Road from Dashmesh Public School to Delux Apptt. Via Mahesh Apptt. In Vasundhara Enclave. | 0.75 | 14.05.16 | 29.06.16 | 0%
17 | Bhagvan Mahavir Swami Marg. | 0.8 | 15.05.16 | 29.06.16 | 0% | Sh. P.K. Singh/ 9968334248 Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. Y.P. Singh/ 9910554287 | Sh. Iqbal Singh/ 9910925748
18 | Sameer Bhan Marg | 0.825 | 15.05.16 | 29.06.16 | 0%
19 | Road from Cell Apartment to Angel Public School in Vasundhara Enclave. | 0.2 | 16.05.16 | 30.06.16 | 0%
20 | Road from Dainik Janyug Apartment to Hindon Apartment (Budh Singh Marg). | 0.5 | 16.05.16 | 30.06.16 | 0%
21 | From Kondli Bridge to Porta Cabin MCD Primary School. | 0.85 | 16.05.16 | 30.06.16 | 0%
22 | Road between Pocket A-1 & A-2 Mayur Vihar Ph-III (Gurudwara Road) | 0.26 | 16.05.16 | 30.06.16 | 0%
23 | Road between Block No. 12 and 13 from Khichripur Chowk to Kalyanvas Road. | 0.75 | 10.05.16 | 10.06.16 | 0% | Sh. Amit Singhal/ 9971032115 | Sh. H.C. Bhatt/ 9990601811 | Sh. Iqbal Singh/ 9910925748
24 | Road between Block No. 11-15 from Block-15 to LBS Hospital through Jalebi Chowk, Kalyanpuri. | 0.67 | 10.05.16 | 10.06.16 | 0%
25 | Road from between Block No. 2 & 3 upto Khichripur Main Road. | 0.3 | 10.05.16 | 10.06.16 | 0%
26 | Khichripur road from Kondli Bridge to Mother Dairy. | 1 | 15.05.16 | 30.06.16 | 0% | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9818085772 | Sh. Iqbal Singh/ 9910925748
Name of MLA :- Sh. Raju Dhingan |  |  |  |  | 0%
Name of Constituency :- Trilokpuri AC (55) |  |  |  |  | 0%
27 | Kotla Road from Trilok Puri Police Station to Khichirpur Bus Stand. | 3 | 03.05.16 | 30.05.16 | 15% | Sh. Amit Singhal/ 9971032115 | Sh. H.C. Bhatt/ 9990601811 | Sh. Iqbal Singh/ 9910925748
28 | East end apartment road. | 0.84 | 16.05.16 | 30.06.16 | 0% | Sh. P.K. Singh/ 9968334248 Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. Y.P. Singh/ 9910554287 | Sh. Iqbal Singh/ 9910925748
29 | Road along Ghazipur Drain | 3.6 | 15.05.16 | 30.06.16 | 0% | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748
30 | Peripherial road from Chilla Chowk to kotla Village. | 1.25 | 15.05.16 | 10.06.16 | 0%
31 | Road from Block No. 35 to 17 Trilokpuri (Mahrishi Balmiki Marg) | 1.07 | 17.05.16 | 10.06.16 | 0%
32 | Road from Block No. 19 to Block No. 13 Trilokpuri | 1.54 | 18.05.16 | 15.06.16 | 0%
33 | Main road from Block No. 33 to Block No. 19. Trilokpuri | 0.52 | 17.05.16 | 10.06.16 | 0%
34 | Road from Block No. 36 to Block No. 31 Trilokpuri. | 0.99 | 18.05.16 | 17.06.16 | 0%
35 | Ambedkar Marg from Block No. 18 Trilokpuri to Kotla Road. | 0.95 | 19.05.16 | 10.06.16 | 0%
36 | Subhash Mkt. from Chand Cinema Turn to Balvikas School | 0.6 | 20.05.16 | 10.06.16 | 0%
37 | Road from Block No. (1) to (11) of Trilokpuri | 0.98 | 20.05.16 | 11.06.16 | 0%
38 | Chilla road from Chilla chowk to Chilla Village. | 0.9 | 21.05.16 | 12.06.16 | 0%
Name of MLA :- Sh. Manish Sisodia |  |  |  |  | 0%
Name of Constituency :- Patparganj (57) |  |  |  |  | 0%
39 | Road No.111 from the Club Avenue to Road along Ghazipur drain. | 0.25 | 21.05.16 | 12.06.16 | 0% | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748
40 | Sadhabhawana marg (111) | 0.5 | 21.05.16 | 12.06.16 | 0%
41 | Club Avenue Marg (112) | 0.45 | 22.05.16 | 13.06.16 | 0% | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748
42 | Sehkarita Marg (113) | 0.65 | 23.05.16 | 15.06.16 | 0%
43 | ASN School to Parwana Apartment to Kala Apartment upto LSC. | 0.8 | 23.05.16 | 15.06.16 | 0%
44 | Samachar Apartment Road (Link Road) Samachar Apartment to Glaxo Apartment. | 0.35 | 23.05.16 | 15.06.16 | 0%
45 | Road from Block No. 1 Khichripur to NH-24. | 0.85 | 16.05.16 | 30.06.16 | 0% | Mohd. Mustaqueem/ 9560834310 | Sh. S.K.Gupta/ 8447748410 | Sh. Iqbal Singh 9910925748
46 | Khichripur Main Road from NH-24 to Mother Dairy. | 0.8 | 16.05.16 | 30.06.16 | 0%
47 | Patparganj Main Road from NH-24 to Patparganj Village. | 0.3 | 16.05.16 | 30.06.16 | 0%
48 | Road between Pocket E & F Mayur Vihar Ph-II. | 0.6 | 16.05.16 | 30.06.16 | 0%
Name of Constituency :- Patparganj (57) |  |  |  |  | 0%
49 | Sai Chowk | 0.67 | 15.05.16 | 30.06.16 | 0% | Sh.Sajjan Saxena 9811840260 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
50 | Kailash Apartment. | 0.354 | 16.05.16 | 30.06.2016 | 0%
51 | Bathla Apartment | 0.328 | 15.05.16 | 30.06.16 | 0%
52 | Gagan Vihar. | 0.4 | 15.05.16 | 30.06.16 | 0%
53 | Agarsain Apartment | 0.61 | 15.05.16 | 30.06.16 | 0%
54 | Mother Dairy Road (Narwana Road) | 2.5 | 16.05.16 | 30.06.2016 | 0%
55 | Mother Dairy Road | 1.5 | 16.05.16 | 30.06.2016 | 0%
56 | Madhu Vihar Road | 1.6 | 16.05.16 | 30.06.2016 | 0%
57 | Balco Market | 0.63 | 15.05.16 | 30.06.16 | 0%
58 | Prince Apartment | 0.59 | 15.05.16 | 30.06.16 | 0%
59 | Oriental Apartment | 0.334 | 15.05.16 | 30.06.16 | 0%
60 | Narwana Apartment | 0.46 | 16.05.16 | 30.06.2016 | 0% | Sh.Sajjan Saxena 9811840260 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
61 | Trilokia Apartment | 0.38 | 15.05.16 | 30.06.16 | 0%
62 | Rama Krishna Apartment | 0.27 | 15.05.16 | 30.06.16 | 0%
63 | Disused canal road (Main Drain with EDMC) | 2.9 | 15.05.16 | 30.06.16 | 0%
64 | New Rajdhani Road | 0.79 | 16.05.16 | 30.06.2016 | 0%
65 | Chitra Vihar Road | 0.69 | 16.05.16 | 30.06.2016 | 0%
66 | Patparganj Road | 2.89 | 05.04.16 | 15.05.16 | 69%
67 | Road No. 57 A (Handed over to DMRC) | 1.13 | 15.05.16 | 30.06.16 | 0%
68 | Vikas Marg (Road No. 75 A & 75 B | 3.14 | 15.04.16 | 15.05.16 | 69%
69 | Patpargunj Road (Preet Vihar) | 1.47 | 15.05.16 | 15.06.16 | 0%
70 | Vikas Marg (Sachivalaya Crossing to ITO Chungi) | 2.2 | 05.05.16 | 30.06.2016 | 0% | Sh. Amit Singhal 9971032115 | Sh. Harish Bhatt 9990601811 | Sh. Iqbal Singh 9910925748
71 | Marginal Bund Road (ITO Chungi to Kailash Nagar) | 4 | 05.05.16 | 30.06.2016 | 0%
72 | Marginal Bund Road (Vikas Marg to NH-24) | 2.75 | 05.05.16 | 30.06.2016 | 0%
73 | Geeta Colony Yamuna Bridge Road | 2.1 | 05.05.16 | 30.06.2016 | 0%
Premonsoon Progress Report For Desilting Work Under PWD SRDP/SD-I
If Agency will provide 3 nos. Super Sucker Machine daily and 60 (3 Gangs 20 nos each) nos. Sewerman daily than desilting work will completed as per schedule.
SRD Project Division, Sub Divn-I
A | Box/Pipe road storm water drain
1 | D.D.U. Marg | 1.98 |  | 05.06.2016 | 0% | Er. Devendra Kumar (Mob. 9953751732) | Er. S.N. Moitra (Mob 9968310379) | Er. Rajiv Lochan 9911058852
2 | Mirdard Road | 0.55 | 22.05.2016 | 25.05.2016 | 0%
3 | Vishnu Digamber Road | 0.32 | 22.05.2016 | 23.05.2016 | 0%
4 | Rajneet Sing Road | 0.45 | 24.05.2016 | 2.05.2016 | 0%
5 | Thomson Road | 0.75 | 25.05.2016 | 27.05.2016 | 0% | Er. Devendra Kumar (Mob. 9953751732) | Er. S.N. Moitra (Mob 9968310379) | Er. Rajiv Lochan 9911058852
6 | Minto Road | 0.7 |  | 08.06.2016 | 0%
7 | Mahawat Khan Road | 0.7 |  | 11.06.2016 | 0%
8 | Barron Road | 0.28 |  | 13.06.2016 | 0%
9 | JLN Marg | 1.86 | 28.05.2016 | 02.06.2016 | 0%
10 | Kotla Road | 1.48 | 03.06.2016 | 07.06.2016 | 0%
11 | Mata Sundri Road | 1.1 | 08.06.2016 | 11.06.2016 | 0%
12 | CNG Crematorium Road | 0.25 |  | 02.06.2016 | 0% | Er. Akhilesh Sharma (Mob. 9953840809)
13 | Turkman Road | 0.6 |  | 27.05.2016 | 0%
14 | Chaman Lal Marg | 0.18 | 23.05.2016 | 23.05.2016 | 0%
15 | S.P.M. Marg | 1.48 | 24.05.2016 | 01.06.2016 | 0%
16 | HC SEN ROAD | 0.4 |  | 05.06.2016 | 0%
17 | KHARI BAWALI ROAD | 0.427 | 02.06.2016 | 07.06.2016 | 0%
18 | ESPLANADE ROAD | 0.43 |  | 20.05.2016 | 90%
19 | NAYA BAZAR ROAD | 0.58 |  | 25.05.2016 | 0%
20 | Zorawar Singh Marg | 1.32 |  | .3.06.2016 | 0%
21 | Mori gate road | 0.38 | 31.05.2016 | 31.05.2016 | 0%
22 | Kela Ghat | 0.175 | 08.06.2016 | 08.06.2016 | 0%
23 | DEWAN HALL ROAD | 0.27 | 09.06.2016 | 10.06.2016 | 0%
24 | NS MARG | 2.22 | 16.05.2016 | 30.05.2016 | 15%
25 | Asaf Ali Road | 1.9 | 23.05.2016 | 30.05.2016 | 0%
26 | Ring Road | 2 |  | 15.06.2016 | 0%
27 | Mahatma Gandhi Road | 4 |  | 05.06.2016 | 30%
28 | Ring Road By-pass | 5.55 | No Drain |  | 0% | Er. Gaurav Sankhwar (Mob. 8447973170) | Er. S.N. Moitra (Mob 9968310379) | Er. Rajiv Lochan (Mob. 9911058852)
29 | Court Road | 1.75 |  | 11.06.2016 | 0%
30 | Club Road | 1.75 | 23.05.2016 | 30.05.2016 | 0%
31 | Lothian Road | 0.925 | 22.05.2016 | 25.05.2016 | 0%
32 | Sarai Phoose Road | 0.71 | 26.05.2016 | 29.05.2016 | 0%
33 | Magazine Road | 1.35 | 30.05.2016 | 04.06.2016 | 0%
34 | Road No.-46 | 0.3 | 05.06.2016 | 06.06.2016 | 0%
35 | Road: Road No.-45 | 2.5 |  | 20.06.2016 | 0%
36 | Under Hill Road | 0.69 | 07.06.2016 | 10.06.2016 | 0%
37 | Flag Staff Road | 0.425 | 11.06.2016 | 13.06.2016 | 100% | Er. Gaurav Sankhwar (Mob. 8447973170) | Er. S.N. Moitra (Mob 9968310379) | Er. Rajiv Lochan (Mob. 9911058852)
38 | Shamnath Marg | 1.3 | 14.06.2016 | 17.06.2016 | 0%
39 | Gokhle Road | 0.876 | 18.06.2016 | 20.06.2016 | 0%
40 | Hamilton Road | 0.24 | 13.06.2016 | 14.06.2016 | 0%
41 | Aproach Road | 0.215 | 15.06.2016 | 15.06.2016 | 0%
42 | Aproach Road | 0.25 | 16.06.2016 | 16.06.2016 | 0%
43 | Rajpur Road | 2.565 | 17.06.2016 | 20.06.2016 | 0%
44 | Rajniwas Marg | 0.926 | 12.06.2016 | 16.06.2016 | 0%
45 | Road No.-47 | 1.04 | 14.06.2016 | 20.06.2016 | 0%
SRD Project Division, Sub Divn-II
1 | Panchkuiya Road | 1.28 |  | 30.05.2016 | 0% | Er. Sunil Kumar Kataria (Mob. 9958068748) | Er. Santosh Dutta (Mob 9213765200) | Er. Rajiv Lochan (Mob. 9911058852)
2 | Nehru Bazar Road | 0.45 |  | 30.05.2016 | 0%
3 | DAV Aram Bagh Road | 0.46 | 22.05.2016 | 01.06.2016 | 0%
4 | Basant Road | 0.77 |  | 30.05.2016 | 0%
5 | Main Bazar Road | 0.95 | 22.05.2016 | 01.06.2016 | 0%
6 | Chitra Gupta Road | 0.68 |  | 30.05.2016 | 0%
7 | CGHS Dispansary Road | 0.23 | 22.05.2016 | 01.06.2016 | 0%
8 | Desh Bandu Gupta Road | 4.4 |  | 05.06.2016 | 0%
10 | Faiz Road | 1.41 | 28.05.2016 | 03.06.2016 | 40%
11 | East Park Road | 0.49 | 28.05.2016 | 03.06.2016 | 0%
12 | Rani Jhansi Road | 1.71 | 28.05.2016 | 03.06.2016 | 0%
13 | Link Road | 0.65 |  | 05.06.2016 | 0%
14 | East Park Road | 0.99 | 01.06.2016 | 06.06.2016 | 0%
15 | New Rohtak Road | 2.5 | 01.06.2016 | 06.06.2016 | 0%
16 | S.K. Dass Road | 1 |  | 05.06.2016 | 0%
17 | Abdul Rehman Road | 0.715 | 01.06.2016 | 06.06.2016 | 0%
18 | Abdul Aziz Road | 0.85 | 05.06.2016 | 11.06.2016 | 0%
19 | Elahi Bux Road | 0.415 |  | 30.05.2016 | 50%
20 | Gurudara Road | 1 |  | 30.05.2016 | 0%
21 | Tank Road | 1 |  | 30.05.2016 | 0%
22 | Hardhyan Singh Road | 1.8 |  | 30.05.2016 | 0%
23 | Saraswati Marg | 1 |  | 15.06.2016 | 0% | Er. Sunil Kumar Kataria (Mob. 9958068748) | Er. Santosh Dutta (Mob 9213765200) | Er. Rajiv Lochan (Mob. 9911058852)
24 | Ajmal Khan Road | 1.6 |  | 15.06.2016 | 0%
25 | Sant. Sujan Singh Marg | 0.375 |  | 15.06.2016 | 0%
26 | Dyanand Saraswati Marg (Road No. 4) | 0.5 | 05.06.2016 | 11.06.2016 | 0%
27 | Road No. 3 | 0.5 | 05.06.2016 | 11.06.2016 | 0%
28 | Gangeshwar Dham Marg | 0.375 |  | 15.06.2016 | 0%
29 | Arya Samaj Road | 1.8 |  | 17.06.2016 | 0%
30 | Khajoor Road | 0.32 |  | 17.06.2016 | 0%
31 | Padam Singh Road | 1.5 |  | 17.06.2016 | 0%
32 | Military Road | 1.4 | 08.06.2016 | 14.06.2016 | 0%
33 | Guru Ravi Das Marg | 2 | 08.06.2016 | 14.06.2016 | 0%
34 | Ganga Mandir Marg | 1.5 | 08.06.2016 | 14.06.2016 | 0%
35 | Vishnu Mandir Marg | 1.5 | 08.06.2016 | 14.06.2016 | 20%
36 | Pyare Lal Road | 2 | 08.06.2016 | 14.06.2016 | 20%
37 | Guru Nanak Road (Road No. 5) | 0.9 | 08.06.2016 | 14.06.2016 | 0%
38 | Military Road | 0.5 |  |  | 0%
39 | Vallabacharya Marg | 0.25 | 08.06.2016 | 14.06.2016 | 0%
Desilting Report (Preparedness for Monsoon) (Division (C&ND) Roads )
Sub-Division -1
1 | Main Burari Road | 7.1 | 22.02.2016 | 21.05.2016 | 70% | Sh. Arun Kumar 9971551958 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
2 | BBM Road from Hakikat Nagar, Red Light to Mukherjee Nagar Bandh | 2.4 | Award letter yet to be issued |  | 10% | Sh. D.C. Jaiswal 8744090383
3 | 60ft Road from Aggarwal Sweets to Nulife Hospital between BBM Road and Burari Road | 0.35 |  |  | Yet to be Start
4 | Sant Parmanand Colony Road | 0.9 |  |  | 20%
5 | Burari Road from Kingsway Camp to Road No. 50 | 3.5 | Award letter yet to be issued |  | Yet to be Start | Sh. D.C. Jaiswal 8744090383 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
6 | Wazirabad Flyover | 1.06 |  |  | Yet to be Start | Sh. Arun Kumar 9971551958
7 | Munshi Ram Road | 0.5 |  |  | Yet to be Start | Sh. D.C. Jaiswal 8744090383
8 | Parmanand School Road | 0.33 |  |  | Yet to be Start
9 | Swaroop Nagar Road | 2.8 |  |  | Yet to be Start
10 | Avtar singh Marg (Nirankari Colony) (Nirankari Colony Gate to culvert Burari Road toward Nirankari Sr. Sec. School) | 1.9 |  |  | Yet to be Start
11 | Gandhi Vihar | 0.67 |  |  | 30%
12 | Police Chowki to Mandir Ortram Lane | 0.44 |  |  | Yet to be Start
13 | BBM Road to Jahagir puri Drain | 0.4 |  |  | Yet to be Start
14 | Tagore Park Main road | 0.9 |  |  | Yet to be Start | Sh. Arun Kumar 9971551958
15 | Road in Tagore Park from H. No. 213 to Gole Chakkar | 0.45 |  |  | Yet to be Start
16 | Road in Tagore Park from H. No. 37 to H. No. 64 | 1.55 |  |  | Yet to be Start
Sub-Division -2
1 | University Road from Mall Road to Petrol Pump Ward-10 | 1.58 | 23.04.2016 | 06.07.2016 | Yet to be Start | Sh. Pankaj Kr. Bind 9821387374 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
2 | Khalsa College road from Mall Road to Roop Nagar (Gurutegh Bahadur Road) | 1.3 |  |  | Yet to be Start
3 | Chhatra Marg Road from Mall Road to Malka Gunj Chowk | 1.65 |  |  | 20%
4 | Shiriya Mishra marg from Jai Jawan Tea Stall to Moris Nagar Thana | 0.42 | 23.04.2016 | 06.07.2016 | Yet to be Start | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
5 | Sudhir Bose Marg from chouburjja chowk to ACP Office | 1.25 |  |  | Yet to be Start
6 | Mahatma Gandhii Road (Ring Road) | 1.6 |  |  | Yet to be Start
7 | Road No. 48 | 1.92 |  |  | Yet to be Start | Sh. Pankaj Kr. Bind 9821387374
8 | Vijay Nagar main road from Royal Palace to E-11 Vijay Nagar | 0.75 |  |  | 40% | Sh. Yogesh Kumar 8010697080
9 | Surjit Singh Marg Camp Chowk to Najafgarh Drain | 0.8 |  |  | Yet to be Start
10 | Bunglow Road from Roop Nagar round about to Hansraj College T-point on Chattra Marg | 0.65 |  |  | Yet to be Start | Sh. Pankaj Kr. Bind 9821387374
11 | Mandelia Road from GT Road to Bunglow Road | 0.7 |  |  | Yet to be Start
12 | Polo Road from Bhama Shah Road to Shani Mandir (Vijay Nagar) | 0.84 |  |  | 40% | Sh. Yogesh Kumar 8010697080
13 | Polo Road from Jahanara Marg to shani Mandir Vijay Nagar | 0.3 |  |  | 40%
14 | Kalyan Vihar Road from 25 Kalyan Vihar to 1 No. Priyadarshni Vihar | 0.9 |  |  | 20%
15 | Gurmandi Road from Tripolia gate GT Road to H. NO. 264 Kalyan Vihar | 0.425 |  |  | 40%
16 | Jahanara Road from Bhamashah Marg to vijay Nagar | 0.83 |  |  | Yet to be Start
17 | Satyawati Marg from Police Station Roop Nagar to Shakti Nagar Chowk | 0.52 |  |  | Yet to be Start
18 | Bhama Shah Road from Mall Road to GT Road Nanak Piao Gurudwara | 1.45 |  |  | 20% | Sh. Yogesh Kumar 8010697080
19 | G.T. Road from Baraf Khana chowk to Clock Tower | 1.2 | 23.04.2016 | 06.07.2016 | 50% | Sh. Pankaj Kr. Bind 9821387374
20 | Roshnara Road from Pulbanash Metro Station to Hans Raj College. | 2.7 |  |  | 50% |  | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
21 | GT Road from Nanak Piao Gurudwara to Clock Tower | 1.95 |  |  | 10%
22 | Inderchand Shastri Marg from Shakti Nagar Chowk to Swami Narayan Marg | 0.9 |  |  | Yet to be Start | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
23 | Timarpur road from Mall Road crossing to Wazirabad Crossing | 1.9 |  |  | Yet to be Start | Sh. Ashutosh Singh 9136151991
24 | Lucknow Road from Mall Road to P.S. Timarpur | 1.7 |  |  | Yet to be Start
Sub-Division -3
1 | Ring Road By-pass | 2.9 | 25.04.2016 | 08.07.2016 | Yet to be Start | Md. Sharafat Hussain 9310098783 | Sh. Dinesh Kumar Gupta 9811689688 | Sh. Anil Trehan 8447001861
2 | Sachivalya Road | 1.6 |  |  | 10%
3 | IP Marg | 0.5 |  |  | 10% | Sh. Jaipal Nagar 9871568159
4 | IG Slip Road | 0.58 |  |  | Yet to be Start | Md. Sharafat Hussain 9310098783
5 | Velodrome Road | 0.57 |  |  | Yet to be Start
6 | Vikas Marg | 0.5 |  |  | Yet to be Start
7 | Satyagrah Marg | 0.5 |  |  | Yet to be Start
8 | Azad Bhawan Road | 0.5 |  |  | Yet to be Start | Sh. Jaipal Nagar 9871568159
9 | Ring Road Bhairon Road T-Jn. to Shanti Van Crossing | 4.2 | 25.04.2016 | 08.07.2016 | 70% | Sh. Anish Kumar 9891486390 | Sh. Dinesh Kumar Gupta 9811689688 | Sh. Anil Trehan 8447001861
10 | JLN Marg (Delhi Gate) | 0.56 |  |  | Yet to be Start | Sh. Jaipal Nagar 9871568159
11 | Ghata Masjid Road | 0.26 |  |  | Yet to be Start
12 | Mathura Road | 0.75 |  |  | Yet to be Start
13 | Bahadur Shah Zafar Marg | 2 |  |  | Yet to be Start
DESILTING UNDER PWD MAINTENANCE UNDER NORTH ZONE AS ON 27.05.2016
Name of Division : EE NWR-I
Name of MLA :- Sh. Som Dutt Sharma
Name of Constituency :- Sadar Bazar
1 | Road No. 40 (Bir Bandha Bairagi Marg) | 3.45 | 25.04.16 | 24.08.16 | 15% | Er. Sheikh Nizam / 9899248998 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
2 | Swamy Narayan Marg | 2.94 | 25.04.16 | 24.08.16 | 10%
3 | Old Rohtak Road | 3 | 25.04.16 | 24.08.16 | 25%
4 | Kalidass marg (sarai rohilla flyover) | 0.7 | 25.04.16 | 24.08.16 | 15%
5 | Nand Lal Marg | 1.11 | 25.04.16 | 24.08.16 | 25%
6 | Azad Road | 1.485 | 25.04.16 | 24.08.16 | 11%
7 | Haji Abdul Salam Quareshi Marg | 0.48 | 25.04.16 | 24.08.16 | 25%
8 | Patap Nagar Road | 0.75 | 25.04.16 | 24.08.16 | 40%
9 | Bhagat Singh Road | 0.31 | 25.04.16 | 24.08.16 | 13%
10 | Link Road (east Moti Bagh) | 0.165 | 25.04.16 | 24.08.16 | 14%
11 | Rampura main road | 1.2 | 25.04.16 | 24.08.16 | 16%
12 | Link Road | 0.207 | 25.04.16 | 24.08.16 | 12%
Name of MLA :- Sh. Jitender Singh Tomar
Name of Constituency :- Tri Nagar
13 | Road No.37 Ext. | 0.32 | 25.04.16 | 24.08.16 | 12% | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
14 | Shyamji Krishan Verma Marg (Road No. 44) | 2 | 25.04.16 | 24.08.16 | 5% | Er. Devender Prasad / 9899894912 | Er. M.L. Garg / 9868383698 | Er. Praveen Kumar Kathuria / 9971669344
15 | Kabir Das Road | 1.59 | 25.04.16 | 24.08.16 | 12%
16 | Railway Road (Sardar Balbir Singh Sandhu Marg) Road No.43 to URB Shakurbasti | 0.99 | 25.04.16 | 24.08.16 | 11%
17 | Eklavya Marg | 0.37 | 25.04.16 | 24.08.16 | 14%
18 | Veer Hemu Marg | 1.085 | 25.04.16 | 24.08.16 | 16%
19 | Maharishi Parshu Ram Marg | 0.75 | 25.04.16 | 24.08.16 | 13%
20 | Triwalubar Marg | 0.29 | 25.04.16 | 24.08.16 | 14%
21 | Main Road of G-Block & H-Block | 0.325 | 25.04.16 | 24.08.16 | 16%
22 | Valmiki Road | 0.6 | 25.04.16 | 24.08.16 | 12%
23 | Abdul Hamid Marg | 0.78 | 25.04.16 | 24.08.16 | 14%
Name of MLA :- Smt. Bandana Kumari
Name of Constituency :- Shalimar Bagh
24 | Outer Ring Road | 2.8 | 25.04.16 | 24.08.16 | 15% | Er. Sheikh Nizam / 9899248998 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
25 | Outer Ring Road | 2.8 | 25.04.16 | 24.08.16 | 10%
26 | RUB Shalimar Bagh Road | 0.6 | 25.04.16 | 24.08.16 | 15%
27 | Jhule Lal Mandir Marg Shalimar Bagh | 1.25 | 25.04.16 | 24.08.16 | 12%
28 | Dividing Road | 0.26 | 25.04.16 | 24.08.16 | 11%
29 | Abhinav model School | 0.4 | 25.04.16 | 24.08.16 | 14% | Er. Subhash Tomar / 9958138151 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
30 | Ahinsa path Road | 0.4 | 25.04.16 | 24.08.16 | 16%
31 | NP - MP Road | 0.46 | 25.04.16 | 24.08.16 | 13%
32 | SP School Road | 0.65 | 25.04.16 | 24.08.16 | 14%
33 | BDFD Road | 0.54 | 25.04.16 | 24.08.16 | 16% | Er. Subhash Tomar / 9958138151 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
34 | Shaheed Udham Singh Marg | 1.6 | 25.04.16 | 24.08.16 | 12% | Er. Sheikh Nizam / 9899248998 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
35 | Swami Shardanand Saraswati Marg | 1.2 | 25.04.16 | 24.08.16 | 14%
36 | T.V Tower Road | 0.66 | 25.04.16 | 24.08.16 | 9% | Er. Subhash Tomar / 9958138151 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
37 | Maharaja Agarsen Road | 2.84 | 25.04.16 | 24.08.16 | 10%
38 | Power House Road | 1.03 | 25.04.16 | 24.08.16 | 10%
39 | Gopal Mandir Road | 1.105 | 25.04.16 | 24.08.16 | 10%
40 | Muni Maya Ram Road | 1.738 | 25.04.16 | 24.08.16 | 12%
41 | Gurudwara Road | 0.6 | 25.04.16 | 24.08.16 | 15% | Er. Sheikh Nizam / 9899248998 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
42 | Gyan Shakti Mandir Marg | 1.25 | 25.04.16 | 24.08.16 | 12%
43 | Maharishi Dayanand Marg | 0.4 | 25.04.16 | 24.08.16 | 11% | Er. Subhash Tomar / 9958138151 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
44 | Bhagwan Mahavir Marg | 0.54 | 25.04.16 | 24.08.16 | 10%
45 | Club Road | 0.6 | 25.04.16 | 24.08.16 | 12% | Er. Sheikh Nizam / 9899248998 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
46 | K.L. Bagga Marg | 0.6 | 25.04.16 | 24.08.16 | 15%
47 | Haiderpur Main Road | 0.9 | 25.04.16 | 24.08.16 | 12%
48 | Canal Road | 0.88 | 25.04.16 | 24.08.16 | 11%
49 | Ram Leela Ground Road | 0.88 | 25.04.16 | 24.08.16 | 14% | Er. Subhash Tomar / 9958138151 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
50 | Ring Road | 3.2 | 25.04.16 | 24.08.16 | 10% | Er. Sheikh Nizam / 9899248998 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
51 | Road No. 41 | 3 | 25.04.16 | 24.08.16 | 15% | Er. Subhash Tomar / 9958138151 | Er. Baljeet Singh Roparia / 9810876838 | Er. Praveen Kumar Kathuria / 9971669344
Name of MLA :- Sh. Rajesh Gupta
Name of Constituency :- Wazirpur
52 | Gulab Singh Marg from G.T. Road to Road No. 37 Prerna Chowk | 3.1 | 25.04.16 | 24.08.16 | 10% | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
53 | Pardeshwar Dham Mandir Marg | 1.1 | 25.04.16 | 24.08.16 | 30%
54 | Ch. Mange Ram Marg | 0.37 | 25.04.16 | 24.08.16 | 15%
55 | Madhav Marg | 1.6 | 25.04.16 | 24.08.16 | 30%
56 | Sh. Guru Nanak Dev Ji Marg | 0.482 | 25.04.16 | 24.08.16 | 11%
57 | Front of Keshavpuram Police station | 0.45 | 25.04.16 | 24.08.16 | 30%
58 | K.C.Goel Marg | 0.756 | 25.04.16 | 24.08.16 | 10%
59 | Maharishi Dayanand Saraswati Marg | 0.455 | 25.04.16 | 24.08.16 | 12%
60 | Shri Ram Kishan Mandir Marg | 0.551 | 25.04.16 | 24.08.16 | 15%
61 | Kulachi Hans Raj School Marg | 0.23 | 25.04.16 | 24.08.16 | 12%
62 | F-Block Market | 0.38 | 25.04.16 | 24.08.16 | 11%
63 | B-Block Market | 0.27 | 25.04.16 | 24.08.16 | 14%
64 | Deep Chand Central Market | 1 | 25.04.16 | 24.08.16 | 10%
65 | Road No. 37 (Maharaja Nahar Singh Marg) | 3 | 25.04.16 | 24.08.16 | 12%
66 | Road No. 38 | 1.45 | 25.04.16 | 24.08.16 | 15%
67 | Jhule Lal Marg | 0.363 | 25.04.16 | 24.08.16 | 12%
68 | Shiv Ram Mandir Marg | 0.3 | 25.04.16 | 24.08.16 | 11%
69 | Lala Lajpat Rai Marg | 0.327 | 25.04.16 | 24.08.16 | 14%
70 | Mata Jai Kaur Road | 0.29 | 25.04.16 | 24.08.16 | 10%
71 | Sunder Lal Jain Road | 0.55 | 25.04.16 | 24.08.16 | 12% | Er. Sudanand / 9968318994 | Er. R.S. Nigam / 9810070665 | Er. Praveen Kumar Kathuria / 9971669344
72 | Bunkar Colony Road | 0.224 | 25.04.16 | 24.08.16 | 15%
73 | Kakaji Lane | 0.328 | 25.04.16 | 24.08.16 | 12%
74 | Laxmi Bai College Road | 0.385 | 25.04.16 | 24.08.16 | 11%
75 | Main GT Road | 1.08 | 25.04.16 | 24.08.16 | 14%
76 | Bharat Nagar Road | 2.09 | 25.04.16 | 24.08.16 | 10%
77 | Nimri Colony Road | 3.4 | 25.04.16 | 24.08.16 | 12%
78 | Tawetia Marg | 1.03 | 25.04.16 | 24.08.16 | 15%
79 | K.C Goel Marg upto Underpass | 0.65 | 25.04.16 | 24.08.16 | 12%
80 | Lawrence Road | 0.87 | 25.04.16 | 24.08.16 | 11%
Name of Division : EE NWR-II
Name of MLA :- Sh. Satyender Jain
Name of Constituency :- Shakur Basti
81 | Ch Balbir Singh Marg from Road No. 30 to Rohtk Road (NH-10) | 1.06 | 12.03.2016 | 09.07.2016 | 80% | Sh. Rajesh Mewada 9873754012 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
82 | Bhao Rao Dev Ras Marg | 1.4 | 12.03.2016 | 09.07.2016 | 10%
83 | Deen Dayal Upadhyay Marg | 0.6 | 12.03.2016 | 09.07.2016 | 10%
84 | Major Ashwani Marg | 1 | 12.03.2016 | 09.07.2016 | 80%
85 | Road between B4 and B5 Block Paschim Vihar | 0.35 | 12.03.2016 | 09.07.2016 | 70%
86 | NH-10 (Delhi Rohtak Road) | 4.5 | 12.03.2016 | 09.07.2016 | 5%
87 | Guru Harkishan Marg (road No. 43) | 1.8 | 08.03.2016 | 05.07.2016 | 5% | Sh. Sunit Singh 9971230165 | Sh. L.K. Tripathi 9891192952 | Sh. Praveen Kathuria 9971669344
88 | Chandra Shekhar Azad Marg (Road No. 42) | 1.23 | 12.03.2016 | 09.07.2016 | 20% | Sh. Narender Singh 9868004850 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
89 | Guru Harkishan Marg (road No. 43) | 1.7 | 12.03.2016 | 09.07.2016 | 5% | Sh. Narender Singh 9868004850 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
90 | Mahatma Hans Raj Marg | 1.4 | 12.03.2016 | 09.07.2016 | 30%
91 | Guru Birja Nand Marg | 1.4 | 12.03.2016 | 09.07.2016 | 10%
92 | Sant Nagar M2K Road | 0.47 | 12.03.2016 | 09.07.2016 | 10%
93 | Amar Shaheed Bismil Marg | 0.94 | 12.03.2016 | 09.07.2016 | 50%
94 | Police Line Road | 0.62 | 12.03.2016 | 09.07.2016 | 10%
95 | Parwana Road, Saraswati Vihar | 2.8 | 12.03.2016 | 09.07.2016 | 50%
96 | Road No.30 | 2 | 12.03.2016 | 09.07.2016 | 50% | Sh. Rajesh Mewada 9873754012 | Er. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
Name of MLA :- Sh. Jitender Singh Tomar
Name of Constituency :- Tri Nagar
97 | Phirni Road | 0.53 | 12.03.2016 | 09.07.2016 | 5% | Sh. Narender Singh 9868004850 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
Name of MLA :- Ms Rakhi Birla
Name of Constituency :- Mangolpuri
98 | Guru Govalkar Marg (Outer ring road Xing Mangolpuri Marble Market to Rajeev Nagar) | 5.8 | 26.02.2016 | 25.02.2017 | 35% | - | Sh. Raj Kishore Raj, AE, 9971409602 | Sh. Praveen Kathuria 9971669344
99 | Road No. 316 | 1.4 | 08.03.2016 | 05.07.2016 | 30% | Sh. Sunit Singh 9971230165 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
100 | Road No. 317 | 0.35 | 08.03.2016 | 05.07.2016 | 30%
101 | Road No. 318 | 0.85 | 08.03.2016 | 05.07.2016 | 30%
102 | Road No. 319 | 0.35 | 08.03.2016 | 05.07.2016 | 30% | Sh. Sunit Singh 9971230165 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
103 | S.N. Hardiker Marg (Road No. A-1) | 1.19 | 08.03.2016 | 05.07.2016 | 30%
104 | Sir Chotu Ram Marg (road No. A-3) | 1 | 08.03.2016 | 05.07.2016 | 30%
105 | Kanjhawala Link road | 0.4 | 08.03.2016 | 05.07.2016 | 30%
106 | Outer Ring Road No. 26 | 0.3 | 08.03.2016 | 05.07.2016 | 30%
107 | Sanjay Gandhi Hospital Road from Road No.316 to J Block Survodya Vidhyalya to Kanjhawla Road. | 1.6 | 08.03.2016 | 05.07.2016 | 50%
108 | Police Station Road from Road No.3 i.e. Kanjhawla Road to Sanjay Gandhi Hospital Road. | 1.3 | 08.03.2016 | 05.07.2016 | 80%
109 | Kala Mandir Cinema Road in Mangolpuri | 0.8 | 08.03.2016 | 05.07.2016 | 50%
110 | LP Road (Tank Road) Mangolpuri | 1.2 | 08.03.2016 | 05.07.2016 | 30%
111 | B-Block Road Mangolpuri | 1.4 | 08.03.2016 | 05.07.2016 | 30%
112 | Road No.A-2 From Pole Star to CSC-II, Sec.1/2, Rohini. | 0.54 | 08.03.2016 | 05.07.2016 | 30%
113 | Road from New Bal Bharti Public School to Road No.3 Sec.2 | 0.4 | 08.03.2016 | 05.07.2016 | 30%
114 | Road from CSC Market Pkt.4 to Mangolpur Kalan Phirni Road Sec.2 | 0.3 | 08.03.2016 | 05.07.2016 | 30%
115 | Roadfrom PocketA-1 to Pocket A-2 in Sec.4 Rohini | 0.225 | 08.03.2016 | 05.07.2016 | 30%
116 | Roadfrom Pocket B-5to Pocket B-9 in Sec.4 Rohini MC Pry. School | 0.31 | 08.03.2016 | 05.07.2016 | 30% | Sh. Sunit Singh 9971230165 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
117 | Road From Pocket A-2 to Pkt.C-13 in Sec.3 Rohini | 1 | 22.05.2016 | 18.10.2016 | 5% | Sh. Jai Singh 9312101073 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
118 | Road from Pocket F-22 to Pocket H-34 in Sec-3 Rohini | 1 | 22.05.2016 | 18.10.2016 | 7%
119 | Road from MC Pry. School 3A to Sarvodaya School in Sec.3, Rohini | 0.325 | 22.05.2016 | 18.10.2016 | 5%
120 | Road from DDA Shopping Centre to Kendriya Vidyalaya in Sec.3, Rohini. | 0.325 | 22.05.2016 | 18.10.2016 | 5%
121 | Jaipur Golden Hospital Road Sec.3 | 1 | 22.05.2016 | 18.10.2016 | 4%
Name of MLA :- Sh. Sandeep Kumar
Name of Constituency :- Sultanpur Majra
122 | Nangloi Rly.Stn to Sultanpuri Bus Terminal via Jalebi Chowk | 2.1 | 08.03.2016 | 05.07.2016 | 55% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
123 | Sultanpuri Bus Terminal to Flood Control Drain. | 1 | 08.03.2016 | 05.07.2016 | 80%
124 | Sultanpuri Main Road | 0.6 | 08.03.2016 | 05.07.2016 | 30%
125 | Shani Bazar Road | 0.6 | 08.03.2016 | 05.07.2016 | 80%
126 | H Block Road | 0.32 | 08.03.2016 | 05.07.2016 | 35%
127 | Jagdamba Road | 0.38 | 08.03.2016 | 05.07.2016 | 35%
128 | Bhalla Factory road | 0.38 | 08.03.2016 | 05.07.2016 | 55%
129 | G-Block Road | 0.15 | 08.03.2016 | 05.07.2016 | 35% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
Name of MLA :- Sh. Ritu Raj Jha
Name of Constituency :- Kirari
130 | 70 ft Road Kirari | 1.25 | 08.03.2016 | 05.07.2016 | 30% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 9891192952 | Sh. Praveen Kathuria 9971669344
Name of MLA :- Vijender Gupta
Name of Constituency :- Rohini
131 | Road No. B-8 | 1.18 | 26.05.2016 | 22.10.2016 | Work just awarded | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
132 | PWD Road to DJB Booster Pump (Length 0.270 KM) | 0.27 | 26.05.2016 | 22.10.2016 | Work just awarded
133 | PWD Road to Baba wala Park (Corner of Booster Pump) (Length 0.590 KM) | 0.59 | 26.05.2016 | 22.10.2016 | Work just awarded
134 | Dr. K.N. Katju Marg(45m wide road) | 3.77 | 26.05.2016 | 22.10.2016 | Work just awarded
135 | Road No. B-4 | 1.4 | 15.05.2016 | 11.09.2016 | 5%
136 | Road No. B-5 | 1.64 | 15.05.2016 | 11.09.2016 | 5%
137 | Road No. B-7 | 1.25 | 15.05.2016 | 11.09.2016 | 5%
138 | Col. Sarna Marg Sec.9 & 13 | 1.02 | 15.05.2016 | 11.09.2016 | 5%
139 | Internal Road of Sec.9 Rohini | 0.325 | 15.05.2016 | 11.09.2016 | 5%
140 | Internal Road of Sec.9 Rohini | 0.33 | 15.05.2016 | 11.09.2016 | 5%
141 | R.N. Gujral Marg Sec.9 | 0.265 | 15.05.2016 | 11.09.2016 | 6%
142 | Chetak Apartment to New Modern Apartment Sec.9 | 0.319 | 15.05.2016 | 11.09.2016 | 5% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
143 | Vidhya Vihar to Neelgiri Apt. Sec.9 | 0.33 | 15.05.2016 | 11.09.2016 | 6%
144 | Captain Dahiya Marg Sec.9 & 13 | 1.68 | 15.05.2016 | 11.09.2016 | 7%
145 | Ahinsha Marg Sec.9 & 13 | 1.68 | 15.05.2016 | 11.09.2016 | 5%
146 | Sunrise Appartment (K. N. Katzu Marg) to Neelkanth Appartment (K. N. Katzu Marg) | 0.975 | 15.05.2016 | 11.09.2016 | 5%
147 | Kawal Kunj Soceity to K.N. Katzu Marg (Length 0.265 KM) | 0.265 | 15.05.2016 | 11.09.2016 | 5%
148 | Fire Station to CRPF School Corner Sec.14 Rohini (Ram Prasad Bismil Marg) | 0.72 | 15.05.2016 | 11.09.2016 | 6%
149 | Babosa Chowk to Tulsi Apartment Sec.14, Rohini. | 0.55 | 15.05.2016 | 11.09.2016 | 7%
150 | PWD Ring Road to Maheswari Apt. Sec.14 toward Sec.13. | 0.845 | 15.05.2016 | 11.09.2016 | 5%
151 | Rukmani Devi Institute to Rohini Court Sec.14 | 0.45 | 15.05.2016 | 11.09.2016 | 5%
152 | Connecting road from ORR to Road No.B-5 passing through CRPF School, Sec.14, Rohini | 0.86 | 15.05.2016 | 11.09.2016 | 5%
153 | Maharaja Aggarsen Marg (Road No. 42-A) | 2.3 | 12.03.2016 | 09.07.2016 | 5% | Sh. Narender Singh 9868004850 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
154 | A-1/1 to G-18/1 (Length 0.600 KM) | 0.6 | 15.05.2016 | 11.09.2016 | 6% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
155 | Western Yamuna Canal to Badli Chowk (Length 0.310 KM) | 0.31 | 26.05.2016 | 22.10.2016 | 5%
156 | G-17/1 to Western Yamuna Canal (Length 0.750 KM) | 0.75 | 15.05.2016 | 11.09.2016 | 5% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
157 | Western Yamuna Canal to Arya Appartment (Length 0.590 KM) | 0.59 | 15.05.2016 | 11.09.2016 | 7%
158 | Western Yamuna Canal to A-11/87 (Length 0.300 KM) | 0.3 | 26.05.2016 | 22.10.2016 | Work just awarded
159 | Pradeep Bhatia Marg (Road No. A-5) | 1 | 22.05.2016 | 18.10.2016 | 5% | Sh. Sunit Singh 9971230165 | Sh.Amar Singh 9891192952 | Sh. Praveen Kathuria 9971669344
160 | Road No. 41-A Bhagwan mahavir Marg. | 3.995 | 22.05.2016 | 18.10.2016 | 7% | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
161 | Road No. B-3 | 1.55 | 22.05.2016 | 18.10.2016 | 5% | Sh. Jai Singh 9312101073 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
162 | G-23/30 to E4/15 Sec.7 | 0.396 | 22.05.2016 | 18.10.2016 | 5% | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
163 | B-6/159 to Naharpur DAV School back side Sec.7 | 0.296 | 22.05.2016 | 18.10.2016 | 5%
164 | B-22/279 to G-21/222 Sec.7 | 0.321 | 22.05.2016 | 18.10.2016 | 5%
165 | B-4/30 to CGHS Dispensary Sec.7 | 0.172 | 22.05.2016 | 18.10.2016 | 5%
166 | H18 to F-25 Sec.6 & 7 dividing road | 1.3 | 22.05.2016 | 18.10.2016 | 5%
167 | Rama Road Sec.8, Rohini | 0.73 | 22.05.2016 | 18.10.2016 | 5%
168 | Road from Road No. 41-A to Rama Road in Sec.8, Rohini | 1.05 | 22.05.2016 | 18.10.2016 | 5%
169 | Road from Road No. 42-A to Rama Road in Sec.8, Rohini | 0.55 | 22.05.2016 | 18.10.2016 | 5% | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
170 | Sawran Jayanti Park Road, Sec.9 &13 | 1.68 | 22.05.2016 | 18.10.2016 | 5%
171 | PWD Road (B-7) to Corner of E-II Ashtha Kunj (Length 0.245 KM) | 0.245 | 26.05.2016 | 22.10.2016 | Work just awarded | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
172 | Corner of Data Ram Society to CEPT (Length 0.390 KM) | 0.39 | 26.05.2016 | 22.10.2016 | Work just awarded
173 | Behind Data Ram Society to Corner of Mt. Abu School (Length 0.390 KM) | 0.39 | 26.05.2016 | 22.10.2016 | Work just awarded
174 | PWD Road (B-7) to CEPT (Length 0.580 KM) | 0.58 | 26.05.2016 | 22.10.2016 | Work just awarded
175 | H-3/53 to DDA Park (Length 0.145 KM) | 0.145 | 26.05.2016 | 22.10.2016 | Work just awarded
Name of MLA :- Mohinder Goyal
Name of Constituency :- Rithala
176 | Deen Bandhu Sir Chotu Ram Marg (Road No. A-4) | 1 | 22.05.2016 | 18.10.2016 | 5% | Sh. Jai Singh 9312101073 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
177 | Road No. B-1 | 0.96 | 22.05.2016 | 18.10.2016 | 5%
178 | Road No. B-6 | 1 | 26.05.2016 | 22.10.2016 | Work just awarded | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
179 | MTNL Godown to C6/137 Sec.5, Rohini | 0.533 | 22.05.2016 | 18.10.2016 | 5% | Sh. Jai Singh 9312101073 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
180 | Som Bazar Road, Sec.5, Rohini | 0.71 | 22.05.2016 | 18.10.2016 | 5%
181 | Shiva Road from Ring Road to Dividing Road of Sec.5 & 6, Rohini. | 2.217 | 22.05.2016 | 18.10.2016 | 5% | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
182 | Vidya Jain Public School, Se.6, Rohini | 0.477 | 22.05.2016 | 18.10.2016 | 5% | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
183 | C-4/253 to C5/253, Sec.6, Rohini | 0.33 | 22.05.2016 | 18.10.2016 | 5%
184 | D-6 and A-1 Road sec.6,Rohini | 0.33 | 22.05.2016 | 18.10.2016 | 5%
185 | Road from F-3 block to H-4 in Sec.11, Rohini | 0.7 | 22.05.2016 | 18.10.2016 | 5%
186 | From A-1 to F-3 Block near NDPL office Sec.11, Rohini. | 1.5 | 22.05.2016 | 18.10.2016 | 5%
187 | From Block H-1 to H-5 Block Sec.11, Rohini | 0.65 | 22.05.2016 | 18.10.2016 | 5%
188 | From F-1 to H-2 Block near NDPL office Sec.11, Rohini. | 0.65 | 22.05.2016 | 18.10.2016 | 5%
189 | From C-4 to A-3 Block near NDPL office Sec.11, Rohini. | 0.65 | 22.05.2016 | 18.10.2016 | 5%
190 | From F-1 to F-3 Block near NDPL office Sec.11, Rohini. | 0.375 | 22.05.2016 | 18.10.2016 | 5%
191 | From A-1 to A-3 Block near NDPL office Sec.11, Rohini. | 0.375 | 22.05.2016 | 18.10.2016 | 5%
192 | From C-1 to C-5 Block near NDPL office Sec.11, Rohini. | 0.375 | 22.05.2016 | 18.10.2016 | 5%
193 | From Community Centre to NDMC Colony, Sec.11, Rohini. | 0.69 | 22.05.2016 | 18.10.2016 | 5%
194 | D-1 TO I-3 (Length 0.463 KM) | 0.463 | 22.05.2016 | 18.10.2016 | 5%
195 | G-1 TO E-5 (Length 0.650 KM) | 0.65 | 22.05.2016 | 18.10.2016 | 5%
196 | G-7 TO G-1 (Length 1.000 KM) | 1 | 22.05.2016 | 18.10.2016 | 5%
197 | H-3 TO H-1 (Length 0.400 KM) | 0.4 | 22.05.2016 | 18.10.2016 | 5% | Sh. Pushkar Raj 9868469769 | Sh. RAS Yadav 9868040252 | Sh. Praveen Kathuria 9971669344
198 | A-2 TO E-3 (Length 0.650 KM) | 0.65 | 22.05.2016 | 18.10.2016 | 5%
199 | C-1 TO I-11 (Length 0.600 KM) | 0.6 | 22.05.2016 | 18.10.2016 | 5%
200 | District Park TO C-1 (Length 0.438 KM) | 0.438 | 22.05.2016 | 18.10.2016 | 5%
201 | F-2 TO F-6 (Length 0.338 KM) | 0.338 | 22.05.2016 | 18.10.2016 | 5%
202 | A-6 TO A-8 (Length 0.263 KM) | 0.263 | 22.05.2016 | 18.10.2016 | 5%
203 | F-3 TO F-5 (Length 0.338 KM) | 0.338 | 22.05.2016 | 18.10.2016 | 5%
204 | I-1 TO Police Station (Length 0.538 KM) | 0.538 | 22.05.2016 | 18.10.2016 | 5%
205 | B-2 TO B-6 (Length 0.210 KM) | 0.21 | 22.05.2016 | 18.10.2016 | 5%
206 | A-8 TO B-6 (Length 0.600 KM) | 0.6 | 22.05.2016 | 18.10.2016 | 5%
207 | B-1 TO C-1 (Length 0.475 KM) | 0.475 | 22.05.2016 | 18.10.2016 | 5%
208 | A-8 TO B-1 ROAD (Length 0.445 KM) | 0.445 | 22.05.2016 | 18.10.2016 | 5%
209 | Road No. B-2 (Ram murthi Passi Marg) | 1.652 | 15.05.2016 | 11.09.2016 | 5% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
Name of MLA :- Sh. Ved Prakash
Name of Constituency :- Bawana
210 | Road from Pkt-10 to Pkt-D-4, Sec-20,Rohini | 0.505 | 15.05.2016 | 11.09.2016 | 5% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
211 | Road from Pkt-14 to Pkt-C-1,Sec-20,Rohini | 1 | 15.05.2016 | 11.09.2016 | 7% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Suresh Kumar 9350005609 | Sh. Praveen Kathuria 9971669344
212 | Road from Pkt-8 to Pkt.-9,Sec-21, Rohini | 0.505 | 15.05.2016 | 11.09.2016 | 7%
213 | Road from Pkt-B to Park, Sec-21, Rohini | 0.187 | 15.05.2016 | 11.09.2016 | 5%
214 | Road from Pkt-13 to Pkt-9,Sec-21, Rohini | 0.448 | 15.05.2016 | 11.09.2016 | 5%
215 | Road from Pkt-5 to Pkt-6, Sec-21, Rohini | 0.115 | 15.05.2016 | 11.09.2016 | 7%
West Circle
Name of Division :- West Road-1
Name of MLA :- Sh. Jagdeep Singh
Name of Constituency :- Hari Nagar (28)
1 | Goswami Tulsi Dass Marg i.e. Road No. 32 | 1.6 | 05.05.2016 | 25.06.2016 | 15% | Ankur Goswami 9950265713 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
2 | Dr. Kundan Lal Marg | 0.42 | 05.05.2016 | 25.06.2016 | 20%
3 | Rajouri Appartment Road | 3 | 05.05.2016 | 25.06.2016 | 35%
4 | H.No. 14/35 to 13/101 Subash Nagar (Near Shandley School) | 0.454 | 05.05.2016 | 25.06.2016 | 3%
5 | Shanti Devi Marg | 0.375 | 05.05.2016 | 25.06.2016 | 5%
6 | Ashok Nagar Road | 0.318 | Yet to start | 25.06.2016 | ----
7 | Ayodhya Prasad Chopra Marg | 0.45 | 05.05.2016 | 25.06.2016 | 5% | Ankur Goswami 9950265713 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
8 | Road No. 32 to 17/117 Subash Nagar | 0.35 | 05.05.2016 | 25.06.2016 | 2%
9 | H.No. 6/1 to 3/200 Subhash Nagar | 0.68 | Yet to start | 25.06.2016 | ----
10 | Vedic Marg | 1.35 | 05.05.2016 | 25.06.2016 | 2%
11 | H.No. 11/76 to 11/85 Subhash Nagar | 0.05 | Yet to start | 25.06.2016 | ----
12 | H.No. 8/1 to 14/149 Subhash Nagar | 0.35 | 05.05.2016 | 25.06.2016 | 5%
13 | H.No. 10/1 to 14/97 Subhash Nagar | 0.292 | Yet to start | 25.06.2016 | ----
14 | Sardar Kulwant Singh Sethi Marg | 1.046 | 05.05.2016 | 25.06.2016 | 5%
15 | DA-1, Hari Nagar to DB-1 Hari Nagar | 0.423 | Yet to start | 25.06.2016 | ----
16 | Shaheed Bhagat Singh Mrg. (Jail Rd) | 2.28 | 05.05.2016 | 25.06.2016 | 35% | Ajay Vishraj 8800146761 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
17 | Shaheed Bhagat Singh Mrg. (Jail Rd) | 1.4 | 05.05.2016 | 25.06.2016 | 5%
18 | B-2/Dharam Marg | 1.38 | 05.05.2016 | 25.06.2016 | 20%
19 | Capt. Anuj Nayyar Marg. | 0.67 | 05.05.2016 | 25.06.2016 | 5% | Ajay Vishraj 8800146761 | G.S.L. Bhatnagar 9868100158 | A.K. Sahana 9747487738
20 | B1- B2 Connecting Road. | 0.59 | Yet to start | 25.06.2016 | ----
21 | Gurudwara Road | 0.63 | Yet to start | 25.06.2016 | ----
22 | BA-BB Block Road | 0.38 | 05.05.2016 | 25.06.2016 | 5%
23 | B2 Block Sabzi Mandi Road | 0.4 | Yet to start | 25.06.2016 | ----
24 | Prem Nagar Gurudwara Rd. | 0.52 | 05.05.2016 | 25.06.2016 | 5%
25 | Major Rajeev Laul Marg | 0.88 | Yet to start | 25.06.2016 | ----
26 | Shaheed Mangal Pandey Marg | 0.74 | 05.05.2016 | 25.06.2016 | 5%
27 | Bhai Kanheya Ji Marg (ITI Road) | 0.67 | 05.05.2016 | 25.06.2016 | 5%
28 | Mangal Pandey Marg (Hari Nagar Clock Tower to Maya Puri) | 0.85 | 05.05.2016 | 25.06.2016 | 5%
Name of Division :- West Road-1
Name of MLA :- Sh. Rajesh Rishi
Name of Constituency :- Janak Puri (30)
29 | Prof. Joginder Singh Marg (In front of Janakpuri Distt. Centre) | 1.18 | 05.05.2016 | 25.06.2016 | 80% | Ranjeet Srivastva 9821691159 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
30 | Authority Road (Janak Puri) | 0.65 | Yet to start | 25.06.2016 | ---- | Ranjeet Srivastva 9821691159 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
31 | Mota Singh Road | 0.98 | 05.05.2016 | 25.06.2016 | 10%
32 | Possangi Pur Road | 0.4 | 05.05.2016 | 25.06.2016 | 5%
33 | Major Deepak Tyagi Marg | 0.97 | 05.05.2016 | 25.06.2016 | 5% | Vishal Seth 9650167976 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
34 | A-1 Block Main Road | 0.62 | Yet to start | 25.06.2016 | ----
35 | Road Opp. A1B Block Janak Puri | 0.28 | 05.05.2016 | 25.06.2016 | 5%
36 | Asalatpur Road | 0.16 | 05.05.2016 | 25.06.2016 | 5%
37 | Asalatpur Road-II | 0.79 | 05.05.2016 | 25.06.2016 | 2%
38 | Najafgarh Road (Shivaji Marg) (Dhauli Piao to Pankha Road Red Light) | 1.25 | Yet to start | 25.06.2016 | ----
Name of MLA :- Jarnal Singh
Name of Constituency :- Rajouri Garden (27)
39 | 100' Road (Patel Chowk to Subhash Nagar Drain (Patel Chowk Road) | 0.8 | Yet to start | 20.06.2016 | ---- | Yogesh Joshi 9795313669 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
40 | 100' Road New Khayala Road | 0.7 | Yet to start | 20.06.2016 | ----
41 | 80' Road Chowkhandi Road | 1 | Yet to start | 20.06.2016 | ----
42 | Ring road to A-31 rajori garden | 0.045 | Yet to start | 20.06.2016 | ----
43 | Najafgarh Road to A-71 Rajouri Garden | 0.04 | Yet to start | 20.06.2016 | ---- | Yogesh Joshi 9795313669 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
44 | Sakti Mandir Marg | 0.2 | Yet to start | 20.06.2016 | ----
45 | Najafgarh Road | 1.95 | Yet to start | 20.06.2016 | ----
46 | Arya Samaj Marg | 0.12 | Yet to start | 20.06.2016 | ----
47 | J.Krishnatrey Marg | 0.11 | Yet to start | 20.06.2016 | ----
48 | AD-1 to BF- 31 (Tagore Garden) | 0.6 | Yet to start | 20.06.2016 | ----
49 | DE-131 to Community Hall | 0.22 | Yet to start | 20.06.2016 | ----
50 | Devki Nandan Marg | 0.78 | Yet to start | 20.06.2016 | ----
51 | Tanki Wala Marg | 0.2 | Yet to start | 20.06.2016 | ----
52 | Sant Berwa Marg with Titar Pur drain | 0.6 | Yet to start | 20.06.2016 | ----
53 | Road No. 28 | 0.5 | Yet to start | 20.06.2016 | ----
54 | Major Sudesh Gadok Marg (J 12/1 to NG Road) | 0.62 | Yet to start | 20.06.2016 | ----
55 | Major Sudesh Marg (NG Road to Ring Road) | 1.9 | Yet to start | 20.06.2016 | ----
Name of MLA :- Jarnal Singh
Name of Constituency :- Tilak Nagar (29)
56 | Lala Ganesh Dass Marg | 1.27 | 07.05.2016 | 15.06.2016 | 30% | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
57 | Road between Two Blocks of G- Block Vikas Puri | 0.24 | 07.05.2016 | 15.06.2016 | 10%
58 | From G-1 Block Vikas Puri to Palican Road VikasPuri | 0.52 | Yet to start | 15.06.2016 | ----
59 | Keshopur Sabzi Mandi Red Light (Outer Ring Road) to Subhash Nagar Drain | 0.386 | 07.05.2016 | 15.06.2016 | 15%
60 | Road No. 235 | 0.35 | 07.05.2016 | 15.06.2016 | 10%
61 | Road No. 235 extension | 0.76 | 07.05.2016 | 15.06.2016 | 15%
62 | Chowkhandi Road | 0.22 | 07.05.2016 | 15.06.2016 | 15%
63 | Najafgarh road from Subhash Nagar Crossing to Dhauli Piao | 4.2 | 07.05.2016 | 15.06.2016 | 5% | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
64 | Tilak Nagar To 20 Block Tilak Vihar | 0.5 | 07.05.2016 | 15.06.2016 | 70%
65 | Road from H-Block To H-3 Block | 0.54 | 07.05.2016 | 15.06.2016 | 40%
66 | Road from Guruvirjanand Marg to Distt. Park,Vikas Puri | 0.14 | 07.05.2016 | 15.06.2016 | 40%
67 | Shaheed Raj Guru Marg Vikas Puri | 1.28 | 07.05.2016 | 15.06.2016 | 15%
68 | Tilak Vihar Main Road | 0.54 | 07.05.2016 | 15.06.2016 | 60%
69 | Road Adjcent to PVR Complex Vikas Puri | 0.15 | 07.05.2016 | 15.06.2016 | 5%
70 | Pelicon Road from Guru Virzanand Marg to Road No. 235 Extension | 0.91 | 07.05.2016 | 15.06.2016 | 15%
71 | Tilak Nagar Main Market Road | 0.07 | 07.05.2016 | 15.06.2016 | 10%
72 | Brain Public School Road | 0.75 | 07.05.2016 | 15.06.2016 | 2%
73 | K. R. Manglam | 0.54 | 07.05.2016 | 15.06.2016 | 15%
74 | H- Block to Vikas Puri | 0.194 | 07.05.2016 | 15.06.2016 | 2%
75 | 70 Block Park Ashok Nagar to Tihar No. 2 School | 0.52 | 07.05.2016 | 15.06.2016 | 2%
76 | 2/1 to 2/10 Ashok Nagar | 0.6 | 07.05.2016 | 15.06.2016 | 2%
Name of MLA :- Sh. Mahender Yadav
Name of Constituency :- Vikas Puri (31)
77 | Road No. 236 | 1.8 | Yet to start | 25.06.2016 | ---- | Rajat 9868014576 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
78 | Road No. 237 | 0.45 | Yet to start | 25.06.2016 | ---- | Rajat 9868014576 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
79 | Road between Krishi Appt. to DAV school (PWD Road) | 0.295 | Yet to start | 25.06.2016 | ----
80 | Road between Devdoot Appt. to Parmarth Appt. PWD Road Vikas Puri | 0.28 | Yet to start | 25.06.2016 | ----
81 | Road between Jupiter Appt. to Priya Appt. PWD Road Vikas Puri | 0.39 | Yet to start | 25.06.2016 | ----
82 | Road Between Nalanda Appt. To Nightingale Appt. Vikas Puri | 0.54 | Yet to start | 25.06.2016 | ----
83 | Road Sunrise Appt. to DAV School (PWD Road) Vikas Puri | 0.435 | Yet to start | 25.06.2016 | ----
84 | Road from F-234 to IFC drain (Over head tank) Vikas Puri | 0.25 | Yet to start | 25.06.2016 | ----
85 | Road from ITI Corner (Flat No. 58) to Central School Corner (Flat No. 391) LIG Flat Hastsal | 0.24 | Yet to start | 25.06.2016 | ----
86 | Road from Navyug Appt. to IFC drain (Brotherhood Appt.) Vikas Puri | 0.38 | Yet to start | 25.06.2016 | ----
87 | Guruvirja Nanad Marg | 2.7 | Yet to start | 25.06.2016 | ----
88 | Road starting from Oxford School to Airport Appt. (PWD Road) Vikas Puri | 0.88 | Yet to start | 25.06.2016 | ----
89 | Road between Lok Vihar Appt. (PWD Road) to Fblock Market Vikas Puri | 0.675 | Yet to start | 25.06.2016 | ----
90 | Nangloi - Najafgarh Road | 5.5 | To be opened on 01.06.16 | 25.06.2016 | ----
Name of MLA :- Sh. Naresh Balyan
Name of Constituency :- Uttam Nagar (32)
91 | Najafgarh Road (Shivaji Marg) (Pankha Road Red Light to Kakrolla Mor) | 3 | Yet to start | 25.06.2016 | ---- | Karam Veer 9654402679 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
WEST Road- II
Name of MLA:-Sh. Sukhbir Singh Dalal
Name of Constituency:- Mundka
1 | Delhi Rohtak Road (NH-10) from Metro Pillar No. 415 to Hiran Kudna more | 4.000 | 05/02/2016 | 30/06/2016 | 65% | Sh. Amandeep Kamboj 9911558786 | Sh. R.B.Nehra (Additonal Charge) 9355666768 | Sh. D.V.S. Kansal 9873601920
2 | Guru Golwalkar Marg (Kanjhawala Road) | 9.800 | 26/02/2016 | 15/06/2016 | 35%
3 | Najafgarh- Nangloi Road from NH-10 | 3.750 | 27/02/2016 | 15/06/2016 | 70%
4 | Road from Ghevra More to Chand Pur More | 7.900 | 22/02/2016 | 15/06/2016 | 35%
5 | Delhi Rohtak Road (NH-10) from Hiran Kudna more to Tikri Boader | 7.000 | 10/03/2016 | 30/06/2016 | 70%
Name of MLA:-Sh. Raghuvinder Shokeen
Name of Constituency:-Nangloi
6 | Delhi Rohtak Road (NH-10) | 2.500 | 05/05/2016 | 15/06/2016 | 20% | Sh. Balbir Singh 9899751635 | Sh. R.B.Nehra 9355666768 | Sh. D.V.S. Kansal 9873601920
|  | 2.700 | 06/04/2016 | 15/06/2016 | 50%
7 | Outer Ring Road No. 26 | 2.800 | 30/04/2016 | 15/06/2016 | 70%
8 | Road from Outer Ring Road Meera Bagh to GH-8 Fire station Paschim Vihar | 1.251 | 20/05/2016 | 15/06/2016 | 5%
9 | Road from GH-6 Chowk to GH-5 and 7 Paschim Vihar | 0.292 | 20/05/2016 | 15/06/2016 | 5%
10 | Road from Garg Plaza to L.I.C. Colony Paschim Vihar | 1.322 | 20/05/2016 | 15/06/2016 | 5%
11 | Road from Sai Baba Mandir GH-12 to GH-8 Fire station Paschim Vihar | 0.963 | 06/04/2016 | 15/06/2016 | 60%
12 | Road from Outer Ring Road Bhera Enclave to Sai Baba Mandir Paschim Vihar | 1.251 | 06/04/2016 | 15/06/2016 | 80%
13 | Road from GH-13 to Sayed Nangloi Village Chowk Paschim Vihar | 0.902 | 20/05/2016 | 15/06/2016 | 6% | Sh. Balbir Singh 9899751635 | Sh. R.B.Nehra 9355666768 | Sh. D.V.S. Kansal 9873601920
14 | Road from Sant Mar'ks School to DDA Mkt. GH-5&7 Paschim Vihar | 0.435 | 20/05/2016 | 15/06/2016 | 8%
15 | Laxmi Narain Marg (N.S. Road) | 0.700 | 06/04/2016 | 15/06/2016 | 90%
16 | Ch. Prem Sukh Road | 1.292 | 06/04/2016 | 15/06/2016 | 90%
17 | 60' road in Jawala Puri | 1.150 | 06/04/2016 | 15/06/2016 | 70%
18 | Road from Capital Plaza Market to Jhaj Aptt. Mianwali Nagar | 0.350 | 20/05/016 | 15/06/2016 | 90%
19 | Road from Vindhachal Aptt. To Viral Co. Op. Society Mianwali Nagar | 0.350 | 20/05/016 | 15/06/2016 | 40%
20 | Road from Rblock jwalapuri to Sai mandir Guru Harkishan Nagar | 0.360 | 20/05/016 | 15/06/2016 | 7%
21 | Road from Durbal Nath Vatica to NH-10 | 0.600 | No drain
Name of MLA:-Sh. Garish Soni
Name of Constituency:-Madi Pur
22 | Road from 48 NWA Ch. Balbir Singh Marg to Road No. 32 | 0.390 | 25/05/2016 | 15/06/2016 | 2% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. D.V.S. Kansal 9873601920
23 | Vashisth Kumar Gulla Marg | 1.390 | 09/05/2016 | 15/06/2016 | 70%
24 | N.A. Road | 1.000 | Yet to start | 30/06/2016 | ----
25 | Ch. Balbir Singh Marg (Club Road) | 0.390 | 09/05/2016 | 15/06/2016 | 70%
26 | Road from Paschim Puri Chowk to New Slum Qtrs. | 0.450 | Yet to start | 30/06/2016 | ----
27 | Road from Shiv Mndir Road (Rohtak Road) to shiv Mandir Madipur Village | 0.700 | 03/05/2016 | 15/06/2016 | 75%
28 | Road from Madipur Main Road from Rohtak Road to Paschim Puri Chowk | 1.000 | Yet to start | 30/06/2016 | ----
29 | Road No. 32 (Hans Raj Model School )to Road No. 33 | 1.510 | 28/04/2016 | 15/06/2016 | 65%
30 | Road from H.No. A-250 to Shiv Mandir Road in C-103 Punjabi Bagh | 0.480 | 23/04/2016 | 15/06/2016 | 70% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. D.V.S. Kansal 9873601920
31 | Road No. 77 (Punjabi Bagh) | 1.410 | 23/04/2016 | 15/06/2016 | 55%
32 | Road No. 28 | 1.930 | 20/05/2016 | 30/06/2016 | 10%
33 | Road No. 29 | 2.800 | 20/05/2016 | 30/06/2016 | 35%
34 | Road from Road No. 41 from H.No. 1 to 81 in West Punjabi Bagh | 1.715 | 20/05/2016 | 30/06/2016 | 10%
35 | Road from Najafgarh Road to WZ-494, Basai Darapur (Sheo Nath Tyagi Marg) | 0.675 | 20/05/2016 | 20/06/2016 | 8%
36 | Road from H-1 Bali Nagar (NG Road) to ESI Hospital (Ring Road) [ Major Sunil Bakshi Marg) | 0.520 | 20/05/2016 | 20/06/2016 | 5%
Name of MLA:-Sh.Shiv Charan Goel
Name of Constituency:-Moti Nagar
37 | Punjab Garden Road | 0.210 | 06/04/2016 | 15/06/2016 | 30% | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. D.V.S. Kansal 9873601920
38 | Smt. Ginni Devi Road | 0.750 | 06/04/2016 | 15/06/2016 | 30%
39 | Bhagwan Dass Marg (K.C. Garg Marg) | 0.300 | 06/04/2016 | 15/06/2016 | 30%
40 | Ring Road | 3.000 | 06/04/2016 | 30/06/2016 | 40%
41 | Najafgarh Road from Zakhira Round about to Moti Nagar | 2.240 | 20/05/2016 | 30/06/2016 | 25%
42 | Shivdass Puri Marg | 2.000 | 20/05/2016 | 30/06/2016 | 5%
43 | Road from Milan Cinema to H. No. 19/289 | 0.420 | 20/05/2016 | 20/06/2016 | 5%
44 | Road from HIL to Bus Terminal of 234, Karampura | 0.412 | 20/05/2016 | 20/06/2016 | 5%
45 | Rohtak Road from Zakhira to Punjabi Bagh | 2.100 | 30/04/2016 | 30/06/2016 | 25%
46 | Rama Road (Satguru Ram Singh Marg) | 1.695 | 30/04/2016 | 30/06/2016 | 35%
47 | Road from Road No. 36 (Sat Guru Ram Singh Marg (Maya Puri Chowk to SD Public School) | 2.000 | Yet to start | 30/06/2016 | -
48 | Rama Road (Satguru Ram Singh Marg) | 1.200 | 20/05/2016 | 30/06/2016 | 5% | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. D.V.S. Kansal 9873601920
49 | Mahatma Gandhi Marg (Ring road) | 1.750 | Yet to start | 30/06/2016 | -
50 | Road from Bus Route B-14 Tagore Market to G-82 Kirti Nagar | 0.910 | Yet to start | 30/06/2016 | -
51 | Major Rajive Bhasin Marg D/Story | 0.325 | 07/05/2016 | 15/06/2016 | 50%
52 | Pankaj Batra Marg | 0.770 | 07/05/2016 | 15/06/2016 | 50%
53 | Lai Sai Mandir Marg D/Story | 0.325 | 20/05/2016 | 15/06/2016 | 5%
54 | 80' wide Road MS Garden Road | 2.490 | 07/05/2016 | 15/06/2016 | 50%
Name of MLA:-Sh.Hazari Lal Chauhan
Name of Constituency:-Patel Nagar
55 | Patel Road | 2.930 | Yet to start | 30/06/2016 | - | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. D.V.S. Kansal 9873601920
56 | Vishwakarma Marg | 1.000 | 07/05/2016 | 30/06/2016 | 15%
57 | T-Sohan Lal Marg | 0.900 | 07/05/2016 | 30/06/2016 | 15%
58 | G.L. Sikka Marg | 0.800 | 07/05/2016 | 30/06/2016 | 15%
59 | Suman Lata Badola Marg | 0.243 | 07/05/2016 | 30/06/2016 | 15%
Circle : North
Name of Division : EE North-Roads
Name of MLA :- Sh. Pawan Kumar Sharma
Name of Constituency :- Adarsh Nagar
1 | Kushal Cinema Road Starting from Raseela Paint Shop to T Point Pryas Road in Jahangirpuri-I, W.No. 16 Civil Line Zone | 1.102 | 21-12-15 | 15-06-16 | 85% | Sh. Anmol Kumar 8742957738 | Sh. S.K. Bali 9717322310 | Sh. Bishamber Dass 9873245771
2 | Dhobhi Ghat Road Starting from Kushal Cinema Chowk to Shah Alam Bandh Road | 0.45 | 21-12-15 | 15-06-16 | 85%
3 | Malik Ram Tandon Marg from Road No. 51 to Shah Alam Bandh Road | 0.89 | 21-12-15 | 15-06-16 | 85%
4 | Shah Alam Bandh Road from Burari Road to 80" Road (ROW) at Malik Ram Tondon Road upto Road No. 51 | 1.55 | 21-12-15 | 15-06-16 | 85%
5 | Shah Alam Bandh Road from Main G.T. Road to Malik Ram Tandon Marg | 1.4 | 21-12-15 | 15-06-16 | 85% | Sh. Anmol Kumar 8742957738 | Sh. S.K. Bali 9717322310 | Sh. Bishamber Dass 9873245771
6 | Mangal Bazar Road starting from Kushal Road Green Belt to Shah Alam Bandh Road | 0.4 | 21-12-15 | 15-06-16 | 85%
7 | Prayas Road (from Shah Alam Bandh Road to Dhalao, Jahangirpuri) | 0.7 | 21-12-15 | 15-06-16 | 85%
8 | Fire Station to Pump House | 0.55 | 21-12-15 | 15-06-16 | 85%
9 | Mall Road Extension from Azadpur Flyover to Mukarba Chowk | 3.35 | 27-03-16 | 15-06-16 | 40% | Sh. Sachin Choudhary 9560134704 | Sh. R.P Verma 9868704799 | Sh. Bishamber Dass 9873245771
10 | Model Town-III Road from Mall Road to Arya Samaj Mandir | 0.727 | 20-05-16 | 15-06-16 | 5%
11 | Indra Park Road | 0.38 | 30-05-16 | 15-06-16 | 0%
12 | Princess Road from Mall road to Road No.51 | 3.1 | 20-05-16 | 15-06-16 | 10%
13 | Road No. 51 from Azadpur Flyover to Outer Ring Road | 2.5 | 30-05-16 | 15-06-16 | 0%
Name of MLA :- Sh. Akhilesh pati Tripati
Name of Constituency :- Model Town
14 | Mahatma Gandhi road (Ring Road) from Camp Chowk to Azadpur Flyover | 3.5 | 10-05-16 | 15-06-16 | 10% | Sh. Sachin Choudhary 9560134704 | Sh. R.P Verma 9868704799 | Sh. Bishamber Dass 9873245771
15 | Lala Auchint Ram Road from Stadium Road to Pambari Road | 0.95 | 30-05-16 | 15-06-16 | 0%
16 | Stadium Road from Chattrashal Stadium Mall Road to GT Road | 0.68 | 30-05-16 | 15-06-16 | 0%
17 | Brahamkumari Marg from Mall Road to G.T. Road | 0.65 | 30-05-16 | 15-06-16 | 0%
18 | Model Town II Road from Mall Road to F-14/56 Model Town | 0.495 | 20-05-16 | 15-06-16 | 5%
19 | G.T Road from Gurudwara Nanakpiao to Azadpur Round about | 2 | 10-05-16 | 15-06-16 | 15%
Name of MLA :- Sh. Sharad Chauhan
Name of Constituency :- Narela
20 | Old G.T. Karnal Road | 3 | 30-05-16 | 15-06-16 | 0% | Sh. Suresh Chand Bairwa 8826718940 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
21 | Narela Alipur Road from Shahpur Grahi to Old GTK Road Alipur | 5.02 | 20-05-16 | 15-06-16 | 5%
22 | New GT Road to Old GT Road (via PHC Alipur) from New GTk Road to Old GTK Road | 0.38 | 20-05-16 | 15-06-16 | 5%
23 | Holambi Khurd Crossing to Shahpur Garhi turn | 1.9 | 20-05-16 | 15-06-16 | 5%
24 | Railway Crossing to Holambi Khurd | 0.7 | 20-05-16 | 15-06-16 | 5%
25 | NH-44 from Mukarba Chowk Flyover to Palla Mor | 7.4 | 30-05-16 | 15-06-16 | 0%
26 | NH-44 (Service Road) L.H.S | 4.5 | 30-05-16 | 15-06-16 | 0%
27 | NH-44 (Service Road) R.H.S | 4.5 | 30-05-16 | 15-06-16 | 0%
28 | Ramdev Chowk Narela to Kanya Gurukul | 1.9 | 16-05-16 | 15-06-16 | 20%
29 | Narela Alipur Road from Narela Y section to Shahpur Garhi | 3.4 | 16-05-16 | 15-06-16 | 10%
30 | Narela Safiabad Road from Narela to Safiabad Border | 2.9 | 16-05-16 | 15-06-16 | 20%
31 | Narela Lampur Road from Narela to Lampur Border | 3.8 | 16-05-16 | 15-06-16 | 10%
32 | New GT Road to Old GT Road (via PHC Alipur) from New GTk Road to Old GTK Road | 0.38 | 30-05-16 | 15-06-16 | 0%
33 | Nangli Puna Underpass to Khera Kalan Railway X-ing. | 3 | 30-05-16 | 15-06-16 | 0%
34 | Khera Kalan to Holambi Kalan via Naya bans | 7 | 30-05-16 | 15-06-16 | 0% | Sh. Suresh Chand Bairwa 8826718940 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
35 | NH-44 to Bakhtawar Pur | 3.5 | 30-05-16 | 15-06-16 | 0%
36 | Subhash Chowk Bhakhtawar Pur to Palla | 3.2 | 30-05-16 | 15-06-16 | 0%
37 | Subhash Chowk Bhakhtawar Pur to Hiranki Bandh | 4.2 | 30-05-16 | 15-06-16 | 0%
38 | NH-44 from Palla More (Shani Mandir) to Singhu Border | 5.4 | 30-05-16 | 15-06-16 | 0%
Name of MLA :- Sh. Ajesh Yadav
Name of Constituency :- Badli
39 | ITI Road from Main Jahangirpuri Road to Metro App. | 0.324 | 21-12-15 | 15-06-16 | 65% | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
40 | Back side K Block Road from Metro App. to dividing road K Block | 0.17 | 21-12-15 | 15-06-16 | 65%
41 | Lucky Park Road from J-51 to J-1951 | 0.5 | 21-12-15 | 15-06-16 | 65%
42 | Lucky Park Road to I-2000 (Back Side Road) | 0.35 | 21-12-15 | 15-06-16 | 65%
43 | Mangal Bazar Road B Block | 0.55 | 21-12-15 | 15-06-16 | 65%
44 | Zonal Park Road C Block | 0.55 | 21-12-15 | 15-06-16 | 65%
45 | Jahangirpuri Main Road from G.T. Road Red Light to Fire Station | 1.395 | 21-12-15 | 15-06-16 | 65%
46 | Bhalswa Dairy Road from Flood Road to C Block along Bhalswa Lake via Shani Bazar | 1.83 | 21-12-15 | 15-06-16 | 65%
47 | Railway Road from NH-44 to Badli Railway Station | 1.25 | 16-05-16 | 15-06-16 | 5%
48 | Swaroop Nagar Road | 2 | 30-05-16 | 15-06-16 | 0%
49 | ORR Mukarba Chowk Flyover | 6.8 | 30-05-16 | 15-06-16 | 0%
50 | G.T. Karnal Road to Libaspur Road | 1.6 | 16-05-16 | 15-06-16 | 5%
51 | 66 Ft. Road Libaspur to Gurudwara Road | 1.7 | 16-05-16 | 15-06-16 | 5% | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
52 | G.T. Karnal Road to Siraspur Village | 2 | 16-05-16 | 15-06-16 | 5%
53 | Libaspur to Siraspur Road | 0.5 | 16-05-16 | 15-06-16 | 5%
54 | Mam Chand Dhania Marg | 2.7 | 16-05-16 | 15-06-16 | 5%
Name of MLA :- Shri Ved Prakash
Name of Constituency :- Bawana
55 | From Western Yamuna Canal to Auchandi Border | 18.5 | 26-02-16 | 15-06-16 | 50% | Sh. Suresh Chand Bairwa 8826718940 | Sh. K.S. Dahiya 9810654956 | Sh. Bishamber Dass 9873245771
56 | Auchandi Border to Tatesar Village | 9.3 | 26-02-16 | 15-06-16 | 50%
57 | Majra Dabbas to Sannoth Mor | 8 | 26-02-16 | 15-06-16 | 50%