## 27.06.16
East Delhi Municipal Corporation Status of De-silting of Drains / Nallah above 4 Ft width / depth
Date 27.06.16
S.No. | Total No. of Drain | No. of Drains where desilting Completed | No. of Drains where desilting In Progress | Lenth of Drain (In KM) | Proposed Qty. of Silt in M.T. (w.e.f. 01.10.15 to 31.05.16) | Quantity of Silt removed from 01.08.13 to 30.09.13 | Total Quantity of Silt removed from 01.10.15 to 19.06.16 | Total of Silt removed from 01.10.15 to 19.06.16 (in Percentage) | Quantity of Silt removed from 20.06.16 and 26.06.16 | Total Quantity of Silt removed from 01.10.15 to 26.06.16 | Total of Silt removed from 01.10.15 to 26.06.16 (in Percentage) | Remark
Shahdara (North) | 112 | 112 | - | 65.947 | 33787 | 4692.69 | 29610 | 87.64% | 1934.07 | 31544.07 | 93.36%
Shahdara (South) | 115 | 115 | - | 62.995 | 17803.64 |  | 17017 | 95.58% | 903.49 | 17920.49 | 100.7%
Total | 227 | 227 | - | 128.942 | 51590.64 | 0 | 41605.66 | 80.65% | 2837.56 | 49465* | 96%
*Balance silt will be transported to SLF Gazipur in 3 or 4 Days