## 27.06.2016
MLA wise Desilting Report (Preparation for Monsoon) under SOUTH (M) ZONE.
Date : 27.06.2016
SI. No. | Name of Roads | Length (inKm) | Date of Start | Date of Completion | % Progress as on Date : 27.06.2016 | JE in charge / Mobile No. | AE in charge / Mobile No. | EE in charge / Mobile No. | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Circle South(M) PWD
Name of MLA :- Sh. Somnath Bharti
Name of Constituency :- Malviya Nagar (43)
1 | Sri Aurobindo Marg | 5 | 18.05.16 | 30.06.2016 | 92% | Sh. Shivendra Singh 7428188709 | Sh. R.K. Joshi 9868958324 | Sh. Jagdish Prasad 9560207879
2 | Outer Ring Road ( IIT Flyover to Jia Sarai) | 1.5 | 18.05.16 | 30.06.2016 | 65% | Sh. Shivendra Singh 7428188709 | Sh. R.K. Joshi 9868958324 | Sh. Jagdish Prasad 9560207879
3 | Ch. Jhandu Singh Marg | 1.53 | 18.05.16 | 30.06.2016 | 80% | Sh. P.K. Meena 9013673061 | Sh. R.K. Joshi 9868958324 | Sh. Jagdish Prasad 9560207879
4 | Ch. Harsukh Marg | 1.83 | 18.05.16 | 30.06.2016 | 70% | Sh. P.K. Meena 9013673061 | Sh. R.K. Joshi 9868958324 | Sh. Jagdish Prasad 9560207879
5 | Ch. Hukum Chand Marg | 0.6 | 18.05.16 | 30.06.2016 | 95% | Sh. P.K. Meena 9013673061 | Sh. R.K. Joshi 9868958324 | Sh. Jagdish Prasad 9560207879
6 | Green Park Market Road | 1 | 18.05.16 | 30.06.2016 | 70% | Sh. P.K. Meena 9013673061 | Sh. R.K. Joshi 9868958324 | Sh. Jagdish Prasad 9560207879
7 | Shaheed Jeet Singh | 2.1 | 18.05.16 | 30.06.2016 | 65% | Sh. Shivendra Singh 7428188709 | Sh. R.K. Joshi 9868958324 | Sh. Jagdish Prasad 9560207879
8 | Road from B 15/7 to BSES Office,Q.I.A. | 0.3 | 18.05.16 | 30.06.2016 | 70% | Sh. Shivendra Singh 7428188709 | Sh. R.K. Joshi 9868958324 | Sh. Jagdish Prasad 9560207879
9 | Road from B 12 to IIM Qutub Institutional Area. | 0.1 | 18.05.16 | 30.06.2016 | 70% | Sh. Shivendra Singh 7428188709 | Sh. R.K. Joshi 9868958324 | Sh. Jagdish Prasad 9560207879
10 | Peripheral Road of A Block of Q.I.A. | 0.41 | 18.05.16 | 30.06.2016 | 72% | Sh. Shivendra Singh 7428188709 | Sh. R.K. Joshi 9868958324 | Sh. Jagdish Prasad 9560207879
11 | Road from USO House to FAI House Q.I.A. | 0.2 | 18.05.16 | 30.06.2016 | 70% | Sh. Shivendra Singh 7428188709 | Sh. R.K. Joshi 9868958324 | Sh. Jagdish Prasad 9560207879
12 | Peripheral Road of C and B Block of Q.I.A. | 1.57 | 18.05.16 | 30.06.2016 | 72% | Sh. Shivendra Singh 7428188709 | Sh. R.K. Joshi 9868958324 | Sh. Jagdish Prasad 9560207879
13 | Narender Kumar Pandey Marg | 1.16 | 18.05.16 | 30.06.2016 | 78% | Sh. P.K. Meena 9013673061 | Sh. R.K. Joshi 9868958324 | Sh. Jagdish Prasad 9560207879
14 | Hauz Khas Village | 0.9 | 18.05.16 | 30.06.2016 | 92% | Sh. P.K. Meena 9013673061 | Sh. R.K. Joshi 9868958324 | Sh. Jagdish Prasad 9560207879
15 | Ring Road | 2.1 | 18.05.16 | 30.06.2016 | 72% | Sh. P.K. Meena 9013673061 | Sh. R.K. Joshi 9868958324 | Sh. Jagdish Prasad 9560207879
16 | August Kranti Marg. | 2.9 | 20.05.2016 | 30.06.2016 | 55% | Sh. Sanjeev Kumar 9873761123 | Sh. O.P. Rai 9868126611 | Sh. Jagdish Prasad 9560207879
17 | Balbir Saxena Marg | 0.8 | 20.05.2016 | 30.06.2016 | 45% | Sh. Sanjeev Kumar 9873761123 | Sh. O.P. Rai 9868126611 | Sh. Jagdish Prasad 9560207879
18 | Ch. Dilip Singh Marg, P.S Hauz Khas | 0.6 | 20.05.2016 | 30.06.2016 | 47% | Sh. Sanjeev Kumar 9873761123 | Sh. O.P. Rai 9868126611 | Sh. Jagdish Prasad 9560207879
19 | Mahinder Singh Jain Marg Road / Gautam Nagar Road | 1.2 | 20.05.2016 | 30.06.2016 | 50% | Sh. Sanjeev Kumar 9873761123 | Sh. O.P. Rai 9868126611 | Sh. Jagdish Prasad 9560207879
20 | P-Block Road from August Kranti Marg via jain Mandir & Dustbin to August Kranti Marg. | 0.34 | 20.05.2016 | 30.06.2016 | 60% | Sh. Sanjeev Kumar 9873761123 | Sh. O.P. Rai 9868126611 | Sh. Jagdish Prasad 9560207879
21 | D-Block Road from H.No.D-27 to C-1, Ring Road ,NDSE-II | 0.3 | 20.05.2016 | 30.06.2016 | 60% | Sh. Sanjeev Kumar 9873761123 | Sh. O.P. Rai 9868126611 | Sh. Jagdish Prasad 9560207879
22 | Sudarshan Cinema Road. | 0.72 | 20.05.2016 | 30.06.2016 | 60% | Sh. Sanjeev Kumar 9873761123 | Sh. O.P. Rai 9868126611 | Sh. Jagdish Prasad 9560207879
23 | Gautam Nagar Road | 0.5 | 20.05.2016 | 30.06.2016 | 60% | Sh. Sanjeev Kumar 9873761123 | Sh. O.P. Rai 9868126611 | Sh. Jagdish Prasad 9560207879
24 | August Kranti Marg to N-15 Panchsheel | 0.08 | 20.05.2016 | 30.06.2016 | 70% | Sh. Sanjeev Kumar 9873761123 | Sh. O.P. Rai 9868126611 | Sh. Jagdish Prasad 9560207879
25 | Road form Balbir Sxsena Marg to Ch. Dalip SinghMarg (NIFT Road), Hauz Khas | 0.6 | 20.05.2016 | 30.06.2016 | 60% | Sh. Sanjeev Kumar 9873761123 | Sh. O.P. Rai 9868126611 | Sh. Jagdish Prasad 9560207879
26 | Road form August Kranti marg to Aurobindo Marg (Subash Chopra Road), Hauz Khas | 0.79 | 20.05.2016 | 30.06.2016 | 60% | Sh. Sanjeev Kumar 9873761123 | Sh. O.P. Rai 9868126611 | Sh. Jagdish Prasad 9560207879
27 | Outer Ring Road (Panchsheel to IIT Gate) | 1 | 14.05.16 | 30.06.2016 | 92% | --- | Sh. Surendra Kumar 9968227376 | Sh. Jagdish Prasad 9560207879
28 | S-Bend Road (Maharishi Dayanand Marg) | 1.8 | 14.05.16 | 30.06.2016 | 82% | --- | Sh. Surendra Kumar 9968227376 | Sh. Jagdish Prasad 9560207879
29 | Shivalik Road (Basant Kaur Marg) | 1.86 | 14.05.2016 | 30.06.2016 | 75% | Sh. Sanjeev Kumar 9873761123 | Sh. O.P. Rai 9868126611 | Sh. Jagdish Prasad 9560207879
30 | Guru Govind Singh Marg | 1.2 | 14.05.2016 | 30.06.2016 | 70% | Sh. Sanjeev Kumar 9873761123 | Sh. O.P. Rai 9868126611 | Sh. Jagdish Prasad 9560207879
31 | Press Enclave (BRT to Saket Court) | 4 | 25.05.2016 | 30.06.2016 | 75% | Sh. Suresh Kumar 9899542920 | Sh. A.K. Sharma 9810576706 | Sh. Narender Mahajan 9933331859
32 | Road in front of H.No. C-11 to C-20 Malviya Nagar | 0.11 | 25.05.2016 | 30.06.2016 | 72% | Sh. Suresh Kumar 9899542920 | Sh. A.K. Sharma 9810576706 | Sh. Narender Mahajan 9933331859
33 | Shekh Sarai Phase-1 | 0.3 | 25.05.2016 | 30.06.2016 | 70% | Sh. Suresh Kumar 9899542920 | Sh. A.K. Sharma 9810576706 | Sh. Narender Mahajan 9933331859
34 | Khirki Road | 0.85 | 25.05.2016 | 30.06.2016 | 70% | Sh. Suresh Kumar 9899542920 | Sh. A.K. Sharma 9810576706 | Sh. Narender Mahajan 9933331859
35 | Road in front of Mother International School | 0.54 | 25.05.2016 | 30.06.2016 | 90% | Sh. Suresh Kumar 9899542920 | Sh. A.K. Sharma 9810576706 | Sh. Narender Mahajan 9933331859
Name of MLA :- Sh. Naresh Yadav
Name of Constituency :- Mehrauli (45)
1 | Anuvart Marg | 2.5 | 17.05.16 | 30.06.2016 | 90% | Sh. Shivendra Singh 7428188709 | Sh. J. R. Meena 9910965798 | Sh. Jagdish Prasad 9560207879
2 | Aruna Asaf Ali Road | 3.5 | 17.05.16 | 30.06.2016 | 75% | Sh. Shivendra Singh 7428188709 | Sh. J. R. Meena 9910965798 | Sh. Jagdish Prasad 9560207879
3 | Vedant Deshika Marg | 0.7 | 17.05.16 | 30.06.2016 | 80% | Sh. Shivendra Singh 7428188709 | Sh. J. R. Meena 9910965798 | Sh. Jagdish Prasad 9560207879
4 | Qutub Minar Round About | 1 | 17.05.16 | 30.06.2016 | 75% | Sh. Shivendra Singh 7428188709 | Sh. J. R. Meena 9910965798 | Sh. Jagdish Prasad 9560207879
5 | B-1 Telephone Exchange Road,Vasant Kunj (Mahipalpur Road to B-5 & B-6 Road) | 0.6 | 17.05.16 | 30.06.2016 | 95% | Sh. Shivendra Singh 7428188709 | Sh. J. R. Meena 9910965798 | Sh. Jagdish Prasad 9560207879
6 | DAV School Road Vasant Kunj | 0.55 | 17.05.16 | 30.06.2016 | 90% | Sh. Shivendra Singh 7428188709 | Sh. J. R. Meena 9910965798 | Sh. Jagdish Prasad 9560207879
7 | Shiv Mandir to B-5 & B-6 Road) | 0.3 | 17.05.16 | 30.06.2016 | 90% | Sh. Shivendra Singh 7428188709 | Sh. J. R. Meena 9910965798 | Sh. Jagdish Prasad 9560207879
8 | D-1 & D-2 Road, Vasant Kunj | 0.24 | 17.05.16 | 30.06.2016 | 95% | Sh. Shivendra Singh 7428188709 | Sh. J. R. Meena 9910965798 | Sh. Jagdish Prasad 9560207879
9 | Sports Complex Road D-2,Vasant Kunj | 0.7 | 17.05.16 | 30.06.2016 | 95% | Sh. Shivendra Singh 7428188709 | Sh. J. R. Meena 9910965798 | Sh. Jagdish Prasad 9560207879
10 | Firni Road | 1 | 25.05.2016 | 30.06.2016 | 70% | Sh. Suresh Kumar 9899542920 | Sh. Sandeep Gupta 9560293030 | Sh. Narender Mahajan 9933331859
11 | J Block Saket | 0.89 | 25.05.2016 | 30.06.2016 | 80% | Sh. Suresh Kumar 9899542920 | Sh. Sandeep Gupta 9560293030 | Sh. Narender Mahajan 9933331859
12 | Old MB Road | 1 | 25.05.2016 | 30.06.2016 | 95% | Sh. Suresh Kumar 9899542920 | Sh. Sandeep Gupta 9560293030 | Sh. Narender Mahajan 9933331859
13 | Apeejay School Road (Gurudwara to J Block Road). | 0.3 | 25.05.2016 | 30.06.2016 | 80% | Sh. Suresh Kumar 9899542920 | Sh. Sandeep Gupta 9560293030 | Sh. Narender Mahajan 9933331859
14 | Pramod Mahajan Marg | 0.89 | 25.05.2016 | 30.06.2016 | 70% | Sh. Suresh Kumar 9899542920 | Sh. A.K. Sharma 9810576706 | Sh. Narender Mahajan 9933331859
Name of MLA :- Sh. Saurabh Bhardwaj
Name of Constituency :- GK-I (50)
1 | Asiad Village peripheral road | 3 | 20.05.2016 | 30.06.2016 | 65% | Sh. Sanjeev Kumar 9873761123 | Sh. O.P. Rai 9868126611 | Sh. Jagdish Prasad 9560207879
2 | Siri Fort Road | 1.2 | 20.05.2016 | 30.06.2016 | 70% | Sh. Sanjeev Kumar 9873761123 | Sh. O.P. Rai 9868126611 | Sh. Jagdish Prasad 9560207879
3 | Appjay School Road | 1.3 | 25.05.2016 | 30.06.2016 | 70% | Sh. Suresh Kumar 9899542920 | Sh. A.K. Sharma 9810576706 | Sh. Narender Mahajan 9933331859
4 | Road between DDA Flat Masjid Moth Ph-II and Jahapanah Forest | 0.5 | 25.05.2016 | 30.06.2016 | 50% | Sh. Suresh Kumar 9899542920 | Sh. A.K. Sharma 9810576706 | Sh. Narender Mahajan 9933331859
5 | Outer Ring Road (Chirag Delhi to Panchsheel) | 2.7 | 14.05.16 | 30.06.2016 | 95% | --- | Sh. Surendra Kumar 9968227376 | Sh. Jagdish Prasad 9560207879
6 | A-1 Block, Panchsheel Enclave Road | 0.5 | 14.05.16 | 30.06.2016 | 95% | --- | Sh. Surendra Kumar 9968227376 | Sh. Jagdish Prasad 9560207879
7 | B,C & D Block Panchsheel Enclave Road | 0.5 | 14.05.16 | 30.06.2016 | 95% | --- | Sh. Surendra Kumar 9968227376 | Sh. Jagdish Prasad 9560207879
Name of MLA :- Sh. Kartar Singh Tanwar
Name of Constituency & Constituency No.:- Chattarpur (46)
1 | IGNOU Road | 2.9 | 25.05.2016 | 30.06.2016 | 95% | Sh. Suresh Kumar 9899542920 | Sh. Sandeep Gupta 9560293030 | Sh. Narender Mahajan 9933331859
2 | West End Marg | 0.8 | 25.05.2016 | 30.06.2016 | 95% | Sh. Suresh Kumar 9899542920 | Sh. Sandeep Gupta 9560293030 | Sh. Narender Mahajan 9933331859
3 | 100 Foota Road Chattarpur | 1.4 | 25.05.2016 | 30.06.2016 | 90% | Dinesh Chandra 9654626313 | Sh. Mahendra Kumar Singh 9716312175 | Sh. Narender Mahajan 9933331859
4 | 60 Foota Road | 0.9 | 25.05.2016 | 30.06.2016 | 75% | Dinesh Chandra 9654626313 | Sh. Mahendra Kumar Singh 9716312175 | Sh. Narender Mahajan 9933331859
5 | SSN Marg | 10.5 | 25.05.2016 | 30.06.2016 | 80% | Dinesh Chandra 9654626313 | Sh. Mahendra Kumar Singh 9716312175 | Sh. Narender Mahajan 9933331859
6 | Gadai Pur Band Road | 3 | 25.05.2016 | 30.06.2016 | 80% | Dinesh Chandra 9654626313 | Sh. Uma Shankar 9810095413 | Sh. Narender Mahajan 9933331859
7 | Mandi Road | 8 | 10.05.2016 | 30.06.2016 | 95% | Dinesh Chandra 9654626313 | Sh. Uma Shankar 9810095413 | Sh. Narender Mahajan 9933331859
8 | Dera Bhati Road | 5.76 | 25.05.2016 | 30.06.2016 | 52% | Dinesh Chandra 9654626313 | Sh. Uma Shankar 9810095413 | Sh. Narender Mahajan 9933331859
9 | M.G. Road | 7.5 | 25.05.2016 | 30.06.2016 | 82% | Dinesh Chandra 9654626313 | Sh. Uma Shankar 9810095413 | Sh. Narender Mahajan 9933331859
10 | Aya Nagr Road | 0.6 | 25.05.2016 | 30.06.2016 | 70% | Dinesh Chandra 9654626313 | Sh. Uma Shankar 9810095413 | Sh. Narender Mahajan 9933331859
Name of MLA :- Sh. Ajay Dutt
Name of Constituency & Constituency No.:- Ambedkar (48)
1 | M.B. Road | 7 | 25.05.2016 | 30.06.2016 | 82% | Sh. Suresh Kumar 9899542920 | Sh. Sandeep Gupta 9560293030 | Sh. Narender Mahajan 9933331859
2 | Devli Road | 2 | 25.05.2016 | 30.06.2016 | 62% | Sh. Suresh Kumar 9899542920 | Sh. Sandeep Gupta 9560293030 | Sh. Narender Mahajan 9933331859
3 | Maharishi Balmiki Marg | 1.8 | 25.05.2016 | 30.06.2016 | 75% | Sh. Suresh Kumar 9899542920 | Sh. Sandeep Gupta 9560293030 | Sh. Narender Mahajan 9933331859
4 | Durbal Nath Marg | 1.09 | 25.05.2016 | 30.06.2016 | 80% | Sh. Suresh Kumar 9899542920 | Sh. Sandeep Gupta 9560293030 | Sh. Narender Mahajan 9933331859
5 | Raja Ram Marg | 0.89 | 25.05.2016 | 30.06.2016 | 60% | Sh. Suresh Kumar 9899542920 | Sh. Sandeep Gupta 9560293030 | Sh. Narender Mahajan 9933331859
6 | H Block Dakshin Puri Road | 0.4 | 25.05.2016 | 30.06.2016 | 70% | Sh. Suresh Kumar 9899542920 | Sh. Sandeep Gupta 9560293030 | Sh. Narender Mahajan 9933331859
7 | Family Court Road | 0.9 | 25.05.2016 | 30.06.2016 | 82% | Sh. Suresh Kumar 9899542920 | Sh. A.K. Sharma 9810576706 | Sh. Narender Mahajan 9933331859
8 | Pushp Vihar (Internal Road) | 4 | 25.05.2016 | 30.06.2016 | 70% | Sh. Suresh Kumar 9899542920 | Sh. A.K. Sharma 9810576706 | Sh. Narender Mahajan 9933331859
9 | H. Block Road | 1 | 25.05.2016 | 30.06.2016 | 70% | Sh. Suresh Kumar 9899542920 | Sh. A.K. Sharma 9810576706 | Sh. Narender Mahajan 9933331859
10 | NBCC Plaza Road | 1.1 | 25.05.2016 | 30.06.2016 | 70% | Sh. Suresh Kumar 9899542920 | Sh. A.K. Sharma 9810576706 | Sh. Narender Mahajan 9933331859
11 | Birla Vidya Niketan | 1 | 25.05.2016 | 30.06.2016 | 75% | Sh. Suresh Kumar 9899542920 | Sh. A.K. Sharma 9810576706 | Sh. Narender Mahajan 9933331859
12 | Mandir Marg | 1.2 | 25.05.2016 | 30.06.2016 | 67% | Sh. Suresh Kumar 9899542920 | Sh. A.K. Sharma 9810576706 | Sh. Narender Mahajan 9933331859
13 | Main Road Sector-1, Pushp Vihar | 0.75 | 25.05.2016 | 30.06.2016 | 65% | Sh. Suresh Kumar 9899542920 | Sh. A.K. Sharma 9810576706 | Sh. Narender Mahajan 9933331859
14 | Pankaj Jewel Marg, Pushp Vihar | 1.1 | 25.05.2016 | 30.06.2016 | 60% | Sh. Suresh Kumar 9899542920 | Sh. A.K. Sharma 9810576706 | Sh. Narender Mahajan 9933331859
15 | Asian Market Road in Pushp Vihar | 0.45 | 25.05.2016 | 30.06.2016 | 60% | Sh. Suresh Kumar 9899542920 | Sh. A.K. Sharma 9810576706 | Sh. Narender Mahajan 9933331859
16 | Metro Enclave Road in Pushp Vihar | 0.45 | 25.05.2016 | 30.06.2016 | 80% | Sh. Suresh Kumar 9899542920 | Sh. A.K. Sharma 9810576706 | Sh. Narender Mahajan 9933331859
Circle South East (M) PWD
EE/SER-I, PWD
Name of MLA :- Sh. Avtar Singh
Name of Constituency :- Kalkaji
1 | S. N. Puri Main Road From Cambridge School To CTC | 1.2 | 08.05.2016 | 04.09.2016 | 80% | Sh. K. Shreedhar 9643839634 | Sh. Daulat Ram 9953116700 | Sh. Virendra Singh 9868284746
2 | S. N. Puri Internal Road Post Office to CPWD Via Jal Board Office | 0.54 | 08.05.2016 | 04.09.2016 | 55% | Sh. K. Shreedhar 9643839634 | Sh. Daulat Ram 9953116700 | Sh. Virendra Singh 9868284746
3 | S.N. Puri Internal Road Opp Police Post S.N. Puri | 0.15 | 08.05.2016 | 04.09.2016 | 58% | Sh. K. Shreedhar 9643839634 | Sh. Daulat Ram 9953116700 | Sh. Virendra Singh 9868284746
4 | S. N. Puri Internal Road MCD Store to round about Via Maternity Home | 0.93 | 08.05.2016 | 04.09.2016 | 54% | Sh. K. Shreedhar 9643839634 | Sh. Daulat Ram 9953116700 | Sh. Virendra Singh 9868284746
5 | Theka Road Sri Niwas Puri | 1 | 08.05.2016 | 04.09.2016 | 80% | Sh. K. Shreedhar 9643839634 | Sh. Daulat Ram 9953116700 | Sh. Virendra Singh 9868284746
6 | Captain Gaur Marg | 2.15 | 08.05.2016 | 04.09.2016 | 90% | Sh. K. Shreedhar 9643839634 | Sh. Daulat Ram 9953116700 | Sh. Virendra Singh 9868284746
7 | C.V. Raman Marg | 2 | 11.05.2016 | 07.09.2016 | 65% | Sh. Deepak 9968266846 | Sh. Sudarshan Kumar 9654097881 | Sh. Virendra Singh 9868284746
8 | Mata Mandir Road | 0.55 | 11.05.2016 | 07.09.2016 | 75% | Sh. Deepak 9968266846 | Sh. Sudarshan Kumar 9654097881 | Sh. Virendra Singh 9868284746
9 | M.P. Road | 1.35 | 11.05.2016 | 07.09.2016 | 75% | Sh. Deepak 9968266846 | Sh. Sudarshan Kumar 9654097881 | Sh. Virendra Singh 9868284746
10 | Sujjan Mahendra Road | 0.66 | 11.05.2016 | 07.09.2016 | 65% | Sh. Deepak 9968266846 | Sh. Sudarshan Kumar 9654097881 | Sh. Virendra Singh 9868284746
11 | Mathura Road (NH2) | 2.05 | 11.05.2016 | 07.09.2016 | 70% | Sh. Deepak 9968266846 | Sh. Sudarshan Kumar 9654097881 | Sh. Virendra Singh 9868284746
12 | Sukhdev Vihar Road | 1 | 11.05.2016 | 07.09.2016 | 60% | Sh. Deepak 9968266846 | Sh. Sudarshan Kumar 9654097881 | Sh. Virendra Singh 9868284746
Name of MLA :- Sh. Madan Lal
Name of Constituency :- Kasturba Nagar
1 | Banglow Road To Gidwani Marg, Lajpat Nagar-4 | 0.12 | 08.05.2016 | 04.09.2016 | 60% | Sh. K. Shreedhar 9643839634 | Sh. Daulat Ram 9953116700 | Sh. Virendra Singh 9868284746
2 | Dr. Moti Lal Jotwani Road, Lajpat Nagar-IV | 0.47 | 08.05.2016 | 04.09.2016 | 60% | Sh. K. Shreedhar 9643839634 | Sh. Daulat Ram 9953116700 | Sh. Virendra Singh 9868284746
3 | Central Road to Back of Ring Road, Lajpat Nagar-IV | 0.35 | 08.05.2016 | 04.09.2016 | 56% | Sh. K. Shreedhar 9643839634 | Sh. Daulat Ram 9953116700 | Sh. Virendra Singh 9868284746
4 | Kalka Devi Marg | 1.12 | 08.05.2016 | 04.09.2016 | 80% | Sh. K. Shreedhar 9643839634 | Sh. Daulat Ram 9953116700 | Sh. Virendra Singh 9868284746
5 | Kalka Devi Marg to Banglow Road, Lajpat Nagar-IV | 0.49 | 08.05.2016 | 04.09.2016 | 55% | Sh. K. Shreedhar 9643839634 | Sh. Daulat Ram 9953116700 | Sh. Virendra Singh 9868284746
6 | Road No. 4 Andrews Ganj | 0.4 | 08.05.2016 | 04.09.2016 | 60% | Sh. K. Shreedhar 9643839634 | Sh. Daulat Ram 9953116700 | Sh. Virendra Singh 9868284746
7 | Road No. 5 Andrews Ganj | 0.13 | 08.05.2016 | 04.09.2016 | 62% | Sh. K. Shreedhar 9643839634 | Sh. Daulat Ram 9953116700 | Sh. Virendra Singh 9868284746
8 | Road No. 7 Andrews Ganj | 0.24 | 08.05.2016 | 04.09.2016 | 62% | Sh. K. Shreedhar 9643839634 | Sh. Daulat Ram 9953116700 | Sh. Virendra Singh 9868284746
9 | Road No. 3 Andrews Ganj | 0.75 | 08.05.2016 | 04.09.2016 | 65% | Sh. K. Shreedhar 9643839634 | Sh. Daulat Ram 9953116700 | Sh. Virendra Singh 9868284746
10 | Bhishma Pitamah Road | 2.3 | 08.05.2016 | 04.09.2016 | 82% | Sh. S.K. Singh 9899782942 | Sh. G.A. Khan 9868079601 | Sh. Virendra Singh 9868284746
11 | Road from B.P.Marg to Round About Defence Colony | 0.16 | 08.05.2016 | 04.09.2016 | 82% | Sh. S.K. Singh 9899782942 | Sh. G.A. Khan 9868079601 | Sh. Virendra Singh 9868284746
12 | Feroz Gandhi Road Lajpat Nagar | 1.05 | 08.05.2016 | 04.09.2016 | 68% | Sh. S.K. Singh 9899782942 | Sh. G.A. Khan 9868079601 | Sh. Virendra Singh 9868284746
13 | F-1 Lodhi colony to BP Flyover | 0.24 | 11.05.2016 | 07.09.2016 | 67% | Sh. Girish Kumar 9643347312 | Sh. V.K. Saini 9868876462 | Sh. Virendra Singh 9868284746
14 | BP Marg to Coffee House, Lodhi colony | 0.35 | 11.05.2016 | 07.09.2016 | 72% | Sh. Girish Kumar 9643347312 | Sh. V.K. Saini 9868876462 | Sh. Virendra Singh 9868284746
15 | Hanuman Mandir to Seva Nagar flyover | 0.46 | 11.05.2016 | 07.09.2016 | 67% | Sh. Girish Kumar 9643347312 | Sh. V.K. Saini 9868876462 | Sh. Virendra Singh 9868284746
16 | IV Avenue Road | 1.22 | 11.05.2016 | 07.09.2016 | 65% | Sh. Girish Kumar 9643347312 | Sh. V.K. Saini 9868876462 | Sh. Virendra Singh 9868284746
17 | Kushak Nallah to Seva nagar flyover | 0.7 | 11.05.2016 | 07.09.2016 | 62% | Sh. Girish Kumar 9643347312 | Sh. V.K. Saini 9868876462 | Sh. Virendra Singh 9868284746
18 | Railway phatak to subhash bazar | 0.26 | 11.05.2016 | 07.09.2016 | 67% | Sh. Girish Kumar 9643347312 | Sh. V.K. Saini 9868876462 | Sh. Virendra Singh 9868284746
19 | Ratan Lal Sahdev Marg | 0.98 | 11.05.2016 | 07.09.2016 | 60% | Sh. Girish Kumar 9643347312 | Sh. V.K. Saini 9868876462 | Sh. Virendra Singh 9868284746
20 | School Road | 0.38 | 11.05.2016 | 07.09.2016 | 56% | Sh. Girish Kumar 9643347312 | Sh. V.K. Saini 9868876462 | Sh. Virendra Singh 9868284746
21 | V Avenue Road | 1 | 11.05.2016 | 07.09.2016 | 62% | Sh. Girish Kumar 9643347312 | Sh. V.K. Saini 9868876462 | Sh. Virendra Singh 9868284746
22 | Vardhman Marg | 0.35 | 11.05.2016 | 07.09.2016 | 60% | Sh. Girish Kumar 9643347312 | Sh. V.K. Saini 9868876462 | Sh. Virendra Singh 9868284746
23 | X-Road between Block no-18 & 15 Lodhi colony | 0.16 | 11.05.2016 | 07.09.2016 | 62% | Sh. Girish Kumar 9643347312 | Sh. V.K. Saini 9868876462 | Sh. Virendra Singh 9868284746
24 | X-Road between C-2(176) &C-2(177)Lodhi Colony | 0.16 | 11.05.2016 | 07.09.2016 | 56% | Sh. Girish Kumar 9643347312 | Sh. V.K. Saini 9868876462 | Sh. Virendra Singh 9868284746
25 | X-Road between D-1 & C-2 Lodhi Colony | 0.16 | 11.05.2016 | 07.09.2016 | 52% | Sh. Girish Kumar 9643347312 | Sh. V.K. Saini 9868876462 | Sh. Virendra Singh 9868284746
26 | Lodhi Road | 1.76 | 11.05.2016 | 07.09.2016 | 80% | Sh. Girish Kumar 9643347312 | Sh. V.K. Saini 9868876462 | Sh. Virendra Singh 9868284746
27 | Kushak Nallah to CPWD Enquiry | 0.3 | 11.05.2016 | 07.09.2016 | 52% | Sh. Girish Kumar 9643347312 | Sh. V.K. Saini 9868876462 | Sh. Virendra Singh 9868284746
Name of MLA :- Sh. Saurabh Bharadwaj
Name of Constituency :- Greater Kailash
1 | Raja Dheer Sain Marg EOK from Sant Nagar to East of Kailash | 0.57 | 08.05.2016 | 04.09.2016 | 80% | Sh. K. Shreedhar 9643839634 | Sh. Daulat Ram 9953116700 | Sh. Virendra Singh 9868284746
2 | Garhi Village to National Heart Hospital | 0.41 | 08.05.2016 | 04.09.2016 | 58% | Sh. K. Shreedhar 9643839634 | Sh. Daulat Ram 9953116700 | Sh. Virendra Singh 9868284746
3 | Raja Dheer Sain Marg | 1.4 | 08.05.2016 | 04.09.2016 | 85% | Sh. K. Shreedhar 9643839634 | Sh. Daulat Ram 9953116700 | Sh. Virendra Singh 9868284746
Name of MLA :- Sh. Amanatullah Khan
Name of Constituency :- Okhla
1 | MMA Road | 3 | 11.05.2016 | 07.09.2016 | 65% | Sh. Deepak 9968266846 | Sh. Sudarshan Kumar 9654097881 | Sh. Virendra Singh 9868284746
2 | Gurudwara Road | 1.35 | 11.05.2016 | 07.09.2016 | 75% | Sh. Deepak 9968266846 | Sh. Sudarshan Kumar 9654097881 | Sh. Virendra Singh 9868284746
3 | Shiv Mandir Marg from Zonal Office to Ring Road | 0.85 | 08.05.2016 | 04.09.2016 | 90% | Sh. S.K. Singh 9899782942 | Sh. G.A. Khan 9868079601 | Sh. Virendra Singh 9868284746
Name of MLA :- Sh. Parveen Kumar
Name of Constituency :- Jungpura
1 | Vir Savarkar Marg, Lajapat Nagar | 1.05 | 08.05.2016 | 04.09.2016 | 77% | Sh. S.K. Singh 9899782942 | Sh. G.A. Khan 9868079601 | Sh. Virendra Singh 9868284746
2 | Ring Road AIIMS to Bhairon Road 'T' Jn | 9.65 | 08.05.2016 | 04.09.2016 | 82% | Sh. S.K. Singh 9899782942 | Sh. G.A. Khan 9868079601 | Sh. Virendra Singh 9868284746
3 | 2 nd Enty Road | 0.6 | 08.05.2016 | 04.09.2016 | 85% | Sh. S.K. Singh 9899782942 | Sh. G.A. Khan 9868079601 | Sh. Virendra Singh 9868284746
4 | Bhairon Road | 0.98 | 08.05.2016 | 04.09.2016 | 90% | Sh. S.K. Singh 9899782942 | Sh. G.A. Khan 9868079601 | Sh. Virendra Singh 9868284746
5 | Mathura Road | 3 | 11.05.2016 | 07.09.2016 | 85% | Sh. Girish Kumar 9643347312 | Sh. V.K. Saini 9868876462 | Sh. Virendra Singh 9868284746
6 | East Nizamuddin Peripheral road | 0.7 | 11.05.2016 | 07.09.2016 | 85% | Sh. Girish Kumar 9643347312 | Sh. V.K. Saini 9868876462 | Sh. Virendra Singh 9868284746
7 | Hospital Road | 0.56 | 11.05.2016 | 07.09.2016 | 15% | Sh. Girish Kumar 9643347312 | Sh. V.K. Saini 9868876462 | Sh. Virendra Singh 9868284746
8 | Neela gumbad to Lodhi flyover, Nazamuddin basti | 0.2 | 11.05.2016 | 07.09.2016 | 62% | Sh. Girish Kumar 9643347312 | Sh. V.K. Saini 9868876462 | Sh. Virendra Singh 9868284746
9 | Preet place to Nizmuddin railway station | 0.7 | 11.05.2016 | 07.09.2016 | 62% | Sh. Girish Kumar 9643347312 | Sh. V.K. Saini 9868876462 | Sh. Virendra Singh 9868284746
10 | Rajdoot Hotel to Preet palace | 0.2 | 11.05.2016 | 07.09.2016 | 52% | Sh. Girish Kumar 9643347312 | Sh. V.K. Saini 9868876462 | Sh. Virendra Singh 9868284746
11 | Sunder Nagar peripheral Road | 1.1 | 11.05.2016 | 07.09.2016 | 90% | Sh. Girish Kumar 9643347312 | Sh. V.K. Saini 9868876462 | Sh. Virendra Singh 9868284746
EE/SER-II, PWD
Name of MLA :- Sh. Avtar Singh
Name of Constituency :- Kalkaji
1 | SA Road (i) 0 - 1800 | 1.8 | 20.05.2016 | 30.06.16 | 70% | Er. Jai Hind 8574933594 | Er. N.R. Meena 9868787374 | Sh. R.S. Garg, EE 9818656184
2 | Hans Raj Sethi Marg from Ring Road to EPDP Road | 1.7 | 10.06.2016 | 30.06.16 | 25% | Er. Jai Hind 8574933594 | Er. N.R. Meena 9868787374 | Sh. R.S. Garg, EE 9818656184
3 | Baba Fateh Singh Marg Ravi Das Marg to Maa Anand Mai Marg | 1 | 05.06.2016 | 30.06.16 | 30% | Er. Jai Hind 8574933594 | Er. N.R. Meena 9868787374 | Sh. R.S. Garg, EE 9818656184
4 | Maharaja Agarsen Marg from Ravi Das Marg to Maa Anandmai Marg. | 0.5 | 20.05.2016 | 30.06.16 | 30% | Er. Jai Hind 8574933594 | Er. N.R. Meena 9868787374 | Sh. R.S. Garg, EE 9818656184
5 | Guru Ravi Das Marg | 2.84 | 25.05.16 | 30.06.16 | 80% | Er. Pranay Rathore 9818984464 | Er. Rakesh Kumar 971172289 | Sh. R.S. Garg, EE 9818656184
Name of MLA :- Sh. Saurabh Bhardwaj
Name of Constituency :- Greater Kailash
1 | Guru Nanak Market to Lala Lajpat Rai Marg | 0.57 | 02.06.16 | 30.06.16 | 30% | Er. Sachin Singhal 9650315678 | Er. Ram Kirti 9873775445 | Sh. R.S. Garg, EE 9818656184
2 | Nandi Vithi Marg | 0.73 | 04.06.16 | 30.06.16 | 30% | Er. Sachin Singhal 9650315678 | Er. Ram Kirti 9873775445 | Sh. R.S. Garg, EE 9818656184
3 | Lala Lajpat Rai Marg | 2.01 | 07.06.16 | 30.06.16 | - | Er. Sachin Singhal 9650315678 | Er. Ram Kirti 9873775445 | Sh. R.S. Garg, EE 9818656184
4 | Road From BRT to Hansraj Gupta Marg. | 0.34 | 02.06.16 | 30.06.16 | 30% | Er. Sachin Singhal 9650315678 | Er. Ram Kirti 9873775445 | Sh. R.S. Garg, EE 9818656184
5 | Road From B-76 to B-111 (G.K-I) | 0.33 | 15.06.16 | 30.06.16 | 30% | Er. Sachin Singhal 9650315678 | Er. Ram Kirti 9873775445 | Sh. R.S. Garg, EE 9818656184
6 | Guru Harkishan Public School to Nehru Place | 0.27 | 15.06.16 | 25.06.2016 | 90% | Er. Sachin Singhal 9650315678 | Er. Ram Kirti 9873775445 | Sh. R.S. Garg, EE 9818656184
7 | R-Block GK-1, Signal to Outer Ring Road | 0.58 | 10.06.16 | 28.06.2016 | 30% | Er. Sachin Singhal 9650315678 | Er. Ram Kirti 9873775445 | Sh. R.S. Garg, EE 9818656184
8 | Outer Ring Road | 3.8 | 14.05.16 | 30.05.16 | 85% | Er. Sachin Singhal 9650315678 | Er. Ram Kirti 9873775445 | Sh. R.S. Garg, EE 9818656184
9 | EPDP | 1.8 | 30.05.16 | 07.07.2016 | 28% | - | Er. Abhishek Singh 9971547245 | Sh. R.S. Garg, EE 9818656184
10 | Market No.2 Desh Bandhu Apartment. | 0.35 | No Drain |  | - | Er. Sachin Singhal 9650315678 | Er. Ram Kirti 9873775445 | Sh. R.S. Garg, EE 9818656184
11 | Vipin Chanderpal marg to Police Station C.R. Park. | 0.37 | No drain |  | - | Er. Sachin Singhal 9650315678 | Er. Ram Kirti 9873775445 | Sh. R.S. Garg, EE 9818656184
12 | Kali Mandir To EPDP Road. | 0.38 | New Drain |  | - | Er. Sachin Singhal 9650315678 | Er. Ram Kirti 9873775445 | Sh. R.S. Garg, EE 9818656184
13 | Hans Raj Gupta Marg | 2.69 | New Drain |  | - | Er. Sachin Singhal 9650315678 | Er. Ram Kirti 9873775445 | Sh. R.S. Garg, EE 9818656184
14 | A Block double storey road from EPDP Road (Arya Samaj Mandir to Hans Raj Sethi Marg (B-Block MCD School). | 0.5 | 12.06.16 | 30.06.2016 | 30% | Er. Sachin Singhal 9650315678 | Er. Ram Kirti 9873775445 | Sh. R.S. Garg, EE 9818656184
15 | DDA Market Road from Shivalik Appartment to Hanuman Mandir (Ravi Dass Marg) | 0.43 | 30.05.16 | 30.06.2016 | 30% | Er. Sachin Singhal 9650315678 | Er. Ram Kirti 9873775445 | Sh. R.S. Garg, EE 9818656184
16 | Bipin Chandra Pal Marg | 1.46 | 05.06.2016 | 07.07.2016 | 30% | - | Er. Abhishek Singh 9971547245 | Sh. R.S. Garg, EE 9818656184
17 | Surya Sen Marg | 0.75 | 10.06.16 | 28.06.2016 | 90% | Er. Sachin Singhal 9650315678 | Er. Ram Kirti 9873775445 | Sh. R.S. Garg, EE 9818656184
18 | Gurudwara Road G.K.II | 1.7 | 01.06.16 | 25.06.2016 | 30% | - | Er. Abhishek Singh 9971547245 | Sh. R.S. Garg, EE 9818656184
19 | Kalka Public School Road from Ravi Dass Marg to Mandakini Enclave | 0.64 | 02.06.16 | 30.06.2016 | 35% | Er. Pranay Rathore 9818984464 | Er. Rakesh Kumar 971172289 | Sh. R.S. Garg, EE 9818656184
20 | Savitri Cinema Road | 3.14 | 01.06.16 | 30.06.2016 | 75% | Er. Sachin Singhal 9650315678 | Er. Ram Kirti 9873775445 | Sh. R.S. Garg, EE 9818656184
21 | Link Road | 0.58 | 05.06.16 | 07.07.2016 | 35% | Er. Sachin Singhal 9650315678 | Er. Ram Kirti 9873775445 | Sh. R.S. Garg, EE 9818656184
Name of MLA :- Sh. N.D. Sharma
Name of Constituency :- Badarpur
1 | Jaitpur Road (Shaheed Bijender Singh Gurjar Marg) | 1.25 | 30.05.16 | 05.07.2016 | 70% | Er. Harbir Singh 9718139610 | Er. Shiv Kumar 9650747902 | Sh. R.S. Garg, EE 9818656184
2 | Jaitpur Road - Meethapur Chowk to Gurudwara | 1.21 | 02.06.16 | 07.07.2016 | 40% | Er. Harbir Singh 9718139610 | Er. Shiv Kumar 9650747902 | Sh. R.S. Garg, EE 9818656184
3 | Higher Secondary School Road - Meethapur | 0.87 | 05.06.16 | 15.07.2016 | 30% | Er. Harbir Singh 9718139610 | Er. Shiv Kumar 9650747902 | Sh. R.S. Garg, EE 9818656184
Name of MLA :- Sh. Imaamtulla Khan
Name of Constituency :- Okhla
1 | Maharaja Agarsain Marg | 0.8 | 20.05.16 | 30.06.2016 | 80% | Er. Harbir Singh 9718139610 | Er. Shiv Kumar 9650747902 | Sh. R.S. Garg, EE 9818656184
2 | Madanpur Khadar Road | 1.2 | 25.05.16 | 30.06.2016 | 70% | Er. Harbir Singh 9718139610 | Er. Shiv Kumar 9650747902 | Sh. R.S. Garg, EE 9818656184
3 | Sarita Vihar Road | 1.35 | 27.05.16 | 30.06.2016 | 80% | Er. Harbir Singh 9718139610 | Er. Shiv Kumar 9650747902 | Sh. R.S. Garg, EE 9818656184
4 | Road No.13A | 3.2 | 25.04.16 | 23.06.2016 | 100% | Er. Harbir Singh 9718139610 | Er. Shiv Kumar 9650747902 | Sh. R.S. Garg, EE 9818656184
5 | NH-2 Mathura Road | 5.8 | 25.05.16 | 28.06.2016 | 75% | Er. Harbir Singh 9718139610 | Er. Shiv Kumar 9650747902 | Sh. R.S. Garg, EE 9818656184
Name of MLA :- Sahi Ram
Name of Constituency :- Tughlakabag
1 | SA Road (i) 1800 - 5460 | 3.66 | 20.05.16 | 28.06.2016 | 75% | Er. Jai Hind 8574933594 | Er. N.R. Meena 9868787374 | Sh. R.S. Garg, EE 9818656184
2 | Road No. 13 | 2.7 | 25.05.16 | 07.07.2016 | 30% | - | Er. Abhishek Singh 9971547245 | Sh. R.S. Garg, EE 9818656184
3 | Guru Ravi Das Marg | 1 | 25.05.16 | 07.07.2016 | 80% | Er. Pranay Rathore 9818984464 | Er. Rakesh Kumar 971172289 | Sh. R.S. Garg, EE 9818656184
4 | MB Road | 5.8 | 17.05.16 | 30.06.2016 | 80% | Er. Pranay Rathore 9818984464 | Er. Rakesh Kumar 971172289 | Sh. R.S. Garg, EE 9818656184
5 | Suraj Kund Road | 0.625 | 05.06.16 | 30.06.2016 | 40% | Er. Pranay Rathore 9818984464 | Er. Rakesh Kumar 971172289 | Sh. R.S. Garg, EE 9818656184
Circle South West (M) PWD
EE/SWR-I, PWD
Name of MLA :- Smt. Promila Tokas
Name of Constituency & Constituency No.:- RK Puram (44)
1 | B.J. Marg | 1.3 | 25.05.16 | 20.06.16 | 15% | Kishan Lal Meena 8800762599 | Uday Chand Meena 9958268343 | Gulshan Sharma 9811134465
2 | Rao Tula Ram Marg (RTR Marg) | 1.7 | 15.05.16 | 20.06.16 | 90% | Kishan Lal Meena 8800762599 | Uday Chand Meena 9958268343 | Gulshan Sharma 9811134465
3 | Zonal road No. 2 (Baba Balak Nath Marg) | 1.1 | 25.05.16 | 20.06.16 | 55% | Kishan Lal Meena 8800762599 | Uday Chand Meena 9958268343 | Gulshan Sharma 9811134465
4 | Zonal Road No. 6 (Hare Krishna Mehto Marg) | 0.7 | 25.05.16 | 20.06.16 | 55% | Kishan Lal Meena 8800762599 | Uday Chand Meena 9958268343 | Gulshan Sharma 9811134465
5 | Baba Gang Nath marg | 1.17 | 25.05.16 | 20.06.16 | 30% | Kishan Lal Meena 8800762599 | Uday Chand Meena 9958268343 | Gulshan Sharma 9811134465
6 | Outer Ring Road | 4.8 | 25.05.16 | 20.06.16 | 65% | Kishan Lal Meena 8800762599 | Uday Chand Meena 9958268343 | Gulshan Sharma 9811134465
7 | Africa Avenue (Road No.9) | 2.2 | 25.05.16 | 20.06.16 | 65% | Ravinder Kumar 9818026779 | G. P. Khanna 9717284189 | Gulshan Sharma 9811134465
8 | Tamil Sangam Marg | 1.1 | 25.05.16 | 20.06.16 | 25% | Ravinder Kumar 9818026779 | G. P. Khanna 9717284189 | Gulshan Sharma 9811134465
9 | Major Som nath marg | 1.6 | 25.05.16 | 20.06.16 | 15% | Ravinder Kumar 9818026779 | G. P. Khanna 9717284189 | Gulshan Sharma 9811134465
10 | Kafi Azami Marg | 0.9 | 25.05.16 | 20.06.16 | 15% | Ravinder Kumar 9818026779 | G. P. Khanna 9717284189 | Gulshan Sharma 9811134465
11 | Church Road, R.K.Puram | 0.85 | 25.05.16 | 20.06.16 | 15% | Ravinder Kumar 9818026779 | G. P. Khanna 9717284189 | Gulshan Sharma 9811134465
12 | Babu Genu Marg, R.K.Puram | 0.6 | 25.05.16 | 20.06.16 | 15% | Ravinder Kumar 9818026779 | G. P. Khanna 9717284189 | Gulshan Sharma 9811134465
13 | Prem nath Dogra marg, R.K.Puram | 0.85 | 10.05.16 | 20.06.16 | 95% | Ravinder Kumar 9818026779 | G. P. Khanna 9717284189 | Gulshan Sharma 9811134465
14 | Kama Koti Marg | 1.75 | 25.05.16 | 20.06.16 | 30% | Ravinder Kumar 9818026779 | G. P. Khanna 9717284189 | Gulshan Sharma 9811134465
15 | Vivekanand Marg | 1.1 | 25.05.16 | 20.06.16 | 35% | Ravinder Kumar 9818026779 | G. P. Khanna 9717284189 | Gulshan Sharma 9811134465
16 | Venketeshwar Marg | 1.1 | 25.05.16 | 20.06.16 | 45% | Ravinder Kumar 9818026779 | G. P. Khanna 9717284189 | Gulshan Sharma 9811134465
17 | Poorvi Marg | 1.65 | 25.05.16 | 20.06.16 | 45% | Ravinder Kumar 9818026779 | G. P. Khanna 9717284189 | Gulshan Sharma 9811134465
18 | Paschimi Marg | 1.25 | 25.05.16 | 20.06.16 | 25% | Ravinder Kumar 9818026779 | G. P. Khanna 9717284189 | Gulshan Sharma 9811134465
19 | Munirka marg | 0.9 | 25.05.16 | 20.06.16 | 25% | Ravinder Kumar 9818026779 | G. P. Khanna 9717284189 | Gulshan Sharma 9811134465
20 | Ring Road from Hyatt Regency to Moti Bagh | 3.5 | 25.05.16 | 20.06.16 | 30% | Ravinder Kumar 9818026779 | G. P. Khanna 9717284189 | Gulshan Sharma 9811134465
Name of MLA:- Shri Naresh Yadav
Name of Constituency & Constituency No.:- Mehrauli (45)
21 | Basant marg-I | 0.9 | 25.05.16 | 20.06.16 | 25% | Ravinder Kumar 9818026779 | G. P. Khanna 9717284189 | Gulshan Sharma 9811134465
22 | Basant Marg-II | 0.5 | 25.05.16 | 20.06.16 | 25% | Ravinder Kumar 9818026779 | G. P. Khanna 9717284189 | Gulshan Sharma 9811134465
23 | A-9 Street Road | 0.65 | 25.05.16 | 20.06.16 | 25% | Ravinder Kumar 9818026779 | G. P. Khanna 9717284189 | Gulshan Sharma 9811134465
24 | Vatika Road (DPS Vasant Kunj to MM road) | 0.7 | 25.05.16 | 20.06.16 | 15% | Kishan Lal Meena 8800762599 | Uday Chand Meena 9958268343 | Gulshan Sharma 9811134465
25 | Nelson Mandela Marg | 4.04 | 25.05.16 | 20.06.16 | 30% | Kishan Lal Meena 8800762599 | Uday Chand Meena 9958268343 | Gulshan Sharma 9811134465
Name of MLA:- Shri Vijender Garg
Name of Constituency & Constituency No.:- Rajender Nagar (139)
26 | Ganga Ram Hospital Road | 1.08 | 25.05.16 | 20.06.16 | 45% | Rukvi Theo 8800645513 | Naurti Ram 8130659730 | Gulshan Sharma 9811134465
27 | PUSA Road | 1.50 Actual 2.00 KM | 25.05.16 | 20.06.16 | 45% | Rukvi Theo 8800645513 | Naurti Ram 8130659730 | Gulshan Sharma 9811134465
28 | Shankar Road | 1.64 | 25.05.16 | 20.06.16 | 55% | Rukvi Theo 8800645513 | Naurti Ram 8130659730 | Gulshan Sharma 9811134465
29 | Dr. K.S. Krishanan Marg | 0.92 | 25.05.16 | 20.06.16 | 75% | Rukvi Theo 8800645513 | Naurti Ram 8130659730 | Gulshan Sharma 9811134465
30 | PUSA Institute (IARI) Internal Road | 0.7 | 25.05.16 | 20.06.16 | 75% | Rukvi Theo 8800645513 | Naurti Ram 8130659730 | Gulshan Sharma 9811134465
31 | Dev Prakash Shastri marg (Road No. 25) | 4.45 | 25.05.16 | 20.06.16 | 65% | Rukvi Theo 8800645513 | Naurti Ram 8130659730 | Gulshan Sharma 9811134465
32 | Girdhari Lal Goswami Marg (Road No. 89) | 3.05 | 25.05.16 | 20.06.16 | 65% | Rukvi Theo 8800645513 | Naurti Ram 8130659730 | Gulshan Sharma 9811134465
33 | Ram Nath Vij Marg | 1.19 | 25.05.16 | 20.06.16 | N/R | Rukvi Theo 8800645513 | Naurti Ram 8130659730 | Gulshan Sharma 9811134465
34 | O.P. Bharti Marg 1 | 0.535 | 25.05.16 | 20.06.16 | 45% | Rukvi Theo 8800645513 | Naurti Ram 8130659730 | Gulshan Sharma 9811134465
35 | O.P. Bharti Marg 2 | 0.762 | 25.05.16 | 20.06.16 | 45% | Rukvi Theo 8800645513 | Naurti Ram 8130659730 | Gulshan Sharma 9811134465
36 | O.P. Bharti Marg 3 | 0.181 | 25.05.16 | 20.06.16 | 45% | Rukvi Theo 8800645513 | Naurti Ram 8130659730 | Gulshan Sharma 9811134465
37 | O.P. Bharti Marg 4 | 0.42 | 25.05.16 | 20.06.16 | 35% | Rukvi Theo 8800645513 | Naurti Ram 8130659730 | Gulshan Sharma 9811134465
38 | Dr. Girdhari Lal Goswami Marg | 0.6 | 25.05.16 | 20.06.16 | 55% | Rukvi Theo 8800645513 | Naurti Ram 8130659730 | Gulshan Sharma 9811134465
39 | Upper Ridge Road (Vande Martram Marg) | 1.5 | 25.05.16 | 20.06.16 | Drain not exist | C. M. Meena 8882355055 | Sh. Yaad Ram Meena 9999109979 | Gulshan Sharma 9811134465
Name of MLA:- Commando Surender Singh
Name of Constituency & Constituency No.:- Delhi Cantt. (38)
40 | Ullan Buttor Marg | 0.7 | 25.05.16 | 20.06.16 | 95% | Kishan Lal Meena 8800762599 | Uday Chand Meena 9958268343 | Gulshan Sharma 9811134465
41 | Ring Road from Moti Bagh to Mayapuri | 8.6 | 25.05.16 | 20.06.16 | 75% | C. M. Meena 8882355055 | Sh. Yaad Ram Meena 9999109979 | Gulshan Sharma 9811134465
42 | NH-8 | 2.9 | 25.05.16 | 20.06.16 | 80% | C. M. Meena 8882355055 | Sh. Yaad Ram Meena 9999109979 | Gulshan Sharma 9811134465
Name of MLA:- Jagdeep Singh
Name of Constituency & Constituency No.:- Hari Nagar (28)
43 | Road No. 36(Sat Guru Ram Singh Marg) | 3.05 | 25.05.16 | 20.06.16 | 65% | C. M. Meena 8882355055 | Sh. Yaad Ram Meena 9999109979 | Gulshan Sharma 9811134465
Name of MLA:- Col. Devender Sehrawat
Name of Constituency & Constituency No.:- Hari Nagar (20)
44 | M.M.Road | 8.1 | 25.05.16 | 20.06.16 | 25% | Kishan Lal Meena 8800762599 | Uday Chand Meena 9958268343 | Gulshan Sharma 9811134465
EE/SWR-II, PWD
Name of MLA :- Sh. Rajesh Rishi (West) Name of Constituency :- Janak Puri (30)
1 | Pankha Road | 5.05 | 17.05.2016 | 02.07.2016 | 50% | Sh. Mithun Kumar 8470876781 | Sh. S.K. VARSHNEY 9212006584 | Sh. J.P. Vasisht 9971396164 | work in progress
2 | Lal Sai Road | 2.525 | 17.05.2016 | 02.07.2016 | 60% | Sh. Mithun Kumar 8470876781 | Sh. S.K. VARSHNEY 9212006584 | Sh. J.P. Vasisht 9971396164 | work in progress
3 | Vidya Marg Road | 1.54 | 17.05.2016 | 02.07.2016 | 80% | Sh. Mithun Kumar 8470876781 | Sh. S.K. VARSHNEY 9212006584 | Sh. J.P. Vasisht 9971396164 | work in progress
4 | Dabri Road | 0.9 | 17.05.2016 | 02.07.2016 | 65% | Sh. Mithun Kumar 8470876781 | Sh. S.K. VARSHNEY 9212006584 | Sh. J.P. Vasisht 9971396164 | work in progress
5 | Mall Road | 0.612 | 17.05.2016 | 02.07.2016 | 50% | Sh. Mithun Kumar 8470876781 | Sh. S.K. VARSHNEY 9212006584 | Sh. J.P. Vasisht 9971396164 | work in progress
6 | Ram Mandir Marg | 0.861 | 17.05.2016 | 02.07.2016 | 60% | Sh. Mithun Kumar 8470876781 | Sh. S.K. VARSHNEY 9212006584 | Sh. J.P. Vasisht 9971396164 | work in progress
7 | Shani Bazr Road | 0.647 | 17.05.2016 | 02.07.2016 | 60% | Sh. Mithun Kumar 8470876781 | Sh. S.K. VARSHNEY 9212006584 | Sh. J.P. Vasisht 9971396164 | work in progress
8 | Fire Station Road | 0.5 | 17.05.2016 | 02.07.2016 | 75% | Sh. Mithun Kumar 8470876781 | Sh. S.K. VARSHNEY 9212006584 | Sh. J.P. Vasisht 9971396164 | work in progress
9 | Connecting Road 1 | 0.35 | 17.05.2016 | 02.07.2016 | 75% | Sh. Mithun Kumar 8470876781 | Sh. S.K. VARSHNEY 9212006584 | Sh. J.P. Vasisht 9971396164 | work in progress
10 | Connecting Road 2 | 0.45 | 17.05.2016 | 02.07.2016 | 70% | Sh. Mithun Kumar 8470876781 | Sh. S.K. VARSHNEY 9212006584 | Sh. J.P. Vasisht 9971396164 | work in progress
11 | Lal Sai to Pankha Road | 0.633 | 17.05.2016 | 02.07.2016 | 60% | Sh. Mithun Kumar 8470876781 | Sh. S.K. VARSHNEY 9212006584 | Sh. J.P. Vasisht 9971396164 | work in progress
12 | C2/22 to C2/274 | 0.762 | 17.05.2016 | 02.07.2016 | 50% | Sh. Mithun Kumar 8470876781 | Sh. S.K. VARSHNEY 9212006584 | Sh. J.P. Vasisht 9971396164 | work in progress
13 | Central School Road | 0.29 | 17.05.2016 | 02.07.2016 | 50% | Sh. Mithun Kumar 8470876781 | Sh. S.K. VARSHNEY 9212006584 | Sh. J.P. Vasisht 9971396164 | work in progress
Name of MLA :- Sh. Adarsh Shastri Name of Constituency :- Dwarka (33)
14 | Sagar Pur Road | 3 | 17.05.2016 | 02.07.2016 | 60% | Sh. Anuj Mishra 9868419032 | Sh. S.K. VARSHNEY 9212006584 | Sh. J.P. Vasisht 9971396164 | work in progress
15 | Nasirpur Road | 2.3 | 17.05.2016 | 02.07.2016 | 55% | Sh. Anuj Mishra 9868419032 | Sh. S.K. VARSHNEY 9212006584 | Sh. J.P. Vasisht 9971396164 | work in progress
16 | Palam Dabri Road | 2.6 | 17.05.2016 | 02.07.2016 | 55% | Sh. Anuj Mishra 9868419032 | Sh. S.K. VARSHNEY 9212006584 | Sh. J.P. Vasisht 9971396164 | work in progress
Name of MLA :- Sh. Jagdeep Singh (West) Name of Constituency :- Hari Nagar(28)
17 | Pandit Vishnu datt Marg | 0.85 | 17.05.2016 | - | 100% | Sh. Mithun Kumar 8252079657 | Sh. S.K. VARSHNEY 9212006584 | Sh. J.P. Vasisht 9971396164 | completed
18 | Satguru Ram Singh Marg | 0.85 | 17.05.2016 | - | 100% | Sh. Mithun Kumar 8252079657 | Sh. S.K. VARSHNEY 9212006584 | Sh. J.P. Vasisht 9971396164 | completed
19 | Connecting Road | 1.77 | 17.05.2016 | - | 100% | Sh. Mithun Kumar 8252079657 | Sh. S.K. VARSHNEY 9212006584 | Sh. J.P. Vasisht 9971396164 | completed
Name of MLA :- Sh. Naresh Balyan (SW) Name of Constituency :- Uttam Nagar
20 | Peer Baba Road | 0.647 | 02.06.2016 | - | 100% | Sh. Anuj Mishra 9868419032 | Sh. S.K. VARSHNEY 9212006584 | Sh. J.P. Vasisht 9971396164 | completed
21 | Police Station Road | 0.3 | 02.06.2016 | - | 100% | Sh. Mithun Kumar 8252079657 | Sh. S.K. VARSHNEY 9212006584 | Sh. J.P. Vasisht 9971396164 | completed
22 | A Block Road | 0.4 | 02.06.2016 | - | 100% | Sh. Mithun Kumar 8252079657 | Sh. S.K. VARSHNEY 9212006584 | Sh. J.P. Vasisht 9971396164 | completed
Name of MLA :- Sh. Kailash Gahlot(SW) Name of Constituency :- Najafgarh (35)
23 | Najafgarh Phirni | 2.2 | 26.04.2016 | 02.07.2016 | 95% | Sh. Navin 8285959206 | Sh.Munna Lal 7503926625 | Sh. J.P. Vasisht 9971396164 | work in progress
24 | NajafgarhDechaun Road | 4.55 | 26.04.2016 | 02.07.2016 | 65% | Sh. Navin 8285959206 | Sh.Munna Lal 7503926625 | Sh. J.P. Vasisht 9971396164 | work in progress
25 | Najafgarh Nangloi Road | 2.6 | 26.04.2016 | - | 100% | Sh. Navin 8285959206 | Sh.Munna Lal 7503926625 | Sh. J.P. Vasisht 9971396164 | completed
`26 | Najafgarh Jharoda Road | 7.2 | 26.04.2016 | 02.07.2016 | 80% | Sh. Navin 8285959206 | Sh. N.K. Sharma 9868768945 | Sh. J.P. Vasisht 9971396164 | work in progress
27 | Najafgarh Dhansa Road | 16.25 | 19.03.2016 | 02.07.2016 | 65% | Sh. Navin 8285959206 | Sh. N.K. Sharma 9868768945 | Sh. J.P. Vasisht 9971396164 | work in progress
28 | Prithivi Singh Dagar Marg | 11.2 | 18.04.2016 | 02.07.2016 | 70% | Sh. A.C. Meena 8802169763 | Sh. N.K. Sharma 9868768945 | Sh. J.P. Vasisht 9971396164 | work in progress
Name of MLA :- Sh. Gulab Singh (SW) Name of Constituency :- Matiala (34)
29 | Najafgarh Bijwasan Road | 11.25 | 19.03.2016 | 02.07.2016 | 50% | Sh. A.C. Meena 8802169763 | Sh. N.K. Sharma 9868768945 | Sh. J.P. Vasisht 9971396164 | work in progress
30 | Laxmi Chand Marg | 11.3 | 19.03.2016 | 02.07.2016 | 70% | Sh. A.C. Meena 8802169763 | Sh. N.K. Sharma 9868768945 | Sh. J.P. Vasisht 9971396164 | work in progress
31 | Goyla Deen Pur Road | 4.2 | 18.04.2016 | 02.07.2016 | 80% | Sh. Anil Yadav 9958130139 | Sh. Rohtash Singh 9911476066 | Sh. J.P. Vasisht 9971396164 | work in progress
Name of MLA :- Col Devinder Sehrawat (SW) Name of Constituency :- Bijwasan
32 | Old DG Road | 2.5 | 02.06.2016 | 02.07.2016 | 50% | Sh. Anil Yadav 9958130139 | Sh. Rohtash Singh 9911476066 | Sh. J.P. Vasisht 9971396164 | work in progress
33 | Link Road | 1.7 | 02.06.2016 | 02.07.2016 | 60% | Sh. Anil Yadav 9958130139 | Sh. Rohtash Singh 9911476066 | Sh. J.P. Vasisht 9971396164 | work in progress
34 | Kapashera Bijwasan Road | 3.8 | 02.06.2016 | 02.07.2016 | 45% | Sh. Anil Yadav 9958130139 | Sh. Rohtash Singh 9911476066 | Sh. J.P. Vasisht 9971396164 | work in progress
35 | Bhartal Road | 3.48 | 02.06.2016 | - | 100% | Sh. Anil Yadav 9958130139 | Sh. Rohtash Singh 9911476066 | Sh. J.P. Vasisht 9971396164 | completed

## Abstract
Abstract of Desilting Report of South Zone (as on 27-06-2016)
Sl. No. | Name of Circle | Total No. of Roads | No. of roads where desilting is in progress (in %) |  |  |  |  | No. of roads where desilting is completed | No. of roads where desilting is yet to be taken up | No. of roads where drain do not exist
|  |  | 1-25 | 26-50 | 51-75 | 76-99 | Total
1 | South East, Road-I | 56 | 1 | 0 | 38 | 17 | 56 | 0 | 0 | 0
2 | South East, Road-II | 39 | 1 | 18 | 6 | 8 | 33 | 1 | 1 | 4
3 | South Road-I | 38 | 0 | 1 | 22 | 15 | 38 | 0 | 0 | 0
4 | South Road-II | 44 | 0 | 3 | 24 | 17 | 44 | 0 | 0 | 0
5 | South West Road-I | 44 | 13 | 13 | 12 | 4 | 42 | 0 | 0 | 2
6 | South West Road-II | 35 | 0 | 7 | 16 | 4 | 27 | 8 | 0 | 0
| TOTAL | 256 | 15 | 42 | 118 | 65 | 240 | 9 | 1 | 6
Note : Report to be submit on daily basis.