## Desilting Report
p
PWD Desilting Report (Preparedness for Monsoon)
DESILTING UNDER PWD MAINTENANCE EAST ZONE AS ON 05.07.2016
Sl. No. | Name of Road | Length of Road | Date of Start of De-silting | Date of completion of De-silting | % Progress | JE in charge / Mobile No. | AE in charge / Mobile No. | EE in charge / Mobile No.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
DESILTING UNDER EAST ZONE as on 05.07.2016
Circle/Div. :- (North East) Road M/ Division M-213 | [7 empty] | (As on 05.07.2016)
Sub Division M-2132
1 | Road No. 66 | 3.8 | 31.01.2016 | 30.05.2016 | 90% | Sh. G.P. Mishra 9871530741 | Sh. Virender Kumar 9205135595 | Sh. K.P.Singh 9810438957
2 | Main Road Maujpur | 0.999 | 07.011.2015 | 30.05.2016 | 100% | Sh. G.P. Mishra 9871530741 | Sh. Virender Kumar 9205135595 | Sh. K.P.Singh 9810438957
3 | Loni Road Wazirabad Road to U.P. Border | 0.5 | 01.03.2016 | 29.04.2016 | 100% | Sh. Sanjeev Kumar 9716311561 | Sh. Virender Kumar 9205135595 | Sh. K.P.Singh 9810438957
4 | Road No. 59 ( Rd 0m to 3450m) | 3.45 | 28.04.2016 | 15.06.2016 | 90% | Sh. Sanjeev Kumar 9716311561 | Sh. Virender Kumar 9205135595 | Sh. K.P.Singh 9810438957
5 | Dividing road from Wazirabad Road red light to DTC Depot near H. No. B-5/18, Yamuna Vihar, Delhi | 0.5 | 28.04.2016 | 15.06.2016 | 100% | Sh. Sanjeev Kumar 9716311561 | Sh. Virender Kumar 9205135595 | Sh. K.P.Singh 9810438957
6 | Gokulpuri Main Road | 0.246 | Newly Constructed Drain |  |  | Sh. Sanjeev Kumar 9716311561 | Sh. Virender Kumar 9205135595 | Sh. K.P.Singh 9810438957
7 | Main Road Noor –E-Illahi Road | 0.98 | 28.04.2016 | 15.06.2016 | 100% | Sh. Sanjeev Kumar 9716311561 | Sh. Virender Kumar 9205135595 | Sh. K.P.Singh 9810438957
8 | Yamuna Vihar Road (C-1 To C-4) | 1.1 | 28.04.2016 | 15.06.2016 | 60% | Sh. Sanjeev Kumar 9716311561 | Sh. Virender Kumar 9205135595 | Sh. K.P.Singh 9810438957
9 | Tanki road to Mobin Chowk | 0.3 | 07.01.2015 | 04.05.2016 | 100% | Sh. Sanjeev Kumar 9716311561 | Sh. Virender Kumar 9205135595 | Sh. K.P.Singh 9810438957
10 | Road No. 63 | 3.18 | 19.02.2016 | 30.06.2016 | 95% | Sh. Sanjeev Kumar 9716311561 | Sh. Virender Kumar 9205135595 | Sh. K.P.Singh 9810438957
11 | Sewadham Road | 2.45 | 19.02.2016 | 30.06.2016 | 90% | Sh. Sanjeev Kumar 9716311561 | Sh. Virender Kumar 9205135595 | Sh. K.P.Singh 9810438957
12 | Babarpur Road (From Road No.66 to G.T. Road) | 2 | 15.05.2016 | 18.08.2016 | 55% | Sh. Sanjeev Kumar 9716311561 | Sh. Virender Kumar 9205135595 | Sh. K.P.Singh 9810438957
13 | Road No. 65 | 1.2 | 22.01.2016 | 22.06.2016 | 2% | Sh. G.P. Mishra 9871530741 | Sh. Virender Kumar 9205135595 | Sh. K.P.Singh 9810438957
14 | Bank Colony Road along western Side of Mandoli Jail Complex | 0.337 | Newly Contructed Drain |  |  | Sh. Sanjeev Kumar 9716311561 | Sh. Virender Kumar 9205135595 | Sh. K.P.Singh 9810438957
Sub Division M-2133
15 | Road No. 62 (Road No. 70 to Apsara Border) | 1.2 | 28.01.2016 | 30.05.2016 | 100% | Sh. Deepak Kumar Shrivastava 9899601254 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
16 | Road No. 70 (Seemapuri to Tahir Pur T-Point) | 1.2 | 24.02.2016 | 22.06.2016 | 100% | Sh. Deepak Kumar Shrivastava 9899601254 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
17 | Seemapuri Road from Road No. 62 to 64 | 1.06 | 24.02.2016 | 22.06.2016 | 100% | Sh. Deepak Kumar Shrivastava 9899601254 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
18 | LIC Road (from Malaria office MCD to GT Road) | 0.3 | 24.02.2016 | 22.06.2016 | 100% | Sh. Deepak Kumar Shrivastava 9899601254 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
19 | Road along Divider road to pummy sweet at Gurudwara road) | 0.36 | 24.02.2016 | 22.06.2016 | 95% | Sh. Deepak Kumar Shrivastava 9899601254 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
20 | Gurudwara Road from DTC bus depot Road No. 70 to GTB Hospital road | 1.75 | 24.02.2016 | 22.06.2016 | 100% | Sh. Deepak Kumar Shrivastava 9899601254 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
21 | Road infront of Hans Raj Public School (Divider Road to Gurudwara road) | 0.36 | 24.02.2016 | 22.06.2016 | 100% | Sh. Deepak Kumar Shrivastava 9899601254 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
22 | Road from T-point, L-pocket to R Block small rotary | 0.86 | 24.02.2016 | 22.06.2016 | 100% | Sh. Deepak Kumar Shrivastava 9899601254 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
23 | GTB Hospital Road (From GT Road to Aggarwal Sweet Dilshad Garden) | 0.6 | 24.02.2016 | 22.06.2016 | 100% | Sh. Deepak Kumar Shrivastava 9899601254 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
24 | R-Block Road (From Divider road Agarwal sweet to GT Road) | 0.5 | 24.02.2016 | 22.06.2016 | 100% | Sh. Deepak Kumar Shrivastava 9899601254 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
25 | Road No. 62 (J & K pocket) to petrol pump GT Road (infront of Red Crosss society). | 0.33 | 24.02.2016 | 22.06.2016 | 100% | Sh. Deepak Kumar Shrivastava 9899601254 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
26 | Road from Gurudwara road (T-point of Kalander Colony) to Gauri Shankar Mandir | 0.31 | 24.02.2016 | 22.06.2016 | 100% | Sh. Deepak Kumar Shrivastava 9899601254 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
27 | Road from Divider Road (Mukherjee Public School to Sant Ram Public School at Gurudwara road) | 0.36 | 24.02.2016 | 22.06.2016 | 80% | Sh. Deepak Kumar Shrivastava 9899601254 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
28 | New Seemapuri Road from Road No. 64 (Mother Dairy) to Road No. 62 near maszid | 1.16 | 24.02.2016 | 22.06.2016 | 90% | Sh. Deepak Kumar Shrivastava 9899601254 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
29 | Road from LIC Colony (T-Point to rotary at Telephone Exchange) | 0.93 | 24.02.2016 | 22.06.2016 | 95% | Sh. Deepak Kumar Shrivastava 9899601254 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
30 | Road No. 64 Swami Dayanand Hospital to DLF More (U.P. Border) | 3 | 24.02.2016 | 22.06.2016 | 90% | Sh. Deepak Kumar Shrivastava 9899601254 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
31 | Divider Road from Seemapuri road to Road No. 64 (near SDN Hospital) | 2.4 | 24.02.2016 | 22.06.2016 | 90% | Sh. Deepak Kumar Shrivastava 9899601254 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
32 | CNG Petrol Pump to deer park (Divider road) west side | 0.2 | 24.02.2016 | 22.06.2016 | 100% | Sh. Deepak Kumar Shrivastava 9899601254 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
33 | CNG Petrol Pump to deer park (Divider road) east side | 0.19 | 24.02.2016 | 22.06.2016 | 100% | Sh. Deepak Kumar Shrivastava 9899601254 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
34 | GTB Hospital road from Red light to Agarwal sweet (Divider road) | 0.19 | 24.02.2016 | 22.06.2016 | 100% | Sh. Deepak Kumar Shrivastava 9899601254 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
35 | Road from GT Road to Road No. 64 via Telephone exchange | 0.41 | 24.02.2016 | 22.06.2016 | 100% | Sh. Deepak Kumar Shrivastava 9899601254 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
36 | Road from General Hospital (Road No. 64 to Shahdara Flyover) | 0.26 | 24.02.2016 | 22.06.2016 | 80% | Sh. Deepak Kumar Shrivastava 9899601254 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
37 | Road No. 68 (Road No. 69 to Road No. 66) | 3.4 | 17.02.2016 | 14.08.2016 | 95% | Sh. Rahul Vashistha 9560599842 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
38 | Loni Road G.T. Road to Loni Gole Chakkar | 2.894 | 22.01.2016 | 22.06.2016 | 95% | Sh. Rahul Vashistha 9560599842 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
39 | Road No. 69 | 1.25 | 20.02.2016 | 18.08.2016 | 100% | Sh. Rahul Vashistha 9560599842 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
40 | Tanga Stand Road from road no. 68 to Wazirabad Road. | 1.35 | 20.02.2016 | 18.08.2016 | 100% | Sh. Rahul Vashistha 9560599842 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
41 | Main Road LIG Flats, East of Loni Road from Loni Road to community centre Ashok Nagar. | 0.375 | 20.02.2016 | 18.08.2016 | 100% | Sh. Rahul Vashistha 9560599842 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
42 | Captain javed Ali Marg | 0.84 | 15.05.2016 | 18.08.2016 | 90% | Sh. Rahul Vashistha 9560599842 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
43 | Main Road LIG flats, Loni Road to Govt. S.S. School Ashok Nagar. | 0.275 | 15.05.2016 | 18.08.2016 | 100% | Sh. Rahul Vashistha 9560599842 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
44 | GTB Road (From Road No. 64 to Road No. 68) | 0.91 | 24.02.2016 | 22.06.2016 | 100% | Sh. Rahul Vashistha 9560599842 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
45 | Mandoli Road (From Loni Road to Nand Nagri Railway crossing) | 1.94 | 24.02.2016 | 22.06.2016 | 100% | Sh. Rahul Vashistha 9560599842 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
46 | From Rajiv Gandhi super hospital specialty hospital to GTB hospital road | 0.95 | 24.02.2016 | 22.06.2016 | 100% | Sh. Rahul Vashistha 9560599842 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
47 | From Road No. 68 (petrol pump) to E-pocket GTB enclave police booth near Nutan Vidya Mandir public school | 0.37 | 24.02.2016 | 22.06.2016 | 100% | Sh. Rahul Vashistha 9560599842 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
48 | From Road No. 69 MIG Flat to GTB Hospital Road Via Nutan Vidya Mandir public school | 0.9 | 24.02.2016 | 22.06.2016 | 100% | Sh. Rahul Vashistha 9560599842 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
49 | Road along khel parisor from NVM school to Green field public school. | 0.25 | 24.02.2016 | 22.06.2016 | 100% | Sh. Rahul Vashistha 9560599842 | Sh. Ram Bir Sharma 8800924701 | Sh. K.P.Singh 9810438957
Sub Division M-2134
50 | Shastri Park To Khajuri Chowk | 3.75 | 01.03.2016 | 30.06.2016 | 95% | Sh. Hanuman Prasad Meena 9810309474 | Sh. Vijay Kumar 8800546098 | Sh. K.P.Singh 9810438957
51 | E.A. Road | 4.2 | 01.03.2016 | 30.06.2016 | 92% | Sh. Manoj Kasana 9650094555 | Sh. Vijay Kumar 8800546098 | Sh. K.P.Singh 9810438957
52 | Seelmapur Road from Road No. 66 to Dhalav. | 0.517 | 29.03.2016 | 30.05.2016 | 98% | Sh. Manoj Kasana 9650094555 | Sh. Vijay Kumar 8800546098 | Sh. K.P.Singh 9810438957
53 | G.T. Road Old Yamuna bridge to Y Point | 0.9 | 29.03.2016 | 30.05.2016 | 100% | Sh. Manoj Kasana 9650094555 | Sh. Vijay Kumar 8800546098 | Sh. K.P.Singh 9810438957
54 | Zero Pusta to Bharampuri culvert | 0.99 | 29.03.2016 | 15.06.2016 | 98% | Sh. Manoj Kasana 9650094555 | Sh. Vijay Kumar 8800546098 | Sh. K.P.Singh 9810438957
55 | Main Brahmpuri Road | 1.62 | 07.011.2015 | 15.06.2016 | 80% | Sh. Hanuman Prasad Meena 9810309474 | Sh. Vijay Kumar 8800546098 | Sh. K.P.Singh 9810438957
56 | Road No. 59 (Rd 3450m to 6450m) | 3 | Not Required |  |  | Sh. Hanuman Prasad Meena 9810309474 | Sh. Virender Kumar 9205135595 | Sh. K.P.Singh 9810438957
57 | Garhi Mendu Road | 4.685 | Not Required |  |  | Sh. Hanuman Prasad Meena 9810309474 | Sh. Virender Kumar 9205135595 | Sh. K.P.Singh 9810438957
58 | Gamri Road | 1.05 | 07.011.2015 | 30.05.2016 | 85% | Sh. Hanuman Prasad Meena 9810309474 | Sh. Virender Kumar 9205135595 | Sh. K.P.Singh 9810438957
Div. EE (SHAHDARA) ROADS / M-211
Name of MLA :- Sh. O.P. Sharma
Name of Constituency :- Vishwas Nagar 59
1 | Road No 56 | 5.6 | 01.02.2016 | 29.06.16 | 90% | Sh. Amar Jeet Singh Solin 9555268645 | Sh. Santosh Datta 9654097881 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
2 | Road No. 71 A | 0.6 | 01.02.2016 | 29.06.16 | 85% | Sh. Amar Jeet Singh Solin 9555268645 | Sh. Santosh Datta 9654097881 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
3 | Road No 72 | 0.91 | 01.02.2016 | 29.06.16 | 75% | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
4 | Road No 72 Extn. | 1 | 01.02.2016 | 29.06.16 | 75% | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
5 | Road No 58 | 2.84 | 01.02.2016 | 29.06.16 | 75% | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
6 | Road No 58 A | 2 | 01.02.2016 | 29.06.16 | 75% | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
7 | Zonal office Road. | 1.03 | 01.02.2016 | 29.06.16 | 65% | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
8 | Surajmal Vihar Market | 1.2 | 01.02.2016 | 29.06.16 | 70% | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
9 | Shrestha Vihar | 1.25 | 01.02.2016 | 29.06.16 | 75% | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
10 | Road No. 57 (Jagat Puri to Telco X-ing) | 2.52 | 01.02.2016 | 29.06.16 | 70% | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
11 | Road No. 56-A. | 1 | 01.02.2016 | 29.06.16 | 65% | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
12 | Bhartendu Harish Chander Marg (75-B Extension) | 2.13 | 01.02.2016 | 29.06.16 | 70% | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
13 | 60' feet Road | 1.17 | 01.02.2016 | 29.06.16 | 70% | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
Name of MLA :- Sh. R.N. Goel
Name of Constituency :- Shahdara AC 62 | [11 empty] | #REF! | #REF!
14 | Road No. 71 | 1.6 | 01.02.2016 | 29.06.16 | 85% | Sh. Amar Jeet Singh Solin 9555268645 | Sh. Santosh Datta 9654097881 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
15 | Shiva Khand Road | 0.9 | 01.02.2016 | 29.06.16 | 70% | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
16 | ITI Vivek Vihar | 1.4 | 01.02.2016 | 29.06.16 | 75% | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
17 | C-Block, Jhilmil | 0.45 | 01.02.2016 | 29.06.16 | 80% | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
18 | Vivek Vihar | 0.617 | 01.02.2016 | 29.06.16 | 75% | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
19 | Ram Mandir via ITI Vivek Vihar | 1.35 | 01.02.2016 | 29.06.16 | 75% | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
20 | Jhilmil Colony | 0.188 | 01.02.2016 | 29.06.16 | 70% | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
21 | DJB opp. B-Block | 0.3 | 01.02.2016 | 29.06.16 | 70% | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
22 | B-Block, Jhilmil, Shaheed Bhagat Singh Marg | 0.355 | 01.02.2016 | 29.06.16 | 65% | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
23 | Link Road GT Road to Vivek Vihar ITI | 0.6 | 01.02.2016 | 29.06.16 | 85% | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
24 | Shahdara Road | 0.6 | 01.02.2016 | 29.06.16 | 70% | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
25 | DCP Office | 0.112 | 01.02.2016 | 29.06.16 | 70% | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
26 | G.T Road Mansarover Park to Apsara Border | 2.6 | 01.02.2016 | 29.06.16 | 75% | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
27 | Bhola Nath Nagar | 0.6 | 01.02.2016 | 29.06.16 | 65% | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh S.K. Modi 9868207966
Name of MLA :- Ms. Sarita Singh
Name of Constituency :-Rohtas Nagar AC 64 | [11 empty] | #REF! | #REF!
28 | G.T Road Shyam lal Collage to Mansarover Park | 2 | 01.02.2016 | 29.06.16 | 70% | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
29 | G.T Road Railway under bridge near Metro Station Shahdara | 0.176 | 01.02.2016 | 29.06.16 | 80% | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
30 | G.T Road Railway under bridge near Railway Station Shahdara | 0.214 | 01.02.2016 | 29.06.16 | 80% | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
31 | Kabool Nagar Gurdwara Road | 0.132 | 01.02.2016 | 29.06.16 | 60% | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh S.K. Modi 9868207966
Name of MLA :- Sh. Anil Kumar Bajpai
Name of Constituency :- Gandhi Nagar AC 61
32 | Gandhi Nagar Road | 1.5 | 01.02.2016 | 29.06.16 | 65% | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh S.K. Modi 9868207966 |  |  |  | #REF! | #REF!
33 | G.T Road Shyam lal Collage to Dharmapura | 1.75 | 01.02.2016 | 29.06.16 | 70% | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh S.K. Modi 9868207966
34 | Road No. 57 from G.T. Road Azad Nagar | 1.5 | 01.02.2016 | 29.06.16 | 65% | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh S.K. Modi 9868207966
Name of MLA :- Sh. S.K. Bagga | [11 empty] | #REF! | #REF!
Name of Constituency :- Krishna Nagar AC (60) | [11 empty] | #REF! | #REF!
35 | Road No. 57 Azad Nagar to Jagat Puri | 1.25 | 01.02.2016 | 29.06.16 | 65% | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh S.K. Modi 9868207966
Circle/Div. :- East-M / East Road (M-212)
Name of MLA :- Sh. Manoj Kumar
Name of Constituency :- Kondli AC (56)
1 | Road from Live stock market to Gali No. 7 Block - C in Ghazipur Dairy Farm. | 0.8 | 15.05.16 | 29.06.16 | 80% | Mohd. Mustaqueem/ 9560834310 | Sh. S.K.Gupta/ 8447748410 | Sh. Iqbal Singh 9910925748 |  |  | #REF! | #REF!
2 | Road from NH-24 to Hindon cut near Ghazipur Slaughter House. | 0.5 | 16.05.16 | 30.06.16 | 80% | Mohd. Mustaqueem/ 9560834310 | Sh. S.K.Gupta/ 8447748410 | Sh. Iqbal Singh 9910925748 |  |  | #REF! | #REF!
3 | NH-24 Ghazipur to Kondli Bridge. | 1.5 | 14.05.16 | 29.06.16 | 80% | Mohd. Mustaqueem/ 9560834310 | Sh. S.K.Gupta/ 8447748410 | Sh. Iqbal Singh 9910925748 |  |  | #REF! | #REF!
4 | Dharamshilla Road | 0.6 | 15.05.16 | 29.06.16 | 80% | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. Y.P. Singh/ 9910554287 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF!
5 | Saheed Budh Singh Marg | 0.28 | 16.05.16 | 30.06.16 | 2% | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. Y.P. Singh/ 9910554287 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF!
6 | Dallupura Road | 1.25 | 16.05.16 | 30.06.16 | 2% | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. Y.P. Singh/ 9910554287 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF! |  |  | 44.03
7 | M.P. Road No. 102 | 2.2 | 16.05.16 | 30.06.16 | 21% | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. Y.P. Singh/ 9910554287 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF! |  |  | 31.92
8 | M.P Road No. 108 | 1.33 | 15.05.16 | 29.06.16 | 21% | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. Y.P. Singh/ 9910554287 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF!
9 | M.P Road 109 | 0.81 | 15.05.16 | 29.06.16 | 21% | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. Y.P. Singh/ 9910554287 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF!
10 | Road from Kondli Village up Gharoli Village X-ing. | 0.75 | 15.05.16 | 29.06.16 | 2% | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. Y.P. Singh/ 9910554287 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF!
11 | Road along Shiv Mandir in Gharoli Dairy Farm 'B' Block. | 0.66 | 15.05.16 | 29.06.16 | 70% | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. Y.P. Singh/ 9910554287 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF!
12 | EWS Flats to DDA Market Mayur Vihar Ph.-III X-ing upto Agarwal Sweet Shop. | 0.66 | 15.05.16 | 29.06.16 | 2% | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. Y.P. Singh/ 9910554287 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF!
13 | Main road between A & B Block New Kondli. | 0.35 | 15.05.16 | 29.06.16 | 2% | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. Y.P. Singh/ 9910554287 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF!
14 | Road from High land Apptt. To Soochna Apptt. In Vasundhara Enclave. | 0.4 | 15.05.16 | 29.06.16 | 2% | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. Y.P. Singh/ 9910554287 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF!
15 | Road from Manav Ashray Apptt. To Hindon Apptt. In Vasundhara Enclave | 0.48 | 14.05.16 | 29.06.16 | 2% | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. Y.P. Singh/ 9910554287 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF!
16 | Road from Dashmesh Public School to Delux Apptt. Via Mahesh Apptt. In Vasundhara Enclave. | 0.75 | 14.05.16 | 29.06.16 | 70% | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. Y.P. Singh/ 9910554287 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF!
17 | Bhagvan Mahavir Swami Marg. | 0.8 | 15.05.16 | 29.06.16 | 2% | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. Y.P. Singh/ 9910554287 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF!
18 | Sameer Bhan Marg | 0.825 | 15.05.16 | 29.06.16 | 2% | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. Y.P. Singh/ 9910554287 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF!
19 | Road from Cell Apartment to Angel Public School in Vasundhara Enclave. | 0.2 | 16.05.16 | 30.06.16 | 2% | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. Y.P. Singh/ 9910554287 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF!
20 | Road from Dainik Janyug Apartment to Hindon Apartment (Budh Singh Marg). | 0.5 | 16.05.16 | 30.06.16 | 2% | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. Y.P. Singh/ 9910554287 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF!
21 | From Kondli Bridge to Porta Cabin MCD Primary School. | 0.85 | 16.05.16 | 30.06.16 | 2% | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. Y.P. Singh/ 9910554287 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF!
22 | Road between Pocket A-1 & A-2 Mayur Vihar Ph-III (Gurudwara Road) | 0.26 | 16.05.16 | 30.06.16 | 2% | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. Y.P. Singh/ 9910554287 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF!
23 | Road between Block No. 12 and 13 from Khichripur Chowk to Kalyanvas Road. | 0.75 | 10.05.16 | 30.06.16 | 75% | Sh. Amit Singhal/ 9971032115 | Sh. H.C. Bhatt/ 9990601811 | Sh. Iqbal Singh/ 9910925748
24 | Road between Block No. 11-15 from Block-15 to LBS Hospital through Jalebi Chowk, Kalyanpuri. | 0.67 | 10.05.16 | 30.06.16 | 80% | Sh. Amit Singhal/ 9971032115 | Sh. H.C. Bhatt/ 9990601811 | Sh. Iqbal Singh/ 9910925748
25 | Road from between Block No. 2 & 3 upto Khichripur Main Road. | 0.3 | 10.05.16 | 30.06.16 | 75% | Sh. Amit Singhal/ 9971032115 | Sh. H.C. Bhatt/ 9990601811 | Sh. Iqbal Singh/ 9910925748
26 | Khichripur road from Kondli Bridge to Mother Dairy. | 1 | 15.05.16 | 30.06.16 | 2% | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. Y.P. Singh/ 9910554287 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF!
Name of MLA :- Sh. Raju Dhingan
Name of Constituency :- Trilokpuri AC (55)
27 | Kotla Road from Trilok Puri Police Station to Khichirpur Bus Stand. | 3 | 03.05.16 | 30.05.16 | 80% | Sh. Amit Singhal/ 9971032115 | Sh. H.C. Bhatt/ 9990601811 | Sh. Iqbal Singh/ 9910925748
28 | East end apartment road. | 0.84 | 16.05.16 | 30.06.16 | 55% | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748 |  | 1 | #REF! | #REF!
29 | Road along Ghazipur Drain | 3.6 | 15.05.16 | 30.06.16 | 15% | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF! | 3.6 | 1
30 | Peripherial road from Chilla Chowk to kotla Village. | 1.25 | 15.05.16 | 30.06.16 | 10% | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF!
31 | Road from Block No. 35 to 17 Trilokpuri (Mahrishi Balmiki Marg) | 1.07 | 17.05.16 | 30.06.16 | 10% | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF!
32 | Road from Block No. 19 to Block No. 13 Trilokpuri | 1.54 | 18.05.16 | 30.06.16 | 55% | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF!
33 | Main road from Block No. 33 to Block No. 19. Trilokpuri | 0.52 | 17.05.16 | 30.06.16 | 10% | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF!
34 | Road from Block No. 36 to Block No. 31 Trilokpuri. | 0.99 | 18.05.16 | 30.06.16 | 15% | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF!
35 | Ambedkar Marg from Block No. 18 Trilokpuri to Kotla Road. | 0.95 | 19.05.16 | 30.06.16 | 10% | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748 | 0.95 | 1 | #REF! | #REF!
36 | Subhash Mkt. from Chand Cinema Turn to Balvikas School | 0.6 | 20.05.16 | 30.06.16 | 10% | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748 | 0.6 | 1 | #REF! | #REF!
37 | Road from Block No. (1) to (11) of Trilokpuri | 0.98 | 20.05.16 | 30.06.16 | 10% | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748
38 | Chilla road from Chilla chowk to Chilla Village. | 0.9 | 21.05.16 | 30.06.16 | 40% | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748
Name of MLA :- Sh. Manish Sisodia
Name of Constituency :- Patparganj (57)
39 | NH-24 Byepass from Noida More to U.P. Border | 4.94 | No Drain |  |  | Md. Mustqeem 9560834310 | Sh. S.K.Gupta 8447748410 | Sh. Iqbal Singh 9910925748
40 | Road No.111 from the Club Avenue to Road along Ghazipur drain. | 0.25 | 21.05.16 | 30.06.16 | 30% | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF!
41 | Sadhabhawana marg (111) | 0.5 | 21.05.16 | 30.06.16 | 30% | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748 | 0.5 | 1 | #REF! | #REF!
42 | Club Avenue Marg (112) | 0.45 | 22.05.16 | 30.06.16 | 40% | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF!
43 | Sehkarita Marg (113) | 0.65 | 23.05.16 | 30.06.16 | 10% | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748
44 | ASN School to Parwana Apartment to Kala Apartment upto LSC. | 0.8 | 23.05.16 | 30.06.16 | 10% | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748
45 | Samachar Apartment Road (Link Road) Samachar Apartment to Glaxo Apartment. | 0.35 | 23.05.16 | 30.06.16 | 10% | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748
46 | Road from Block No. 1 Khichripur to NH-24. | 0.85 | 16.05.16 | 30.06.16 | 85% | Mohd. Mustaqueem/ 9560834310 | Sh. S.K.Gupta/ 8447748410 | Sh. Iqbal Singh 9910925748 |  |  | #REF! | #REF!
47 | Khichripur Main Road from NH-24 to Mother Dairy. | 0.8 | 16.05.16 | 30.06.16 | 80% | Mohd. Mustaqueem/ 9560834310 | Sh. S.K.Gupta/ 8447748410 | Sh. Iqbal Singh 9910925748 |  |  | #REF! | #REF!
48 | Patparganj Main Road from NH-24 to Patparganj Village. | 0.3 | 16.05.16 | 30.06.16 | 80% | Mohd. Mustaqueem/ 9560834310 | Sh. S.K.Gupta/ 8447748410 | Sh. Iqbal Singh 9910925748 |  |  | #REF! | #REF!
49 | Road between Pocket E & F Mayur Vihar Ph-II. | 0.6 | 16.05.16 | 30.06.16 | 100% | Mohd. Mustaqueem/ 9560834310 | Sh. S.K.Gupta/ 8447748410 | Sh. Iqbal Singh 9910925748 |  |  | #REF! | #REF!
50 | Noida Link Road with Slip Roads | 4.11 | No Drain |  |  | Sh. Amit Singhal/ 9971032115 | Sh. H.C. Bhatt/ 9990601811 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF!
51 | NH 24 (Ring Road Crossing to MB Road) | 3.34 | No Drain |  |  | Sh. Amit Singhal/ 9971032115 | Sh. H.C. Bhatt/ 9990601811 | Sh. Iqbal Singh/ 9910925748 |  |  | #REF! | #REF!
Name of Constituency :- Patparganj (57)
52 | Sai Chowk | 0.67 | 15.05.16 | 30.06.16 | 40% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748 |  |  | #REF! | #REF!
53 | Kailash Apartment. | 0.354 | 16.05.16 | 30.06.2016 | 40% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748 | 0.354 | 1 | #REF! | #REF!
54 | Bathla Apartment | 0.328 | 15.05.16 | 30.06.16 | 2% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748 |  |  | #REF! | #REF!
55 | Gagan Vihar. | 0.4 | 15.05.16 | 30.06.16 | 2% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
56 | Agarsain Apartment | 0.61 | 15.05.16 | 30.06.16 | 2% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
57 | Mother Dairy Road (Narwana Road) | 2.5 | 16.05.16 | 30.06.2016 | 30% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
58 | Mother Dairy Road | 1.5 | 16.05.16 | 30.06.2016 | 55% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748 |  |  | #REF! | #REF!
59 | Madhu Vihar Road | 1.6 | 16.05.16 | 30.06.2016 | 20% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748 |  |  | #REF! | #REF!
60 | Balco Market | 0.63 | 15.05.16 | 30.06.16 | 10% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
61 | Prince Apartment | 0.59 | 15.05.16 | 30.06.16 | 10% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
62 | Oriental Apartment | 0.334 | 15.05.16 | 30.06.16 | 10% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
63 | Narwana Apartment | 0.46 | 16.05.16 | 30.06.2016 | 10% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
64 | Trilokia Apartment | 0.38 | 15.05.16 | 30.06.16 | 10% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
65 | Rama Krishna Apartment | 0.27 | 15.05.16 | 30.06.16 | 10% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
66 | Disused canal road (Main Drain with EDMC) | 2.9 | 15.05.16 | 30.06.16 | 90% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
67 | New Rajdhani Road | 0.79 | 16.05.16 | 30.06.2016 | 100% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
68 | Chitra Vihar Road | 0.69 | 16.05.16 | 30.06.2016 | 90% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
69 | Patparganj Road | 2.89 | 05.04.16 | 30.06.16 | 90% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
70 | Road No. 57 A (Handed over to DMRC) | 1.13 | (Handed over to DMRC) |  |  | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
71 | Vikas Marg (Road No. 75 A & 75 B | 3.14 | 15.04.16 | 30.06.16 | 85% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
72 | Patpargunj Road (Preet Vihar) | 1.47 | 15.05.16 | 30.06.16 | 60% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
73 | Vikas Marg (Sachivalaya Crossing to ITO Chungi) | 2.2 | 05.05.16 | 30.06.2016 | 90% | Sh. Amit Singhal 9971032115 | Sh. Harish Bhatt 9990601811 | Sh. Iqbal Singh 9910925748
74 | Marginal Bund Road (ITO Chungi to Kailash Nagar) | 4 | 05.05.16 | 30.06.2016 | 80% | Sh. Amit Singhal 9971032115 | Sh. Harish Bhatt 9990601811 | Sh. Iqbal Singh 9910925748
75 | Marginal Bund Road (Vikas Marg to NH-24) | 2.75 | 05.05.16 | 30.06.2016 | 90% | Sh. Amit Singhal 9971032115 | Sh. Harish Bhatt 9990601811 | Sh. Iqbal Singh 9910925748
76 | Geeta Colony Yamuna Bridge Road | 2.1 | 05.05.16 | 30.06.2016 | 90% | Sh. Amit Singhal 9971032115 | Sh. Harish Bhatt 9990601811 | Sh. Iqbal Singh 9910925748
Project Circle | [8 empty] | 0 | 1 | #REF! | #REF!
Name of MLA :- Sh. Som Dutt | [8 empty] | 0 | 1 | #REF! | #REF!
Name of Constituency & Constituency No.:- Sadar Bazar, 19 | [8 empty] | 0 | 1 | #REF! | #REF!
1 | Azad Market Road | 0.79 | 15.6.2016 | 10.07.2016 | 95% | Er. Thonchulo Magh 9711048979 (M) | Er. S.P. Singh 8800534846 (M) | Er. J.P. Sharma 7838694446 (M)
2 | Bahadur Garth Road | 0.91 | 15.6.2016 | 10.07.2016 | 95%
3 | Pahari Dheeraj Road | 1.2 | 15.6.2016 | 10.07.2016 | 90%
4 | Qutub Road | 0.3 | 08.6.2016 | 10.07.2016 | 95%
5 | Foota Road | 0.25 | 15.6.2016 | 10.07.2016 | 95%
Name of MLA :- Ms. Alka lamba
Name of Constituency & Constituency No.:- Chandni Chowk 20
6 | Ring Road By-pass | 5.55 | No Drain |  |  | Er. Gaurav Sankhwar (Mob. 8447973170) | Er. S.N. Moitra (Mob 9968310379) | Er. Rajiv Lochan 9911058852
7 | Court Road | 1.75 | 15.6.2016 | 10.07.2016 | 80%
8 | Club Road | 1.75 | 15.6.2016 | 10.07.2016 | 80%
9 | Lothian Road | 0.925 | 10.6.2016 | 10.07.2016 | 65%
10 | Sarai Phoose Road | 0.71 | 10.6.2016 | 10.07.2016 | 65%
11 | Magazine Road | 1.35 | 10.6.2016 | 10.07.2016 | 80%
12 | Road No.-46 | 0.3 | 10.6.2016 | 10.07.2016 | 80%
13 | Road: Road No.-45 | 2.5 | 12.6.2016 | 10.07.2016 | 80%
14 | Under Hill Road | 0.69 | 13.6.2016 | 10.07.2016 | 80%
15 | Flag Staff Road | 0.425 | 13.6.2016 | 25.06.2016 | 100%
16 | Shamnath Marg | 1.3 | 13.6.2016 | 10.07.2016 | 80%
17 | Gokhle Road | 0.876 | 15.6.2016 | 10.07.2016 | 80%
18 | Hamilton Road | 0.24 | 13.06.2016 | 10.07.2016 | 80%
19 | Aproach Road | 0.215 | 15.06.2016 | 10.07.2016 | 75%
20 | Aproach Road | 0.25 | 16.06.2016 | 10.07.2016 | 80%
21 | Rajpur Road | 2.565 | 17.06.2016 | 10.07.2016 | 80%
22 | Rajniwas Marg | 0.926 | 12.06.2016 | 10.07.2016 | 90%
23 | Road No.-47 | 1.04 | 14.06.2016 | 10.07.2016 | 70%
24 | CNG Crematorium Road | 0.25 | 11.6.2016 | 10.07.2016 | 55% | Er. Gaurav Sankhwar (Mob. 8447973170) | Er. S.N. Moitra (Mob 9968310379) | Er. Rajiv Lochan 9911058852
25 | Turkman Road | 0.6 | 11.6.2016 | 10.07.2016 | 80%
26 | Chaman Lal Marg | 0.18 | 11.6.2016 | 10.07.2016 | 80%
27 | S.P.M. Marg | 1.48 | 12.6.2016 | 10.07.2016 | 60%
28 | HC SEN ROAD | 0.4 | 12.6.2016 | 10.07.2016 | 40%
29 | KHARI BAWALI ROAD | 0.427 | 13.6.2016 | 10.07.2016 | 80%
30 | ESPLANADE ROAD | 0.43 | 05.6.2016 | 10.07.2016 | 90%
31 | NAYA BAZAR ROAD | 0.58 | 13.6.2016 | 10.07.2016 | 75%
32 | Zorawar Singh Marg | 1.32 | 13.6.2016 | 10.07.2016 | 75%
33 | Mori gate road | 0.38 | 13.6.2016 | 10.07.2016 | 55%
34 | Kela Ghat | 0.175 | 13.6.2016 | 10.07.2016 | 60%
35 | DEWAN HALL ROAD | 0.27 | 13.6.2016 | 10.07.2016 | 80%
36 | NS MARG | 2.22 | 8.6.2016 | 10.07.2016 | 60%
37 | Asaf Ali Road | 1.9 | 11.6.2016 | 10.07.2016 | 75%
38 | Ring Road | 2 | 05.6.2016 | 10.07.2016 | 75%
39 | Mahatma Gandhi Road | 4 | 05.06.2016 | 10.07.2016 | 85%
40 | Chandni Chowk | 1.28 | 13.6.2016 | 10.07.2016 | 90%
Name of MLA :- Sh. Asim Ahmed Khan
Name of Constituency & Constituency No.:- Matia Mahal 21
41 | D.D.U. Marg | 1.98 | 12.6.2016 | 10.07.2016 | 90% | Er. Akhilesh Sharma (Mob. 9953840809) | Er. Devendra Kumar (Mob. 9953751732) | Er. Rajiv Lochan 9911058852
42 | Mirdard Road | 0.55 | 11.6.2016 | 10.07.2016 | 90%
43 | Vishnu Digamber Road | 0.32 | 11.6.2016 | 10.07.2016 | 90%
44 | Rajneet Sing Road | 0.45 | 11.6.2016 | 10.07.2016 | 90%
45 | Thomson Road | 0.75 | 11.6.2016 | 10.07.2016 | 80%
46 | Minto Road | 0.7 | 30.5.52016 | 10.07.2016 | 90%
47 | Mahawat Khan Road | 0.7 | 11.6.2016 | 10.07.2016 | 90%
48 | Barron Road | 0.28 | 11.6.2016 | 10.07.2016 | 80%
49 | JLN Marg | 1.86 | 12.6.2016 | 10.07.2016 | 80%
50 | Kotla Road | 1.48 | 03.06.2016 | 25.06.2016 | 100%
51 | Mata Sundri Road | 1.1 | 10.6.2016 | 10.07.2016 | 80%
Name of MLA :- Imran Hussain
Name of Constituency & Constituency No.:- Ballimaran - 22
52 | Chemsford Road | 0.39 | 15.6.2016 | 10.07.2016 | 50% | Er. Thonchulo Magh 9711048979 (M) | Er.S.P. Singh 8800534846 (M) | Er. J.P. Sharma 7838694446 (M)
53 | Sadar Thana Road | 0.5 | 15.6.2016 | 10.07.2016 | 90%
54 | Desh Raj Bhatiya Marg | 0.83 | 15.6.2016 | 10.07.2016 | 60%
55 | Ram Kumar Marg | 0.45 | 15.6.2016 | 10.07.2016 | 90%
56 | Idgah Road | 1.09 | 15.6.2016 | 10.07.2016 | 95%
57 | G.B. Road | 0.5 | 15.6.2016 | 10.07.2016 | 90%
58 | S.N. Marg | 0.95 | 15.6.2016 | 10.07.2016 | 60%
59 | Qutub Road | 1.85 | 15.6.2016 | 10.07.2016 | 90%
Name of MLA :- Sh. Vishesh Ravi | [8 empty] | 0 | 1 | #REF! | #REF!
Name of Constituency & Constituency No.:- Karol Bagh, 23 | [8 empty] | 0 | 1 | #REF! | #REF!
60 | Panchkuiya Road | 1.28 | 15.6.2016 | 10.07.2016 | 97% | Er. Sunil Kumar Kataria (Mob. 9958068748) | Er. Santosh Dutta (Mob 9213765200) | Er. J.P. Sharma 7838694446 (M)
61 | Nehru Bazar Road | 0.45 | 15.6.2016 | 10.07.2016 | 35%
62 | DAV Aram Bagh Road | 0.46 | 15.6.2016 | 10.07.2016 | 35%
63 | Basant Road | 0.77 | 15.6.2016 | 10.07.2016 | 0%
64 | Main Bazar Road | No Drain
65 | Chitra Gupta Road | 0.68 | 16.6.2016 | 10.07.2016 | 0%
66 | CGHS Dispansary Road | 0.23 | 15.6.2016 | 10.07.2016 | 45%
67 | Desh Bandu Gupta Road | 4.4 | 8.6.2016 | 10.07.2016 | 84%
68 | Faiz Road | 1.41 | 07.6.2016 | 10.07.2016 | 60%
69 | East Park Road | 0.49 | 10.6.2016 | 10.07.2016 | 50%
70 | Rani Jhansi Road | 1.71 | 15.6.2016 | 10.07.2016 | 35% |  |  |  | 1.71 | 1
71 | Link Road | 0.65 | 15.6.2016 | 10.07.2016 | 95% |  |  |  | 0.65 | 1
72 | New Rohtak Road | 2.5 | 15.6.2016 | 10.07.2016 | 70%
73 | S.K. Dass Road | 1 | 07.6.2016 | 10.07.2016 | 95%
74 | Abdul Rehman Road | 0.715 | 15.6.2016 | 10.07.2016 | 95%
75 | Abdul Aziz Road | 0.85 | 15.6.2016 | 10.07.2016 | 0%
76 | Elahi Bux Road | 0.415 | 08.6.2016 | 10.07.2016 | 95%
77 | Gurudara Road | 1 | 15.6.2016 | 10.07.2016 | 50%
78 | Tank Road | 1 | 15.6.2016 | 10.07.2016 | 30%
79 | Hardhyan Singh Road | 1.8 | 10.6.2016 | 10.07.2016 | 84%
80 | Saraswati Marg | 1 | 10.6.2016 | 10.07.2016 | 80%
81 | Ajmal Khan Road | 1.6 | 10.6.2016 | 10.07.2016 | 95%
82 | Sant. Sujan Singh Marg | 0.375 | 15.6.2016 | 10.07.2016 | 40%
83 | Dyanand Saraswati Marg (Road No. 4) | 0.5 | 10.6.2016 | 10.07.2016 | 80%
84 | Road No. 3 | 0.5 | 15.6.2016 | 10.07.2016 | 0%
85 | Gangeshwar Dham Marg | 0.375 | 15.6.2016 | 10.07.2016 | 95%
86 | Arya Samaj Road | 1.8 | 15.6.2016 | 10.07.2016 | 60%
87 | Khajoor Road | 0.32 | 15.6.2016 | 10.07.2016 | 0%
88 | Padam Singh Road | 1.5 | 15.6.2016 | 10.07.2016 | 70%
89 | Military Road | 1.4 | 06.6.2016 | 10.07.2016 | 70%
90 | Guru Ravi Das Marg | 2 | 11.6.2016 | 10.07.2016 | 75% | [9 empty] | 95
91 | Ganga Mandir Marg | 1.5 | 11.6.2016 | 10.07.2016 | 60%
92 | Vishnu Mandir Marg | 1.5 | 08.06.2016 | 10.07.2016 | 60%
93 | Pyare Lal Road | 2 | 08.06.2016 | 10.07.2016 | 70%
94 | Guru Nanak Road (Road No. 5) | 0.9 | 15.6.2016 | 10.07.2016 | 30%
95 | Vallabacharya marg | 0.25 | 15.6.2016 | 10.07.2016 | 0%
C&ND Road Divn.
MLA. Sh. Sanjeev Jha (Burari Consitituency)
1 | Main Burari Road | 7.1 | 22.02.2016 | 21.05.2016 | 95% | Sh. Arun Kumar 9971551958 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
2 | Swaroop Nagar Road | 2.8 | 20.05.2016 | 02.08.2016 | 60% | Sh. D.C. Jaiswal 8744090383 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
MLA Sh. Pawan Sharma (Adarsh Nagar Constituency)
3 | Gandhi Vihar | 0.67 | 20.05.2016 | 02.08.2016 | 90% | Sh. D.C. Jaiswal 8744090383 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
MLA Sh. Pankaj Pushkar (Timarpur Constituency)
4 | BBM Road from Hakikat Nagar, Red Light to Mukherjee Nagar Bandh | 2.4 | 20.05.2016 | 02.08.2016 | 60% | Sh. D.C. Jaiswal 8744090383 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
5 | 60ft Road from Aggarwal Sweets to Nulife Hospital between BBM Road and Burari Road | 0.35 | 20.05.2016 | 02.08.2016 | 95% | Sh. D.C. Jaiswal 8744090383 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
6 | Sant Parmanand Colony Road | 0.9 | 20.05.2016 | 02.08.2016 | 90% | Sh. D.C. Jaiswal 8744090383 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
7 | Burari Road from Kingsway Camp to Road No. 50 | 3.5 | 20.05.2016 | 02.08.2016 | 40% | Sh. D.C. Jaiswal 8744090383 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
8 | Wazirabad Flyover | 1.06 | 20.05.2016 | 02.08.2016 | No Drain | Sh. Arun Kumar 9971551958 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
9 | Munshi Ram Road | 0.5 | 20.05.2016 | 02.08.2016 | 70% | Sh. D.C. Jaiswal 8744090383 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
10 | Parmanand School Road | 0.33 | 20.05.2016 | 02.08.2016 | 80% | Sh. D.C. Jaiswal 8744090383 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
11 | Avtar singh Marg (Nirankari Colony) (Nirankari Colony Gate to culvert Burari Road toward Nirankari Sr. Sec. School) | 1.9 | 20.05.2016 | 02.08.2016 | 80% | Sh. D.C. Jaiswal 8744090383 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
12 | Police Chowki to Mandir Outram Lane | 0.44 | 20.05.2016 | 02.08.2016 | 78% | Sh. D.C. Jaiswal 8744090383 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
13 | BBM Road to Jahagir puri Drain | 0.4 | 20.05.2016 | 02.08.2016 | 15% | Sh. D.C. Jaiswal 8744090383 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
14 | Tagore Park Main road | 0.9 | 20.05.2016 | 02.08.2016 | 20% | Sh. Arun Kumar 9971551958 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
15 | Road in Tagore Park from H. No. 213 to Gole Chakkar | 0.45 | 20.05.2016 | 02.08.2016 | 15% | Sh. Arun Kumar 9971551958 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
16 | Road in Tagore Park from H. No. 37 to H. No. 64 | 1.55 | 20.05.2016 | 02.08.2016 | 10% | Sh. Arun Kumar 9971551958 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
17 | University Road from Mall Road to Petrol Pump Ward-10 | 1.58 | 23.04.2016 | 06.07.2016 | 80% | Sh. Pankaj Kr. Bind 9821387374 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
18 | Khalsa College road from Mall Road to Roop Nagar (Gurutegh Bahadur Road) | 1.3 | 23.04.2016 | 06.07.2016 | 80% | Sh. Pankaj Kr. Bind 9821387374 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
19 | Chhatra Marg Road from Mall Road to Malka Gunj Chowk | 1.65 | 23.04.2016 | 06.07.2016 | 80% | Sh. Pankaj Kr. Bind 9821387374 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
20 | Shiriya Mishra marg from Jai Jawan Tea Stall to Moris Nagar Thana | 0.42 | 23.04.2016 | 06.07.2016 | 80% | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
21 | Sudhir Bose Marg from chouburjja chowk to ACP Office | 1.25 | 23.04.2016 | 06.07.2016 | 85% | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
22 | Polo Road from Jahanara Marg to shani Mandir Vijay Nagar | 0.3 | 23.04.2016 | 06.07.2016 | 80% | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
23 | Mahatma Gandhii Road (Ring Road) | 1.6 | 23.04.2016 | 06.07.2016 | 80% | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
24 | Vijay Nagar main road from Royal Palace to E-11 Vijay Nagar | 0.75 | 23.04.2016 | 06.07.2016 | 80% | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
25 | G.T. Road from Baraf Khana chowk to Clock Tower | 1.2 | 23.04.2016 | 06.07.2016 | 80% | Sh. Pankaj Kr. Bind 9821387374 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
26 | Roshnara Road from Pulbanash Metro Station to Hans Raj College. | 2.7 | 23.04.2016 | 06.07.2016 | 83% | Sh. Pankaj Kr. Bind 9821387374 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
27 | Surjit Singh Marg Camp Chowk to Najafgarh Drain | 0.8 | 23.04.2016 | 06.07.2016 | 80% | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
28 | Timarpur road from Mall Road crossing to Wazirabad Crossing | 1.9 | 23.04.2016 | 06.07.2016 | 82% | Sh. Ashutosh Singh 9136151991 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
29 | Lucknow Road from Mall Road to P.S. Timarpur | 1.7 | 23.04.2016 | 06.07.2016 | 80% | Sh. Ashutosh Singh 9136151991 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
MLA Sh. Akhilesh Pati Tripathi ( Model Town Constituency)
30 | Road No. 48 | 1.92 | 23.04.2016 | 06.07.2016 | 70% | Sh. Pankaj Kr. Bind 9821387374 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
31 | Bunglow Road from Roop Nagar round about to Hansraj College T-point on Chattra Marg | 0.65 | 23.04.2016 | 06.07.2016 | 70% | Sh. Pankaj Kr. Bind 9821387374 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
32 | Mandelia Road from GT Road to Bunglow Road | 0.7 | 23.04.2016 | 06.07.2016 | 80% | Sh. Pankaj Kr. Bind 9821387374 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
33 | Polo Road from Bhama Shah Road to Shani Mandir (Vijay Nagar) | 0.84 | 23.04.2016 | 06.07.2016 | 70% | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
34 | Gurmandi Road from Tripolia gate GT Road to H. NO. 264 Kalyan Vihar | 0.425 | 23.04.2016 | 06.07.2016 | 70% | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
35 | Kalyan Vihar Road from 25 Kalyan Vihar to 1 No. Priyadarshni Vihar | 0.9 | 23.04.2016 | 06.07.2016 | 70% | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
36 | Jahanara Road from Bhamashah Marg to vijay Nagar | 0.83 | 23.04.2016 | 06.07.2016 | 70% | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
37 | Satyawati Marg from Police Station Roop Nagar to Shakti Nagar Chowk | 0.52 | 23.04.2016 | 06.07.2016 | 80% | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
38 | Bhama Shah Road from Mall Road to GT Road Nanak Piao Gurudwara | 1.45 | 23.04.2016 | 06.07.2016 | 80% | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
39 | GT Road from Nanak Piao Gurudwara to Clock Tower | 1.95 | 23.04.2016 | 06.07.2016 | 70% | Sh. Pankaj Kr. Bind 9821387374 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
40 | Inderchand Shastri Marg from Shakti Nagar Chowk to Swami Narayan Marg | 0.9 | 23.04.2016 | 06.07.2016 | 70% | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
MLA. Sh. Praveen Kumar (Jungpura Constitueuncy)
41 | Ring Road By-pass | 2.9 | 25.04.2016 | 08.07.2016 | 90% | Md. Sharafat Hussain 9310098783 | Sh. Dinesh Kumar Gupta 9811689688 | Sh. Anil Trehan 8447001861
42 | Sachivalya Road | 1.6 | 25.04.2016 | 08.07.2016 | 90% | Md. Sharafat Hussain 9310098783 | Sh. Dinesh Kumar Gupta 9811689688 | Sh. Anil Trehan 8447001861
43 | IP Marg | 0.5 | 25.04.2016 | 08.07.2016 | 90% | Sh. Anish Kumar 9891486390 | Sh. Dinesh Kumar Gupta 9811689688 | Sh. Anil Trehan 8447001861
44 | IG Slip Road | 0.58 | 25.04.2016 | 08.07.2016 | 90% | Md. Sharafat Hussain 9310098783 | Sh. Dinesh Kumar Gupta 9811689688 | Sh. Anil Trehan 8447001861
45 | Velodrome Road | 0.57 | 25.04.2016 | 08.07.2016 | 90% | Md. Sharafat Hussain 9310098783 | Sh. Dinesh Kumar Gupta 9811689688 | Sh. Anil Trehan 8447001861
46 | Vikas Marg | 0.5 | 25.04.2016 | 08.07.2016 | 90% | Md. Sharafat Hussain 9310098783 | Sh. Dinesh Kumar Gupta 9811689688 | Sh. Anil Trehan 8447001861
47 | Satyagrah Marg | 0.5 | 25.04.2016 | 08.07.2016 | 90% | Md. Sharafat Hussain 9310098783 | Sh. Dinesh Kumar Gupta 9811689688 | Sh. Anil Trehan 8447001861
48 | Azad Bhawan Road | 0.5 | 25.04.2016 | 08.07.2016 | 55% | Sh. Anish Kumar 9891486390 | Sh. Dinesh Kumar Gupta 9811689688 | Sh. Anil Trehan 8447001861
49 | Ring Road Bhairon Road T-Jn. to Shanti Van Crossing | 4.2 | 25.04.2016 | 08.07.2016 | 90% | Sh. Anish Kumar 9891486390 | Sh. Dinesh Kumar Gupta 9811689688 | Sh. Anil Trehan 8447001861
50 | JLN Marg (Delhi Gate) | 0.56 | 25.04.2016 | 08.07.2016 | 90% | Sh. Anish Kumar 9891486390 | Sh. Dinesh Kumar Gupta 9811689688 | Sh. Anil Trehan 8447001861
51 | Ghata Masjid Road | 0.26 | 25.04.2016 | 08.07.2016 | 90% | Sh. Anish Kumar 9891486390 | Sh. Dinesh Kumar Gupta 9811689688 | Sh. Anil Trehan 8447001861
52 | Mathura Road | 0.75 | 25.04.2016 | 08.07.2016 | 90% | Sh. Anish Kumar 9891486390 | Sh. Dinesh Kumar Gupta 9811689688 | Sh. Anil Trehan 8447001861
53 | Bahadur Shah Zafar Marg | 2 | 25.04.2016 | 08.07.2016 | 90% | Sh. Anish Kumar 9891486390 | Sh. Dinesh Kumar Gupta 9811689688 | Sh. Anil Trehan 8447001861
1 | No Drain/Newly Constructed Drain
2 | 100% Completed

## Abstract
Abstract of Desilting Report of East Zone (as on 05-07-2016)
S. No. | Name of Circle | Total No. of Roads | No. of roads where desilting is in progress (in %) |  |  |  |  | No. of roads where desilting is completed | No. of roads where desilting is yet to be taken up | No. of roads where drain do not exist
|  |  | 1-25 | 26-50 | 51-75 | 76-99 | Total
1 | North-East | 58 | 1 | 0 | 2 | 20 | 23 | 31 | 0 | 4
2 | Shahdara | 35 | 0 | 0 | 28 | 7 | 35 | 0 | 0 | 0
3 | East | 76 | 38 | 7 | 8 | 17 | 70 | 2 | 0 | 4
4 | Project | 95 | 0 | 11 | 25 | 49 | 85 | 2 | 6 | 2
5 | C&ND | 53 | 4 | 1 | 12 | 35 | 52 | 0 | 0 | 1
| Total | 317 | 43 | 19 | 75 | 128 | 265 | 35 | 6 | 11
TOTAL
Note : Report to be submit on daily basis.