## East Zone
PWD Desilting Report (Preparedness for Monsoon)
DESILTING UNDER PWD MAINTENANCE EAST ZONE AS ON 17.04.2017
Sl. No. | Name of Road | Length of Road | Date of Start of De-silting | Date of completion of De-silting (Ist Cycle) | % Progress | JE in charge / Mobile No. | AE in charge / Mobile No. | EE in charge / Mobile No.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Circle/Div. :- (North East) Road M/ Division M-213
Sub Division M-2132
1 | Road No. 63 ( Part of Wazirabad Road) Bhopura Border (U.P.) to Loni Flyover near Loni Gole Chakkar | 3.45 | 2017-03-20 | 31.05.2017 | 28% | Sh. Sanjeev Kumar 9716311561 | Sh. Krishan Avtar 9810993123 | Sh. K.P.Singh 9810438957
2 | Road No. 59 ( Part of Wazirabad Road) Loni Gole Chakkar to | 0.5 | 2017-03-26 | 31.05.2017 | 24% | Sh. Sanjeev Kumar 9716311561 | Sh. Krishan Avtar 9810993123 | Sh. K.P.Singh 9810438957
3 | Sewadham Road ( Nand Nagri Red Light on Road No. 63 to U.P. Border) | 0.35 | work not started | 31.05.2017 | 0% | Sh. Sanjeev Kumar 9716311561 | Sh. Krishan Avtar 9810993123 | Sh. K.P.Singh 9810438957
4 | Loni Road G.T. Road to U.P. Border (Loni gole Chakkar to U.P. Border (Loni)) | 0.246 | work not started | 31.05.2017 | 0% | Sh. Sanjeev Kumar 9716311561 | Sh. Krishan Avtar 9810993123 | Sh. K.P.Singh 9810438957
5 | Gokulpuri Main Road (Wazirabad Road H. No. A-1 to Gokulpuri H. No. B-22) | 0.45 | 2017-04-09 | 31.05.2017 | 2% | Sh. Sanjeev Kumar 9716311561 | Sh. Krishan Avtar 9810993123 | Sh. K.P.Singh 9810438957
6 | Yamuna Vihar Dividing road (Wazirabad Road Yamuna Vihar Red Light to DTC Depot near H. No. B-5/18, Yamuna Vihar, Delhi) | 0.98 | work not started | 31.05.2017 | 0% | Sh. Sanjeev Kumar 9716311561 | Sh. Krishan Avtar 9810993123 | Sh. K.P.Singh 9810438957
7 | Yamuna Vihar Road (C-1 to C-4) | 0.999 | work not started | 31.05.2017 | 0% | Sh. Sanjeev Kumar 9716311561 | Sh. Krishan Avtar 9810993123 | Sh. K.P.Singh 9810438957
8 | Tanki Road (DTC Depot dividing road to Tikona park Subhash Vihar Water Tank) | 1.17 | work not started | 31.05.2017 | 0% | Sh. Sanjeev Kumar 9716311561 | Sh. Krishan Avtar 9810993123 | Sh. K.P.Singh 9810438957
9 | Main Road Noor –E-Illahi Road (DTC Depot Yamuna Vihar to Ghonda Chowk) | 0.22 | work not started | 31.05.2017 | 0% | Sh. Sanjeev Kumar 9716311561 | Sh. Krishan Avtar 9810993123 | Sh. K.P.Singh 9810438957
10 | Main Brahmpuri Road (Ghonda Chowk to Brahampuri Dhalav) | 1.1 | work not started | 31.05.2017 | 0% | Sh. Mahendra Kumar (JE) 9711714588 | Sh. Krishan Avtar 9810993123 | Sh. K.P.Singh 9810438957
11 | Main Road Maujpur (Ghonda Chowk to Red Light on Road No.-66) | 1.125 | work not started | 31.05.2017 | 0% | Sh. Mahendra Kumar (JE) 9711714588 | Sh. Krishan Avtar 9810993123 | Sh. K.P.Singh 9810438957
12 | Road No. 66 (Seelampur Red Light on G.T. Road to Gokalpuri Flyover) | 0.3 | work not started | 31.05.2017 | 0% | Sh. Mahendra Kumar (JE) 9711714588 | Sh. Krishan Avtar 9810993123 | Sh. K.P.Singh 9810438957
13 | Bank Colony Road along western Side of Mandoli Jail Complex (Mandoli Bank Colony to Harsh Vihar Colony.) | 0.337 | work not started | 31.05.2017 | 0% | Sh. Sanjeev Kumar 9716311561 | Sh. Krishan Avtar 9810993123 | Sh. K.P.Singh 9810438957
14 | Road No. 59 (Rd 3450m to 6450m) | 3 | Drain does not exist |  |  | Sh. Mahendra Kumar (JE) 9711714588 | Sh. Krishan Avtar 9810993123 | Sh. K.P.Singh 9810438957
Sub Division M-2134
15 | MB Road (Shastri Park To Khajuri Chowk) | 3.75 | 10.04.2017 | 31.05.2017 | 0% | Sh. Hanuman Prasad Meena 9810309474 | Sh. Vijay Kumar 8800546098 | Sh. K.P.Singh 9810438957
16 | Zero Pusta (Zero Pusta to Bharampuri culvert) | 0.99 | 15.03.2017 | 31.05.2017 | 5% | Sh. Manoj Kasana 9650094555 | Sh. Vijay Kumar 8800546098 | Sh. K.P.Singh 9810438957
17 | Gamri Road (5th Pusta to Ghonda Chowk) | 1.85 | 15.03.2017 | 31.05.2017 | 20% | Sh. Hanuman Prasad Meena 9810309474 | Sh. Vijay Kumar 8800546098 | Sh. K.P.Singh 9810438957
18 | Seelmapur Road (Road No. 66 to Dhalav) | 0.517 | 07.04.2017 | 31.05.2017 | 10% | Sh. Manoj Kasana 9650094555 | Sh. Vijay Kumar 8800546098 | Sh. K.P.Singh 9810438957
19 | Grudwara Road (G. T Road to seelampur main Road) | 0.3 | 07.04.2017 | 31.05.2017 | 15% | Sh. Manoj Kasana 9650094555 | Sh. Vijay Kumar 8800546098 | Sh. K.P.Singh 9810438957
20 | E.A. Road (Dharam Pura T-Point to ISBT) (Service road Hotel de aqua) | 4.2 | 07.04.2017 | 31.05.2017 | 20% | Sh. Manoj Kasana 9650094555 | Sh. Vijay Kumar 8800546098 | Sh. K.P.Singh 9810438957
21 | Old G.T. Road (Old Yamuna bridge to Darampura Y- Point) | 0.9 | Drain does not exist |  |  | Sh. Manoj Kasana 9650094555 | Sh. Vijay Kumar 8800546098 | Sh. K.P.Singh 9810438957
22 | Garhi Mendu Road (3rd Pusta to Wazirabad Road) | 4.685 | Drain does not exist |  |  | Sh. Hanuman Prasad Meena 9810309474 | Sh. Vijay Kumar 8800546098 | Sh. K.P.Singh 9810438957
Div. EE (SHAHDARA) ROADS / M-211
Name of MLA :- Sh. O.P. Sharma
Name of Constituency :- Vishwas Nagar 59
1 | Road No 56 | 5.6 | agmt. 25.02.17 actual str.- 25.03.17 | 31.05.2017 | 7% | Sh. Shivam Yadav 9899839210 | Sh. A.S. Yadav 9350677427 | Sh Vijay Singh 8802028700
2 | Road No. 71 A | 0.6 | agmt. 25.02.17 actual str.- 25.03.17 | 31.05.2017 | 5% | Sh. Shivam Yadav 9899839210 | Sh. A.S. Yadav 9350677427 | Sh Vijay Singh 8802028700
3 | Road No 72 | 0.91 | 07.04.2017 | 31.05.2017 | Yet to be start | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh Vijay Singh 8802028700
4 | Road No 72 Extn. | 1 | 17.04.2017 | 31.05.2017 | Yet to be start | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh Vijay Singh 8802028700
5 | Road No 58 | 2.84 |  |  | Tender under process | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh Vijay Singh 8802028700
6 | Road No 58 A | 2 |  |  | Tender under process | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh Vijay Singh 8802028700
7 | Zonal office Road. | 1.03 | 07.04.2017 | 31.05.2017 | 30% | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh Vijay Singh 8802028700
8 | Surajmal Vihar Market | 1.2 | 01.05.2017 | 31.05.2017 | Yet to be start | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh Vijay Singh 8802028700
9 | Shrestha Vihar | 1.25 | 15.05.2017 | 31.05.2017 | Yet to be start | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh Vijay Singh 8802028700
10 | Road No. 57 (Jagat Puri to Telco X-ing) | 2.52 | 04.05.2017 | 31.05.2017 | Yet to be start | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh Vijay Singh 8802028700
11 | Road No. 56-A. | 1 |  |  | Tender under process | Sh. Amar Jeet Singh Solin 9555268645 | Sh. A.S. Yadav 9350677427 | Sh Vijay Singh 8802028700
12 | Bhartendu Harish Chander Marg (75-B Extension) | 2.13 |  |  | Tender under process | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh Vijay Singh 8802028700
13 | 60' feet Road | 1.17 | 01.04.2017 | 31.05.2017 | 8% | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh Vijay Singh 8802028700
Name of MLA :- Sh. Ram Niwas Goel
Name of Constituency :- Shahdara AC 62
14 | Road No. 71 | 1.6 | agmt. 25.02.17 actual str.- 25.03.17 | 31.05.2017 | 6% | Sh. Shivam Yadav 9899839210 | Sh. A.S. Yadav 9350677427 | Sh Vijay Singh 8802028700
15 | Shiva Khand Road | 0.9 |  |  | Tender under process | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh Vijay Singh 8802028700
16 | ITI Vivek Vihar | 1.4 |  |  | Tender under process | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh Vijay Singh 8802028700
17 | C-Block, Jhilmil | 0.45 |  |  | Tender under process | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh Vijay Singh 8802028700
18 | Vivek Vihar | 0.617 |  |  | Tender under process | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh Vijay Singh 8802028700
19 | Ram Mandir via ITI Vivek Vihar | 1.35 |  |  | Tender under process | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh Vijay Singh 8802028700
20 | Jhilmil Colony | 0.188 |  |  | Tender under process | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh Vijay Singh 8802028700
21 | DJB opp. B-Block | 0.3 |  |  | Tender under process | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh Vijay Singh 8802028700
22 | B-Block, Jhilmil, Shaheed Bhagat Singh Marg | 0.355 |  |  | Tender under process | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh Vijay Singh 8802028700
23 | Link Road GT Road to Vivek Vihar ITI | 0.6 |  |  | Tender under process | Sh. Jitendra Kirad 9818961231 | Sh. Suresh Chand 9868700938 | Sh Vijay Singh 8802028700
24 | Shahdara Road | 0.6 | 20.04.2017 | 31.05.2017 | Yet to be start | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh Vijay Singh 8802028700
25 | DCP Office | 0.112 | 20.04.2017 | 31.05.2017 | Yet to be start | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh Vijay Singh 8802028700
26 | G.T Road Mansarover Park to Apsara Border | 2.6 |  |  | Tender under process | Sh. Amar Jeet Singh Solin 9555268645 | Sh. A.S. Yadav 9350677427 | Sh Vijay Singh 8802028700
27 | Bhola Nath Nagar | 0.6 | 20.04.2017 | 31.05.2017 | 10% | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh Vijay Singh 8802028700
28 | Road No. 62 (Road No. 70 to Apsara Border) | 1.2 |  |  | 5% | Sh. Deepak Kumar Shrivastava 7838989633 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
29 | Seemapuri Road from Road No. 62 to 64 | 1.06 |  |  | 5% | Sh. Deepak Kumar Shrivastava 7838989633 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
30 | LIC Road (from Malaria office MCD to GT Road) | 0.3 | 22.03.2017 | 31.05.2017 | 90% | Sh. Deepak Kumar Shrivastava 7838989633 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
31 | Road along Divider road to pummy sweet at Gurudwara road) | 0.36 |  |  | 5% | Sh. Deepak Kumar Shrivastava 7838989633 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
32 | Gurudwara Road from DTC bus depot Road No. 70 to GTB Hospital road | 1.75 |  |  | 5% | Sh. Deepak Kumar Shrivastava 7838989633 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
33 | Road infront of Hans Raj Public School (Divider Road to Gurudwara road) | 0.36 |  |  | 5% | Sh. Deepak Kumar Shrivastava 7838989633 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
34 | Road from T-point, L-pocket to R Block small rotary | 0.86 |  |  | 5% | Sh. Deepak Kumar Shrivastava 7838989633 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
35 | GTB Hospital Road (From GT Road to Aggarwal Sweet Dilshad Garden) | 0.6 |  |  | 5% | Sh. Deepak Kumar Shrivastava 7838989633 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
36 | R-Block Road (From Divider road Agarwal sweet to GT Road) | 0.5 |  |  | 5% | Sh. Deepak Kumar Shrivastava 7838989633 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
37 | Road No. 62 (J & K pocket) to petrol pump GT Road (infront of Red Crosss society). | 0.33 |  |  | 6% | Sh. Deepak Kumar Shrivastava 7838989633 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
38 | Road from Gurudwara road (T-point of Kalander Colony) to Gauri Shankar Mandir | 0.31 |  |  | 4% | Sh. Deepak Kumar Shrivastava 7838989633 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
39 | Road from Divider Road (Mukherjee Public School to Sant Ram Public School at Gurudwara road) | 0.36 |  |  | 5% | Sh. Deepak Kumar Shrivastava 7838989633 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
40 | New Seemapuri Road from Road No. 64 (Mother Dairy) to Road No. 62 near maszid | 1.16 |  |  | 7% | Sh. Deepak Kumar Shrivastava 7838989633 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
41 | Road from LIC Colony (T-Point to rotary at Telephone Exchange) | 0.93 |  |  | 6% | Sh. Deepak Kumar Shrivastava 7838989633 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
42 | Road from GT Road to Road No. 64 via Telephone exchange | 0.41 |  |  | 4% | Sh. Deepak Kumar Shrivastava 7838989633 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
43 | Road from General Hospital (Road No. 64 to Shahdara Flyover) | 0.26 |  |  | 5% | Sh. Deepak Kumar Shrivastava 7838989633 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
Name of MLA :- Ms. Sarita Singh
Name of Constituency :-Rohtas Nagar AC 64
44 | G.T Road Shyam lal Collage to Mansarover Park | 2 | 10.04.2017 | 31.05.2017 | Yet to be start | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh Vijay Singh 8802028700
45 | G.T Road Railway under bridge near Metro Station Shahdara | 0.176 | 20.04.2017 | 31.05.2017 | Yet to be start | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh Vijay Singh 8802028700
46 | G.T Road Railway under bridge near Railway Station Shahdara | 0.214 | 20.04.2018 | 31.05.2017 | Yet to be start | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh Vijay Singh 8802028700
47 | Kabool Nagar Gurdwara Road | 0.132 | 20.04.2019 | 31.05.2017 | Yet to be start | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh Vijay Singh 8802028700
48 | Loni Road G.T. Road to Loni Gole Chakkar | 2.894 | 24.03.2017 | 31.05.2017 | 20% | Sh.Bipin Yadav 9891580713 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
49 | Main Road LIG Flats, East of Loni Road from Loni Road to community centre Ashok Nagar. | 0.375 |  |  | 5% | Sh.Bipin Yadav 9891580713 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
50 | Main Road LIG flats, Loni Road to Govt. S.S. School Ashok Nagar. | 0.275 |  |  | 5% | Sh.Bipin Yadav 9891580713 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
51 | Mandoli Road (From Loni Road to Nand Nagri Railway crossing) | 1.94 |  |  | 6% | Sh.Bipin Yadav 9891580713 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
Name of MLA :- Sh. Anil Kumar Bajpai
Name of Constituency :- Gandhi Nagar AC 61
52 | Gandhi Nagar Road | 1.5 | 01.04.2017 | 31.05.2017 | 15% | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh Vijay Singh 8802028700
53 | G.T Road Shyam lal Collage to Dharmapura | 1.75 | 10.04.2017 | 31.05.2017 | Yet to be start | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh Vijay Singh 8802028700
54 | Road No. 57 from G.T. Road Azad Nagar | 1.5 |  |  | Tender under process | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh Vijay Singh 8802028700
Name of MLA :- Sh. S.K. Bagga
Name of Constituency :- Krishna Nagar AC (60)
55 | Road No. 57 Azad Nagar to Jagat Puri | 1.25 | 01.05.2017 | 31.05.2017 | Yet to be start | Sh. A.K. Singh 9810255098 | Sh.Vinod Kumar Goel 9873760538 | Sh Vijay Singh 8802028700
Name of MLA :- Sh. Gopal Rai
Name of Constituency :- Babarpur AC 67
56 | Babarpur Road (From Road No. 66 to G.T. Road | 2 |  |  | Yet to be start | Sh.Bipin Yadav 9891580713 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
57 | Road No. 65 | 1.2 |  |  | Yet to be start | Sh.Bipin Yadav 9891580713 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
58 | Road No. 68 (Road No. 69 to Road No. 66) | 3.4 |  |  | Yet to be start | Sh.Bipin Yadav 9891580713 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
59 | Loni Road G.T. Road to Loni Gole Chakkar | 2.894 | 24.03.2017 | 31.05.2017 | 20% | Sh.Bipin Yadav 9891580713 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
Name of MLA :- Sh. Rajender Pal Gautam
Name of Constituency :- Seemapuri AC 63
60 | Road No. 70 (Seemapuri to Tahir Pur T-Point) | 1.2 |  |  | 4% | Sh. Deepak Kumar Shrivastava 7838989633 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
61 | Road No. 64 Swami Dayanand Hospital to DLF More (U.P. Border) | 3 |  |  | 5% | Sh. Deepak Kumar Shrivastava 7838989633 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
62 | Divider Road from Seemapuri road to Road No. 64 (near SDN Hospital) | 2.4 |  |  | 4% | Sh. Deepak Kumar Shrivastava 7838989633 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
63 | CNG Petrol Pump to deer park (Divider road) west side | 0.2 |  |  | 6% | Sh. Deepak Kumar Shrivastava 7838989633 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
64 | CNG Petrol Pump to deer park (Divider road) east side | 0.19 |  |  | 4% | Sh. Deepak Kumar Shrivastava 7838989633 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
65 | GTB Hospital road from Red light to Agarwal sweet (Divider road) | 0.19 |  |  | 5% | Sh. Deepak Kumar Shrivastava 7838989633 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
66 | Road No. 68 (Road No. 69 to Road No. 66) | 3.4 |  |  | 6% | Sh.Bipin Yadav 9891580713 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
67 | Road No. 69 | 1.25 |  |  | 7% | Sh.Bipin Yadav 9891580713 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
68 | Tanga Stand Road from road no. 68 to Wazirabad Road. | 1.35 |  |  | 8% | Sh.Bipin Yadav 9891580713 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
69 | Captain javed Ali Marg | 0.84 |  |  | 5% | Sh.Bipin Yadav 9891580713 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
70 | GTB Road (From Road No. 64 to Road No. 68) | 0.91 |  |  | 5% | Sh.Bipin Yadav 9891580713 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
71 | From Rajiv Gandhi super hospital specialty hospital to GTB hospital road | 0.95 |  |  | 6% | Sh.Bipin Yadav 9891580713 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
72 | From Road No. 68 (petrol pump) to E-pocket GTB enclave police booth near Nutan Vidya Mandir public school | 0.37 | 07.04.2017 | 31.05.2017 | 50% | Sh.Bipin Yadav 9891580713 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
73 | From Road No. 69 MIG Flat to GTB Hospital Road Via Nutan Vidya Mandir public school | 0.9 |  |  | 5% | Sh.Bipin Yadav 9891580713 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
74 | Road along khel parisor from NVM school to Green field public school. | 0.25 |  |  | 9% | Sh.Bipin Yadav 9891580713 | Sh. Ram Bir Sharma 8800924701 | Sh Vijay Singh 8802028700
Circle/Div. :- East-M / East Road (M-212)
Name of MLA :- Sh. Manoj Kumar
Name of Constituency :- Kondli AC (56)
1 | Road from Live stock market to Gali No. 7 Block - C in Ghazipur Dairy Farm. | 0.8 | 15.03.2017 | 15.05.2017 |  | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. B.L. Morya/ 9891309076 | Sh. Iqbal Singh 9910925748
2 | Road from NH-24 to Hindon cut near Ghazipur Slaughter House. | 0.5 | 15.03.2017 | 15.05.2017 |  | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. B.L. Morya/ 9891309076 | Sh. Iqbal Singh 9910925748
3 | NH-24 Ghazipur to Kondli Bridge. | 1.5 | 15.03.2017 | 15.05.2017 |  | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. B.L. Morya/ 9891309076 | Sh. Iqbal Singh 9910925748
4 | Dharamshilla Road | 0.6 | 15.03.2017 | 15.05.2017 |  | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. B.L. Morya/ 9891309076 | Sh. Iqbal Singh/ 9910925748
5 | Saheed Budh Singh Marg | 0.28 | 15.03.2017 | 15.05.2017 |  | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. B.L. Morya/ 9891309076 | Sh. Iqbal Singh/ 9910925748
6 | Dallupura Road | 1.25 | 15.03.2017 | 15.05.2017 |  | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. B.L. Morya/ 9891309076 | Sh. Iqbal Singh/ 9910925748
7 | M.P. Road No. 102 | 2.2 | 15.03.2017 | 15.05.2017 | 60% | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. B.L. Morya/ 9891309076 | Sh. Iqbal Singh/ 9910925748
8 | M.P Road No. 108 | 1.33 | 15.03.2017 | 15.05.2017 |  | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. B.L. Morya/ 9891309076 | Sh. Iqbal Singh/ 9910925748
9 | M.P Road 109 | 0.81 | 15.03.2017 | 15.05.2017 | 55% | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. B.L. Morya/ 9891309076 | Sh. Iqbal Singh/ 9910925748
10 | Road from Kondli Village up Gharoli Village X-ing. | 0.75 | 15.03.2017 | 15.05.2017 | 60% | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. B.L. Morya/ 9891309076 | Sh. Iqbal Singh/ 9910925748
11 | Road along Shiv Mandir in Gharoli Dairy Farm 'B' Block. | 0.66 | 15.03.2017 | 15.05.2017 | 55% | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. B.L. Morya/ 9891309076 | Sh. Iqbal Singh/ 9910925748
12 | EWS Flats to DDA Market Mayur Vihar Ph.-III X-ing upto Agarwal Sweet Shop. | 0.66 | 15.03.2017 | 15.05.2017 |  | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. B.L. Morya/ 9891309076 | Sh. Iqbal Singh/ 9910925748
13 | Main road between A & B Block New Kondli. | 0.35 | 15.03.2017 | 15.05.2017 |  | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. B.L. Morya/ 9891309076 | Sh. Iqbal Singh/ 9910925748
14 | Road from High land Apptt. To Soochna Apptt. In Vasundhara Enclave. | 0.4 | 15.03.2017 | 15.05.2017 |  | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. B.L. Morya/ 9891309076 | Sh. Iqbal Singh/ 9910925748
15 | Road from Manav Ashray Apptt. To Hindon Apptt. In Vasundhara Enclave | 0.48 | 15.03.2017 | 15.05.2017 |  | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. B.L. Morya/ 9891309076 | Sh. Iqbal Singh/ 9910925748
16 | Road from Dashmesh Public School to Delux Apptt. Via Mahesh Apptt. In Vasundhara Enclave. | 0.75 | 15.03.2017 | 15.05.2017 |  | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. B.L. Morya/ 9891309076 | Sh. Iqbal Singh/ 9910925748
17 | Bhagvan Mahavir Swami Marg. | 0.8 | 15.03.2017 | 15.05.2017 |  | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. B.L. Morya/ 9891309076 | Sh. Iqbal Singh/ 9910925748
18 | Sameer Bhan Marg | 0.825 | 15.03.2017 | 15.05.2017 |  | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. B.L. Morya/ 9891309076 | Sh. Iqbal Singh/ 9910925748
19 | Road from Cell Apartment to Angel Public School in Vasundhara Enclave. | 0.2 | 15.03.2017 | 15.05.2017 |  | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. B.L. Morya/ 9891309076 | Sh. Iqbal Singh/ 9910925748
20 | Road from Dainik Janyug Apartment to Hindon Apartment (Budh Singh Marg). | 0.5 | 15.03.2017 | 15.05.2017 |  | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. B.L. Morya/ 9891309076 | Sh. Iqbal Singh/ 9910925748
21 | From Kondli Bridge to Porta Cabin MCD Primary School. | 0.85 | 15.03.2017 | 15.05.2017 |  | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. B.L. Morya/ 9891309076 | Sh. Iqbal Singh/ 9910925748
22 | Road between Pocket A-1 & A-2 Mayur Vihar Ph-III (Gurudwara Road) | 0.26 | 15.03.2017 | 15.05.2017 |  | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. B.L. Morya/ 9891309076 | Sh. Iqbal Singh/ 9910925748
23 | Road between Block No. 12 and 13 from Khichripur Chowk to Kalyanvas Road. | 0.75 | 15.03.2017 | 15.05.2017 |  | Sh. Amit Singhal/ 9971032115 | Sh. H.C. Bhatt/ 9990601811 | Sh. Iqbal Singh/ 9910925748
24 | Road between Block No. 11-15 from Block-15 to LBS Hospital through Jalebi Chowk, Kalyanpuri. | 0.67 | 15.03.2017 | 15.05.2017 |  | Sh. Amit Singhal/ 9971032115 | Sh. H.C. Bhatt/ 9990601811 | Sh. Iqbal Singh/ 9910925748
25 | Road from between Block No. 2 & 3 upto Khichripur Main Road. | 0.3 | 15.03.2017 | 15.05.2017 |  | Sh. Amit Singhal/ 9971032115 | Sh. H.C. Bhatt/ 9990601811 | Sh. Iqbal Singh/ 9910925748
26 | Khichripur road from Kondli Bridge to Mother Dairy. | 1 | 15.03.2017 | 15.05.2017 |  | Sh. Dinesh Kumar/ 9650366375 Sh. Om Pal Singh/ 9350315199 | Sh. B.L. Morya/ 9891309076 | Sh. Iqbal Singh/ 9910925748
Name of MLA :- Sh. Raju Dhingan
Name of Constituency :- Trilokpuri AC (55)
27 | Kotla Road from Trilok Puri Police Station to Khichirpur Bus Stand. | 3 | 15.03.2017 | 15.05.2017 | 40% | Mohd. Mustaqueem/ 9560834310 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748
28 | East end apartment road. | 0.84 | 15.03.2017 | 15.05.2017 |  | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748
29 | Road along Ghazipur Drain | 3.6 | 15.03.2017 | 15.05.2017 | 55% | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748
30 | Peripherial road from Chilla Chowk to kotla Village. | 1.25 | 15.03.2017 | 15.05.2017 |  | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748
31 | Road from Block No. 35 to 17 Trilokpuri (Mahrishi Balmiki Marg) | 1.07 | 15.03.2017 | 15.05.2017 |  | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748
32 | Road from Block No. 19 to Block No. 13 Trilokpuri | 1.54 | 15.03.2017 | 15.05.2017 |  | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748
33 | Main road from Block No. 33 to Block No. 19. Trilokpuri | 0.52 | 15.03.2017 | 15.05.2017 |  | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748
34 | Road from Block No. 36 to Block No. 31 Trilokpuri. | 0.99 | 15.03.2017 | 15.05.2017 |  | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748
35 | Ambedkar Marg from Block No. 18 Trilokpuri to Kotla Road. | 0.95 | 15.03.2017 | 15.05.2017 |  | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748
36 | Subhash Mkt. from Chand Cinema Turn to Balvikas School | 0.6 | 15.03.2017 | 15.05.2017 |  | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748
37 | Road from Block No. (1) to (11) of Trilokpuri | 0.98 | 15.03.2017 | 15.05.2017 |  | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748
38 | Chilla road from Chilla chowk to Chilla Village. | 0.9 | 15.03.2017 | 15.05.2017 |  | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748
Name of MLA :- Sh. Manish Sisodia
Name of Constituency :- Patparganj (57)
40 | Road No.111 from the Club Avenue to Road along Ghazipur drain. | 0.25 | 15.03.2017 | 15.05.2017 |  | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748
41 | Sadhabhawana marg (111) | 0.5 | 15.03.2017 | 15.05.2017 |  | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748
42 | Club Avenue Marg (112) | 0.45 | 15.03.2017 | 15.05.2017 |  | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748
43 | Sehkarita Marg (113) | 0.65 | 15.03.2017 | 15.05.2017 |  | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748
44 | ASN School to Parwana Apartment to Kala Apartment upto LSC. | 0.8 | 15.03.2017 | 15.05.2017 |  | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748
45 | Samachar Apartment Road (Link Road) Samachar Apartment to Glaxo Apartment. | 0.35 | 15.03.2017 | 15.05.2017 |  | Sh. Mehkar Singh/ 9891235929 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh/ 9910925748
46 | Road from Block No. 1 Khichripur to NH-24. | 0.85 | 15.03.2017 | 15.05.2017 |  | Mohd. Mustaqueem/ 9560834310 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh 9910925748
47 | Khichripur Main Road from NH-24 to Mother Dairy. | 0.8 | 15.03.2017 | 15.05.2017 |  | Mohd. Mustaqueem/ 9560834310 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh 9910925748
48 | Patparganj Main Road from NH-24 to Patparganj Village. | 0.3 | 15.03.2017 | 15.05.2017 |  | Mohd. Mustaqueem/ 9560834310 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh 9910925748
49 | Road between Pocket E & F Mayur Vihar Ph-II. | 0.6 | 15.03.2017 | 15.05.2017 |  | Mohd. Mustaqueem/ 9560834310 | Sh. N.K. Meena/ 9013278677 | Sh. Iqbal Singh 9910925748
50 | Noida Link Road with Slip Roads | 4.11 | 15.03.2017 | 15.05.2017 |  | Sh. Amit Singhal/ 9971032115 | Sh. H.C. Bhatt/ 9990601811 | Sh. Iqbal Singh/ 9910925748
Name of Constituency :- Patparganj (57)
52 | Sai Chowk | 0.67 | 15.03.2017 | 15.05.2017 |  | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
53 | Kailash Apartment. | 0.354 | 15.03.2017 | 15.05.2017 | 40% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748 | 0.354 | 1
54 | Bathla Apartment | 0.328 | 15.03.2017 | 15.05.2017 | 35% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
55 | Gagan Vihar. | 0.4 | 15.03.2017 | 15.05.2017 | 35% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
56 | Agarsain Apartment | 0.61 | 15.03.2017 | 15.05.2017 | 40% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
57 | Mother Dairy Road (Narwana Road) | 2.5 | 15.03.2017 | 15.05.2017 |  | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
58 | Mother Dairy Road | 1.5 | 15.03.2017 | 15.05.2017 |  | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
59 | Madhu Vihar Road | 1.6 | 15.03.2017 | 15.05.2017 |  | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
60 | Balco Market | 0.63 | 15.03.2017 | 15.05.2017 | 35% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
61 | Prince Apartment | 0.59 | 15.03.2017 | 15.05.2017 | 40% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
62 | Oriental Apartment | 0.334 | 15.03.2017 | 15.05.2017 | 35% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
63 | Narwana Apartment | 0.46 | 15.03.2017 | 15.05.2017 | 35% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
64 | Trilokia Apartment | 0.38 | 15.03.2017 | 15.05.2017 | 30% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
65 | Rama Krishna Apartment | 0.27 | 15.03.2017 | 15.05.2017 | 35% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
66 | Disused canal road (Main Drain with EDMC) | 2.9 | 15.03.2017 | 15.05.2017 | 25% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
67 | New Rajdhani Road | 0.79 | 15.03.2017 | 15.05.2017 |  | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
68 | Chitra Vihar Road | 0.69 | 15.03.2017 | 15.05.2017 |  | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
69 | Patparganj Road | 2.89 | 15.03.2017 | 15.05.2017 | 15% | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
70 | Vikas Marg (Road No. 75 A & 75 B | 3.14 | 15.03.2017 | 15.05.2017 |  | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
71 | Patpargunj Road (Preet Vihar) | 1.47 | 15.03.2017 | 15.05.2017 |  | Sh. P.K. Singh/ 9968334248 Sh. Dipankar Koli 9810811670 | Sh. R.K.Sharma 9958998336 | Sh. Iqbal Singh 9910925748
72 | Vikas Marg (Sachivalaya Crossing to ITO Chungi) | 2.2 | 15.03.2017 | 15.05.2017 |  | Sh. Amit Singhal 9971032115 | Sh. Harish Bhatt 9990601811 | Sh. Iqbal Singh 9910925748
73 | Marginal Bund Road (ITO Chungi to Kailash Nagar) | 4 | 15.03.2017 | 15.05.2017 |  | Sh. Amit Singhal 9971032115 | Sh. Harish Bhatt 9990601811 | Sh. Iqbal Singh 9910925748
74 | Marginal Bund Road (Vikas Marg to NH-24) | 2.75 | 15.03.2017 | 15.05.2017 |  | Sh. Amit Singhal 9971032115 | Sh. Harish Bhatt 9990601811 | Sh. Iqbal Singh 9910925748
75 | Geeta Colony Yamuna Bridge Road | 2.1 | 15.03.2017 | 15.05.2017 |  | Sh. Amit Singhal 9971032115 | Sh. Harish Bhatt 9990601811 | Sh. Iqbal Singh 9910925748
Project Circle
SRD-I
Name of MLA :- Sh. Asim Ahmed Khan
Name of Constituency & Constituency No.:- Matia Mahal 21
1 | Barron Road | 0.28 | 24.03.2017 | 31.05.2017 | 15% | Er. Akhilesh Sharma (Mob. 9953840809) | Er. Devendra Kumar (Mob. 9953751732) | Er. Rajiv Lochan (Mob. 9911058852)
2 | Thomson Road | 0.75 | 24.03.2017 | 31.05.2017 | ---
3 | Mir Dard Road | 0.55 | 24.03.2017 | 31.05.2017 | ---
4 | DDU Marg | 1.98 | 24.03.2017 | 31.05.2017 | ---
5 | Mahawat Khan Road | 1.1 | 24.03.2017 | 31.05.2017 | ---
6 | Vishnu Dignamber Marg | 0.32 | 24.03.2017 | 31.05.2017 | 15%
7 | Ranjit Singh Road | 0.45 | 24.03.2017 | 31.05.2017 | ---
8 | Minto Road | 0.7 | 24.03.2017 | 31.05.2017 | ---
9 | Mata Sundri Road | 1.1 | 24.03.2017 | 31.05.2017 | ---
10 | Turkman Road | 0.6 | 24.03.2017 | 31.05.2017 | ---
11 | JLN Marg | 1.86 | 24.03.2017 | 31.05.2017 | ---
12 | Kotla Road | 1.48 | 24.03.2017 | 31.05.2017 | ---
13 | N S Marg | 2.22 | 24.03.2017 | 31.05.2017 | 5%
14 | Asaf Ali Marg | 1.9 | 24.03.2017 | 31.05.2017 | ---
15 | Chaman Lal Marg | 0.18 | 24.03.2017 | 31.05.2017 | ---
Name of MLA :- Ms. Alka lamba
Name of Constituency & Constituency No.:- Chandni Chowk 20
16 | S.P.M. Marg | 1.48 | 24.03.2017 | 31.05.2017 | 10% | Er. Gaurav Sankhwar (Mob. 8447973170) | Er. S.N. Moitra (Mob 9968310379) | Er. Rajiv Lochan (Mob. 9911058852)
17 | HC Sen Road | 0.4 | 24.03.2017 | 31.05.2017 | 7%
18 | Khari Bawali Road | 0.427 | 24.03.2017 | 31.05.2017 | ---
19 | Esplanade Road | 0.43 | 24.03.2017 | 31.05.2017 | ---
20 | Naya Bazar Road | 0.58 | 24.03.2017 | 31.05.2017 | ---
21 | Zorawar Singh Marg | 1.32 | 24.03.2017 | 31.05.2017 | ---
22 | Mori Gate Road | 0.38 | 24.03.2017 | 31.05.2017 | ---
23 | Kela Ghat | 0.175 | 24.03.2017 | 31.05.2017 | --- | Er. Gaurav Sankhwar (Mob. 8447973170) | Er. S.N. Moitra (Mob 9968310379) | Er. Rajiv Lochan (Mob. 9911058852)
24 | Dewan Hall Road | 0.27 | 24.03.2017 | 31.05.2017 | 5%
25 | Jama Masjid Road | 1.45 | 24.03.2017 | 31.05.2017 | ---
26 | Chandni Chowk Road | 1.29 | 24.03.2017 | 31.05.2017 | ---
27 | Road No.- 47 (Boulevard Road) | 1.04 | 24.03.2017 | 31.05.2017 | ---
28 | Rajpur Road | 2.565 | 24.03.2017 | 31.05.2017 | ---
29 | Approach Road | 0.25 | 24.03.2017 | 31.05.2017 | ---
30 | Approach Road | 0.215 | 24.03.2017 | 31.05.2017 | ---
31 | Hamilton Road | 0.24 | 24.03.2017 | 31.05.2017 | ---
32 | Gokhle Road | 0.876 | 24.03.2017 | 31.05.2017 | ---
33 | Sarai Phose Road | 0.71 | 24.03.2017 | 31.05.2017 | ---
34 | Lothein Road | 0.925 | 24.03.2017 | 31.05.2017 | ---
SRD-II
Name of MLA :- Sh. Vishesh Ravi
Name of Constituency & Constituency No.:- Karol Bagh, 23
1 | Panchkuiya Road | 1.28 | 10-04-2017 | 31.05.2017 | --- | Er. Abhinav Kishor (Mob. 9451776636) | Er. Santosh Dutta (Mob 9213765200) | Er. J.P. Sharma (Mob. 7838694446)
2 | Nehru Bazar Road | 0.45 | 10-04-2017 | 31.05.2017 | ---
3 | DAV Aram Bagh Road | 0.46 | 10-04-2017 | 31.05.2017 | ---
4 | Basant Road | 0.77 | 10-04-2017 | 31.05.2017 | ---
5 | Main Bazar Road | 0.95 | 10-04-2017 | 31.05.2017 | ---
6 | Chitra Gupta Road | 0.68 | 10-04-2017 | 31.05.2017 | ---
7 | CGHS Dispansary Road | 0.23 | 10-04-2017 | 31.05.2017 | ---
8 | Desh Bandu Gupta Road | 4.4 | 10-04-2017 | 31.05.2017 | ---
9 | New Rohtak Road | 2.2 | 15-03-2017 | 31.05.2017 | 50%
10 | Faiz Road | 1.41 | 10-04-2017 | 31.05.2017 | ---
11 | Rani Jhansi Road | 1.71 | 10-04-2017 | 31.05.2017 | ---
12 | Link Road | 0.65 | No Drain | No Drain | ---
13 | Vallabacharya marg | 0.25 | 10-04-2017 | 31.05.2017 | ---
14 | Ajmal Khan Road | 1.6 | 10-04-2017 | 31.05.2017 | --- | Er. Mohd. Yunus (Mob. 9654290714) | Er. Sunil Kumar Kataria (Mob. 9958068748) | Er. J.P. Sharma (Mob. 7838694446)
15 | Road No. 3 | 0.5 | 15-03-2017 | 20-03-2017 | 100%
16 | Dyanand Saraswati Marg (Road No. 4) | 0.5 | 17-03-2017 | 2017-03-24 | 100%
17 | Guru Nanak Road (Road No. 5) | 0.9 | 17-03-2017 | 2017-03-24 | 100%
18 | Military Road | 1.4 | 15-03-2017 | 31.05.2017 | 75%
19 | Pyare Lal Road | 2 | 18-03-2017 | 2017-03-25 | 100% | Er. Mohd. Yunus (Mob. 9654290714) | Er. Sunil Kumar Kataria (Mob. 9958068748) | Er. J.P. Sharma (Mob. 7838694446)
20 | Hardhyan Singh Road | 1.8 | 10-04-2017 | 31.05.2017 | ---
21 | Padam Singh Road | 1.5 | 20-04-2017 | 31.05.2017 | ---
22 | Tank Road | 1 | 20-04-2017 | 31.05.2017 | ---
23 | Guru Ravi Das Marg | 2 | 24-03-2017 | 31.05.2017 | 90%
24 | East Park Road | 0.99 | 01-05-2017 | 31.05.2017 |  | Er. Amarnath (Mob. 9821863995) | Er. Sunil Kumar Kataria (Mob. 9958068748) | Er. J.P. Sharma (Mob. 7838694446)
25 | S.K. Dass Road | 1 | 20-03-2017 | 2017-03-26 | 100%
26 | Abdul Rehman Road | 0.715 | 10-05-2017 | 31.05.2017 | ---
27 | Abdul Aziz Road | 0.85 | 10-05-2017 | 31.05.2017 | ---
28 | Elahi Bux Road | 0.415 | 10-05-2017 | 31.05.2017
29 | Gurudara Road | 1 | 20-03-2017 | 31.05.2017 | 95%
30 | Saraswati Marg | 1 | 25-03-2017 | 31.05.2017 | 96%
31 | Sant. Sujan Singh Marg | 0.375 | 10-05-2017 | 31.05.2017 | ---
32 | Gangeshwar Dham Marg | 0.375 | 10-05-2017 | 31.05.2017 | ---
33 | D.B Gupta Road | 2 | 22-03-2017 | 31.05.2017 | 65%
34 | Arya Samaj Road | 1.8 | 25-05-2017 | 31.05.2017 | ---
35 | Military Road | 0.9 | 2017-03-15 | 31.05.2017 | 70%
36 | Gaushala Road / DCM Road | 1.4 | 25-05-2017 | 31.05.2017 | ---
37 | Khajoor Road | 0.32 | 22-03-2017 | 2017-03-29 | 100%
38 | Ganga Mandir Marg | 1.5 | 10-05-2017 | 31.05.2017 | ---
39 | Vishnu Mandir Marg | 1.5 | 20-05-2017 | 31.05.2017 | ---
Name of MLA:- Imran Hussain
Name of Constituency & Constituency No.:- Ballimaran - 22
40 | Chelmsford Road | 0.39 | 10-05-2017 | 31.05.2017 | --- | Er. Abhishek Prakash (Mob. 8587959492) | Er.S.P. Singh (Mob. 8800534846) | Er. J.P. Sharma (Mob. 7838694446)
41 | Sadar Thana Road | 0.5 | 10-05-2017 | 31.05.2017 | ---
42 | Desh Raj Bhatiya Marg | 0.83 | 20-05-2017 | 31.05.2017 | ---
43 | Ram Kumar Marg | 0.45 | 20-05-2017 | 31.05.2017 | ---
44 | Idgah Road | 1.09 | 20-05-2017 | 31.05.2017 | ---
45 | G.B. Road | 0.5 | 10-05-2017 | 31.05.2017 | ---
46 | S.N. Marg | 0.95 | 10-05-2017 | 31.05.2017 | ---
47 | Qutub Road | 1.85 | 10-05-2017 | 31.05.2017 | ---
Name of MLA :- Sh. Som Dutt
Name of Constituency & Constituency No.:- Sadar Bazar, 19
48 | Azad Market Road | 0.79 | 20-05-2017 | 31.05.2017 | --- | Er. Thonchulo Magh (Mob. 9711048979) | Er. S.P. Singh (Mob. 8800534846) | Er. J.P. Sharma (Mob. 7838694446)
49 | Bahadur Garth Road | 0.91 | 20-05-2017 | 31.05.2017 | ---
50 | Pahari Dheeraj Road | 1.2 | 20-05-2017 | 31.05.2017 | ---
51 | Qutub Road | 0.3 | 10-05-2017 | 31.05.2017 | ---
52 | Foota Road | 0.25 | 10-05-2017 | 31.05.2017 | ---
53 | New Rohtak Road | 1 | 10-05-2017 | 31.05.2017 | ---
54 | Gali No. 10 | 0.3 | 20-05-2017 | 31.05.2017 | ---
55 | Gali No. 10 | 0.5 | 20-05-2017 | 31.05.2017 | ---
56 | Zakhira Flyover | 1.6 | 20-05-2017 | 31.05.2017 | ---
57 | Vishwakarma Marg | 1 | 20-05-2017 | 31.05.2017 | ---
C&ND Road Divn.
MLA. Sh. Sanjeev Jha (Burari Consitituency)
1 | Main Burari Road | 7.1 | 04.03.2017 | 31.05.2017 | 35% | Sh. Arun Kumar 9971551958 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
2 | Swaroop Nagar Road | 2.8 | 04.03.2017 | 31.05.2017 | 5% | Sh. D.C. Jaiswal 8744090383 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
MLA Mrs. Alka Lamba (Chandni Chowk Constituency)
3 | Magazine Road | 1.35 | 04.03.2017 | 31.05.2017 | 10% | Sh. D.C. Jaiswal 8744090383 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
4 | Road No. -46 | 0.3 | 04.03.2017 | 31.05.2017 | 20% | Sh. D.C. Jaiswal 8744090383 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
5 | Road No. -45 | 2.5 | 04.03.2017 | 31.05.2017 | 20% | Sh. D.C. Jaiswal 8744090383 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
MLA Sh. Pawan Sharma (Adarsh Nagar Constituency)
6 | Gandhi Vihar | 0.67 | 04.03.2017 | 31.05.2017 | 50% | Sh. D.C. Jaiswal 8744090383 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
MLA Sh. Pankaj Pushkar (Timarpur Constituency)
7 | BBM Road from Hakikat Nagar, Red Light to Mukherjee Nagar Bandh | 2.4 | 04.03.2017 | 31.05.2017 | 15% | Sh. D.C. Jaiswal 8744090383 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
8 | 60ft Road from Aggarwal Sweets to Nulife Hospital between BBM Road and Burari Road | 0.35 | 04.03.2017 | 31.05.2017 | 15% | Sh. D.C. Jaiswal 8744090383 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
9 | Sant Parmanand Colony Road | 0.9 | 04.03.2017 | 31.05.2017 | 15% | Sh. D.C. Jaiswal 8744090383 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
10 | Burari Road from Kingsway Camp to Road No. 50 | 3.5 | 04.03.2017 | 31.05.2017 | 15% | Sh. D.C. Jaiswal 8744090383 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
11 | Wazirabad Flyover | 1.06 | 04.03.2017 | 31.05.2017 | 18% | Sh. Arun Kumar 9971551958 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
12 | Munshi Ram Road | 0.5 | 04.03.2017 | 31.05.2017 | 15% | Sh. D.C. Jaiswal 8744090383 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
13 | Parmanand School Road | 0.33 | 04.03.2017 | 31.05.2017 | 20% | Sh. D.C. Jaiswal 8744090383 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
14 | Avtar singh Marg (Nirankari Colony) (Nirankari Colony Gate to culvert Burari Road toward Nirankari Sr. Sec. School) | 1.9 | 04.03.2017 | 31.05.2017 | 15% | Sh. D.C. Jaiswal 8744090383 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
15 | Police Chowki to Mandir Outram Lane | 0.44 | 04.03.2017 | 31.05.2017 | 17% | Sh. D.C. Jaiswal 8744090383 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
16 | BBM Road to Jahagir puri Drain | 0.4 | 04.03.2017 | 31.05.2017 | 15% | Sh. D.C. Jaiswal 8744090383 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
17 | Tagore Park Main road | 0.9 | 04.03.2017 | 31.05.2017 | 10% | Sh. Arun Kumar 9971551958 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
18 | Road in Tagore Park from H. No. 213 to Gole Chakkar | 0.45 | 04.03.2017 | 31.05.2017 | 20% | Sh. Arun Kumar 9971551958 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
19 | Road in Tagore Park from H. No. 37 to H. No. 64 | 1.55 | 04.03.2017 | 31.05.2017 | 0% | Sh. Arun Kumar 9971551958 | Sh. Jaswinder Pal 9650371895 | Sh. Anil Trehan 8447001861
20 | University Road from Mall Road to Petrol Pump Ward-10 | 1.58 | 04.03.2017 | 31.05.2017 | 50% | Sh. Pankaj Kr. Bind 9821387374 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
21 | Khalsa College road from Mall Road to Roop Nagar (Gurutegh Bahadur Road) | 1.3 | 04.03.2017 | 31.05.2017 | 70% | Sh. Pankaj Kr. Bind 9821387374 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
22 | Chhatra Marg Road from Mall Road to Malka Gunj Chowk | 1.65 | 04.03.2017 | 31.05.2017 | 10% | Sh. Pankaj Kr. Bind 9821387374 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
23 | Shiriya Mishra marg from Jai Jawan Tea Stall to Moris Nagar Thana | 0.42 | 04.03.2017 | 31.05.2017 | 70% | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
24 | Sudhir Bose Marg from chouburjja chowk to ACP Office | 1.25 | 04.03.2017 | 31.05.2017 | 0% | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
25 | Polo Road from Jahanara Marg to shani Mandir Vijay Nagar | 0.3 | 04.03.2017 | 31.05.2017 | 0% | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
26 | Mahatma Gandhii Road (Ring Road) | 1.6 | 04.03.2017 | 31.05.2017 | 100% | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
27 | Vijay Nagar main road from Royal Palace to E-11 Vijay Nagar | 0.75 | 04.03.2017 | 31.05.2017 | 0% | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
28 | G.T. Road from Baraf Khana chowk to Clock Tower | 1.2 | 04.03.2017 | 31.05.2017 | 50% | Sh. Pankaj Kr. Bind 9821387374 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
29 | Roshnara Road from Pulbanash Metro Station to Hans Raj College. | 2.7 | 04.03.2017 | 31.05.2017 | 30% | Sh. Pankaj Kr. Bind 9821387374 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
30 | Surjit Singh Marg Camp Chowk to Najafgarh Drain | 0.8 | 04.03.2017 | 31.05.2017 | 0% | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
31 | Timarpur road from Mall Road crossing to Wazirabad Crossing | 1.9 | 04.03.2017 | 31.05.2017 | 0% | Sh. Ashutosh Singh 9136151991 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
32 | Lucknow Road from Mall Road to P.S. Timarpur | 1.7 | 04.03.2017 | 31.05.2017 | 20% | Sh. Ashutosh Singh 9136151991 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
MLA Sh. Akhilesh Pati Tripathi ( Model Town Constituency)
33 | Road No. 48 | 1.92 | 04.03.2017 | 31.05.2017 | 0% | Sh. Pankaj Kr. Bind 9821387374 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
34 | Bunglow Road from Roop Nagar round about to Hansraj College T-point on Chattra Marg | 0.65 | 04.03.2017 | 31.05.2017 | 25% | Sh. Pankaj Kr. Bind 9821387374 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
35 | Mandelia Road from GT Road to Bunglow Road | 0.7 | 04.03.2017 | 31.05.2017 | 25% | Sh. Pankaj Kr. Bind 9821387374 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
36 | Polo Road from Bhama Shah Road to Shani Mandir (Vijay Nagar) | 0.84 | 04.03.2017 | 31.05.2017 | 0% | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
37 | Gurmandi Road from Tripolia gate GT Road to H. NO. 264 Kalyan Vihar | 0.425 | 04.03.2017 | 31.05.2017 | 0% | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
38 | Kalyan Vihar Road from 25 Kalyan Vihar to 1 No. Priyadarshni Vihar | 0.9 | 04.03.2017 | 31.05.2017 | 0% | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
39 | Jahanara Road from Bhamashah Marg to vijay Nagar | 0.83 | 04.03.2017 | 31.05.2017 | 0% | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
40 | Satyawati Marg from Police Station Roop Nagar to Shakti Nagar Chowk | 0.52 | 04.03.2017 | 31.05.2017 | 0% | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
41 | Bhama Shah Road from Mall Road to GT Road Nanak Piao Gurudwara | 1.45 | 04.03.2017 | 31.05.2017 | 0% | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
42 | GT Road from Nanak Piao Gurudwara to Clock Tower | 1.95 | 04.03.2017 | 31.05.2017 | 0% | Sh. Pankaj Kr. Bind 9821387374 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
43 | Inderchand Shastri Marg from Shakti Nagar Chowk to Swami Narayan Marg | 0.9 | 04.03.2017 | 31.05.2017 | 0% | Sh. Yogesh Kumar 8010697080 | Sh. Rajiv Khare 9911190886 | Sh. Anil Trehan 8447001861
MLA. Sh. Praveen Kumar (Jungpura Constitueuncy)
44 | Ring Road By-pass | 2.9 | 07.03.2017 | 31.05.2017 | 70% | Md. Sharafat Hussain 9310098783 | Sh.Vinod Kumar Garg 9212498959 | Sh. Anil Trehan 8447001861
45 | Sachivalya Road | 1.6 | 07.03.2017 | 31.05.2017 | 70% | Md. Sharafat Hussain 9310098783 | Sh.Vinod Kumar Garg 9212498959 | Sh. Anil Trehan 8447001861
46 | IP Marg | 0.5 | 07.03.2017 | 31.05.2017 | 70% | Sh. Anish Kumar 9891486390 | Sh.Vinod Kumar Garg 9212498959 | Sh. Anil Trehan 8447001861
47 | IG Slip Road | 0.58 | 07.03.2017 | 31.05.2017 | 60% | Md. Sharafat Hussain 9310098783 | Sh.Vinod Kumar Garg 9212498959 | Sh. Anil Trehan 8447001861
48 | Velodrome Road | 0.57 | 07.03.2017 | 31.05.2017 | 50% | Md. Sharafat Hussain 9310098783 | Sh.Vinod Kumar Garg 9212498959 | Sh. Anil Trehan 8447001861
49 | Vikas Marg | 0.5 | 07.03.2017 | 31.05.2017 | 40% | Md. Sharafat Hussain 9310098783 | Sh.Vinod Kumar Garg 9212498959 | Sh. Anil Trehan 8447001861
50 | Satyagrah Marg | 0.5 | 07.03.2017 | 31.05.2017 | 0% | Md. Sharafat Hussain 9310098783 | Sh.Vinod Kumar Garg 9212498959 | Sh. Anil Trehan 8447001861
51 | Azad Bhawan Road | 0.5 | 07.03.2017 | 31.05.2017 | 90% | Sh. Anish Kumar 9891486390 | Sh.Vinod Kumar Garg 9212498959 | Sh. Anil Trehan 8447001861
52 | Ring Road Bhairon Road T-Jn. to Shanti Van Crossing | 4.2 | 07.03.2017 | 31.05.2017 | 40% | Sh. Anish Kumar 9891486390 | Sh.Vinod Kumar Garg 9212498959 | Sh. Anil Trehan 8447001861
53 | JLN Marg (Delhi Gate) | 0.56 | 07.03.2017 | 31.05.2017 | 30% | Sh. Anish Kumar 9891486390 | Sh.Vinod Kumar Garg 9212498959 | Sh. Anil Trehan 8447001861
54 | Ghata Masjid Road | 0.26 | 07.03.2017 | 31.05.2017 | 35% | Sh. Anish Kumar 9891486390 | Sh.Vinod Kumar Garg 9212498959 | Sh. Anil Trehan 8447001861
55 | Mathura Road | 0.75 | 07.03.2017 | 31.05.2017 | 45% | Sh. Anish Kumar 9891486390 | Sh.Vinod Kumar Garg 9212498959 | Sh. Anil Trehan 8447001861
56 | Bahadur Shah Zafar Marg | 2 | 07.03.2017 | 31.05.2017 | 50% | Sh. Anish Kumar 9891486390 | Sh.Vinod Kumar Garg 9212498959 | Sh. Anil Trehan 8447001861
Name of MLA :- Ms. Alka lamba
Name of Constituency & Constituency No.:- Chandni Chowk 20
57 | Ring Road By-pass | 2.65 | 07.03.2017 | 31.05.2017 | 80% | Sh. Kunwar Pal Singh 9599460598 | Sh.Vinod Kumar Garg 9212498959 | Sh. Anil Trehan 8447001861
58 | Court Road | 1.75 | 07.03.2017 | 31.05.2017 | 10% | Sh. Kunwar Pal Singh 9599460598 | Sh.Vinod Kumar Garg 9212498959 | Sh. Anil Trehan 8447001861
59 | Club Road | 1.75 | 07.03.2017 | 31.05.2017 | 10% | Sh. Kunwar Pal Singh 9599460598 | Sh.Vinod Kumar Garg 9212498959 | Sh. Anil Trehan 8447001861
60 | Under Hill Road | 0.69 | 07.03.2017 | 31.05.2017 | 10% | Sh. Kunwar Pal Singh 9599460598 | Sh.Vinod Kumar Garg 9212498959 | Sh. Anil Trehan 8447001861
61 | Flag Staff Road | 0.425 | 07.03.2017 | 31.05.2017 | 20% | Sh. Kunwar Pal Singh 9599460598 | Sh.Vinod Kumar Garg 9212498959 | Sh. Anil Trehan 8447001861
62 | Shamnath Marg | 1.3 | 07.03.2017 | 31.05.2017 | 80% | Sh. Kunwar Pal Singh 9599460598 | Sh.Vinod Kumar Garg 9212498959 | Sh. Anil Trehan 8447001861
63 | Rajniwas Marg | 0.926 | 07.03.2017 | 31.05.2017 | 30% | Sh. Kunwar Pal Singh 9599460598 | Sh.Vinod Kumar Garg 9212498959 | Sh. Anil Trehan 8447001861
64 | CNG Crematorium Road | 0.25 | 07.03.2017 | 31.05.2017 | 50% | Md. Sharafat Hussain 9310098783 | Sh.Vinod Kumar Garg 9212498959 | Sh. Anil Trehan 8447001861
65 | Ring Road | 2 | 07.03.2017 | 31.05.2017 | 70% | Md. Sharafat Hussain 9310098783 | Sh.Vinod Kumar Garg 9212498959 | Sh. Anil Trehan 8447001861
66 | Mahatma Gandhi Road | 4 | 07.03.2017 | 31.05.2017 | 60% | Sh. Kunwar Pal Singh 9599460598 Md. Sharafat Hussain 9310098783 | Sh.Vinod Kumar Garg 9212498959 | Sh. Anil Trehan 8447001861
67 | Nishad Raj Marg | 0.55 | 07.03.2017 | 31.05.2017 | 50% | Sh. Anish Kumar 9891486390 | Sh.Vinod Kumar Garg 9212498959 | Sh. Anil Trehan 8447001861