## North Zone
PWD Desilting Report (Preparedness for Monsoon)
DESILTING UNDER PWD MAINTENANCE NORTH ZONE AS ON 28.04.2017
Sl. No. | Name of Roads | Length (in Km) | Date of Start | Date of Completion (Ist Cycle) | % Progress | JE in charge / Mobile No. | AE in charge / Mobile No. | EE in charge / Mobile No.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
NORTH WEST CIRCLE
1 | Road No. 40 (Bir Bandha Bairagi Marg) | 3.45 | 22-4-17 | 31.05.2017 | 0% | Er. Lalit Pal / 9899409171 | Er. R.S. Nigam / 9810070665 | Er. R. K. Khanna / 8826818787
2 | Swamy Narayan Marg | 2.94 | 22-4-17 | 31.05.2017 | 0% | Er. Lalit Pal / 9899409171 | Er. R.S. Nigam / 9810070665 | Er. R. K. Khanna / 8826818787
3 | Swamy Narayan Marg | 3 | 22-4-17 | 31.05.2017 | 0% | Er. Lalit Pal / 9899409171 | Er. R.S. Nigam / 9810070665 | Er. R. K. Khanna / 8826818787
4 | Old Rohtak Road | 0.7 | 22-4-17 | 31.05.2017 | 0% | Er. Lalit Pal / 9899409171 | Er. R.S. Nigam / 9810070665 | Er. R. K. Khanna / 8826818787
5 | Old Rohtak Road | 1.11 | 22-4-17 | 31.05.2017 | 10% | Er. Lalit Pal / 9899409171 | Er. R.S. Nigam / 9810070665 | Er. R. K. Khanna / 8826818787
6 | Kalidass marg (sarai rohilla flyover) | 1.485 | 22-4-17 | 31.05.2017 | 0% | Er. Lalit Pal / 9899409171 | Er. R.S. Nigam / 9810070665 | Er. R. K. Khanna / 8826818787
7 | Nand Lal Marg | 0.48 | 22-4-17 | 31.05.2017 | 0% | Er. Lalit Pal / 9899409171 | Er. R.S. Nigam / 9810070665 | Er. R. K. Khanna / 8826818787
8 | Azad Road | 0.75 | 22-4-17 | 31.05.2017 | 0% | Er. Lalit Pal / 9899409171 | Er. R.S. Nigam / 9810070665 | Er. R. K. Khanna / 8826818787
9 | Haji Abdul Salam Quareshi Marg | 0.31 | 22-4-17 | 31.05.2017 | 0% | Er. Lalit Pal / 9899409171 | Er. R.S. Nigam / 9810070665 | Er. R. K. Khanna / 8826818787
10 | Mata Jai Kaur Road | 0.165 | 22-4-17 | 31.05.2017 | 0% | Er. Lalit Pal / 9899409171 | Er. R.S. Nigam / 9810070665 | Er. R. K. Khanna / 8826818787
11 | Swamy Narayan underpass road | 1.2 | 22-4-17 | 31.05.2017 | 0% | Er. Lalit Pal / 9899409171 | Er. R.S. Nigam / 9810070665 | Er. R. K. Khanna / 8826818787
12 | Patap Nagar Road | 0.207 | 22-4-17 | 31.05.2017 | 0% | Er. Lalit Pal / 9899409171 | Er. R.S. Nigam / 9810070665 | Er. R. K. Khanna / 8826818787
13 | Bhagat Singh Road | 0.32 | 22-4-17 | 31.05.2017 | 0% | Er. Lalit Pal / 9899409171 | Er. R.S. Nigam / 9810070665 | Er. R. K. Khanna / 8826818787
14 | Link Road (east Moti Bagh) | 2 | 22-4-17 | 31.05.2017 | 0% | Er. Lalit Pal / 9899409171 | Er. R.S. Nigam / 9810070665 | Er. R. K. Khanna / 8826818787
15 | Rana Pratap Bagh | 1.59 | 22-4-17 | 31.05.2017 | 0% | Er. Lalit Pal / 9899409171 | Er. R.S. Nigam / 9810070665 | Er. R. K. Khanna / 8826818787
16 | Pardeshwar Dham Mandir Marg | 1.1 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
17 | Ch. Mange Ram Marg | 0.371 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
18 | Madhav Marg | 1.6 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
19 | Sh. Guru Nanak Dev Ji Marg | 0.482 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
20 | Front of Keshavpuram Police Station | 0.45 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
21 | K.C. Goel Marg | 1.43 | 22-4-17 | 31.05.2017 | 15% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
22 | Maharishi Dayanand Saraswati Marg | 0.455 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
23 | Shri Ram Krishan Mandir Marg | 0.551 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
24 | Kulachi Hans Raj School Marg | 0.23 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
25 | F-Block Market | 0.38 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
26 | B-Block Market | 0.27 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
27 | Deep Chand Central Market | 1 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
28 | Ch. Gulab Singh Marg | 3.1 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
29 | Road No. 37 (Maharaja Nahar Singh Marg) | 3 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
30 | Jhule Lal Marg | 0.363 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
31 | Shiv Ram Mandir Marg | 0.3 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
32 | Road No. 38 | 0.7 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
33 | Mata Jai Kaur Road | 0.29 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
34 | Sunder Lal Jain Road | 0.55 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
35 | Bunkar Colony Road | 0.224 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
36 | Kakaji Lane | 0.32 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
37 | Laxmi Bai College Road | 0.385 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
38 | Swamy Narayan underpass road | 0.5 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
39 | Bharat Nagar Road | 2.09 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
40 | Nimri Colony Road | 0.3 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
41 | Nimri Colony Road | 0.175 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
42 | Nimri Colony Road | 0.175 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
43 | Nimri Colony Road | 0.35 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
44 | Nimri Colony Road | 0.095 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
45 | Nimri Colony Road | 0.322 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
46 | Nimri Colony Road | 0.773 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
47 | Nimri Colony Road | 0.328 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
48 | Tawetia Marg | 1.03 | 22-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. Sudhanand / 9968318994 | Er. R. K. Khanna / 8826818787
49 | Guru Harikishan Marg (Road No. 43) (From RD 0m to RD 1745m) | 1.463 | 28-4-17 | 31.05.2017 | 0% | Er.Subash Tomar / 7827726254 | Er. M. L. Garg / 9868383698 | Er. R. K. Khanna / 8826818787
50 | Shyamji Krishan Verma Marg (Road No.44) | 2 | 28-4-17 | 31.05.2017 | 10% | Er.Subash Tomar / 7827726254 | Er. M. L. Garg / 9868383698 | Er. R. K. Khanna / 8826818787
51 | Kabir Das Road | 1.59 | 28-4-17 | 31.05.2017 | 0% | Er.Subash Tomar / 7827726254 | Er. M. L. Garg / 9868383698 | Er. R. K. Khanna / 8826818787
52 | Railway Road (Sardar Balbir Singh Siddhu Marg) Road No. 43 to URB Shakurbasti | 0.99 | 28-4-17 | 31.05.2017 | 0% | Er.Subash Tomar / 7827726254 | Er. M. L. Garg / 9868383698 | Er. R. K. Khanna / 8826818787
53 | Eklavya Marg | 0.37 | 28-4-17 | 31.05.2017 | 0% | Er.Subash Tomar / 7827726254 | Er. M. L. Garg / 9868383698 | Er. R. K. Khanna / 8826818787
54 | Veer Hemu Marg | 1.085 | 28-4-17 | 31.05.2017 | 0% | Er.Subash Tomar / 7827726254 | Er. M. L. Garg / 9868383698 | Er. R. K. Khanna / 8826818787
55 | Maharishi Parshu Ram Marg | 0.75 | 28-4-17 | 31.05.2017 | 0% | Er.Subash Tomar / 7827726254 | Er. M. L. Garg / 9868383698 | Er. R. K. Khanna / 8826818787
56 | Triwalubar Marg | 0.29 | 28-4-17 | 31.05.2017 | 0% | Er.Subash Tomar / 7827726254 | Er. M. L. Garg / 9868383698 | Er. R. K. Khanna / 8826818787
57 | Main Road of G-Block & H-Block | 0.325 | 28-4-17 | 31.05.2017 | 0% | Er.Subash Tomar / 7827726254 | Er. M. L. Garg / 9868383698 | Er. R. K. Khanna / 8826818787
58 | Valmiki Road | 0.6 | 28-4-17 | 31.05.2017 | 0% | Er.Subash Tomar / 7827726254 | Er. M. L. Garg / 9868383698 | Er. R. K. Khanna / 8826818787
59 | Abdul Hameed Marg | 0.78 | 28-4-17 | 31.05.2017 | 0% | Er.Subash Tomar / 7827726254 | Er. M. L. Garg / 9868383698 | Er. R. K. Khanna / 8826818787
60 | Phirni Road | 0.53 | 28-4-17 | 31.05.2017 | 0% | Er.Subash Tomar / 7827726254 | Er. M. L. Garg / 9868383698 | Er. R. K. Khanna / 8826818787
61 | Lawrence Road | 0.6 | 28-4-17 | 31.05.2017 | 0% | Er.Subash Tomar / 7827726254 | Er. M. L. Garg / 9868383698 | Er. R. K. Khanna / 8826818787
62 | Rampura Main Road | 1.2 | 28-4-17 | 31.05.2017 | 0% | Er.Subash Tomar / 7827726254 | Er. M. L. Garg / 9868383698 | Er. R. K. Khanna / 8826818787
63 | Lala Lajpat Rai Marg | 0.37 | 28-4-17 | 31.05.2017 | 0% | Er.Subash Tomar / 7827726254 | Er. M. L. Garg / 9868383698 | Er. R. K. Khanna / 8826818787
64 | Parwana road | 0.375 | 28-4-17 | 31.05.2017 | 0% | Er.Subash Tomar / 7827726254 | Er. M. L. Garg / 9868383698 | Er. R. K. Khanna / 8826818787
65 | Road No. 41 | 3 | 22-4-17 | 31.05.2017 | 0% | Er.Sheikh Nizam / 9899248998 | Er. Baljeet Singh / 9911371317 | Er. R. K. Khanna / 8826818787
66 | Ring Road | 3.2 | 22-4-17 | 31.05.2017 | 10% | Er.Sheikh Nizam / 9899248998 | Er. Baljeet Singh / 9911371317 | Er. R. K. Khanna / 8826818787
67 | Road No.37 Ext. | 0.32 | 22-4-17 | 31.05.2017 | 0% | Er.Sheikh Nizam / 9899248998 | Er. Baljeet Singh / 9911371317 | Er. R. K. Khanna / 8826818787
68 | RUB Shalimar Bagh Road | 0.6 | 22-4-17 | 31.05.2017 | 0% | Er.Sheikh Nizam / 9899248998 | Er. Baljeet Singh / 9911371317 | Er. R. K. Khanna / 8826818787
69 | Jhule Lal Mandir Marg Shalimar Bagh | 1.25 | 22-4-17 | 31.05.2017 | 0% | Er.Sheikh Nizam / 9899248998 | Er. Baljeet Singh / 9911371317 | Er. R. K. Khanna / 8826818787
70 | Dividing Road | 0.26 | 22-4-17 | 31.05.2017 | 0% | Er.Sheikh Nizam / 9899248998 | Er. Baljeet Singh / 9911371317 | Er. R. K. Khanna / 8826818787
71 | Abhinav model School | 0.4 | 22-4-17 | 31.05.2017 | 0% | Er.Sheikh Nizam / 9899248998 | Er. Baljeet Singh / 9911371317 | Er. R. K. Khanna / 8826818787
72 | Ahinsa path Road | 0.4 | 22-4-17 | 31.05.2017 | 0% | Er.Sheikh Nizam / 9899248998 | Er. Baljeet Singh / 9911371317 | Er. R. K. Khanna / 8826818787
73 | NP - MP Road | 0.46 | 22-4-17 | 31.05.2017 | 0% | Er.Sheikh Nizam / 9899248998 | Er. Baljeet Singh / 9911371317 | Er. R. K. Khanna / 8826818787
74 | SP School Road | 0.65 | 22-4-17 | 31.05.2017 | 0% | Er.Sheikh Nizam / 9899248998 | Er. Baljeet Singh / 9911371317 | Er. R. K. Khanna / 8826818787
75 | Shaheed Udham Singh Marg | 1.6 | 22-4-17 | 31.05.2017 | 10% | Er.Sheikh Nizam / 9899248998 | Er. Baljeet Singh / 9911371317 | Er. R. K. Khanna / 8826818787
76 | Swami Shardanand Saraswati Marg | 1.2 | 22-4-17 | 31.05.2017 | 0% | Er.Sheikh Nizam / 9899248998 | Er. Baljeet Singh / 9911371317 | Er. R. K. Khanna / 8826818787
77 | Maharaja Agarsen Road | 2.84 | 22-4-17 | 31.05.2017 | 0% | Er.Sheikh Nizam / 9899248998 | Er. Baljeet Singh / 9911371317 | Er. R. K. Khanna / 8826818787
78 | Gopal Mandir Road | 1.105 | 22-4-17 | 31.05.2017 | 0% | Er.Sheikh Nizam / 9899248998 | Er. Baljeet Singh / 9911371317 | Er. R. K. Khanna / 8826818787
79 | Gurudwara Road | 0.6 | 22-4-17 | 31.05.2017 | 0% | Er.Sheikh Nizam / 9899248998 | Er. Baljeet Singh / 9911371317 | Er. R. K. Khanna / 8826818787
80 | Gyan Shakti Mandir Marg | 1.25 | 22-4-17 | 31.05.2017 | 0% | Er.Sheikh Nizam / 9899248998 | Er. Baljeet Singh / 9911371317 | Er. R. K. Khanna / 8826818787
81 | Maharishi Dayanand Marg | 0.4 | 22-4-17 | 31.05.2017 | 0% | Er.Sheikh Nizam / 9899248998 | Er. Baljeet Singh / 9911371317 | Er. R. K. Khanna / 8826818787
82 | Bhagwan Mahavir Marg | 0.54 | 22-4-17 | 31.05.2017 | 0% | Er.Sheikh Nizam / 9899248998 | Er. Baljeet Singh / 9911371317 | Er. R. K. Khanna / 8826818787
83 | Club Road | 0.6 | 22-4-17 | 31.05.2017 | 0% | Er.Sheikh Nizam / 9899248998 | Er. Baljeet Singh / 9911371317 | Er. R. K. Khanna / 8826818787
84 | K.L. Bagga Marg | 0.6 | 22-4-17 | 31.05.2017 | 0% | Er.Sheikh Nizam / 9899248998 | Er. Baljeet Singh / 9911371317 | Er. R. K. Khanna / 8826818787
85 | Haiderpur Main Road | 0.9 | 22-4-17 | 31.05.2017 | 0% | Er.Sheikh Nizam / 9899248998 | Er. Baljeet Singh / 9911371317 | Er. R. K. Khanna / 8826818787
86 | Canal Road | 0.88 | 22-4-17 | 31.05.2017 | 0% | Er.Sheikh Nizam / 9899248998 | Er. Baljeet Singh / 9911371317 | Er. R. K. Khanna / 8826818787
87 | Ram Leela Ground Road | 0.88 | 22-4-17 | 31.05.2017 | 0% | Er.Sheikh Nizam / 9899248998 | Er. Baljeet Singh / 9911371317 | Er. R. K. Khanna / 8826818787
88 | Elevated portion | 1.78 | 22-4-17 | 31.05.2017 | 0% | Er.Sheikh Nizam / 9899248998 | Er. Baljeet Singh / 9911371317 | Er. R. K. Khanna / 8826818787
89 | BDFD Road | 0.54 | 15-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. A.S.Bharija / 9718423533 | Er. R. K. Khanna / 8826818787
90 | T.V Tower Road | 0.66 | 15-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. A.S.Bharija / 9718423533 | Er. R. K. Khanna / 8826818787
91 | Power House Road | 1.03 | 15-4-17 | 31.05.2017 | 10% | Er.Sanjay Luthra / 9868154719 | Er. A.S.Bharija / 9718423533 | Er. R. K. Khanna / 8826818787
92 | Muni Maya Ram Road | 1.738 | 15-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. A.S.Bharija / 9718423533 | Er. R. K. Khanna / 8826818787
93 | Outer Ringh Road ( Madhuban Chowk to Haider pur metro Station) | 3.8 | 15-4-17 | 31.05.2017 | 0% | Er.Sanjay Luthra / 9868154719 | Er. A.S.Bharija / 9718423533 | Er. R. K. Khanna / 8826818787
N W R-2
1 | Ch Balbir Singh Marg from Road No. 30 to Rohtak Road (NH-10) | 1.06 | 14.04.2017 | 31.05.2017 | 0% | Sh. Rajesh Mewada 9873754012 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
2 | Bhao Rao Dev Ras Marg | 1.4 | 14.04.2017 | 31.05.2017 | 0% | Sh. Rajesh Mewada 9873754012 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
3 | Deen Dayal Upadhyay Marg | 0.6 | 14.04.2017 | 31.05.2017 | 0% | Sh. Rajesh Mewada 9873754012 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
4 | Major Ashwani Marg | 1 | 14.04.2017 | 31.05.2017 | 0% | Sh. Rajesh Mewada 9873754012 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
5 | Road between B4 and B5 Block Paschim Vihar | 0.35 | 14.04.2017 | 31.05.2017 | 0% | Sh. Rajesh Mewada 9873754012 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
6 | Guru Harkishan Marg (road No. 43) | 1.8 | 14.04.2017 | 31.05.2017 | 0% | Sh. Rajesh Mewada 9873754012 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
7 | Chandra Shekhar Azad Marg (Road No. 42) | 1.23 | 14.04.2017 | 31.05.2017 | 0% | Sh. Rajesh Mewada 9873754012 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
8 | Guru Harkishan Marg (road No. 43) | 1.7 | 14.04.2017 | 31.05.2017 | 0% | Sh. Rajesh Mewada 9873754012 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
9 | Mahatma Hans Raj Marg | 1.4 | 14.04.2017 | 31.05.2017 | 0% | Sh. Rajesh Mewada 9873754012 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
10 | Guru Birja Nand Marg | 1.4 | 14.04.2017 | 31.05.2017 | 0% | Sh. Rajesh Mewada 9873754012 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
11 | Sant Nagar M2K Road | 0.47 | 14.04.2017 | 31.05.2017 | 0% | Sh. Rajesh Mewada 9873754012 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
12 | Amar Shaheed Bismil Marg | 0.94 | 14.04.2017 | 31.05.2017 | 0% | Sh. Rajesh Mewada 9873754012 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
13 | Police Line Road | 0.62 | 14.04.2017 | 31.05.2017 | 0% | Sh. Rajesh Mewada 9873754012 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
14 | Parwana Road, Saraswati Vihar | 2.8 | 14.04.2017 | 31.05.2017 | 5% | Sh. Rajesh Mewada 9873754012 | Sh. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
15 | Road No.30 | 2 | 14.04.2017 | 31.05.2017 | 0% | Sh. Rajesh Mewada 9873754012 | Er. Kartar Singh 9910877172 | Sh. Praveen Kathuria 9971669344
16 | Guru Govalkar Marg (Outer ring road Xing Mangolpuri Marble Market to Rajeev Nagar) | 5.8 | 27.04.2017 | 31.05.2017 | 25% | Sh. Bhudev 9910104476 | Sh. Raj Kishore Raj, AE, 9971409602 | Sh. Praveen Kathuria 9971669344
17 | Road No. 316 | 1.4 | 14.04.2017 | 31.05.2017 | 0% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 | Sh. Praveen Kathuria 9971669344
18 | Road No. 317 | 0.35 | 14.04.2017 | 31.05.2017 | 0% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 | Sh. Praveen Kathuria 9971669344
19 | Road No. 318 | 0.85 | 14.04.2017 | 31.05.2017 | 0% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 | Sh. Praveen Kathuria 9971669344
20 | Road No. 319 | 0.35 | 14.04.2017 | 31.05.2017 | 0% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 | Sh. Praveen Kathuria 9971669344
21 | S.N. Hardiker Marg (Road No. A-1) | 1.19 | 14.04.2017 | 31.05.2017 | 8% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 | Sh. Praveen Kathuria 9971669344
22 | Sir Chotu Ram Marg (road No. A-3) | 1 | 14.04.2017 | 31.05.2017 | 0% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 | Sh. Praveen Kathuria 9971669344
23 | Kanjhawala Link road | 0.4 | 27.04.2017 | 31.05.2017 | 0% | Sh. Bhudev 9910104476 | Sh. Raj Kishore Raj, AE, 9971409602 | Sh. Praveen Kathuria 9971669344
24 | Outer Ring Road No. 26 | 0.3 | 27.04.2017 | 31.05.2017 | 18% | Sh. Bhudev 9910104476 | Sh. Raj Kishore Raj, AE, 9971409602 | Sh. Praveen Kathuria 9971669344
25 | Sanjay Gandhi Hospital Road from Road No.316 to J Block Survodya Vidhyalya to Kanjhawla Road. | 1.6 | 14.04.2017 | 31.05.2017 | 0% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 | Sh. Praveen Kathuria 9971669344
26 | Police Station Road from Road No.3 i.e. Kanjhawla Road to Sanjay Gandhi Hospital Road. | 1.3 | 14.04.2017 | 31.05.2017 | 0% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 | Sh. Praveen Kathuria 9971669344
27 | Kala Mandir Cinema Road in Mangolpuri | 0.8 | 14.04.2017 | 31.05.2017 | 0% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 | Sh. Praveen Kathuria 9971669344
28 | LP Road (Tank Road) Mangolpuri | 1.2 | 14.04.2017 | 31.05.2017 | 0% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 | Sh. Praveen Kathuria 9971669344
29 | B-Block Road Mangolpuri | 1.4 | 14.04.2017 | 31.05.2017 | 0% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 | Sh. Praveen Kathuria 9971669344
30 | Road No.A-2 From Pole Star to CSC-II, Sec.1/2, Rohini. | 0.54 | 14.04.2017 | 31.05.2017 | 0% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 | Sh. Praveen Kathuria 9971669344
31 | Road from New Bal Bharti Public School to Road No.3 Sec.2 | 0.4 | 14.04.2017 | 31.05.2017 | 0% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 | Sh. Praveen Kathuria 9971669344
32 | Road from CSC Market Pkt.4 to Mangolpur Kalan Phirni Road Sec.2 | 0.3 | 14.04.2017 | 31.05.2017 | 0% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 | Sh. Praveen Kathuria 9971669344
33 | Roadfrom PocketA-1 to Pocket A-2 in Sec.4 Rohini | 0.225 | 14.04.2017 | 31.05.2017 | 0% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 | Sh. Praveen Kathuria 9971669344
34 | Roadfrom Pocket B-5to Pocket B-9 in Sec.4 Rohini MC Pry. School | 0.31 | 14.04.2017 | 31.05.2017 | 0% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 | Sh. Praveen Kathuria 9971669344
35 | Road From Pocket A-2 to Pkt.C-13 in Sec.3 Rohini | 1 | 14.04.2017 | 31.05.2017 | 0% | Sh. Jai Singh 9312101073 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
36 | Road from Pocket F-22 to Pocket H-34 in Sec-3 Rohini | 1 | 14.04.2017 | 31.05.2017 | 10% | Sh. Jai Singh 9312101073 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
37 | Road from MC Pry. School 3A to Sarvodaya School in Sec.3, Rohini | 0.325 | 14.04.2017 | 31.05.2017 | 0% | Sh. Jai Singh 9312101073 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
38 | Road from DDA Shopping Centre to Kendriya Vidyalaya in Sec.3, Rohini. | 0.325 | 14.04.2017 | 31.05.2017 | 0% | Sh. Jai Singh 9312101073 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
39 | Jaipur Golden Hospital Road Sec.3 | 1 | 14.04.2017 | 31.05.2017 | 0% | Sh. Jai Singh 9312101073 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
40 | G-Block Road | 0.15 | 14.04.2017 | 31.05.2017 | 0% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 | Sh. Praveen Kathuria 9971669344
41 | Nangloi Rly.Stn to Sultanpuri Bus Terminal via Jalebi Chowk | 2.1 | 14.04.2017 | 31.05.2017 | 7% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 | Sh. Praveen Kathuria 9971669344
42 | Sultanpuri Bus Terminal to Flood Control Drain. | 1 | 14.04.2017 | 31.05.2017 | 5% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 | Sh. Praveen Kathuria 9971669344
43 | Sultanpuri Main Road | 0.6 | 14.04.2017 | 31.05.2017 | 0% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 | Sh. Praveen Kathuria 9971669344
44 | Shani Bazar Road | 0.6 | 14.04.2017 | 31.05.2017 | 0% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 | Sh. Praveen Kathuria 9971669344
45 | H Block Road | 0.32 | 14.04.2017 | 31.05.2017 | 0% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 | Sh. Praveen Kathuria 9971669344
46 | Jagdamba Road | 0.38 | 14.04.2017 | 31.05.2017 | 0% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 | Sh. Praveen Kathuria 9971669344
47 | Bhalla Factory road | 0.38 | 14.04.2017 | 31.05.2017 | 0% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 | Sh. Praveen Kathuria 9971669344
48 | 70 ft Road Kirari | 1.25 | 14.04.2017 | 31.05.2017 | 8% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 | Sh. Praveen Kathuria 9971669344
49 | PWD Road to DJB Booster Pump (Length 0.270 KM) Sec.19 Rohini | 0.27 | 21.04.2017 | 31.05.2017 | 30% | Sh. Onkar Nath Prasad 9911854514 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
50 | PWD Road to Baba wala Park (Corner of Booster Pump) (Length 0.590 KM) | 0.59 | 21.04.2017 | 31.05.2017 | 0% | Sh. Onkar Nath Prasad 9911854514 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
51 | Western Yamuna Canal to Badli Chowk (Length 0.310 KM) | 0.31 | 21.04.2017 | 31.05.2017 | 0% | Sh. Onkar Nath Prasad 9911854514 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
52 | Road No. B-8 | 1.18 | 21.04.2017 | 31.05.2017 | 0% | Sh. Onkar Nath Prasad 9911854514 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
53 | Dr. K.N. Katju Marg(45m wide road) | 3.77 | 21.04.2017 | 31.05.2017 | 10% | Sh. Onkar Nath Prasad 9911854514 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
54 | Road No. B-4 | 1.4 | 21.04.2017 | 31.05.2017 | 0% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
55 | Road No. B-5 | 1.64 | 21.04.2017 | 31.05.2017 | 0% | Sh. Onkar Nath Prasad 9911854514 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
56 | Road No. B-7 | 1.25 | 21.04.2017 | 31.05.2017 | 0% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
57 | Col. Sarna Marg Sec.9 & 13 | 1.02 | 21.04.2017 | 31.05.2017 | 0% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
58 | Internal Road of Sec.9 Rohini | 0.325 | 21.04.2017 | 31.05.2017 | 0% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
59 | Internal Road of Sec.9 Rohini | 0.33 | 21.04.2017 | 31.05.2017 | 0% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
60 | R.N. Gujral Marg Sec.9 | 0.265 | 21.04.2017 | 31.05.2017 | 0% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
61 | Chetak Apartment to New Modern Apartment Sec.9 | 0.319 | 21.04.2017 | 31.05.2017 | 0% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
62 | Vidhya Vihar to Neelgiri Apt. Sec.9 | 0.33 | 21.04.2017 | 31.05.2017 | 0% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
63 | Captain Dahiya Marg Sec.9 & 13 | 1.68 | 21.04.2017 | 31.05.2017 | 0% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
64 | Ahinsha Marg Sec.9 & 13 | 1.68 | 21.04.2017 | 31.05.2017 | 0% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
65 | Sunrise Appartment (K. N. Katzu Marg) to Neelkanth Appartment (K. N. Katzu Marg) | 0.975 | 21.04.2017 | 31.05.2017 | 0% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
66 | Kawal Kunj Soceity to K.N. Katzu Marg (Length 0.265 KM) | 0.265 | 21.04.2017 | 31.05.2017 | 0% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
67 | Fire Station to CRPF School Corner Sec.14 Rohini (Ram Prasad Bismil Marg) | 0.72 | 21.04.2017 | 31.05.2017 | 12% | Sh. Onkar Nath Prasad 9911854514 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
68 | Babosa Chowk to Tulsi Apartment Sec.14, Rohini. | 0.55 | 21.04.2017 | 31.05.2017 | 0% | Sh. Onkar Nath Prasad 9911854514 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
69 | PWD Ring Road to Maheswari Apt. Sec.14 toward Sec.13. | 0.845 | 21.04.2017 | 31.05.2017 | 0% | Sh. Onkar Nath Prasad 9911854514 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
70 | Rukmani Devi Institute to Rohini Court Sec.14 | 0.45 | 21.04.2017 | 31.05.2017 | 0% | Sh. Onkar Nath Prasad 9911854514 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
71 | Connecting road from ORR to Road No.B-5 passing through CRPF School, Sec.14, Rohini | 0.86 | 21.04.2017 | 31.05.2017 | 0% | Sh. Onkar Nath Prasad 9911854514 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
72 | Maharaja Aggarsen Marg (Road No. 42-A) | 2.3 | 21.04.2017 | 31.05.2017 | 0% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 | Sh. Praveen Kathuria 9971669344
73 | A-1/1 to G-18/1 (Length 0.600 KM) | 0.6 | 21.04.2017 | 31.05.2017 | 0% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
74 | G-17/1 to Western Yamuna Canal (Length 0.750 KM) | 0.75 | 21.04.2017 | 31.05.2017 | 0% | Sh. Onkar Nath Prasad 9911854514 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
75 | Western Yamuna Canal to Arya Appartment (Length 0.590 KM) | 0.59 | 21.04.2017 | 31.05.2017 | 0% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
76 | Western Yamuna Canal to A-11/87 (Length 0.300 KM) | 0.3 | 21.04.2017 | 31.05.2017 | 0% | Sh. Onkar Nath Prasad 9911854514 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
77 | Pradeep Bhatia Marg (Road No. A-5) | 1 | 21.04.2017 | 31.05.2017 | 0% | Dharmendra Kumar 8287756785 | Sh L.K Tripathi 9811573503 | Sh. Praveen Kathuria 9971669344
78 | Road No. 41-A Bhagwan mahavir Marg. | 3.995 | 21.04.2017 | 31.05.2017 | 50% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
80 | G-23/30 to E4/15 Sec.7 | 0.396 | 21.04.2017 | 31.05.2017 | 0% | Sh. Jai Singh 9312101073 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
81 | B-6/159 to Naharpur DAV School back side Sec.7 | 0.296 | 21.04.2017 | 31.05.2017 | 0% | Sh. Jai Singh 9312101073 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
82 | B-22/279 to G-21/222 Sec.7 | 0.321 | 21.04.2017 | 31.05.2017 | 0% | Sh. Jai Singh 9312101073 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
83 | B-4/30 to CGHS Dispensary Sec.7 | 0.172 | 21.04.2017 | 31.05.2017 | 0% | Sh. Jai Singh 9312101073 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
84 | H18 to F-25 Sec.6 & 7 dividing road | 1.3 | 21.04.2017 | 31.05.2017 | 0% | Sh. Jai Singh 9312101073 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
85 | Rama Road Sec.8, Rohini | 0.73 | 21.04.2017 | 31.05.2017 | 0% | Sh. Jai Singh 9312101073 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
86 | Road from Road No. 41-A to Rama Road in Sec.8, Rohini | 1.05 | 21.04.2017 | 31.05.2017 | 0% | Sh. Jai Singh 9312101073 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
87 | Road from Road No. 42-A to Rama Road in Sec.8, Rohini | 0.55 | 21.04.2017 | 31.05.2017 | 0% | Sh. Jai Singh 9312101073 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
88 | Sawran Jayanti Park Road, Sec.9 &13 | 1.68 | 21.04.2017 | 31.05.2017 | 0% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
89 | PWD Road (B-7) to Corner of E-II Ashtha Kunj (Length 0.245 KM) | 0.245 | 21.04.2017 | 31.05.2017 | 0% | Sh. Onkar Nath Prasad 9911854514 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
90 | Corner of Data Ram Society to CEPT (Length 0.390 KM) | 0.39 | 21.04.2017 | 31.05.2017 | 0% | Sh. Onkar Nath Prasad 9911854514 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
91 | Behind Data Ram Society to Corner of Mt. Abu School (Length 0.390 KM) | 0.39 | 21.04.2017 | 31.05.2017 | 0% | Sh. Onkar Nath Prasad 9911854514 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
92 | PWD Road (B-7) to CEPT (Length 0.580 KM) | 0.58 | 21.04.2017 | 31.05.2017 | 0% | Sh. Onkar Nath Prasad 9911854514 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
93 | H-3/53 to DDA Park (Length 0.145 KM) | 0.145 | 21.04.2017 | 31.05.2017 | 0% | Sh. Onkar Nath Prasad 9911854514 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
94 | Deen Bandhu Sir Chotu Ram Marg (Road No. A-4) | 1 | 31.03.2017 | 31.05.2017 | 0% | Sh. Jai Singh 9312101073 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
95 | Shiva Road from Ring Road to Dividing Road of Sec.5 & 6, Rohini. | 2.217 | 31.03.2017 | 31.05.2017 | 0% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
96 | Road No. B-3 | 1.55 | 31.03.2017 | 31.05.2017 | 0% | Sh. Jai Singh 9312101073 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
97 | Road No. B-1 | 0.96 | 31.03.2017 | 31.05.2017 | 0% | Sh. Jai Singh 9312101073 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
98 | Road No. B-6 | 1 | 21.04.2017 | 31.05.2017 | 0% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
99 | MTNL Godown to C6/137 Sec.5, Rohini | 0.533 | 31.03.2017 | 31.05.2017 | 0% | Sh. Jai Singh 9312101073 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
100 | Som Bazar Road, Sec.5, Rohini | 0.71 | 31.03.2017 | 31.05.2017 | 60% | Sh. Jai Singh 9312101073 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
101 | Vidya Jain Public School, Se.6, Rohini | 0.477 | 31.03.2017 | 31.05.2017 | 0% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
102 | C-4/253 to C5/253, Sec.6, Rohini | 0.33 | 31.03.2017 | 31.05.2017 | 90% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
103 | D-6 and A-1 Road sec.6,Rohini | 0.33 | 31.03.2017 | 31.05.2017 | 0% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
104 | Road from F-3 block to H-4 in Sec.11, Rohini | 0.7 | 31.03.2017 | 31.05.2017 | 0% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
105 | From A-1 to F-3 Block near NDPL office Sec.11, Rohini. | 1.5 | 31.03.2017 | 31.05.2017 | 0% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
106 | From Block H-1 to H-5 Block Sec.11, Rohini | 0.65 | 31.03.2017 | 31.05.2017 | 0% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
107 | From F-1 to H-2 Block near NDPL office Sec.11, Rohini. | 0.65 | 31.03.2017 | 31.05.2017 | 0% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
108 | From C-4 to A-3 Block near NDPL office Sec.11, Rohini. | 0.65 | 31.03.2017 | 31.05.2017 | 0% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
109 | From F-1 to F-3 Block near NDPL office Sec.11, Rohini. | 0.375 | 31.03.2017 | 31.05.2017 | 0% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
110 | From A-1 to A-3 Block near NDPL office Sec.11, Rohini. | 0.375 | 31.03.2017 | 31.05.2017 | 10% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
111 | From C-1 to C-5 Block near NDPL office Sec.11, Rohini. | 0.375 | 31.03.2017 | 31.05.2017 | 0% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
112 | From Community Centre to NDMC Colony, Sec.11, Rohini. | 0.69 | 31.03.2017 | 31.05.2017 | 0% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
113 | D-1 TO I-3 (Length 0.463 KM) sec.16 | 0.463 | 31.03.2017 | 31.05.2017 | 0% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
114 | G-1 TO E-5 (Length 0.650 KM) | 0.65 | 31.03.2017 | 31.05.2017 | 0% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
115 | G-7 TO G-1 (Length 1.000 KM) | 1 | 31.03.2017 | 31.05.2017 | 0% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
116 | H-3 TO H-1 (Length 0.400 KM) | 0.4 | 31.03.2017 | 31.05.2017 | 0% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
117 | A-2 TO E-3 (Length 0.650 KM) | 0.65 | 31.03.2017 | 31.05.2017 | 0% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
118 | C-1 TO I-11 (Length 0.600 KM) | 0.6 | 31.03.2017 | 31.05.2017 | 0% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
119 | District Park TO C-1 (Length 0.438 KM) | 0.438 | 31.03.2017 | 31.05.2017 | 0% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
120 | F-2 TO F-6 (Length 0.338 KM) | 0.338 | 31.03.2017 | 31.05.2017 | 0% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
121 | A-6 TO A-8 (Length 0.263 KM) | 0.263 | 31.03.2017 | 31.05.2017 | 0% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
122 | F-3 TO F-5 (Length 0.338 KM) | 0.338 | 31.03.2017 | 31.05.2017 | 0% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
123 | I-1 TO Police Station (Length 0.538 KM) | 0.538 | 31.03.2017 | 31.05.2017 | 0% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
124 | B-2 TO B-6 (Length 0.210 KM) | 0.21 | 31.03.2017 | 31.05.2017 | 0% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
125 | A-8 TO B-6 (Length 0.600 KM) | 0.6 | 31.03.2017 | 31.05.2017 | 0% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
126 | B-1 TO C-1 (Length 0.475 KM) | 0.475 | 31.03.2017 | 31.05.2017 | 0% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
127 | A-8 TO B-1 ROAD (Length 0.445 KM) | 0.445 | 31.03.2017 | 31.05.2017 | 0% | Sh. Pushkar Raj 9868469769 | Sh. Ram Prakash 9868626887 | Sh. Praveen Kathuria 9971669344
128 | Road No. B-2 (Ram murthi Passi Marg) | 1.652 | 21.04.2017 | 31.05.2017 | 0% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
129 | Road from Pkt-10 to Pkt-D-4, Sec-20,Rohini | 0.505 | 21.04.2017 | 31.05.2017 | 0% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
130 | Road from Pkt-14 to Pkt-C-1,Sec-20,Rohini | 1 | 21.04.2017 | 31.05.2017 | 30% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
131 | Road from Pkt-8 to Pkt.-9,Sec-21, Rohini | 0.505 | 21.04.2017 | 31.05.2017 | 0% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
132 | Road from Pkt-B to Park, Sec-21, Rohini | 0.187 | 21.04.2017 | 31.05.2017 | 0% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
133 | Road from Pkt-13 to Pkt-9,Sec-21, Rohini | 0.448 | 21.04.2017 | 31.05.2017 | 0% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
134 | Road from Pkt-5 to Pkt-6, Sec-21, Rohini | 0.115 | 21.04.2017 | 31.05.2017 | 0% | Sh. Sri Bhagwan Rana 9810503635 | Sh. Mukesh Kumar 9911924591 | Sh. Praveen Kathuria 9971669344
North
North-Roads
1 | Kushal Cinema Road Starting from Raseela Paint Shop to T Point Pryas Road in Jahangirpuri-I, W.No. 16 Civil Line Zone | 1.102 | 25-03-17 | 31.05.2017 | 15% | Sh. Anmol Kumar 8742957738 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
2 | Dhobhi Ghat Road Starting from Kushal Cinema Chowk to Shah Alam Bandh Road | 0.45 | 25-03-17 | 31.05.2017 | 15% | Sh. Anmol Kumar 8742957738 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
3 | Malik Ram Tandon Marg from Road No. 51 to Shah Alam Bandh Road | 0.89 | 25-03-17 | 31.05.2017 | 5% | Sh. Anmol Kumar 8742957738 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
4 | Shah Alam Bandh Road from Burari Road to 80" Road (ROW) at Malik Ram Tondon Road upto Road No. 51 | 1.55 | 25-03-17 | 31.05.2017 | 5% | Sh. Anmol Kumar 8742957738 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
5 | Shah Alam Bandh Road from Main G.T. Road to Malik Ram Tandon Marg | 1.4 | 25-03-17 | 31.05.2017 | 5% | Sh. Anmol Kumar 8742957738 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
6 | Mangal Bazar Road starting from Kushal Road Green Belt to Shah Alam Bandh Road | 0.4 | 25-03-17 | 31.05.2017 | 20% | Sh. Anmol Kumar 8742957738 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
7 | Prayas Road (from Shah Alam Bandh Road to Dhalao, Jahangirpuri) | 0.7 | 25-03-17 | 31.05.2017 | 5% | Sh. Anmol Kumar 8742957738 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
8 | Fire Station to Pump House | 0.55 | 25-03-17 | 31.05.2017 | 15% | Sh. Anmol Kumar 8742957738 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
9 | Mall Road Extension from Azadpur Flyover to Mukarba Chowk | 3.5 | 26-03-17 | 31.05.2017 | 15% | Sh. Sachin Choudhary 9560134704 | Sh. R.P Verma 9868704799 | Sh. Bishamber Dass 9873245771
10 | Model Town-III Road from Mall Road to Arya Samaj Mandir | 0.727 | 26-03-17 | 31.05.2017 | 5% | Sh. Sachin Choudhary 9560134704 | Sh. R.P Verma 9868704799 | Sh. Bishamber Dass 9873245771
11 | Indra Park Road | 0.38 | 26-03-17 | 31.05.2017 | 5% | Sh. Sachin Choudhary 9560134704 | Sh. R.P Verma 9868704799 | Sh. Bishamber Dass 9873245771
12 | Princess Road from Mall road to Road No.51 | 3.1 | 26-03-17 | 31.05.2017 | 15% | Sh. Sachin Choudhary 9560134704 | Sh. R.P Verma 9868704799 | Sh. Bishamber Dass 9873245771
13 | Road No. 51 from Azadpur Flyover to Outer Ring Road | 2.5 | 26-03-17 | 31.05.2017 | 5% | Sh. Sachin Choudhary 9560134704 | Sh. R.P Verma 9868704799 | Sh. Bishamber Dass 9873245771
14 | Mahatma Gandhi road (Ring Road) from Camp Chowk to Azadpur Flyover | 3.5 | 26-03-17 | 31.05.2017 | 5% | Sh. Sachin Choudhary 9560134704 | Sh. R.P Verma 9868704799 | Sh. Bishamber Dass 9873245771
15 | Lala Auchint Ram Road from Stadium Road to Pambari Road | 0.95 | 26-03-17 | 31.05.2017 | 5% | Sh. Maneesh Kumar, 8470933600 | Sh. R.P Verma 9868704799 | Sh. Bishamber Dass 9873245771
16 | Stadium Road from Chattrashal Stadium Mall Road to GT Road | 0.68 | 26-03-17 | 31.05.2017 | 5% | Sh. Maneesh Kumar, 8470933600 | Sh. R.P Verma 9868704799 | Sh. Bishamber Dass 9873245771
17 | Brahamkumari Marg from Mall Road to G.T. Road | 0.65 | 26-03-17 | 31.05.2017 | 5% | Sh. Maneesh Kumar, 8470933600 | Sh. R.P Verma 9868704799 | Sh. Bishamber Dass 9873245771
18 | Model Town II Road from Mall Road to F-14/56 Model Town | 0.495 | 26-03-17 | 31.05.2017 | 5% | Sh. Maneesh Kumar, 8470933600 | Sh. R.P Verma 9868704799 | Sh. Bishamber Dass 9873245771
19 | G.T Road from Gurudwara Nanakpiao to Azadpur Round about | 2 | 26-03-17 | 31.05.2017 | 5% | Sh. Maneesh Kumar, 8470933600 | Sh. R.P Verma 9868704799 | Sh. Bishamber Dass 9873245771
20 | Old G.T. Karnal Road | 3 | 20-03-17 | 31.05.2017 | 5% | Sh. Uttam Kumar 7827857462 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
21 | Narela Alipur Road from Shahpur Grahi to Old GTK Road Alipur | 5.02 | 20-03-17 | 31.05.2017 | 5% | Sh. Uttam Kumar 7827857462 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
22 | New GT Road to Old GT Road (via PHC Alipur) from New GTk Road to Old GTK Road | 0.38 | 20-03-17 | 31.05.2017 | 5% | Sh. Uttam Kumar 7827857462 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
23 | Holambi Khurd Crossing to Shahpur Garhi turn | 1.9 | 20-03-17 | 31.05.2017 | 5% | Sh. Uttam Kumar 7827857462 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
24 | Railway Crossing to Holambi Khurd | 0.7 | 20-03-17 | 31.05.2017 | 5% | Sh. Uttam Kumar 7827857462 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
25 | Ramdev Chowk Narela to Kanya Gurukul | 1.9 | 20-03-17 | 31.05.2017 | 5% | Sh. Uttam Kumar 7827857462 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
26 | Narela Alipur Road from Narela Y section to Shahpur Garhi | 3.4 | 20-03-17 | 31.05.2017 | 5% | Sh. Uttam Kumar 7827857462 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
27 | Narela Safiabad Road from Narela to Safiabad Border | 2.9 | 20-03-17 | 31.05.2017 | 5% | Sh. Uttam Kumar 7827857462 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
28 | Narela Lampur Road from Narela to Lampur Border | 3.8 | 20-03-17 | 31.05.2017 | 5% | Sh. Uttam Kumar 7827857462 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
29 | Nangli Puna Underpass to Khera Kalan Railway X-ing. | 3 | 20-03-17 | 31.05.2017 | 5% | Sh. Uttam Kumar 7827857462 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
30 | Khera Kalan to Holambi Kalan via Naya bans | 7 | 20-03-17 | 31.05.2017 | 5% | Sh. Uttam Kumar 7827857462 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
31 | NH-44 to Bakhtawar Pur | 3.5 | 20-03-17 | 31.05.2017 | 5% | Sh. Uttam Kumar 7827857462 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
32 | Subhash Chowk Bhakhtawar Pur to Palla | 3.2 | 20-03-17 | 31.05.2017 | 5% | Sh. Uttam Kumar 7827857462 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
33 | Subhash Chowk Bhakhtawar Pur to Hiranki Bandh | 4.2 | 20-03-17 | 31.05.2017 | 15% | Sh. Uttam Kumar 7827857462 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
34 | Holambi Khurd Crossing to Metro Vihar | 3 | 20-03-17 | 31.05.2017 | 5% | Sh. Uttam Kumar 7827857462 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
35 | Bawana Narela Road From CRPF to Singhu Border | 10.4 | 20-03-17 | 31.05.2017 | 5% | Sh. Uttam Kumar 7827857462 | Sh. S.P . Khaneja 9811081453 | Sh. Bishamber Dass 9873245771
36 | Swaroop Nagar Road | 2 | 26-03-17 | 31.05.2017 | 5% | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
37 | Railway Road from NH-44 to Badli Railway Station | 1.25 | 26-03-17 | 31.05.2017 | 5% | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
38 | ORR Mukarba Chowk Flyover | 6.8 | 26-03-17 | 31.05.2017 | 5% | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
39 | Libaspur to Siraspur Road | 0.5 | 26-03-17 | 31.05.2017 | 5% | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
40 | G.T. Karnal Road to Libaspur Road | 1.6 | 26-03-17 | 31.05.2017 | 5% | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
41 | 66 Ft. Road Libaspur to Gurudwara Road | 1.7 | 26-03-17 | 31.05.2017 | 15% | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
42 | G.T. Karnal Road to Siraspur Village | 2 | 26-03-17 | 31.05.2017 | 5% | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
43 | Mamchand Dhania Marg | 2.7 | 26-03-17 | 31.05.2017 | 5% | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
44 | ITI Road from Main Jahangirpuri Road to Metro App. | 0.324 | 26-03-17 | 31.05.2017 | 5% | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
45 | Back side K Block Road from Metro App. to dividing road K Block | 0.17 | 26-03-17 | 31.05.2017 | 5% | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
46 | Lucky Park Road from J-51 to J-1951 | 0.5 | 26-03-17 | 31.05.2017 | 5% | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
47 | Lucky Park Road to I-2000 (Back Side Road) | 0.35 | 26-03-17 | 31.05.2017 | 5% | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
48 | Mangal Bazar Road B Block | 0.55 | 26-03-17 | 31.05.2017 | 5% | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
49 | Zonal Park Road C Block | 0.55 | 26-03-17 | 31.05.2017 | 5% | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
50 | Jahangirpuri Main Road from G.T. Road Red Light to Fire Station | 1.395 | 26-03-17 | 31.05.2017 | 15% | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
51 | Bhalswa Dairy Road from Flood Road to C Block along Bhalswa Lake via Shani Bazar | 1.83 | 26-03-17 | 31.05.2017 | 5% | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
52 | G.T Road to Western Yamuna Canal | 2.77 | 26-03-17 | 31.05.2017 | 5% | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
53 | NH-44 with service Lane | 3 | 26-03-17 | 31.05.2017 | 5% | Sh. Arvind Kumar 9990297795 | Sh. Suresh Pal 9868219266 | Sh. Bishamber Dass 9873245771
54 | From Western Yamuna Canal to Auchandi Border | 18.5 | 20-03-17 | 31.05.2017 | 20% | Sh. Suresh Chand Bairwa 8826718940 | Sh. K.S. Dahiya 9810654956 | Sh. Bishamber Dass 9873245771
55 | Auchandi Border to Tatesar Village | 9.3 | 20-03-17 | 31.05.2017 | 20% | Sh. Suresh Chand Bairwa 8826718940 | Sh. K.S. Dahiya 9810654956 | Sh. Bishamber Dass 9873245771
56 | Majra Dabbas to Sannoth Mor | 8 | 20-03-17 | 31.05.2017 | 20% | Sh. Suresh Chand Bairwa 8826718940 | Sh. K.S. Dahiya 9810654956 | Sh. Bishamber Dass 9873245771
West
Name of Division :- West Road-1
1 | Goswami Tulsi Dass Marg i.e. Road No. 32 | 1.6 | 05.05.2016 | 31.05.2017 | The tender (2nd Call) opened on 25.04.17. No Bid is received, Tender yet to be recalled. | Ajay Vishraj 8800146761 | Kehar Singh 7291872370 | A.K. Sahana 9747487738
2 | Dr. Kundan Lal Marg | 0.42 | 05.05.2016 | 31.05.2017 | - do - | Ajay Vishraj 8800146761 | Kehar Singh 7291872370 | A.K. Sahana 9747487738
3 | Rajouri Appartment Road | 3 | 05.05.2016 | 31.05.2017 | - do - | Ajay Vishraj 8800146761 | Kehar Singh 7291872370 | A.K. Sahana 9747487738
4 | H.No. 14/35 to 13/101 Subash Nagar (Near Shandley School) | 0.454 | 05.05.2016 | 31.05.2017 | - do - | Ajay Vishraj 8800146761 | Kehar Singh 7291872370 | A.K. Sahana 9747487738
5 | Shanti Devi Marg | 0.375 | 05.05.2016 | 31.05.2017 | - do - | Ajay Vishraj 8800146761 | Kehar Singh 7291872370 | A.K. Sahana 9747487738
6 | Ayodhya Prasad Chopra Marg | 0.45 | 05.05.2016 | 31.05.2017 | - do - | Ajay Vishraj 8800146761 | Kehar Singh 7291872370 | A.K. Sahana 9747487738
7 | Road No. 32 to 17/117 Subash Nagar | 0.35 | 05.05.2016 | 31.05.2017 | - do - | Ajay Vishraj 8800146761 | Kehar Singh 7291872370 | A.K. Sahana 9747487738
8 | H.No. 6/1 to 3/200 Subhash Nagar | 0.68 | 05.05.2016 | 31.05.2017 | - do - | Ajay Vishraj 8800146761 | Kehar Singh 7291872370 | A.K. Sahana 9747487738
9 | Vedic Marg | 1.35 | 05.05.2016 | 31.05.2017 | - do -
10 | H.No. 11/76 to 11/85 Subhash Nagar | 0.05 | 05.05.2016 | 31.05.2017 | - do - | Ajay Vishraj 8800146761 | Kehar Singh 7291872370 | A.K. Sahana 9747487738
11 | H.No. 8/1 to 14/149 Subhash Nagar | 0.35 | 05.05.2016 | 31.05.2017 | - do -
12 | H.No. 10/1 to 14/97 Subhash Nagar | 0.292 | 05.05.2016 | 31.05.2017 | - do -
13 | Sardar Kulwant Singh Sethi Marg | 1.046 | 05.05.2016 | 31.05.2017 | The tender (3rd Call) opened on 25.04.17. No Bid is received, Tender yet to be recalled. | Ajay Vishraj 8800146761 | Kehar Singh 7291872370 | A.K. Sahana 9747487738
14 | DA-1, Hari Nagar to DB-1 Hari Nagar | 0.423 | 05.05.2016 | 31.05.2017 | - do - | Ajay Vishraj 8800146761 | Kehar Singh 7291872370 | A.K. Sahana 9747487738
15 | Shaheed Bhagat Singh Mrg. (Jail Rd) | 2.28 | 05.05.2016 | 31.05.2017 | - do - | Ajay Vishraj 8800146761 | Kehar Singh 7291872370 | A.K. Sahana 9747487738
16 | Shaheed Bhagat Singh Mrg. (Jail Rd) | 1.4 | 05.05.2016 | 31.05.2017 | - do - | Ajay Vishraj 8800146761 | Kehar Singh 7291872370 | A.K. Sahana 9747487738
17 | B-2/Dharam Marg | 1.38 | 05.05.2016 | 31.05.2017 | - do - | Ajay Vishraj 8800146761 | Kehar Singh 7291872370 | A.K. Sahana 9747487738
18 | Capt. Anuj Nayyar Marg. | 0.67 | 05.05.2016 | 31.05.2017 | - do - | Ajay Vishraj 8800146761 | Kehar Singh 7291872370 | A.K. Sahana 9747487738
19 | B1- B2 Connecting Road. | 0.59 | 05.05.2016 | 31.05.2017 | - do - | Ajay Vishraj 8800146761 | Kehar Singh 7291872370 | A.K. Sahana 9747487738
20 | Gurudwara Road | 0.63 | 05.05.2016 | 31.05.2017 | - do - | Ajay Vishraj 8800146761 | Kehar Singh 7291872370 | A.K. Sahana 9747487738
21 | BA-BB Block Road | 0.38 | 05.05.2016 | 31.05.2017 | - do - | Ajay Vishraj 8800146761 | Kehar Singh 7291872370 | A.K. Sahana 9747487738
22 | B2 Block Sabzi Mandi Road | 0.4 | 05.05.2016 | 31.05.2017 | - do - | Ajay Vishraj 8800146761 | Kehar Singh 7291872370 | A.K. Sahana 9747487738
23 | Prem Nagar Gurudwara Rd. | 0.52 | 05.05.2016 | 31.05.2017 | - do - | Ajay Vishraj 8800146761 | Kehar Singh 7291872370 | A.K. Sahana 9747487738
24 | Major Rajeev Laul Marg | 0.88 | 05.05.2016 | 31.05.2017 | - do - | Ajay Vishraj 8800146761 | Kehar Singh 7291872370 | A.K. Sahana 9747487738
25 | Shaheed Mangal Pandey Marg | 0.74 | 05.05.2016 | 31.05.2017 | - do - | Ajay Vishraj 8800146761 | Kehar Singh 7291872370 | A.K. Sahana 9747487738
26 | Bhai Kanheya Ji Marg (ITI Road) | 0.67 | 05.05.2016 | 31.05.2017 | - do - | Ajay Vishraj 8800146761 | Kehar Singh 7291872370 | A.K. Sahana 9747487738
27 | Mangal Pandey Marg (Hari Nagar Clock Tower to Maya Puri) | 0.85 | 05.05.2016 | 31.05.2017 | - do - | Ajay Vishraj 8800146761 | Kehar Singh 7291872370 | A.K. Sahana 9747487738
28 | Prof. Joginder Singh Marg (In front of Janakpuri Distt. Centre) | 1.18 | 05.05.2016 | 31.05.2017 | The tender (3rd Call) opened on 25.04.17. No Bid is received, Tender yet to be recalled. | Ranjeet Srivastva 9821691159 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
29 | Authority Road (Janak Puri) | 0.65 | 05.05.2016 | 31.05.2017 | - do - | Ranjeet Srivastva 9821691159 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
30 | Mota Singh Road | 0.98 | 05.05.2016 | 31.05.2017 | - do - | Ranjeet Srivastva 9821691159 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
31 | Possangi Pur Road | 0.4 | 05.05.2016 | 31.05.2017 | - do - | Ranjeet Srivastva 9821691159 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
32 | Major Deepak Tyagi Marg | 0.97 | 05.05.2016 | 31.05.2017 | - do - | Vishal Seth 9650167976 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
33 | A-1 Block Main Road | 0.62 | 25.05.2016 | 31.05.2017 | - do - | Vishal Seth 9650167976 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
34 | Road Opp. A1B Block Janak Puri | 0.28 | 05.05.2016 | 31.05.2017 | - do - | Vishal Seth 9650167976 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
35 | Asalatpur Road | 0.16 | 05.05.2016 | 31.05.2017 | - do - | Vishal Seth 9650167976 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
36 | Asalatpur Road-II | 0.79 | 05.05.2016 | 31.05.2017 | - do - | Vishal Seth 9650167976 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
37 | Najafgarh Road (Shivaji Marg) (Dhauli Piao to Pankha Road Red Light) | 1.25 | 25.05.2016 | 31.05.2017 | - do - | Vishal Seth 9650167976 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
38 | Keshav Marg | 0.6 | 25.05.2016 | 31.05.2017 | Work awarded & Work is in progress | Devendra Singh 9555888616 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
39 | Ring road to A-31 rajori garden | 0.045 | 25.05.2016 | 31.05.2017 |  | Devendra Singh 9555888616 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
40 | Najafgarh Road to A-71 Rajouri Garden | 0.04 | 25.05.2016 | 31.05.2017 |  | Devendra Singh 9555888616 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
41 | Sakti Mandir Marg | 0.2 | 25.05.2016 | 31.05.2017 | - do - | Devendra Singh 9555888616 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
42 | Najafgarh Road | 1.95 | 25.05.2016 | 31.05.2017 | - do - | Devendra Singh 9555888616 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
43 | Major Sudesh Gadok Marg (J 12/1 to NG Road) | 0.62 | 25.05.2016 | 31.05.2017 | - do - | Devendra Singh 9555888616 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
44 | Major Sudesh Marg (NG Road to Ring Road) | 1.9 | 25.05.2016 | 31.05.2017 | - do - | Devendra Singh 9555888616 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
45 | 100' Road (Patel Chowk to Subhash Nagar Drain (Patel Chowk Road) | 0.8 | 25.05.2016 | 31.05.2017 | Work awarded & Work is in progress | Yogesh Joshi 9795313669 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
46 | 100' Road New Khayala Road | 0.7 | 25.05.2016 | 31.05.2017 | - do - | Yogesh Joshi 9795313669 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
47 | 80' Road Chowkhandi Road | 1 | 25.05.2016 | 31.05.2017 | - do - | Yogesh Joshi 9795313669 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
48 | Arya Samaj Marg | 0.12 | 25.05.2016 | 31.05.2017 | - do - | Yogesh Joshi 9795313669 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
49 | J.Krishnatrey Marg | 0.11 | 25.05.2016 | 31.05.2017 | - do - | Yogesh Joshi 9795313669 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
50 | AD-1 to BF- 31 (Tagore Garden) | 0.6 | 25.05.2016 | 31.05.2017 | - do - | Yogesh Joshi 9795313669 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
51 | DE-131 to Community Hall | 0.22 | 25.05.2016 | 31.05.2017 | - do - | Yogesh Joshi 9795313669 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
52 | Devki Nandan Marg | 0.78 | 25.05.2016 | 31.05.2017 | - do - | Yogesh Joshi 9795313669 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
53 | Tanki Wala Marg | 0.2 | 25.05.2016 | 31.05.2017 | - do - | Yogesh Joshi 9795313669 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
54 | Sant Berwa Marg with Titar Pur drain | 0.6 | 25.05.2016 | 31.05.2017 | - do - | Yogesh Joshi 9795313669 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
55 | Road No. 28 | 0.5 | 25.05.2016 | 31.05.2017 | - do - | Yogesh Joshi 9795313669 | Sudesh Kumar 9818011179 | A.K. Sahana 9747487738
56 | Lala Ganesh Dass Marg | 1.27 | 07.05.2016 | 31.05.2017 | The tender (3rd Call) opened on 25.04.17. 1No. Bid is received | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
57 | Road between Two Blocks of G- Block Vikas Puri | 0.24 | 07.05.2016 | 31.05.2017 | - do - | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
58 | From G-1 Block Vikas Puri to Palican Road VikasPuri | 0.52 | 07.05.2016 | 31.05.2017 | - do - | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
59 | Keshopur Sabzi Mandi Red Light (Outer Ring Road) to Subhash Nagar Drain | 0.386 | 07.05.2016 | 31.05.2017 | - do - | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
60 | Road No. 235 | 0.35 | 07.05.2016 | 31.05.2017 | - do - | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
61 | Road No. 235 extension | 0.76 | 07.05.2016 | 31.05.2017 | - do - | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
62 | Chowkhandi Road | 0.22 | 07.05.2016 | 31.05.2017 | The tender (3rd Call) opened on 25.04.17. 1No. Bid is received | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
63 | Najafgarh road from Subhash Nagar Crossing to Dhauli Piao | 4.2 | 07.05.2016 | 31.05.2017 | - do - | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
64 | Tilak Nagar To 20 Block Tilak Vihar | 0.5 | 07.05.2016 | 31.05.2017 | - do - | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
65 | Road from H-Block To H-3 Block | 0.54 | 07.05.2016 | 31.05.2017 | - do - | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
66 | Road from Guruvirjanand Marg to Distt. Park,Vikas Puri | 0.14 | 07.05.2016 | 31.05.2017 | - do - | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
67 | Shaheed Raj Guru Marg Vikas Puri | 1.28 | 07.05.2016 | 31.05.2017 | - do - | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
68 | Tilak Vihar Main Road | 0.54 | 07.05.2016 | 31.05.2017 | - do - | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
69 | Road Adjcent to PVR Complex Vikas Puri | 0.15 | 07.05.2016 | 31.05.2017 | - do - | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
70 | Pelicon Road from Guru Virzanand Marg to Road No. 235 Extension | 0.91 | 07.05.2016 | 31.05.2017 | - do - | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
71 | Tilak Nagar Main Market Road | 0.07 | 07.05.2016 | 31.05.2017 | - do - | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
72 | Brain Public School Road | 0.75 | 07.05.2016 | 31.05.2017 | - do - | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
73 | K. R. Manglam | 0.54 | 07.05.2016 | 31.05.2017 | - do - | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
74 | H- Block to Vikas Puri | 0.194 | 07.05.2016 | 31.05.2017 | - do - | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
75 | 70 Block Park Ashok Nagar to Tihar No. 2 School | 0.52 | 07.05.2016 | 31.05.2017 | - do - | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
76 | 2/1 to 2/10 Ashok Nagar | 0.6 | 07.05.2016 | 31.05.2017 | - do - | Pavanendra 9991514242 | Balbir Bhardwaj 9811950358 | A.K. Sahana 9747487738
77 | Ashok Nagar Road | 0.318 | 05.05.2016 | 31.05.2017 | - do -
78 | Road No. 236 | 1.8 | 25.05.2016 | 31.05.2017 | Signal Tender (2nd Called ) has been accepted & PG letter issued on 24.04.17 | Rajat 9868014576 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
79 | Road No. 237 | 0.45 | 25.05.2016 | 31.05.2017 |  | Rajat 9868014576 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
80 | Road between Krishi Appt. to DAV school (PWD Road) | 0.295 | 25.05.2016 | 31.05.2017 |  | Rajat 9868014576 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
81 | Road between Devdoot Appt. to Parmarth Appt. PWD Road Vikas Puri | 0.28 | 25.05.2016 | 31.05.2017 |  | Rajat 9868014576 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
82 | Road between Jupiter Appt. to Priya Appt. PWD Road Vikas Puri | 0.39 | 25.05.2016 | 31.05.2017 |  | Rajat 9868014576 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
83 | Road Between Nalanda Appt. To Nightingale Appt. Vikas Puri | 0.54 | 25.05.2016 | 31.05.2017 |  | Rajat 9868014576 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
84 | Road Sunrise Appt. to DAV School (PWD Road) Vikas Puri | 0.435 | 25.05.2016 | 31.05.2017 | - do - | Rajat 9868014576 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
85 | Road from F-234 to IFC drain (Over head tank) Vikas Puri | 0.25 | 25.05.2016 | 31.05.2017 | - do - | Rajat 9868014576 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
86 | Road from ITI Corner (Flat No. 58) to Central School Corner (Flat No. 391) LIG Flat Hastsal | 0.24 | 25.05.2016 | 31.05.2017 | - do - | Rajat 9868014576 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
87 | Road from Navyug Appt. to IFC drain (Brotherhood Appt.) Vikas Puri | 0.38 | 25.05.2016 | 31.05.2017 | - do - | Rajat 9868014576 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
88 | Guruvirja Nanad Marg | 2.7 | 25.05.2016 | 31.05.2017 | - do - | Jai Raghuvinder 9868053348 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
89 | Road starting from Oxford School to Airport Appt. (PWD Road) Vikas Puri | 0.88 | 25.05.2016 | 31.05.2017 | - do - | Jai Raghuvinder 9868053348 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
90 | Road between Lok Vihar Appt. (PWD Road) to Fblock Market Vikas Puri | 0.675 | 25.05.2016 | 31.05.2017 | - do - | Jai Raghuvinder 9868053348 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
91 | Nangloi - Najafgarh Road | 5.5 | 23.06.2016 | 31.05.2017 | - do - | Karam Veer 9654402679 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
92 | Najafgarh Road (Shivaji Marg) (Pankha Road Red Light to Kakrolla Mor) | 4 | 25.05.2016 | 31.05.2017 | - do - | Karam Veer 9654402679 | Sanjay Kumar Rao 8447023542 | A.K. Sahana 9747487738
93 | Rohtak Road from Zakhira to Punjabi Bagh | 2.1 | ....... | ........ | .......... | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. Manish Kaushik 9650167297
94 | Road from House No. H-1 to I-47 near Milan Cinema Karmapura | 0.4 | ....... | ........ | .......... | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. Manish Kaushik 9650167297
95 | Shivdass Puri Marg | 2 | ....... | ........ | .......... | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. Manish Kaushik 9650167297
96 | Road from Milan Cinema to H. No. 19/289 | 0.42 | ....... | ........ | .......... | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. Manish Kaushik 9650167297
97 | Road from HIL to Bus Terminal of 234, Karampura | 0.412 | ....... | ........ | .......... | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. Manish Kaushik 9650167297
98 | Road from Bus Route B-14 Tagore Market to G-82 Kirti Nagar | 0.91 | ....... | ........ | .......... | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. Manish Kaushik 9650167297
99 | Najafgarh Road from Moti Nagar to Raja Garden | 2.2 | ....... | ........ | .......... | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. Manish Kaushik 9650167297
100 | Hemvati Nandan Bahnguma Marg | 0.8 | ....... | ........ | .......... | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. Manish Kaushik 9650167297
101 | Rama Road (Satguru Ram Singh Marg) | 1.695 | ....... | ........ | .......... | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. Manish Kaushik 9650167297
102 | Road from Road No. 36 (Sat Guru Ram Singh Marg (Maya Puri Chowk to SD Public School) | 2 | ....... | ........ | .......... | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. Manish Kaushik 9650167297
103 | Rama Road (Satguru Ram Singh Marg) | 1.2 | ....... | ........ | .......... | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. Manish Kaushik 9650167297
104 | Ring Road from Punjabi Bagh to Mayapuri Flyover | 4.75 | ....... | ........ | .......... | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. Manish Kaushik 9650167297
105 | 80' wide Road MS Garden Road | 2.49 | ....... | ........ | .......... | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. Manish Kaushik 9650167297
106 | Punjab Garden Road | 0.21 | ....... | ........ | .......... | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. Manish Kaushik 9650167297
107 | Smt. Ginni Devi Road | 0.75 | ....... | ........ | .......... | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. Manish Kaushik 9650167297
108 | Bhagwan Dass Marg (K.C. Garg Marg) | 0.3 | ....... | ........ | .......... | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. Manish Kaushik 9650167297
109 | Najafgarh Road from Zakhira Round about to Moti Nagar | 2.24 | ....... | ........ | .......... | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. Manish Kaushik 9650167297
110 | Major Rajive Bhasin Marg D/Story | 0.325 | ....... | ........ | .......... | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. Manish Kaushik 9650167297
111 | Pankaj Batra Marg | 0.77 | ....... | ........ | .......... | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. Manish Kaushik 9650167297
112 | Lai Sai Mandir Marg D/Story | 0.325 | ....... | ........ | .......... | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. Manish Kaushik 9650167297
113 | Patel Road | 2.93 | ....... | ........ | .......... | Sh. Ashish Kujur 9818990594 | Sh. Harpinder Singh 9811356083 | Sh. Manish Kaushik 9650167297
114 | Madhav Setu Marg | 0.605 | ....... | ........ | .......... | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. Manish Kaushik 9650167297
115 | Vishwakarma Marg | 1 | ....... | ........ | .......... | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. Manish Kaushik 9650167297
116 | Suman Lata Badola Marg | 0.243 | ....... | ........ | .......... | Sh. Rajveer Meena 8802352659 | Sh. Harpinder Singh 9811356083 | Sh. Manish Kaushik 9650167297
117 | Delhi Rohtak Road (NH-10) from Metro Pillar No. 415 to Mundka Phirni | 4 | 22.04.2017 | 31.05.2017 | 25% | Sh. Amandeep Kamboj 9911558786 | Sh. Narender Singh 9868004850 | Sh. Manish Kaushik 9650167297
118 | Delhi Rohtak Road (NH-10) from Mundka Phirni to Tikri Boader | 7 | 22.04.2017 | 31.05.2017 | 0% | Sh. Amandeep Kamboj 9911558786 | Sh. Narender Singh 9868004850 | Sh. Manish Kaushik 9650167297
119 | Delhi Rohtak Road (NH-10) | 2.7 | 22.04.2017 | 31.05.2017 | 0% | Sh. Amandeep Kamboj 9911558786 | Sh. Narender Singh 9868004850 | Sh. Manish Kaushik 9650167297
120 | Guru Golwalkar Marg (Kanjhawala Road) | 9.8 | 22.04.2017 | 31.05.2017 | 2% | Sh. Amandeep Kamboj 9911558786 | Sh. Narender Singh 9868004850 | Sh. Manish Kaushik 9650167297
121 | Road from Ghevra More to Chand Pur More | 7.9 | 22.04.2017 | 31.05.2017 | 0% | Sh. Amandeep Kamboj 9911558786 | Sh. Narender Singh 9868004850 | Sh. Manish Kaushik 9650167297
122 | Delhi Rohtak Road (NH-10) , Peeragarhi Nangloi Road | 4.5 | 23/03/2017 | 31.05.2017 | 0% | Sh. Kharimulla S 7503050737 | Sh. R.B.Nehra 9355666768 | Sh. Manish Kaushik 9650167297
123 | Road from Rblock jawalapuri to Sai mandir Guru Harkishan Nagar | 0.36 | 23/03/2017 | 31.05.2017 | 0% | Sh. Kharimulla S 7503050737 | Sh. R.B.Nehra 9355666768 | Sh. Manish Kaushik 9650167297
124 | Road from GH-13 to Sayed Nangloi Village Chowk Paschim Vihar | 0.902 | 23/03/2017 | 31.05.2017 | 0% | Sh. Kharimulla S 7503050737 | Sh. R.B.Nehra 9355666768 | Sh. Manish Kaushik 9650167297
125 | Road from Outer Ring Road Meera Bagh to GH-8 Fire station Paschim Vihar | 1.251 | 23/03/2017 | 31.05.2017 | 50% | Sh. Kharimulla S 7503050737 | Sh. R.B.Nehra 9355666768 | Sh. Manish Kaushik 9650167297
126 | Road from Garg Plaza to L.I.C. Colony Paschim Vihar | 1.322 | 23/03/2017 | 31.05.2017 | 5% | Sh. Kharimulla S 7503050737 | Sh. R.B.Nehra 9355666768 | Sh. Manish Kaushik 9650167297
127 | Najafgarh- Nangloi Road from NH-10 to Rishal Garden | 3.75 | 23/03/2017 | 31.05.2017 | 50% | Sh. Kharimulla S 7503050737 | Sh. R.B.Nehra 9355666768 | Sh. Manish Kaushik 9650167297
128 | Outer Ring Road No. 26 | 2.8 | 23/03/2017 | 31.05.2017 | 0% | Sh. Kharimulla S 7503050737 | Sh. R.B.Nehra 9355666768 | Sh. Manish Kaushik 9650167297
129 | Road from GH-6 Chowk to GH-5 and 7 Paschim Vihar | 0.292 | 23/03/2017 | 31.05.2017 | 0% | Sh. Kharimulla S 7503050737 | Sh. R.B.Nehra 9355666768 | Sh. Manish Kaushik 9650167297
130 | Road from Sai Baba Mandir GH-12 to GH-8 Fire station Paschim Vihar | 0.963 | 23/03/2017 | 31.05.2017 | 0% | Sh. Kharimulla S 7503050737 | Sh. R.B.Nehra 9355666768 | Sh. Manish Kaushik 9650167297
131 | Road from Outer Ring Road Bhera Enclave to Sai Baba Mandir Paschim Vihar | 1.251 | 23/03/2017 | 31.05.2017 | 0% | Sh. Kharimulla S 7503050737 | Sh. R.B.Nehra 9355666768 | Sh. Manish Kaushik 9650167297
132 | Road from Sant Mar'ks School to DDA Mkt. GH-5&7 Paschim Vihar | 0.435 | 23/03/2017 | 31.05.2017 | 0% | Sh. Kharimulla S 7503050737 | Sh. R.B.Nehra 9355666768 | Sh. Manish Kaushik 9650167297
133 | Laxmi Narain Marg (N.S. Road) | 0.7 | 23/03/2017 | 31.05.2017 | 0% | Sh. Kharimulla S 7503050737 | Sh. R.B.Nehra 9355666768 | Sh. Manish Kaushik 9650167297
134 | Ch. Prem Sukh Road | 1.292 | 23/03/2017 | 31.05.2017 | 50% | Sh. Kharimulla S 7503050737 | Sh. R.B.Nehra 9355666768 | Sh. Manish Kaushik 9650167297
135 | 60' road in Jawala Puri | 1.15 | 23/03/2017 | 31.05.2017 | 0% | Sh. Kharimulla S 7503050737 | Sh. R.B.Nehra 9355666768 | Sh. Manish Kaushik 9650167297
136 | Road from Capital Plaza Market to Jhaj Aptt. Mianwali Nagar | 0.35 | 23/03/2017 | 31.05.2017 | 0% | Sh. Kharimulla S 7503050737 | Sh. R.B.Nehra 9355666768 | Sh. Manish Kaushik 9650167297
137 | Road from Vindhachal Aptt. To Viral Co. Op. Society Mianwali Nagar | 0.35 | 23/03/2017 | 31.05.2017 | 0% | Sh. Kharimulla S 7503050737 | Sh. R.B.Nehra 9355666768 | Sh. Manish Kaushik 9650167297
138 | Shri Krishan Gyan Mandir Marg | 0.66 | 23/03/2017 | 31.05.2017 | 0% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
139 | Road from front of Ambedkar Market from Shop No. 1 to 130, Raghubir Nagar | 0.305 | 23/03/2017 | 31.05.2017 | 0% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
140 | Road No. 28 | 1.93 | 23/03/2017 | 31.05.2017 | 10% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
141 | Road from H.No. A-250 to Shiv Mandir Road in C-103 Punjabi Bagh | 0.48 | 23/03/2017 | 31.05.2017 | 90% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
142 | Road from Road No. 41 from H.No. 1 to 81 in West Punjabi Bagh | 1.715 | 23/03/2017 | 31.05.2017 | 0% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
143 | Road from Bhagat Singh Colony (opp. Plot No. 66 Shivaji Enclave) to FA-33 Shivaji Enclave (On PWD Road No. 28) | 0.6 | 23/03/2017 | 31.05.2017 | 50% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
144 | Road from Shivaji College (PWD Road No. 28) to Bhagat Singh Colony | 0.71 | 23/03/2017 | 31.05.2017 | 30% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
145 | Ch. Balbir Singh Marg (Club Road) | 0.39 | 23/03/2017 | 31.05.2017 | 0% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
146 | Road from Shiv Mndir Road (Rohtak Road) to shiv Mandir Madipur Village | 0.7 | 23/03/2017 | 31.05.2017 | 50% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
147 | Road from Madipur Main Road from Rohtak Road to Paschim Puri Chowk | 1 | 23/03/2017 | 31.05.2017 | 0% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
148 | Road No. 77 (Punjabi Bagh) | 1.41 | 23/03/2017 | 31.05.2017 | 0% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
149 | Road from H-1 Bali Nagar (NG Road) to ESI Hospital (Ring Road) [ Major Sunil Bakshi Marg) | 0.52 | 23/03/2017 | 31.05.2017 | 0% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
150 | Road from 48 NWA Ch. Balbir Singh Marg to Road No. 32 (Road No. 33) | 0.39 | 23/03/2017 | 31.05.2017 | 0% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
151 | Vashisth Kumar Gulla Marg | 1.39 | 23/03/2017 | 31.05.2017 | 0% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
152 | N.A. Road | 1 | 23/03/2017 | 31.05.2017 | 0% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
153 | Road from Paschim Puri Chowk to New Slum Qtrs. | 0.45 | 23/03/2017 | 31.05.2017 | 0% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
154 | Road No. 32 (Hans Raj Model School )to Road No. 33 | 1.51 | 23/03/2017 | 31.05.2017 | 0% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
155 | Road No. 29 | 2.8 | 23/03/2017 | 31.05.2017 | 0% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
156 | Road from Najafgarh Road to WZ-494, Basai Darapur (Sheo Nath Tyagi Marg) | 0.675 | 23/03/2017 | 31.05.2017 | 0% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
157 | Road from Sant Bairwa Marg to Road No. 28 | 0.39 | 23/03/2017 | 31.05.2017 | 0% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
158 | Road from R-17 to D-335 Raghubir Nagar | 0.192 | 23/03/2017 | 31.05.2017 | 0% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
159 | Road from C-1 to C-494 Raghubir Nagar | 0.188 | 23/03/2017 | 31.05.2017 | 0% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
160 | Road from Road no. 29 to R Block "T" Hart | 1.18 | 23/03/2017 | 31.05.2017 | 0% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
161 | Road from Najafgarh Road to Flat No. 13, Four Storey Qtrs. Tagore Garden Extension | 0.19 | 23/03/2017 | 31.05.2017 | 0% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
162 | Road from A-23 Vishal Enclave (NG Road) to B-33 Vishal Enclave (PWD Road No. 28) (Vishal Cinema Road) | 0.7 | 23/03/2017 | 31.05.2017 | 0% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
163 | Road from Flat No. 157 Four Story to Vishal Road (opp. Police Station Rajouri Garden) | 0.47 | 23/03/2017 | 31.05.2017 | 0% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
164 | Maharishi Road from B-1 to C-17 | 0.475 | 23/03/2017 | 31.05.2017 | 0% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
165 | Road No. 4 from H. No. 11 and North West Avenue Road to 23/4 in Punjabi Bagh Extn. | 0.15 | 23/03/2017 | 31.05.2017 | 0% | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297
No. of roads where drain do not exist
1 | G.L. Sikka Marg, Patel Nagar | 0.8 |  |  |  | Sh. Ashish Kujur 9818990594 | Sh. Harpinder Singh 9811356083 | Sh. Manish Kaushik 9650167297
2 | Link Road No. 1 , Patel Nagar | 0.23 |  |  |  | Sh. Ashish Kujur 9818990594 | Sh. Harpinder Singh 9811356083 | Sh. Manish Kaushik 9650167297
3 | Link Road No. 2 , Patel Nagar | 0.18 |  |  |  | Sh. Ashish Kujur 9818990594 | Sh. Harpinder Singh 9811356083 | Sh. Manish Kaushik 9650167297
4 | Road from Durbal Nath Vatica to NH-10, Nangloi | 0.6 |  |  |  | Sh. Kharimulla S 7503050737 | Sh. R.B.Nehra 9355666768 | Sh. Manish Kaushik 9650167297
5 | Road from Park to B-8, Vishal Enclave, Madi pur | 0.1 |  |  |  | Sh. Shivakant 8860035127 | Sh. Virendera Singh 9968296526 | Sh. Manish Kaushik 9650167297

## SE, C&ND Abstract of Desilting (hidden)
Abstract of Desilting Report
(As on 27-06-2016)
S. No. | Name of Circle | Total No. of Roads | No. of roads where desilting is in progress (in %) |  |  |  |  | No. of roads where desilting is completed | No. of roads where desilting is yet to be taken up | No. of roads where drain do not exist
|  |  | 1-25 | 26 - 50 | 51 - 75 | 76 - 99 | Total
1 | North West | 212 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | West | 165 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | North | 55 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | TOTAL |  |  |  | #REF!