## East Zone
PWD Desilting Report (Preparedness for Monsoon)
DESILTING UNDER PWD MAINTENANCE SOUTH ZONE AS ON 23.05.2017
Sl. No. | Name of Road / Drain | Length of Road (Km) | Contractor | Date of Start of De-silting | Date of completion (Ist Cycle) | % Drain cleaned (Length wise) | Estimate Qty. of silt (cum) | Qty. of silt lifted and disposed off (cum) | EE in charge / Mobile No.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
South Circle
EE/SR-1
1 | M.B. Road | 5.25 | Nasir Ali | 16.03.2017 | 15.06.2017 | 65% | 2150 | 880 | Sh. Narender Mahajan 9933331859
2 | Devli Road | 2 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 15.06.2017 | 20%
3 | IGNOU Road | 2.9 | M/s RichCon Engineering Company | 16.03.2017 | 15.06.2017 | 95%
4 | Maharishi Balmiki Marg | 1.8 | Nasir Ali | 16.03.2017 | 15.06.2017 | 90%
5 | Durbal Nath Marg | 1.09 |  | 16.03.2017 | 15.06.2017 | 65%
6 | Raja Ram Marg | 0.89 |  | 16.03.2017 | 15.06.2017 | 80%
7 | H Block Dakshin Puri Road | 0.4 |  | 16.03.2017 | 15.06.2017 | 38%
8 | Firni Road | 1 |  | 16.03.2017 | 15.06.2017 | 50%
9 | West End Marg | 0.8 |  | 16.03.2017 | 15.06.2017 | 65%
10 | Old MB Road | 1 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 15.06.2017 | 95%
11 | 100 Foota Road Chattarpur | 1.4 | Ravi Tanwar | 16.03.2017 | 15.06.2017 | 20% | 840 | 350
12 | 60 Foota Road | 0.9 |  | 16.03.2017 | 15.06.2017 | 20%
13 | SSN Marg | 10.5 |  | 16.03.2017 | 15.06.2017 | 25%
14 | Gadai Pur Band Road | 3 | Ravi Tanwar | 16.03.2017 | 15.06.2017 | 20% | 765 | 335
15 | Mandi Road | 8 |  | 16.03.2017 | 15.06.2017 | 38%
16 | Dera Bhati Road | 5.76 |  | 16.03.2017 | 15.06.2017 | 20%
17 | M.G. Road | 7.5 |  | 16.03.2017 | 15.06.2017 | 18%
18 | Aya Nagr Road | 0.6 |  | 16.03.2017 | 15.06.2017 | 20%
19 | Press Enclave (BRT to Saket Court) | 4 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 15.06.2017 | 45% | 3200 | 1545
20 | Family Court Road | 0.9 |  | 16.03.2017 | 15.06.2017 | 50%
21 | Pushp Vihar (Internal Road) | 4 |  | 16.03.2017 | 15.06.2017 | 45%
22 | H. Block Road | 1 |  | 16.03.2017 | 15.06.2017 | 45%
23 | Road in front of H.No. C-11 to C-20 Malviya Nagar | 0.11 |  | 16.03.2017 | 15.06.2017 | 45%
24 | Appjay School Road | 1.3 |  | 16.03.2017 | 15.06.2017 | 45%
25 | Shekh Sarai Phase-1 | 0.3 |  | 16.03.2017 | 15.06.2017 | 45%
26 | Khirki Road | 0.85 |  | 16.03.2017 | 15.06.2017 | 45%
27 | NBCC Plaza Road | 1.1 |  | 16.03.2017 | 15.06.2017 | 45%
28 | Birla Vidya Niketan | 1 |  | 16.03.2017 | 15.06.2017 | 45%
29 | Mandir Marg | 1.2 |  | 16.03.2017 | 15.06.2017 | 45%
30 | Pramod Mahajan Marg | 0.89 |  | 16.03.2017 | 15.06.2017 | 45%
31 | Main Road Sector-1, Pushp Vihar | 0.75 |  | 16.03.2017 | 15.06.2017 | 100%
32 | Pankaj Jewel Marg, Pushp Vihar | 1.1 |  | 16.03.2017 | 15.06.2017 | 100%
33 | Asian Market Road in Pushp Vihar | 0.45 |  | 16.03.2017 | 15.06.2017 | 50%
34 | Metro Enclave Road in Pushp Vihar | 0.45 |  | 16.03.2017 | 15.06.2017 | 50%
35 | Road between DDA Flat Masjid Moth Ph-II and Jahapanah Forest | 0.5 |  | 16.03.2017 | 15.06.2017 | 50%
36 | Road in front of Mother International School | 0.54 |  | 16.03.2017 | 15.06.2017 | 50%
37 | J Block Saket | 0.89 |  | 16.03.2017 | 15.06.2017 | 50%
38 | Apeejay School Road (Gurudwara to J Block Road). | 0.3 |  | 16.03.2017 | 15.06.2017 | 50%
EE/SR-2
39 | August Kranti Marg. | 3.24 | M/s Vision Constructions | 02.03.2017 | 15.06.2017 | 68% | 3064 | 2089 | Sh. Jagdish Prasad 9560207879
40 | Balbir Saxena Marg | 0.8
41 | Ch. Dilip Singh Marg, P.S. Hauz Khas | 0.6
42 | Mahinder Singh Jain Marg Road / Gautam Nagar Road | 1.2
43 | P-Block Road from August Kranti Marg via jain Mandir & Dustbin to August Kranti Marg. | 0.34
44 | Sudarshan Cinema Road. | 0.72
45 | Gautam Nagar Road | 0.5
46 | Road form Balbir Sxsena Marg to Ch. Dalip SinghMarg (NIFT Road), Hauz Khas | 0.6
47 | Road form August Kranti marg to Aurobindo Marg (Subash Chopra Road), Hauz Khas | 0.79
48 | Asiad Village peripheral road | 3
49 | Siri Fort Road | 1.2
50 | Sri Aurobindo Marg | 5 | M/s Samridhi Construction, | 02.03.2017 | 15.06.2017 | 90% | 5768 | 5191
51 | Outer Ring Road ( IIT Flyover to Africa Avenue Junction) | 1.8
52 | Ch. Jhandu Singh Marg | 1.53
53 | Ch. Harsukh Marg | 1.83
54 | Ch. Hukum Chand Marg | 0.6
55 | Green Park Market Road | 1
56 | Narender Kumar Pandey Marg | 1.16
57 | Hauz Khas Village Road | 0.9
58 | Ring Road (Safdarjung to Hyatt) | 2.1
59 | Anuvart Marg | 2.5 | Sh. Jagdish Prasad Meena | 02.03.2017 | 15.06.2017 | 83.33% | 4212 | 3510
60 | Aruna Asaf Ali Road | 3.5
61 | Vedant Deshika Marg | 0.7
62 | B-1 Telephone Exchange Road,Vasant Kunj (Mahipalpur Road to B-5 & B-6 Road) | 0.6
63 | DAV School Road Vasant Kunj | 0.55
64 | Shiv Mandir to B-5 & B-6 Road) | 0.3
65 | D-1 & D-2 Road, Vasant Kunj | 0.24
66 | Sports Complex Road D-2,Vasant Kunj | 0.7
67 | Shaheed Jeet Singh | 2.1
68 | Road from B 15/7 to BSES Office,Q.I.A. | 0.3
69 | Peripheral Road of A Block of Q.I.A. | 0.41
70 | Peripheral Road of C and B Block of Q.I.A. | 1.57
71 | Outer Ring Road (Panchsheel to IIT Gate) | 1 | Sh. Narendra Singh Yadav | 02.03.2017 | 15.06.2017 | 85% | 1085 | 922
72 | Outer Ring Road (Chirag Delhi to Panchsheel) | 3.7
73 | A-1 Block, Panchsheel Enclave Road | 0.5
74 | S-Bend Road (Maharishi Dayanand Marg) | 1.8 | Sh. Narendra Singh Yadav | 02.03.2017 | 15.06.2017 | 77% | 1680 | 1288
75 | Shivalik Road (Basant Kaur Marg) | 1.86
76 | Guru Govind Singh Marg | 1.2
South-East Circle
EE/SER-I
77 | Raja Dheer Sain marg | 2.38 | Sh. Jagdish Prasad Meena | 01.05.2017 | 15.06.17 | 80% | 511.7 | 262 | Sh. Virendra Singh, 9868284746
78 | Kalka Devi Marg | 1.12 |  | 01.05.2017 | 15.06.17 | 20% | 346.21 | 69
79 | Gaptain Gaur Marg | 2.15 |  | 01.05.2017 | 15.06.17 | 5% | 1272.15 | 63.6
80 | Road No. 3 Andrews Ganj | 0.75 |  | 01.05.2017 | 15.06.17 | 5% | 18.48 | 0
81 | Road No. 7 Andrews Ganj | 0.24 |  | 01.05.2017 | 15.06.17 | 5% | 5.96 | 0
82 | Road No. 5 Andrews Ganj | 0.13 |  | 01.05.2017 | 15.06.17 | 5% | 13.28 | 0
83 | Road No. 2 Andrews Ganj | 0.4 |  | 01.05.2017 | 15.06.17 | 5% | 6.76 | 0.33
84 | Road No. 6 Andrews Ganj | 0.24 |  | 01.05.2017 | 15.06.17 | 5% | 12.48 | 0
85 | Kalka Devi Marg to Banglow Road | 0.47 |  | 01.05.2017 | 15.06.17 | 5% | 166.99 | 8.35
86 | Central Road to Back Ring Road to Lajpat Nagar-IV | 0.35 |  | 01.05.2017 | 15.06.17 | 5% | 158.19 | 7.91
87 | Dr. Moti Lal Jotwani Road to Lajpat Nagar-IV | 0.49 |  | 01.05.2017 | 15.06.17 | 5% | 195.28 | 9.76
88 | Theka Road S.N. Puri | 0.25 |  | 01.05.2017 | 15.06.17 | 5% | 89.74 | 4.49
89 | Shri Niwas Puri internal Road MCD Store Round about via Maternity Home. | 0.91 |  | 01.05.2017 | 15.06.17 | 5% | 279.98 | 14
90 | S.N. Puri internal Road opposite Police Post S.N. Puri | 0.15 |  | 01.05.2017 | 15.06.17 | 5% | 11.23 | 0
91 | S.N. Puri internal Road Post office to CPWD Via Jal Board | 0.54 |  | 01.05.2017 | 15.06.17 | 5% | 216.92 | 10.85
92 | Banglow Road to Gidwani Marg Lajpat | 0.12 |  | 01.05.2017 | 15.06.17 | 5% | 39.74 | 1.98
93 | S.N. Puri Main Road from Cambridge School to CTC | 1.4 |  | 01.05.2017 | 15.06.17 | 5% | 370.94 | 18.55
94 | Mathura Road | 2.00 km | M/s TripurariPrasad Singh | 2017-04-20 | 15.06.17 | 10% | 900 | 90
95 | C.V. Raman Marg | 2.00 km |  | 2017-05-01 | 15.06.17 | 5% | 750 | 38
96 | M.P. Road | 1.00 km |  | 2017-05-10 | 15.06.17 | 10% | 320 | 32
97 | Gurudwara Road | 1.20 km |  | 2017-05-10 | 15.06.17 | 2% | 260 | 5
98 | MMA Road | 3.00 km |  | 2017-05-12 | 15.06.17 | 2% | 360 | 7
99 | Sukhdev Vihar | 1.00 km |  | 2017-05-12 | 15.06.17 | 0% | 280 | 0
100 | Mata Mandir Road | 600 m |  | 2017-05-15 | 15.06.17 | 0% | 180 | 0
101 | Ring Road from AIIMS to Bhairon Road 'T' Point | 9.75 | M/s Tripiurari Prasad Singh | 2017-03-31 | 2017-06-15 | 40% | 1936 | 390
102 | Feroz Gandhi Road, Lajpat Nagar | 1.05 |  | _do_ | 2017-06-15 | 30% | 208 | 50
103 | Vir Savarkar Marg, Lajpat Nagar | 1.05 |  | _do_ | 2017-06-15 | 30% | 208 | 50
104 | Shiv Mandir Marg from Zonal Office to Ring Road | 0.85 |  | _do_ | 2017-06-15 | 40% | 169 | 30
105 | Bhisma Pitamah Road | 2.6 |  | _do_ | 2017-06-15 | 30% | 516 | 60
106 | Road from B.P.Marg to Round about Defence Colony | 0.156 |  | _do_ | 2017-06-15 | 40% | 31 | 20
107 | Josef Brass Titoo Marg (B.R.T.) (Lajpat Nagar Metro Station to Ambedkar Nagar) | 6.25 |  | _do_ | 2017-06-15 | 30% | 1241 | 500
108 | 2nd Entry (Sarai Kale Khan Red Light to Nizamuddin Railway Station) | 0.6 |  | _do_ | 2017-06-15 | 30% | 119 | 50
109 | Bhairon Road | 0.98 |  | _do_ | 2017-06-15 | 40% | 195 | 40
110 | Mathura Roads from DPS ro Ashram Chowk | 2.65 | Sh. Chander Pal | 15.04.2017 | 15.06.17 | 12% | 650 | 40
111 | Hospital Road, Bhogal | 0.56 |  | 15.04.2017 | 15.06.17 | 5% | 75 | 5
112 | East Nixzamuddin Peripheral Road from Mathura Road to Railway Station, East Nizamudin | 0.7 |  | 15.04.2017 | 15.06.17 | 5% | 85 | 5
113 | Rajdoot Hotal to Preet Place, Jangpura, Extn | 0.2 |  | 15.04.2017 | 15.06.17 | 5% | 30 | 5
114 | Preet Place to Nizamuddin Railway Station, Jangura | 0.7 |  | 15.04.2017 | 15.06.17 | 5% | 85 | 3
115 | School Road, Jangpura Extn. | 0.38 |  | 15.04.2017 | 15.06.17 | 5% | 45 | 5
116 | Neela Gumbad to Lodhi Flyover, Nizamudin Basti | 0.2 |  | 15.04.2017 | 15.06.17 | 15% | 85 | 7
117 | Maharani Bagh from Manokarma Mandir to Sunlight Colony | 0.55 |  | 15.04.2017 | 15.06.17 | 50% | 125 | 35
118 | IV th Avenue Road, Lodhi Colony | 1.22 |  | 15.04.2017 | 15.06.17 | 15% | 350 | 28
119 | V th Avenue Road, Lodhi Colony | 1 |  | 15.04.2017 | 15.06.17 | 5% | 120 | 3
120 | X Road between Block No. 18 & 14 Lodhi Colony | 0.16 |  | 15.04.2017 | 15.06.17 | 0% | 30 | -
121 | Lodhi Road Indian Habitat Centre to Lodhi Flyover | 1.76 |  | 15.04.2017 | 15.06.17 | 5% | 475 | 14
122 | X Road between D-1 & C-2 (F-24) Lodhi Colony | 0.16 |  | 15.04.2017 | 15.06.17 | 0% | 30 | -
123 | X Road btween Block No. C-2 (176) & C-2 (177) Lodhi Colony | 0.16 |  | 15.04.2017 | 15.06.17 | 0% | 30 | -
124 | B.P.Marg to Coffee House Lodhi Colony | 0.35 |  | 15.04.2017 | 15.06.17 | 5% | 75 | 5
125 | F-1 Lodhi Colony to B.P. Flyover, Lodhi Colony | 0.24 |  | 15.04.2017 | 15.06.17 | 5% | 25 | 5
126 | Verdhman Marg from IV-th Avenue Road, B.P.Marg , Lodhi Colony | 0.35 |  | 15.04.2017 | 15.06.17 | 0% | 90 | -
127 | Kushak Nallah to Sewa Nagar flyover , Sewa Nagar | 0.7 |  | 15.04.2017 | 15.06.17 | 60% | 200 | 100
128 | Kushak Nallah to CPWD Enquiry (Near O Block), Sewa Nagar | 0.3 |  | 15.04.2017 | 15.06.17 | 60% | 125 | 65
129 | Hanuman Mandir to Sewa Nagar Flyover, Sewa Nagar | 0.46 |  | 15.04.2017 | 15.06.17 | 60% | 125 | 65
130 | Railway Phatak to Subhasg Bazar, Sewa Nagar | 0.258 |  | 15.04.2017 | 15.06.17 | 5% | 35 | 5
131 | BRT from Bhairon Road T- Point to Defence Colony Flyover | 3 |  | 15.04.2017 | 15.06.17 | 25% | 285 | 75
132 | Sunder Nagar Peripherial Road, Sunder Nagar | 1.1 |  | 15.04.2017 | 15.06.17 | 10% | 150 | 9
133 | Ratan Lal Sahdev Marg, Defence Colony | 0.978 |  | 15.04.2017 | 15.06.17 | 60% | 225 | 110
134 | Gang Nath Marg, Safdurjunf Flyover to round about near Khushak Nallah | 0.625 |  | 15.04.2017 | 15.06.17 | 5% | 150 | 5
EE/SER-II
135 | SA Road | 5.46 Km | Sh. Suresh | 27.03.2017 | 15.06.2017 | 30% | 2400 | 480 | Sh. R.S. Garg, 9818656184
136 | Maharaja Agarsen Marg | 0.50 Km |  | 27.03.2017 | 15.06.2017 | 0% | 100 | 0
137 | Baba Fateh Singh Marg | 1.00 Km |  | 27.03.2017 | 15.06.2017 | 0% | 380 | 0
138 | Hans Raj Sethi Marg | 1.70 Km |  | 27.03.2017 | 15.06.2017 | 0% | 350 | 0
139 | A Block Double Storey (EPDP to Hans Raj Sethi Marg) | 0.45 Km |  | 27.03.2017 | 15.06.2017 | 0% | 50 | 0
140 | Jaitpur Road | 1.25 Km | Sh. Naresh Kumar | 04.12.2016 | 03.06.2017 | 90% | 800 | 100 cum
141 | Jaitpur Road -Meethapur Chowk to Gurudwara | 1.21 Km |  | 04.12.2016 | 03.06.2017 | 85% |  | 100 cum
142 | Higher Secondary School Meethapur | 0.87 Km |  | 04.12.2016 | 03.06.2017 | 95% |  | 500 cum
143 | Maharaja Agarsen marg | 0.80 Km | M/s R.N. Construction Co | 30.03.2017 | 15.06.17 | 95% | 700 | 550 cum
144 | Madanpur Khadar Road | 1.20 Km |  | 30.03.17 | 15.06.17 | 10% | 400 | 60cum
145 | Sarita Vihar Road | 1.10 Km |  | 30.03.17 | 15.06.17 | 40% | 550 | 260 cum
146 | Road No. 13 A | 2.50 Km |  | 30.03.17 | 15.06.17 | 60% | 2000 | 700 cum
147 | Mathura Road | 5.50 Km |  | 30.03.17 | 15.06.17 | 25% | 3200 | 720 cum
148 | Lala Lajpat Rai Marg to Raja Dheer Sen Marg | 0.30 Km | M/s Gaurav Construction Co. | 30.03.17 | 15.06.17 | 50% | 170 | 20
149 | Guru Nanak Market to lala Lajpat Rai Marg | 0.57 Km |  | 2017-03-30 | 15.06.17 | 50% | 180 | 90
150 | Nandi Vithi Marg | 0.73 Km |  | 30.03.17 | 15.06.17 | 25% | 150 | 40
151 | Link Road | 0.58 Km |  | - | 15.06.17 | 0% | 250
152 | Road from BRT to Hans Raj Gupta Marg | 0.34 Km |  | 30.3.17 | 15.06.17 | 50% | 50 | 25
153 | Hans Raj Gupta Marg | 2.65 Km |  | - | 15.06.17 | 0% | 700
154 | Lala Lajpat Rai Marg | 2.4 Km |  | - | 15.06.17 | 0% | 180
155 | Guru Harkishan Public School to Nehru Place | 0.27 Km |  | 2017-03-30 | 15.06.17 | 90% | 100 | 90
156 | R Block GK-1 signal to Outer Ring Road | 0.58 Km |  | 2017-03-30 | 15.06.17 | 80% | 96 | 77
157 | Outer Ring Road | 2.10 Km |  | 2017-03-30 | 15.06.17 | 50% | 1240 | 620
158 | Road from Vipin Chander Pal Marg to Police Station CR Park | 0.37 Km |  | 30.03.17 | 15.06.17 | 15% | 96 | 16
159 | Savitri Cinema Road | 3.10 Km |  | 2017-03-30 | 15.06.17 | 60% | 1300 | 705
160 | Surya Sen Marg | 0.75 Km |  | 30.03.17 | 05.06.17 | 95% | 225 | 202
161 | MB Road | 5.25 Km | M/s Buland Construction | 28.03.17 | 15.06.17 | 5% | 2000 | 70 cum
162 | Guru Ravi Dass Marg | 3.75 Km |  | 28.03.17 | 15.06.17 | 65% | 3300 | 1090 cum
163 | DDA Market Road | 0.43 Km |  | 28.03.17 | 15.06.17 | 10% | 200 | 22 cum
164 | KPS Road | 0.64 KM |  | 28.03.17 | 15.06.17 | 30% | 150 | 55 cum
165 | Suraj Kund Road | 0.60 Km |  | 28.03.17 | 15.06.17 | 5% | 300 | 15 cum
166 | Road No13 | 2.7 Km | M/s Buland Construction | 10.4.2017 | 15.06.17 | 25% | 2450 | 490
167 | EPDP Road | 1.80 km |  | 10.04.2017 | 15.06.17 | 0% | 800 | 0
168 | Outer Ring Road | 3.2 Km |  | 10.04.2017 | 15.06.17 | 15% | 1500 | 0
169 | Gurudwara Road GK-II | 1.70 Km |  | 10.04.2017 | 15.06.17 | 90% | 208 | 0
170 | Vipin Chander Pal Marg | 1.50 Km |  | 10.04.2017 | 15.06.17 | 0% | 720 | 0
South-West Circle
EE/SWR-I
171 | B.J. Marg | 1.3 | M/s Amocon | 15.05.2017 | 15.06.2017 | 5% | 500 | 25 | Sh. S K Sinha 9958469778
172 | Rao Tula Ram Marg (RTR Marg) | 1.7 |  | 15.04.2017 | 15.06.2017 | 75% | 400 | 400
173 | Zonal road No. 2 (Baba Balak Nath Marg) | 1750 |  | 01.06.2017 | 15.06.2017 | - | 504 | -
174 | Zonal Road No. 6 (Hare Krishna Mehto Marg) | 700 |  | 01.06.2017 | 15.06.2017 | - | 201.6 | -
175 | M.M.Road | 6.8 | Sh. T.P. Singh | 15.04.2017 | 15.06.2017 | 50% | 850 | 400
176 | Ullan Buttor Marg | 5500 | Sh. Vinay Shankar | 01.06.2017 | 15.06.2017 | - | 1584 | -
177 | Nelson Mandela Marg | 4.01 | Sh. T.P. Singh | 15.04.2017 | 15.06.2017 | 25% | 700 | 175
178 | Baba Gang Nath marg | 1.17 |  | 15.05.2017 | 15.06.2017 | 20% | 400 | 80
179 | Outer Ring Road | 4.8 | Sh. Vinay Shankar | 15.05.2017 | 15.06.2017 | 2% | 950 | 20
180 | Vatika Road (DPS Vasant Kunj to MM road) | 1.7 |  | 15.04.2017 | 15.06.2017 | 10% | 350 | 35
181 | Africa Avenue (Road No.9 | 2.2 | Sh. Brijpal Sing | 18.05.17 | 15.06.17 | 15% | 600 | 90
182 | Venketeshwar Marg | 1.1 |  | 18.05.2017 | 15.06.2017 | 10% | 200 | 20
183 | Dr. K.S. Krishanan Marg | 0.92 | Sh. Bishwa Mohan Jha | 03.04.2017 | 15.06.2017 | 60% | 250 | 160
184 | PUSA Institute (IARI) Internal Road | 0.7 |  | 03.04.2017 | 15.06.2017 | 10% | 200 | 20
185 | Dev Prakash Shastri marg (Road No. 25) | 4.45 |  | 03.04.2017 | 15.06.2017 | 25% | 1200 | 300
186 | Girdhari Lal Goswami Marg (Road No. 89) | 3.65 |  | 03.04.2017 | 15.06.2017 | 25% | 1000 | 250
187 | O.P. Bharti Marg 2 | 0.76 |  | 03.04.2017 | 15.06.2017 | 5% | 200 | 10
188 | O.P. Bharti Marg 3 | 0.18 |  | 03.04.2017 | 15.06.2017 | 50% | 50 | 25
189 | Mahatma gandhi Marg (Ring Road) (both side) | 5.5 |  | 04.04.2017 | 15.06.2017 | 55% | 1850 | 600
190 | NH-8 (both side) | 2.9 |  | 04.04.2017 | 15.06.2017 | 40% | 400 | 250
191 | Road No. 36(Sat Guru Ram Singh Marg) (both side) | 3.4 | Sh. Rajnish Yadav | 25.03.2017 | 15.06.2017 | 30% | 1400 | 300
EE/SWR-II
192 | 60 futa Road | 0.45 | M/s Ram Charan Bansal | 21.03.2017 | 15.06.2017 | 40% | work to be executed by super sucker machine. NIL | The drain is being cleaned by super sucker machines hence quanitity cannot be ascertained. However approx. Silt disposed out by S/S till date is 180 MT | Sh. J. P. Vashist M- 9971396164
193 | A Block Road | 0.2 |  | 21.03.2017 | 15.06.2017 | 100%
194 | Central School Road | 0.29 |  | 21.03.2017 | 15.06.2017 | 80%
195 | Dabri Road | 0.9 |  | 21.03.2017 | 15.06.2017 | 60%
196 | Fire Station Road | 0.4 |  | 21.03.2017 | 15.06.2017 | 80%
197 | Lal Sai Marg to Pankha Road | 0.65 |  | 21.03.2017 | 15.06.2017 | 60%
198 | Lal Sai Road | 2.5 |  | 21.03.2017 | 15.06.2017 | 30%
199 | Mall Road | 0.65 |  | 21.03.2017 | 15.06.2017 | 70%
200 | Old Pankha Road | 0.5 |  | 21.03.2017 | 15.06.2017 | 40%
201 | Pankha Road | 6.6 |  | 21.03.2017 | 15.06.2017 | 40%
202 | Ram Mandir Marg | 0.86 |  | 21.03.2017 | 15.06.2017 | -
203 | Road C-2/22 C-2/274 Road Janakpuri | 0.76 |  | 21.03.2017 | 15.06.2017 | 80%
204 | Road from Ram Mandir Marg to Mall Road (Connecting Road) | 0.3 |  | 21.03.2017 | 15.06.2017 | -
205 | Road From Shani Bazar to Ram Mandir Marg (Connecting Road) | 0.3 |  | 21.03.2017 | 15.06.2017 | -
206 | Shani Bazar Road | 0.65 |  | 21.03.2017 | 15.06.2017 | 60%
207 | Vidya Marg | 1.6 |  | 21.03.2017 | 15.06.2017 | 40%
208 | Nasir Pur Road | 0.34 |  | 21.03.2017 | 15.06.2017 | 80% | 750 MT | The drain is being cleaned by super sucker machines hence quanitity cannot be ascertained. However approx. Silt disposed out by S/S till date is 300 MT
209 | Internal Road C-1 to C-1A Block | 0.3 |  | 21.03.2017 | 15.06.2017 | 60%
210 | Palam Dabri Road | 1.39 |  | 21.03.2017 | 15.06.2017 | 80%
211 | Paras Public schol to L-103 Pocket-4 Chankya Puri Binda Pur | 0.24 |  | 21.03.2017 | 15.06.2017 | 70%
212 | Peer Baba Road | 0.6 |  | 21.03.2017 | 15.06.2017 | 100%
213 | Police Station Road | 0.37 |  | 21.03.2017 | 15.06.2017 | 80%
214 | Pt. Vishnu Dutt Marg | 0.75 |  | 21.03.2017 | 15.06.2017 | 75%
215 | Sagar Pur Road | 2.54 |  | 21.03.2017 | 15.06.2017 | 80%
216 | Satguru Ram Singh Marg | 0.9 |  | 21.03.2017 | 15.06.2017 | 75%
217 | Link Road (Pt. Vishnu Dutt Marg to Satguru Ram Singh Marg) | 0.3 |  | 21.03.2017 | 15.06.2017 | 75%
218 | Najafgarh Nagloi Road | 2.6 | Sh. Surender Singh, | 21.03.2017 | 15.06.2017 | 60% | 382 MT | The drain is being cleaned by super sucker machines hence quanitity cannot be ascertained. However approx. Silt disposed out by S/S till date is 250 MT
219 | Najafgarh Phirni | 2.2 |  | 21.03.2017 | 15.06.2017 | 40%
220 | Najafgarh Dhansa Road | 16.25 |  | 21.03.2017 | 15.06.2017 | 60%
221 | Najafgarh Dechaun Road | 4.55 | M/s Anmol Infratech Pvt Ltd. | 21.03.2017 | 15.06.2017 | 60% | work to be executed by super sucker machine. NIL | The drain is being cleaned by super sucker machines hence quanitity cannot be ascertained. However approx. Silt disposed out by S/S till date is 125 MT
222 | Najafgarh Jaroda Road | 7.2 |  | 21.03.2017 | 15.06.2017 | 35%
223 | Najafgarh Kakrola Road | 4 |  | 21.03.2017 | 15.06.2017 | 100%
224 | Laxmi Chand Marg | 11.3 | Sh. Surender Singh, | 21.03.2017 | 15.06.2017 | 15% | 1090 MT | The drain is being cleaned by super sucker machines hence quanitity cannot be ascertained. However approx. Silt disposed out by S/S till date is 400 MT
225 | Prithvi Singh Dagar Marg | 11.2 |  | 21.03.2017 | 15.06.2017 | 15%
226 | Jhatikara Morh to Jhatikara | 8.55 | Sh. Surender Singh, | 21.03.2017 | 15.06.2017 | 88% | 890 MT | The drain is being cleaned by super sucker machines hence quanitity cannot be ascertained. However approx. Silt disposed out by S/S till date is 330 MT
227 | Najafgarh Bijwasan Road | 11.25 |  | 21.03.2017 | 15.06.2017 | 15%
228 | Bhartal Road | 3.48 | M/s Anmol Infratech Pvt Ltd. | 21.03.2017 | 15.06.2017 | not required | not required | The drain is being cleaned by super sucker machines hence quanitity cannot be ascertained. However approx. Silt disposed out by S/S till date is 550 MT
229 | Goyla Deenpur Road | 4.2 |  | 21.03.2017 | 15.06.2017 | nil
230 | Kapashera Bijwasan Road | 3.8 |  | 21.03.2017 | 15.06.2017 | 35% | 1470 MT
231 | Link Road | 1.7 |  | 21.03.2017 | 15.06.2017 | 70%
232 | Old DG Road | 2.5 |  | 21.03.2017 | 15.06.2017 | nil