## East Zone
As on 29.05.2017
PWD Desilting Report (Preparedness for Monsoon)
DESILTING UNDER PWD MAINTENANCE ………. ZONE AS ON 19.05.2017
Sl. No. | Name of Road / Drain | Length of Road (Km) | Contractor | Date of Start of De-silting | Date of completion (Ist Cycle) | % Drain cleaned (Lengthwise) | Estimate Qty. of silt (cum) | Qty. of silt lifted and disposed off (cum) | EE in charge / Mobile No.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Circle/ Div. :- Shahdara (Road)
1 | Road No- 56 | 5.6 | M/s T.K.N. Developers | 25.02.2017 | 31.05.2017 | 80% | 1100 | 850 | Sh Vijay Singh, 8802028700
2 | Road No- 71 A | 0.6 |  | 25.02.2017 | 31.05.2017
3 | Road No- 71 | 1.6 |  | 25.02.2017 | 31.05.2017
4 | Road No. 56-A. | 1 |  | 25.02.2017 | 31.05.2017
5 | G.T Road Mansarover Park to Apsara Border | 2.6 | Sh. Mudassir Hussain | 16.05.2017 | 31.05.2017 | 0% (Work recently awarded) | 1685 | Nil
6 | Road No 72 | 0.91 | M/s T.K.N. Developers | 25.02.2017 | 31.05.2017 | 15% | 1500 | 225
7 | Road No 72 Extn. | 1 |  | 25.02.2017 | 31.05.2017
8 | Zonal office Road. | 1.03 |  | 25.02.2017 | 31.05.2017
9 | Surajmal Vihar Market | 1.2 |  | 25.02.2017 | 31.05.2017
10 | Shrestha Vihar | 1.25 |  | 25.02.2017 | 31.05.2017
11 | Road No 58 | 2.84 |  |  |  | 0% (Tender called) | 2544 | Nil
12 | Road No 58 A | 2
13 | Shiva Khand Road | 0.9 | Sh. Ram Kumar Sharma | 16.05.2017 | 31.05.2017 | 0% (Work recently awarded) | 2227 | Nil
14 | ITI Vivek Vihar | 1.4 |  | 16.05.2017 | 31.05.2017
15 | C-Block, Jhilmil | 0.45 |  | 16.05.2017 | 31.05.2017
16 | Vivek Vihar | 0.617 |  | 16.05.2017 | 31.05.2017
17 | Ram Mandir via ITI Vivek Vihar | 1.35 |  | 16.05.2017 | 31.05.2017
18 | Jhilmil Colony | 0.188 |  | 16.05.2017 | 31.05.2017
19 | DJB opp. B-Block | 0.3 |  | 16.05.2017 | 31.05.2017
20 | B-Block, Jhilmil, Shaheed Bhagat Singh Marg | 0.355 |  | 16.05.2017 | 31.05.2017
21 | Link Road GT Road to Vivek Vihar ITI | 0.6 |  | 16.05.2017 | 31.05.2017
22 | Road No. 57 (Jagat Puri to Telco X-ing) | 2.52 | M/s T.K.N. Developers | 25.02.2017 | 31.05.2017 | 20% | 1600 | 320
23 | Road No. 57 from G.T. Road Azad Nagar | 1.5 |  | 25.02.2017 | 31.05.2017
24 | Road No. 57 Azad Nagar to Jagat Puri | 1.25 |  | 25.02.2017 | 31.05.2017
25 | Bhartendu Harish Chander Marg (75-B Extension) | 2.13 |  | 25.02.2017 | 31.05.2017
26 | Bhola Nath Nagar | 0.6 |  | 25.02.2017 | 31.05.2017
27 | 60' feet Road | 1.17 |  | 25.02.2017 | 31.05.2017
28 | Shahdara Road | 0.6 |  | 25.02.2017 | 31.05.2017
29 | DCP Office | 0.112 |  | 25.02.2017 | 31.05.2017
30 | G.T Road Shyam lal Collage to Mansarover Park | 2 |  | 25.02.2017 | 31.05.2017 | 65% | 750 | 480
31 | G.T Road Railway under bridge near Metro Station Shahdara | 0.176 |  | 25.02.2017 | 31.05.2017
32 | G.T Road Railway under bridge near Railway Station Shahdara | 0.214 |  | 25.02.2017 | 31.05.2017
33 | G.T Road Shyam lal Collage to Dharmapura | 1.75 |  | 25.02.2017 | 31.05.2017
34 | Kabool Nagar Gurdwara Road | 0.132 |  | 25.02.2017 | 31.05.2017 | 80% | 800 | 600
35 | Gandhi Nagar Road | 1.5 |  | 25.02.2017 | 31.05.2017
36 | Road No. 62 (Road No. 70 to Apsara Border) | 1.2 | M/s Sai Tube Well | 09.03.2017 | 31.05.2017 | 20% | 14842 | 1650 | Sh Vijay Singh, 8802028700
37 | Road No. 70 (Seemapuri to Tahir Pur T-Point) | 1.2 |  | 09.03.2017
38 | Seemapuri Road from Road No. 62 to 64 | 1.06 | M/s Sai Tube Well | 09.03.2017 | 31.05.2017
39 | LIC Road (from Malaria office MCD to GT Road) | 0.3 |  | 09.03.2017 | 31.05.2017
40 | Road along Divider road to pummy sweet at Gurudwara road) | 0.36 |  | 09.03.2017 | 31.05.2017
41 | Gurudwara Road from DTC bus depot Road No. 70 to GTB Hospital road | 1.75 |  | 09.03.2017 | 31.05.2017
42 | Road infront of Hans Raj Public School (Divider Road to Gurudwara road) | 0.36 |  | 09.03.2017 | 31.05.2017
43 | Road from T-point, L-pocket to R Block small rotary | 0.86 |  | 09.03.2017 | 31.05.2017
44 | GTB Hospital Road (From GT Road to Aggarwal Sweet Dilshad Garden) | 0.6 |  | 09.03.2017 | 31.05.2017
45 | R-Block Road (From Divider road Agarwal sweet to GT Road) | 0.5 |  | 09.03.2017 | 31.05.2017
46 | Road No. 62 (J & K pocket) to petrol pump GT Road (infront of Red Crosss society). | 0.33 |  | 09.03.2017 | 31.05.2017
47 | Road from Gurudwara road (T-point of Kalander Colony) to Gauri Shankar Mandir | 0.31 |  | 09.03.2017 | 31.05.2017
48 | Road from Divider Road (Mukherjee Public School to Sant Ram Public School at Gurudwara road) | 0.36 |  | 09.03.2017 | 31.05.2017
49 | New Seemapuri Road from Road No. 64 (Mother Dairy) to Road No. 62 near maszid | 1.16 |  | 09.03.2017 | 31.05.2017
50 | Road from LIC Colony (T-Point to rotary at Telephone Exchange) | 0.93 |  | 09.03.2017 | 31.05.2017
51 | Road No. 64 Swami Dayanand Hospital to DLF More (U.P. Border) | 3 |  | 09.03.2017 | 31.05.2017
52 | Divider Road from Seemapuri road to Road No. 64 (near SDN Hospital) | 2.4 |  | 09.03.2017 | 31.05.2017
53 | CNG Petrol Pump to deer park (Divider road) west side | 0.2 |  | 09.03.2017 | 31.05.2017
54 | CNG Petrol Pump to deer park (Divider road) east side | 0.19 |  | 09.03.2017 | 31.05.2017
55 | GTB Hospital road from Red light to Agarwal sweet (Divider road) | 0.19 |  | 09.03.2017 | 31.05.2017
56 | Road from GT Road to Road No. 64 via Telephone exchange | 0.41 |  | 09.03.2017 | 31.05.2017
57 | Road from General Hospital (Road No. 64 to Shahdara Flyover) | 0.26 |  | 09.03.2017 | 31.05.2017
58 | Road No. 68 (Road No. 69 to Road No. 66) | 3.4 |  | 09.03.2017 | 31.05.2017
59 | Loni Road G.T. Road to Loni Gole Chakkar | 2.894 | M/s Sai Tube Well | 09.03.2017 | 31.05.2017 | 20% | 14842 | 1650 | Sh Vijay Singh, 8802028700
60 | Road No. 69 | 1.25 |  | 09.03.2017 | 31.05.2017
61 | Tanga Stand Road from road no. 68 to Wazirabad Road. | 1.35 |  | 09.03.2017 | 31.05.2017
62 | Main Road LIG Flats, East of Loni Road from Loni Road to community centre Ashok Nagar. | 0.375 |  | 09.03.2017 | 31.05.2017
63 | Captain javed Ali Marg | 0.84 |  | 09.03.2017 | 31.05.2017
64 | Main Road LIG flats, Loni Road to Govt. S.S. School Ashok Nagar. | 0.275 |  | 09.03.2017 | 31.05.2017
65 | GTB Road (From Road No. 64 to Road No. 68) | 0.91 |  | 09.03.2017 | 31.05.2017
66 | Mandoli Road (From Loni Road to Nand Nagri Railway crossing) | 1.94 |  | 09.03.2017 | 31.05.2017
67 | From Rajiv Gandhi super hospital specialty hospital to GTB hospital road | 0.95 |  | 09.03.2017 | 31.05.2017
68 | From Road No. 68 (petrol pump) to E-pocket GTB enclave police booth near Nutan Vidya Mandir public school | 0.37 |  | 09.03.2017 | 31.05.2017
69 | From Road No. 69 MIG Flat to GTB Hospital Road Via Nutan Vidya Mandir public school | 0.9 |  | 09.03.2017 | 31.05.2017
70 | Road along khel parisor from NVM school to Green field public school. | 0.25 |  | 09.03.2017 | 31.05.2017
71 | Road No-65 (GT Road to Road no.-66) | 1.2 |  | 09.03.2017 | 31.05.2017
72 | Babarpur Road (GT Road to Road no.-66 | 2 |  | 09.03.2017 | 31.05.2017
Circle/Div. :- East-M / East Road (M-212)
Name of MLA :- Sh. Manoj Kumar
Name of Constituency :- Kondli AC (56)
1 | Road from Live stock market to Gali No. 7 Block - C in Ghazipur Dairy Farm. | 0.8 | M/s Shiva Construction Co. | 15.03.2017 | Continuous process to remove the gober from Drain by JCB |  | 15570 | 13800 | Sh. Iqbal Singh/ Mob:- 9910925748
2 | NH-24 Ghazipur to Kondli Bridge. | 1.5 |  | 15.03.2017
3 | Road from NH-24 to Hindon cut near Ghazipur Slaughter House. | 0.5 |  | 15.03.2017 | 30.06.2017 | 0% | 50
4 | Dharamshilla Road | 0.6 |  | 15.03.2017 | 30.06.2017 | 70% | 256
5 | Saheed Budh Singh Marg | 0.28 |  | 15.03.2017 | 30.06.2017 | 0% | 100
6 | Dallupura Road | 1.25 |  | 15.03.2017 | 30.06.2017 | 60% | 530
7 | M.P. Road No. 102 | 2.2 |  | 15.03.2017 | 30.06.2017 | 90% | 500
8 | M.P Road No. 108 | 1.33 |  | 15.03.2017 | 30.06.2017 | 90% | 720
9 | M.P Road 109 | 0.81 |  | 15.03.2017 | 30.06.2017 | 50% | 550
10 | Road from Kondli Village up Gharoli Village X-ing. | 0.75 |  | 15.03.2017 | 30.06.2017 | 90% | 400
11 | Road along Shiv Mandir in Gharoli Dairy Farm 'B' Block. | 0.66 |  | 15.03.2017 | 30.06.2017 | 95% | 250
12 | EWS Flats to DDA Market Mayur Vihar Ph.-III X-ing upto Agarwal Sweet Shop. | 0.66 |  | 15.03.2017 | 30.06.2017 | 100% | 250
13 | Main road between A & B Block New Kondli. | 0.35 |  | 15.03.2017 | 30.06.2017 | 50% | 150
14 | Road from High land Apptt. To Soochna Apptt. In Vasundhara Enclave. | 0.4 |  | 15.03.2017 | 30.06.2017 | 0% | 150
15 | Road from Manav Ashray Apptt. To Hindon Apptt. In Vasundhara Enclave | 0.48 | M/s Shiva Construction Co. | 15.03.2017 | 30.06.2017 | 0% | 180 |  | Sh. Iqbal Singh/ Mob:- 9910925748
16 | Road from Dashmesh Public School to Delux Apptt. Via Mahesh Apptt. In Vasundhara Enclave. | 0.75 |  | 15.03.2017 | 30.06.2017 | 90% | 315
17 | Bhagvan Mahavir Swami Marg. | 0.8 | M/s Shiva Construction Co. | 15.03.2017 | 30.06.2017 | 0% | 350
18 | Sameer Bhan Marg | 0.825 |  | 15.03.2017 | 30.06.2017 | 95% | 300
19 | Road from Cell Apartment to Angel Public School in Vasundhara Enclave. | 0.2 |  | 15.03.2017 | 30.06.2017 | 80% | 80
20 | Road from Dainik Janyug Apartment to Hindon Apartment (Budh Singh Marg). | 0.5 |  | 15.03.2017 | 30.06.2017 | 100% | 180
21 | From Kondli Bridge to Porta Cabin MCD Primary School. | 0.85 |  | 15.03.2017 | 30.06.2017 | 100% | 200
22 | Road between Pocket A-1 & A-2 Mayur Vihar Ph-III (Gurudwara Road) | 0.26 |  | 15.03.2017 | 30.06.2017 | 0% | 70
23 | Road between Block No. 12 and 13 from Khichripur Chowk to Kalyanvas Road. | 0.75 |  | 15.03.2017 | 30.06.2017 | 40% | 100
24 | Road between Block No. 11-15 from Block-15 to LBS Hospital through Jalebi Chowk, Kalyanpuri. | 0.67 |  | 15.03.2017 | 30.06.2017 | 70% | 300
25 | Road from between Block No. 2 & 3 upto Khichripur Main Road. | 0.3 |  | 15.03.2017 | 30.06.2017 | 0% | 50
26 | Khichripur road from Kondli Bridge to Mother Dairy. | 1 |  | 15.03.2017 | 30.06.2017 | 0% | 250
Name of MLA :- Sh. Raju Dhingan
Name of Constituency :- Trilokpuri AC (55)
27 | Kotla Road from Trilok Puri Police Station to Khichirpur Bus Stand. | 3 | M/s Shiva Construction Co. | 15.03.2017 | 30.06.2017 | 80% | 1760 | 1408
28 | East end apartment road. | 0.84 | M/s Anmol Infrastructure Pvt. Ltd | 15.03.2017 | 30.06.2017 | 60% | 330 | 200
29 | Road along Ghazipur Drain | 3.6 |  | 15.03.2017 | 30.06.2017 | 85% | 2900 | 2400
30 | Peripherial road from Chilla Chowk to kotla Village. | 1.25 |  | 15.03.2017 | 30.06.2017 | 95% | 360 | 330
31 | Road from Block No. 35 to 17 Trilokpuri (Mahrishi Balmiki Marg) | 1.07 |  | 15.03.2017 | 30.06.2017 | 0% | 175 | -
32 | Road from Block No. 19 to Block No. 13 Trilokpuri | 1.54 |  | 15.03.2017 | 30.06.2017 | 95% | 780 | 700
33 | Main road from Block No. 33 to Block No. 19. Trilokpuri | 0.52 |  | 15.03.2017 | 30.06.2017 | 0% | 60 | -
34 | Road from Block No. 36 to Block No. 31 Trilokpuri. | 0.99 |  | 15.03.2017 | 30.06.2017 | 90% | 560 | 450
35 | Ambedkar Marg from Block No. 18 Trilokpuri to Kotla Road. | 0.95 |  | 15.03.2017 | 30.06.2017 | 95% | 200 | 180
36 | Subhash Mkt. from Chand Cinema Turn to Balvikas School | 0.6 |  | 15.03.2017 | 30.06.2017 | 0% | 245 | -
37 | Road from Block No. (1) to (11) of Trilokpuri | 0.98 |  | 15.03.2017 | 30.06.2017 | 0% | 210 | -
38 | Chilla road from Chilla chowk to Chilla Village. | 0.9 |  | 15.03.2017 | 30.06.2017 | 60% | 1045 | 440
Name of MLA :- Sh. Manish Sisodia
Name of Constituency :- Patparganj (57)
39 | Sadhabhawana marg (111) | 0.75 | M/s Anmol Infrastructure Pvt. Ltd | 15.03.2017 | 30.06.2017 | 90% | 90 | 75
40 | Club Avenue Marg (112) | 0.45 |  | 15.03.2017 | 30.06.2017 | 90% | 175 | 140 | Sh. Iqbal Singh/ Mob:- 9910925748
41 | Sehkarita Marg (113) | 0.65 |  | 15.03.2017 | 30.06.2017 | 90% | 340 | 250
42 | ASN School to Parwana Apartment to Kala Apartment upto LSC. | 0.8 |  | 15.03.2017 | 30.06.2017 | 90% | 400 | 340
43 | Samachar Apartment Road (Link Road) Samachar Apartment to Glaxo Apartment. | 0.35 |  | 15.03.2017 | 30.06.2017 | 0% | 300 | -
44 | Road from Block No. 1 Khichripur to NH-24. | 0.85 | M/s Shiva Construction Co. | 15.03.2017 | 30.06.2017 | 90% | 460 | 414
45 | Khichripur Main Road from NH-24 to Mother Dairy. | 0.8 |  | 15.03.2017 | 30.06.2017 | 0% | 350 | -
46 | Patparganj Main Road from NH-24 to Patparganj Village. | 0.3 |  | 15.03.2017 | 30.06.2017 | 0% | 95 | -
47 | Road between Pocket E & F Mayur Vihar Ph-II. | 0.6 |  | 15.03.2017 | 30.06.2017 | 0% | 110 | -
48 | Road from NH-24 to DJB Office,Mayur Vihar Ph2 | 0.9 |  | 15.03.2017 | 30.06.2017 | 90% | 200 | 180
49 | Road from T-point Mayur vihar ph2 to chand Cinema crossing,kalyanvas road | 1.7 |  | 15.03.2017 | 30.06.2017 | 90% | - | 500
50 | Road infront of LBS Hospital (from Kalyanvas road to main market khichripur road) | 0.5 |  | 15.03.2017 | 30.06.2017 | 0% | - | -
Name of Constituency :- Patparganj (57)
51 | Sai Chowk | 0.67 | M/s Sai Tube Well | 15.03.2017 | 30.06.2017 | 8% | 684.33 | 241
52 | Kailash Apartment. | 0.354 |  | 15.03.2017 | 30.06.2017 | 0% | 333.65 | 0
53 | Bathla Apartment | 0.328 |  | 15.03.2017 | 30.06.2017 | 0% | 300 | 0
54 | Gagan Vihar. | 0.4 |  | 15.03.2017 | 30.06.2017 | 0% | 90 | 0
55 | Agarsain Apartment | 0.61 |  | 15.03.2017 | 30.06.2017 | 4% | 300 | 180
56 | Mother Dairy Road (Narwana Road) | 2.5 |  | 15.03.2017 | 30.06.2017 | 14% | 1214 | 310
57 | Mother Dairy Road | 1.5 |  | 15.03.2017 | 30.06.2017 | 0% | 874.65 | 0
58 | Madhu Vihar Road | 1.6 |  | 15.03.2017 | 30.06.2017 | 15% | 1578.67 | 0
59 | Balco Market | 0.63 |  | 15.03.2017 | 30.06.2017 | 16% | 153.45 | 210
60 | Prince Apartment | 0.59 |  | 15.03.2017 | 30.06.2017 | 0% | 567.88 | 0
61 | Oriental Apartment | 0.334 |  | 15.03.2017 | 30.06.2017 | 0% | 222.11 | 0
62 | Narwana Apartment | 0.46 |  | 15.03.2017 | 30.06.2017 | 7% | 262.2 | 0
63 | Trilokia Apartment | 0.38 |  | 15.03.2017 | 30.06.2017 | 17% | 216.6 | 150
64 | Rama Krishna Apartment | 0.27 |  | 15.03.2017 | 30.06.2017 | 0% | 99.9 | 0
65 | Disused canal road (Main Drain with EDMC) | 2.9 |  | 15.03.2017 | 30.06.2017 | 0% | 870 | 0
66 | New Rajdhani Road | 0.79 |  | 15.03.2017 | 30.06.2017 | 0% | 537.2 | 0
67 | Chitra Vihar Road | 0.69 |  | 15.03.2017 | 30.06.2017 | 0% | 393.3 | 0
68 | Patparganj Road | 2.89 |  | 15.03.2017 | 30.06.2017 | 25% | 2691.67 | 550
69 | Vikas Marg (Road No. 75 A & 75 B | 3.14 |  | 15.03.2017 | 30.06.2017 | 6% | 494.55 | 250
70 | Patpargunj Road (Preet Vihar) | 1.47 |  | 15.03.2017 | 30.06.2017 | 0% | 1651.86 | 0
(North-East) Road Division/M-213
1 | Road No. 66 (Seelampur Red Light on G.T. Road to Moujpur Red Light) | 2.1 | M/s Sai Tube Well | 25.04.2017 | 15.06.2017 | 4% | 20 | 20 | Sh. K.P.Singh 9810438957
2 | Main Road Maujpur (Ghonda Chowk to Red Light on Road No.-66) | 0.999 |  | 25.04.2017 | 15.06.2017 | 45% | 304 | 300
3 | Road No. 59 ( Part of Wazirabad Road) Loni Gole Chakkar to Khajuri Chowk) | 3.45 |  | 26.03.2017 | 15.06.2017 | 45% | 1120 | 1050
4 | Tanki Road (DTC Depot dividing road to Tikona park Subhash Vihar Water Tank) | 0.65 | M/s Sai Tube Well | work not started | 15.06.2017 | 0% | Nil | Nil | Sh. K.P.Singh 9810438957
5 | Road No. 59 (Rd 3450m to 6450m) | 3 | Drain does not exist
6 | Yamuna Vihar Road (C-1 to C-4) | 1.1 | M/s Sai Tube Well | 2017-05-01 | 15.06.2017 | 100% | 200 | 200 | Sh. K.P.Singh 9810438957
7 | Yamuna Vihar Road C block Service Road (From gokalpuri Flyover to Bhajanpura Petrol Pump) | 1.7 |  | 2017-04-30 | 01.05.2017 | 100% | 340 | 340
8 | Yamuna Vihar Dividing road (Wazirabad Road Yamuna Vihar Red Light to DTC Depot near H. No. B-5/18, Yamuna Vihar, Delhi) | 0.5 |  | work not started | 15.06.2017 | 0% | Nil | Nil
9 | Road No. 66 (Moujpur Red Light to Gokalpuri Flyover) | 1.5 |  | work not started | 15.06.2017 | 0% | Nil | Nil
10 | Main Road Noor –E-Illahi Road (DTC Depot Yamuna Vihar to Ghonda Chowk) | 0.98 |  | work not started | 15.06.2017 | 15% | 100 | 80
11 | Road No. 63 ( Part of Wazirabad Road) Bhopura Border (U.P.) to Loni Flyover near Loni Gole Chakkar | 3.18 |  | 20.03.2017 | 15.06.2017 | 45% | 965 | 850
12 | Sewadham Road ( Nand Nagri Red Light on Road No. 63 to U.P. Border) | 2.45 |  | 15.05.2017 | 15.06.2017 | 30% | 580 | 225
13 | Loni Road G.T. Road to U.P. Border (Loni gole Chakkar to U.P. Border (Loni)) | 0.5 |  | work not started | 15.06.2017 | 0% | Nil | Nil
14 | Gokulpuri Main Road (Wazirabad Road H. No. A-1 to Gokulpuri H. No. B-22) | 0.246 |  | 09.04.2017 | 15.06.2017 | 2% | 10 | 10
15 | Bank Colony Road along western Side of Mandoli Jail Complex (Mandoli Bank Colony to Harsh Vihar Colony.) | 0.337 |  | 30.04.2017 | 01.05.2017 | 100% | 90 | 90
16 | Main Brahmpuri Road (Ghonda Chowk to Brahampuri Dhalav) | 1.84 |  | 20.05.2017 | 15.06.2017 | 7% | 68 | 50
17 | Old G.T. Road (Old Yamuna bridge to Darampura Y- Point) | 0.9 | Sh. Vinod Kumar | 01.05.2017 | 31.05.2017 | 70% | 300 | 265
18 | Zero Pusta (Zero Pusta to Bharampuri culvert) | 0.99 |  | 15.03.2017 | 31.05.2017 | 45% | 470 | 330
19 | Seelmapur Road (Road No. 66 to Dhalav) | 0.517 |  | 07.04.2017 | 31.05.2017 | 100% | 370 | 170
20 | E.A. Road (Dharam Pura T-Point to ISBT) (Service road Hotel de aqua) | 4.2 |  | 07.04.2017 | 31.05.2017 | 50% | 300 | 250
21 | Grudwara Road (G. T Road to seelampur main Road) | 0.3 |  | 07.04.2017 | 31.05.2017 | 100% | 250 | 160
22 | MB Road (Shastri Park To Khajuri Chowk) | 3.75 |  | 10.04.2017 | 31.05.2017 | 100% | 350 | 120
23 | Garhi Mendu Road (3rd Pusta to Wazirabad Road) | 4.685 | Drain does not exist
24 | Gamri Road (5th Pusta to Ghonda Chowk) | 1.85 | Sh. Vinod Kumar | 15.03.2017 | 31.05.2017 | 62% | 775 | 630
Circle / Divn. : SRD Project Circle / SRD Project Division-I
Name of MLA :- Sh. Asim Ahmed Khan | [8 empty] | Er. Rajeev Lochan (Mob. 9911058852)
Name of Constituency & Constituency No.:- Matia Mahal AC 21
1 | Barron Road | 0.28 | M/s Shiva Costruction Co. | 24.03.2017 | 31.05.2017 | 50% | 1600 | 250
2 | Thomson Road | 0.75 |  | 24.03.2017 | 31.05.2017 | 40%
3 | Mir Dard Road | 0.55 |  | 24.03.2017 | 31.05.2017 | 20%
4 | DDU Marg | 1.98 |  | 24.03.2017 | 31.05.2017 | 80%
5 | Mahawat Khan Road | 1.1 |  | 24.03.2017 | 31.05.2017 | 25%
6 | Vishnu Dignamber Marg | 0.32 |  | 24.03.2017 | 31.05.2017 | 30%
7 | Ranjit Singh Road | 0.45 |  | 24.03.2017 | 31.05.2017 | 20%
8 | Minto Road | 0.7 |  | 24.03.2017 | 31.05.2017 | 90%
9 | Mata Sundri Road | 1.1 |  | 24.03.2017 | 31.05.2017 | 45%
10 | Turkman Road | 0.6 |  | 24.03.2017 | 31.05.2017 | 20%
11 | JLN Marg | 1.86 |  | 24.03.2017 | 31.05.2017 | 50%
12 | Kotla Road | 1.48 |  | 24.03.2017 | 31.05.2017 | 50%
13 | N S Marg | 2.22 |  | 24.03.2017 | 31.05.2017 | 30%
14 | Asaf Ali Marg | 1.9 |  | 24.03.2017 | 31.05.2017 | 50%
15 | Chaman Lal Marg | 0.18 |  | 24.03.2017 | 31.05.2017 | 70%
Name of MLA :- Ms. Alka lamba | [8 empty] | Er. Rajeev Lochan (Mob. 9911058852)
Name of Constituency & Constituency No.:- Chandni Chowk AC 20
16 | S.P.M. Marg | 1.48 | M/s Shiva Costruction Co. | 24.03.2017 | 31.05.2017 | 60% | 1800 | 250
17 | HC Sen Road | 0.4 |  | 24.03.2017 | 31.05.2017 | 100%
18 | Khari Bawali Road | 0.427 |  | 24.03.2017 | 31.05.2017 | 30%
19 | Esplanade Road | 0.43 |  | 24.03.2017 | 31.05.2017 | 100%
20 | Naya Bazar Road | 0.58 |  | 24.03.2017 | 31.05.2017 | 15%
21 | Zorawar Singh Marg | 1.32 |  | 24.03.2017 | 31.05.2017 | 10%
22 | Mori Gate Road | 0.38 |  | 24.03.2017 | 31.05.2017 | 40%
23 | Kela Ghat | 0.175 |  | 24.03.2017 | 31.05.2017 | 100%
24 | Dewan Hall Road | 0.27 |  | 24.03.2017 | 31.05.2017 | 35%
25 | Jama Masjid Road | 1.45 |  | 24.03.2017 | 31.05.2017 | 15%
26 | Chandni Chowk Road | 1.29 |  | 24.03.2017 | 31.05.2017 | 30%
27 | Road No.- 47 (Boulevard Road) | 1.04 |  | 24.03.2017 | 31.05.2017 | 35%
28 | Rajpur Road | 2.565 |  | 24.03.2017 | 31.05.2017 | 30%
29 | Approach Road | 0.25 |  | 24.03.2017 | 31.05.2017 | 30%
30 | Approach Road | 0.215 |  | 24.03.2017 | 31.05.2017 | 50%
31 | Hamilton Road | 0.24 |  | 24.03.2017 | 31.05.2017 | 40%
32 | Gokhle Road | 0.876 |  | 24.03.2017 | 31.05.2017 | 20%
33 | Sarai Phose Road | 0.71 |  | 24.03.2017 | 31.05.2017 | 30
34 | Lothein Road | 0.925 |  | 24.03.2017 | 31.05.2017 | 10%
SRD Project Division-II
Karol Bagh, Constituency
1 | Panchkuiya Road | 1.28 | M/s S.K. Associates | 10-04-2017 | 31-05-2017 | 90% | 2750 | 483.2 | Er. J.P. Sharma (Mob. 7838694446)
2 | Nehru Bazar Road | 0.45 |  | 23-05-2017 | 15-06-2017 | 0%
3 | DAV Aram Bagh Road | 0.46 |  | 10-04-2017 | 15-06-2017 | 70%
4 | Basant Road | 0.77 |  | 24-05-2017 | 15-06-2017 | 0%
5 | Main Bazar Road | 0.95 |  | 24-05-2017 | 15-06-2017 | 0%
6 | Chitra Gupta Road | 0.68 |  | 22-05-2017 | 15-06-2017 | 5%
7 | C.G.H.S. Dispansary Road | 0.23 |  | 25-05-2017 | 15-06-2017 | 0%
8 | Desh Bandu Gupta Road | 2.4 |  | 25-05-2017 | 15-06-2017 | 0%
9 | New Rohtak Road | 2.2 |  | 15-03-2017 | 31-05-2017 | 65%
10 | Faiz Road | 1.41 |  | 25-05-2017 | 31-05-2017 | 0%
11 | Rani Jhansi Road | 1.71 |  | 25-05-2017 | 31-05-2017 | 0% |  |  | Er. J.P. Sharma (Mob. 7838694446)
12 | Vallabacharya marg | 0.25 |  | 10-05-2017 | 31-05-2017 | 30%
13 | Ajmal Khan Road | 1.6 |  | 25-05-2017 | 31-05-2017 | 0%
14 | Road No. 3 | 0.5 |  | 15-03-2017 | 31-05-2017 | 90%
15 | Dyanand Saraswati Marg (Road No. 4) | 0.5 |  | 17-03-2017 | 31-05-2017 | 55%
16 | Guru Nanak Road (Road No. 5) | 0.9 |  | 23-05-2017 | 31-05-2017 | 7%
17 | Military Road | 1.4 |  | 15-03-2017 | 31-03-2017 | 100%
18 | Pyare Lal Road | 2 |  | 18-03-2017 | 31-05-2017 | 85%
19 | Hardhyan Singh Road | 1.8 |  | 20-04-2017 | 31-05-2017 | 30%
20 | Padam Singh Road | 1.5 |  | 25-05-2017 | 15-06-2017 | 0%
21 | Tank Road | 1 |  | 25-05-2017 | 15-06-2017 | 10%
22 | Guru Ravi Das Marg | 2 |  | 24-03-2017 | 31-05-2017 | 65%
23 | East Park Road | 0.99 |  | 25-05-2017 | 10-06-2017 | 0%
24 | S.K. Dass Road | 1 |  | 20-05-2017 | 15-06-2017 | 15%
25 | Abdul Rehman Road | 0.715 |  | 25-05-2017 | 15-06-2017 | 0%
26 | Abdul Aziz Road | 0.85 |  | 25-05-2017 | 15-06-2017 | 0%
27 | Elahi Bux Road | 0.415 |  | 25-05-2017 | 15-06-2017 | 0%
28 | Gurudara Road | 1 |  | 20-05-2017 | 15-06-2017 | 40%
29 | Saraswati Marg | 1 |  | 25-03-2017 | 31-05-2017 | 90%
30 | Gangeshwar Dham Marg | 0.375 |  | 25-05-2017 | 31-05-2017 | 0%
31 | D.B Gupta Road | 2 |  | 01-05-2017 | 31-05-2017 | 80%
32 | Arya Samaj Road | 1.8 |  | 25-05-2017 | 15-06-2017 | 0%
33 | Khajoor Road | 0.32 |  | 22-05-2017 | 31-05-2017 | 15%
34 | Ganga Mandir Marg | 1.5 |  | 10-05-2017 | 15-06-2017 | 55%
35 | Vishnu Mandir Marg | 1.5 |  | 20-05-2017 | 15-06-2017 | 30%
36 | Chelmsford Road | 0.39 | M/s Sakur Ahmad & Sons | 10-05-2017 | 31-05-2017 | 100% | 750 | 0 | Er. J.P. Sharma (Mob. 7838694446)
37 | Sadar Thana Road | 0.5 |  | 25-05-2017 | 15-06-2017 | 0%
38 | Desh Raj Bhatiya Marg | 0.83 |  | 25-05-2017 | 10-06-2017 | 0%
39 | Ram Kumar Marg | 0.45 |  | 25-05-2017 | 10-06-2017 | 0%
40 | Idgah Road | 1.09 |  | 25-05-2017 | 10-06-2017 | 0%
41 | G.B. Road | 0.5 |  | 26-05-2017 | 15-06-2017 | 0%
42 | S.N. Marg | 0.95 |  | 26-05-2017 | 15-06-2017 | 0%
43 | Qutub Road | 1.85 |  | 10-05-2017 | 31-05-2017 | 90%
Sadar Bazar Constituency
44 | Azad Market Road | 0.79 |  | 20-05-2017 | 10-06-2017 | 90%
45 | Bahadur Garth Road | 0.91 |  | 20-05-2017 | 10-06-2017 | 0%
46 | Pahari Dheeraj Road | 1.2 |  | 20-05-2017 | 10-06-2017 | 0%
47 | Foota Road | 0.25 |  | 25-05-2017 | 31-05-2017 | 0%
48 | New Rohtak Road | 1 |  | 25-05-2017 | 10-06-2017 | 30%
49 | Gali No. 10 | 0.8 |  | 01-06-2017 | 15-06-2017 | 0%
C&ND Road Division (M-413)
1 | Main Burari Road | 7.1 | Sh. Sher Singh | 27.01.2017 | 30.06.2017 | 80% | 8000 | 3800 | Sh. Anil Trehan / 8447001861
2 | BBM Road from Hakikat Nagar, Red Light to Mukherjee Nagar Bandh | 2.4 | Sh. Mangat Ram Gupta | 10.03.2017 | 30.06.2017 | 70%
3 | 60ft Road from Aggarwal Sweets to Nulife Hospital between BBM Road and Burari Road | 0.35 |  | 10.03.2017 | 30.06.2017 | 30% | 8000 | 3800 | Sh. Anil Trehan / 8447001861
4 | Sant Parmanand Colony Road | 0.9 |  | 10.03.2017 | 30.06.2017 | 80%
5 | Burari Road from Kingsway Camp to Road No. 50 | 3.5 |  | 10.03.2017 | 30.06.2017 | 25%
6 | Wazirabad Flyover | 1.06 |  | 10.03.2017 | 30.06.2017 | No Drain
7 | Munshi Ram Road | 0.5 |  | 10.03.2017 | 30.06.2017 | 20%
8 | Parmanand School Road | 0.33 |  | 10.03.2017 | 30.06.2017 | 35%
9 | Swaroop Nagar Road | 2.2 |  | 10.03.2017 | 30.06.2017 | 20%
10 | Police Chowki to Mandir Ortram Lane | 0.44 |  | 10.03.2017 | 30.06.2017 | 35%
11 | Tagore Park Main road | 0.9 |  | 10.03.2017 | 30.06.2017 | 40%
12 | Avtar Singh Marg (Nirankari colony) (Nirankari Colony Gate to culvert Burari Road towards Nirankari Sr. Sec. School) | 1.9 |  | 10.03.2017 | 30.06.2017 | 60%
13 | BBM Road to Jahangirpuri Drain | 0.4 |  | 10.03.2017 | 30.06.2017 | 35%
14 | Gandhi Vihar | 0.67 |  | 10.03.2017 | 30.06.2017 | 80%
15 | Road in Tagore Park from H. No. 213 to Gole Chakkar | 0.45 |  | 10.03.2017 | 30.06.2017 | 25%
16 | Road in tagore Park from H. No. 37 to H. No. 64 | 1.55 |  | 10.03.2017 | 30.06.2017 | 25%
17 | Magazine Road | 1.35 |  | 10.03.2017 | 30.06.2017 | 60%
18 | Road No. -46 | 0.3 |  | 10.03.2017 | 30.06.2017 | 20%
19 | Road No. -45 | 2.5 |  | 10.03.2017 | 30.06.2017 | 25%
20 | Parallel CC Road | 7.24 |  | 10.03.2017 | 30.06.2017 | 10%
21 | University Road from Mall Road to Petrol Pump Ward-10 | 1.58 | Sh. Jitender Kumar | 04.03.2017 | 30.06.2017 | 80% | 4350 | 3500
22 | Khalsa College road from Mall Road to Roop Nagar (Gurutegh Bahadur Road) | 1.3 |  | 04.03.2017 | 30.06.2017 | 80%
23 | Chhatra Marg Road from Mall Road to Malka Gunj Chowk | 1.65 |  | 04.03.2017 | 30.06.2017 | 70%
24 | Shiriya Mishra marg from Jai Jawan Tea Stall to Moris Nagar Thana | 0.42 |  | 04.03.2017 | 30.06.2017 | 85%
25 | Sudhir Bose Marg from chouburjja chowk to ACP Office | 1.25 |  | 04.03.2017 | 30.06.2017 | 80%
26 | Mahatma Gandhii Road (Ring Road) | 1.6 |  | 04.03.2017 | 30.06.2017 | 90%
27 | Road No. 48 | 1.92 |  | 04.03.2017 | 30.06.2017 | 85%
28 | Vijay Nagar main road from Royal Palace to E-11 Vijay Nagar | 0.75 |  | 04.03.2017 | 30.06.2017 | 70%
29 | Surjit Singh Marg Camp Chowk to Najafgarh Drain | 0.8 |  | 04.03.2017 | 30.06.2017 | 80%
30 | Bunglow Road from Roop Nagar round about to Hansraj College T-point on Chattra Marg | 0.65 |  | 04.03.2017 | 30.06.2017 | 85%
31 | Mandelia Road from GT Road to Bunglow Road | 0.7 |  | 04.03.2017 | 30.06.2017 | 70%
32 | Polo Road from Bhama Shah Road to Shani Mandir (Vijay Nagar) | 0.84 |  | 04.03.2017 | 30.06.2017 | 70%
33 | Polo Road from Jahanara Marg to shani Mandir Vijay Nagar | 0.3 |  | 04.03.2017 | 30.06.2017 | 70%
34 | Kalyan Vihar Road from 25 Kalyan Vihar to 1 No. Priyadarshni Vihar | 0.9 |  | 04.03.2017 | 30.06.2017 | 70%
35 | Gurmandi Road from Tripolia gate GT Road to H. NO. 264 Kalyan Vihar | 0.425 | Sh. Jitender Kumar | 04.03.2017 | 30.06.2017 | 60% | 4350 | 3500 | Sh. Anil Trehan / 8447001861
36 | Jahanara Road from Bhamashah Marg to vijay Nagar | 0.83 |  | 04.03.2017 | 30.06.2017 | 100%
37 | Satyawati Marg from Police Station Roop Nagar to Shakti Nagar Chowk | 0.52 |  | 04.03.2017 | 30.06.2017 | 100%
38 | Bhama Shah Road from Mall Road to GT Road Nanak Piao Gurudwara | 1.45 |  | 04.03.2017 | 30.06.2017 | 100%
39 | G.T. Road from Baraf Khana chowk to Clock Tower | 1.2 |  | 04.03.2017 | 30.06.2017 | 80%
40 | Roshnara Road from Pulbanash Metro Station to Hans Raj College. | 2.7 |  | 04.03.2017 | 30.06.2017 | 85%
41 | GT Road | 1.95 |  | 04.03.2017 | 30.06.2017 | 80%
42 | Inderchand Shastri Marg from Shakti Nagar Chowk to Swami Narayan Marg | 0.9 |  | 04.03.2017 | 30.06.2017 | 85%
43 | Timarpur road from Mall Road crossing to Wazirabad Crossing | 1.9 |  | 04.03.2017 | 30.06.2017 | 90%
44 | Lucknow Road from Mall Road to P.S. Timarpur | 1.7 |  | 04.03.2017 | 30.06.2017 | 90%
45 | Ring Road By-pass | 2.9 | M/s Satyam Construction Co. | 07.03.2017 | 30.06.2017 | 70% | 7300 | 3000
46 | Sachivalya Road | 1.6 |  | 07.03.2017 | 30.06.2017 | 75%
47 | IP Marg | 0.5 |  | 07.03.2017 | 30.06.2017 | 75%
48 | IG Slip Road | 0.58 |  | 07.03.2017 | 30.06.2017 | 70%
49 | Velodrome Road | 0.57 |  | 07.03.2017 | 30.06.2017 | 60%
50 | Vikas Marg | 0.5 |  | 07.03.2017 | 30.06.2017 | 50%
51 | Satyagrah Marg | 0.5 |  | 07.03.2017 | 30.06.2017 | 20%
52 | Azad Bhawan Road | 0.5 |  | 07.03.2017 | 30.06.2017 | 90%
53 | Ring Road Bhairon Road T-Jn. to Shanti Van Crossing | 4.2 |  | 07.03.2017 | 30.06.2017 | 60%
54 | JLN Marg (Delhi Gate) | 0.56 |  | 07.03.2017 | 30.06.2017 | 30%
55 | Ghata Masjid Road | 0.26 |  | 07.03.2017 | 30.06.2017 | 35%
56 | Mathura Road | 0.75 |  | 07.03.2017 | 30.06.2017 | 45%
57 | Bahadur Shah Zafar Marg | 2 |  | 07.03.2017 | 30.06.2017 | 50%
58 | Ring Road By-pass | 2.65 |  | 07.03.2017 | 30.06.2017 | 80%
59 | Court Road | 1.75 |  | 07.03.2017 | 30.06.2017 | 10%
60 | Club Road | 1.75 |  | 07.03.2017 | 30.06.2017 | 10%
61 | Under Hill Road | 0.69 |  | 07.03.2017 | 30.06.2017 | 20%
62 | Flag Staff Road | 0.425 |  | 07.03.2017 | 30.06.2017 | 30%
63 | Shamnath Marg | 1.3 |  | 07.03.2017 | 30.06.2017 | 80%
64 | Rajniwas Marg | 0.926 |  | 07.03.2017 | 30.06.2017 | 30%
65 | CNG Crematorium Road | 0.25 |  | 07.03.2017 | 30.06.2017 | 50%
66 | Ring Road | 2 |  | 07.03.2017 | 30.06.2017 | 70%
67 | Mahatma Gandhi Road | 4 |  | 07.03.2017 | 30.06.2017 | 70%
68 | Nishad Raj Marg | 0.55 |  | 07.03.2017 | 30.06.2017 | 50%