## South Zone
PWD Desilting Report (Preparedness for Monsoon)
DESILTING REPORT UNDER PWD MAINTENANCE SOUTH ZONE
AS ON 05.06.2017
Sl. No. | Name of Road / Drain | Length of Road (Km) | Contractor | Date of Start of De-silting | Date of completion (Ist Cycle) | % Drain cleaned (Lengthwise) | Estimate Qty. of silt (cum) | Qty. of silt lifted and disposed off (cum) | EE in charge / Mobile No.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
South West Road Division-1
1 | B.J. Marg | 1800 Mtr. | M/s Amocon | 15.05.2017 | 15.06.2017 | 25% | 500 | 135 | S K Sinha 9958469778
2 | Rao Tula Ram Marg (RTR Marg) | 3200 Mtr. | M/s Amocon | 15.04.2017 | 15.06.2017 | 80% | 400 | 400
3 | Zonal road No. 2 (Baba Balak Nath Marg) | 1750 Mtr. | M/s Amocon | 01.06.2017 | 15.06.2017 | - | -- | --
4 | Zonal Road No. 6 (Hare Krishna Mehto Marg) | 700 Mtr. | M/s Amocon | 01.06.2017 | 15.06.2017 | - | -- | --
5 | M.M.Road | 4250 Mtr. | Sh. T.P. Singh | 15.04.2017 | 15.06.2017 | 50% | 850 | 430
6 | Ullan Buttor Marg | 550 Mtr. | Sh. Vinay Shankar | 01.06.2017 | 15.06.2017 | - | -- | --
7 | Nelson Mandela Marg | 5200 Mtr. | Sh. T.P. Singh | 15.04.2017 | 15.06.2017 | 30% | 700 | 230
8 | Baba Gang Nath marg | 2150 Mtr. | Sh. T.P. Singh | 15.05.2017 | 15.06.2017 | 22% | 400 | 88
9 | Outer Ring Road | 6160 Mtr. | Sh. Vinay Shankar | 15.05.2017 | 15.06.2017 | 8% | 950 | 110
10 | Vatika Road (DPS Vasant Kunj to MM road) | 2150 Mtr. | Sh. Vinay Shankar | 15.04.2017 | 15.06.2017 | 10% | 350 | 95
11 | Africa Avenue (Road No.9) | 4400 Mtr. | Sh. Brijpal Singh | 18.05.2017 | 15.06.2017 | 16% | 600 | 90
12 | Tamil Sangam Marg | - | - | - | - | - | -- | --
13 | Major Som nath marg | - | - | - | - | - | -- | --
14 | Kafi Azami Marg | - | - | - | - | - | -- | --
15 | Church Road, R.K.Puram | - | - | - | - | - | -- | --
16 | Babu Genu Marg, R.K.Puram | - | - | - | - | - | -- | --
17 | Prem nath Dogra marg, R.K.Puram | - | - | - | - | - | -- | --
18 | Kama Koti Marg | - | - | - | - | - | -- | --
19 | Vivekanand Marg | - | - | - | - | - | -- | --
20 | Venketeshwar Marg | 2200 Mtr. | Sh. Brijpal Singh | 18.05.2017 | 15.06.2017 | 15% | 200 | 30
21 | Ring Road (Under DMRC) | - | - | - | - | - | -- | --
22 | Basant marg-I | - | - | - | - | - | -- | --
23 | Basant Marg-II | - | - | - | - | - | -- | --
24 | Poorvi Marg | - | - | - | - | - | -- | --
25 | Paschimi Marg | - | - | - | - | - | -- | --
26 | Munirka marg | - | - | - | - | - | -- | --
27 | A-9 Street Road | - | - | - | - | - | -- | --
28 | Ganga Ram Hospital Road | 1.08 | Sh. Bishwa Mohan Jha | -- |  | - | -- | --
29 | PUSA Road | 1.50 actual 2.00 KM | Sh. Bishwa Mohan Jha | -- |  | - | -- | --
30 | Shankar Road | 1.64 | Sh. Bishwa Mohan Jha | -- |  | - | -- | --
31 | Dr. K.S. Krishanan Marg | 0.92 | Sh. Bishwa Mohan Jha | 03.04.2017 | 15.06.2017 | 80% | 250 | 200
32 | PUSA Institute (IARI) Internal Road | 0.7 | Sh. Bishwa Mohan Jha | 03.04.2017 | 15.06.2017 | 10% | 200 | 20
33 | Dev Prakash Shastri marg (Road No. 25) | 4.45 | Sh. Bishwa Mohan Jha | 03.04.2017 | 15.06.2017 | 35% | 1200 | 420
34 | Girdhari Lal Goswami Marg (Road No. 89) | 3.65 | Sh. Bishwa Mohan Jha | 03.04.2017 | 15.06.2017 | 40% | 1000 | 400
35 | Ram Nath Vij Marg | 1.19 | Sh. Bishwa Mohan Jha | -- | -- | - | -- | -- | S K Sinha 9958469778
36 | O.P. Bharti Marg 1 | 0.54 | Sh. Bishwa Mohan Jha | -- | -- | - | -- | --
37 | O.P. Bharti Marg 2 | 0.76 | Sh. Bishwa Mohan Jha | 03.04.2017 | 15.06.2017 | 10% | 200 | 20
38 | O.P. Bharti Marg 3 | 0.18 | Sh. Bishwa Mohan Jha | 03.04.2017 | 15.06.2017 | 60% | 50 | 30
39 | O.P. Bharti Marg 4 | 0.42 | Sh. Bishwa Mohan Jha | -- | -- | - | -- | --
40 | Mahatma gandhi Marg (Ring Road) | 8.6 | Sh. Bishwa Mohan Jha | 04.04.2017 | 15.06.2017 | 60% | 1850 | 600
41 | NH-8 | 2.9 | Sh. Bishwa Mohan Jha | 04.04.2017 | 15.06.2017 | 55% | 400 | 300
42 | Upper Ridge Road (Vande Martram Marg) | No Drainage exit
43 | Road No. 36(Sat Guru Ram Singh Marg) | 3.4 | Sh. Rajnish Yadav | 25.03.2017 | 15.06.2017 | 40% | 1400 | 500
44 | MM Road | 6800 Mtr. | M/s R.R. construction | 10.05.2017 | 15.06.2017 | 50% | 1000 | 500
South West Road Division-II
45 | 60 futa Road | 0.45 | M/s Ram Charan Bansal | 21.03.2017 | 15.06.2017 | 40% | work to be executed by super sucker machine. NIL | 1) The drain is being cleaned by super sucker machines hence quanitity cannot be ascertained. And 2) Work of desiliting are in progress. Silt/Sludge/malba taken out from drain is being disposed out by the agency which will be informed after getting MCD receipt at a later date | Sh. J. P. Vashist M- 9971396164
46 | A Block Road | 0.2 |  | 21.03.2017 | 15.06.2017 | 100%
47 | Central School Road | 0.29 |  | 21.03.2017 | 15.06.2017 | 80%
48 | Dabri Road | 0.9 |  | 21.03.2017 | 15.06.2017 | 60%
49 | Fire Station Road | 0.4 |  | 21.03.2017 | 15.06.2017 | 80%
50 | Lal Sai Marg to Pankha Road | 0.65 |  | 21.03.2017 | 15.06.2017 | 60%
51 | Lal Sai Road | 2.5 |  | 21.03.2017 | 15.06.2017 | 30%
52 | Mall Road | 0.65 |  | 21.03.2017 | 15.06.2017 | 70%
53 | Old Pankha Road | 0.5 |  | 21.03.2017 | 15.06.2017 | 40%
54 | Pankha Road | 6.6 |  | 21.03.2017 | 15.06.2017 | 40%
55 | Ram Mandir Marg | 0.86 |  | 21.03.2017 | 15.06.2017 | -
56 | Road C-2/22 C-2/274 Road Janakpuri | 0.76 |  | 21.03.2017 | 15.06.2017 | 80%
57 | Road from Ram Mandir Marg to Mall Road (Connecting Road) | 0.3 |  | 21.03.2017 | 15.06.2017 | -
58 | Road From Shani Bazar to Ram Mandir Marg (Connecting Road) | 0.3 |  | 21.03.2017 | 15.06.2017 | -
59 | Shani Bazar Road | 0.65 |  | 21.03.2017 | 15.06.2017 | 60%
60 | Vidya Marg | 1.6 |  | 21.03.2017 | 15.06.2017 | 40%
61
62 | Nasir Pur Road | 0.34 | M/s Ram Charan Bansal | 21.03.2017 | 15.06.2017 | 80% | 750 MT |  | Sh. J. P. Vashist M- 9971396164
63 | Internal Road C-1 to C-1A Block | 0.3 |  | 21.03.2017 | 15.06.2017 | 60%
64 | Palam Dabri Road | 1.39 |  | 21.03.2017 | 15.06.2017 | 80%
65 | Paras Public schol to L-103 Pocket-4 Chankya Puri Binda Pur | 0.24 |  | 21.03.2017 | 15.06.2017 | 70%
66 | Peer Baba Road | 0.6 |  | 21.03.2017 | 15.06.2017 | 100%
67 | Police Station Road | 0.37 |  | 21.03.2017 | 15.06.2017 | 80%
68 | Pt. Vishnu Dutt Marg | 0.75 |  | 21.03.2017 | 15.06.2017 | 75%
69 | Sagar Pur Road | 2.54 |  | 21.03.2017 | 15.06.2017 | 80%
70 | Satguru Ram Singh Marg | 0.9 |  | 21.03.2017 | 15.06.2017 | 75%
71 | Link Road (Pt. Vishnu Dutt Marg to Satguru Ram Singh Marg) | 0.3 |  | 21.03.2017 | 15.06.2017 | 75%
72 | Najafgarh Nagloi Road | 2.6 | Sh. Surender Singh, | 21.03.2017 | 15.06.2017 | 60% | 382 MT | 1) The drain is being cleaned by super sucker machines hence quanitity cannot be ascertained. And 2) Work of desiliting are in progress. Silt/Sludge/malba taken out from drain is being disposed out by the agency which will be informed after getting MCD receipt at a later date | Sh. J. P. Vashist M- 9971396164
73 | Najafgarh Phirni | 2.2 |  | 21.03.2017 | 15.06.2017 | 40%
74 | Najafgarh Dhansa Road | 16.25 |  | 21.03.2017 | 15.06.2017 | 60%
75
76 | Najafgarh Dechaun Road | 4.55 | M/s Anmol Infratech Pvt Ltd. | 21.03.2017 | 15.06.2017 | 60% | work to be executed by super sucker machine. NIL
77 | Najafgarh Jaroda Road | 7.2 |  | 21.03.2017 | 15.06.2017 | 35%
78 | Najafgarh Kakrola Road | 4 |  | 21.03.2017 | 15.06.2017 | 100%
79
80
81 | Laxmi Chand Marg | 11.3 | Sh. Surender Singh, | 21.03.2017 | 15.06.2017 | 15% | 1090 MT
82 | Prithvi Singh Dagar Marg | 11.2 |  | 21.03.2017 | 15.06.2017 | 15%
83
84 | Jhatikara Morh to Jhatikara | 8.55 | Sh. Surender Singh, | 21.03.2017 | 15.06.2017 | 88% | 890 MT
85 | Najafgarh Bijwasan Road | 11.25 |  | 21.03.2017 | 15.06.2017 | 15%
86
87 | Bhartal Road | 3.48 | M/s Anmol Infratech Pvt Ltd. | 21.03.2017 | 15.06.2017 | not required | not required
88 | Goyla Deenpur Road | 4.2 |  | 21.03.2017 | 15.06.2017 | nil
89 | Kapashera Bijwasan Road | 3.8 |  | 21.03.2017 | 15.06.2017 | 35% | 1470 MT
90 | Link Road | 1.7 |  | 21.03.2017 | 15.06.2017 | 70%
91 | Old DG Road | 2.5 |  | 21.03.2017 | 15.06.2017 | nil
South-East Road Division-1
92 | Raja Dheer Sain marg | 2.38 | Sh. Jagdish Prasad Meena | 01.05.2017 | 15.06.2017 | 80% | 511.7 | 262 | Er. Virendra Singh, 9868284746
93 | Kalka Devi Marg | 1.12 | do | 01.05.2017 | 15.06.2017 | 20% | 346.21 | 69
94 | Gaptain Gaur Marg | 2.15 | do | 01.05.2017 | 15.06.2017 | 5% | 1272.15 | 63.6
95 | Road No. 3 Andrews Ganj | 0.75 | do | 01.05.2017 | 15.06.2017 | 5% | 18.48 | 0
96 | Road No. 7 Andrews Ganj | 0.24 | do | 01.05.2017 | 15.06.2017 | 5% | 5.96 | 0
97 | Road No. 5 Andrews Ganj | 0.13 | do | 01.05.2017 | 15.06.2017 | 5% | 13.28 | 0
98 | Road No. 2 Andrews Ganj | 0.4 | do | 01.05.2017 | 15.06.2017 | 5% | 6.76 | 0.33
99 | Road No. 6 Andrews Ganj | 0.24 | do | 01.05.2017 | 15.06.2017 | 5% | 12.48 | 0
100 | Kalka Devi Marg to Banglow Road | 0.47 | do | 01.05.2017 | 15.06.2017 | 5% | 166.99 | 8.35
101 | Central Road to Back Ring Road to Lajpat Nagar-IV | 0.35 | do | 01.05.2017 | 15.06.2017 | 5% | 158.19 | 7.91
102 | Dr. Moti Lal Jotwani Road to Lajpat Nagar-IV | 0.49 | do | 01.05.2017 | 15.06.2017 | 5% | 195.28 | 9.76
103 | Theka Road S.N. Puri | 0.25 | do | 01.05.2017 | 15.06.2017 | 5% | 89.74 | 4.49
104 | Shri Niwas Puri internal Road MCD Store Round about via Maternity Home. | 0.91 | do | 01.05.2017 | 15.06.2017 | 5% | 279.98 | 14
105 | S.N. Puri internal Road opposite Police Post S.N. Puri | 0.15 | do | 01.05.2017 | 15.06.2017 | 5% | 11.23 | 0
106 | S.N. Puri internal Road Post office to CPWD Via Jal Board | 0.54 | do | 01.05.2017 | 15.06.2017 | 5% | 216.92 | 10.85
107 | Banglow Road to Gidwani Marg Lajpat | 0.12 | do | 01.05.2017 | 15.06.2017 | 5% | 39.74 | 1.98
108 | S.N. Puri Main Road from Cambridge School to CTC | 1.4 | do | 01.05.2017 | 15.06.2017 | 5% | 370.94 | 18.55
109 | Mathura Road | 2.00 km | M/s TripurariPrasad Singh | 2017-04-20 | 15.06.2017 | 10% | 900 | 90
110 | C.V. Raman Marg | 2.00 km | -do- | 2017-05-01 | 15.06.2017 | 5% | 750 | 38
111 | M.P. Road | 1.00 km | -do- | 2017-05-10 | 15.06.2017 | 10% | 320 | 32 | Er. Virendra Singh, 9868284746
112 | Gurudwara Road | 1.20 km | -do- | 2017-05-10 | 15.06.2017 | 2% | 260 | 5
113 | MMA Road | 3.00 km | -do- | 2017-05-12 | 15.06.2017 | 2% | 360 | 7
114 | Sukhdev Vihar | 1.00 km | -do- | 2017-05-12 | 15.06.2017 | 0% | 280 | 0
115 | Mata Mandir Road | 600 m | -do- | 2017-05-15 | 15.06.2017 | 0% | 180 | 0
116 | Ring Road from AIIMS to Bhairon Road 'T' Point | 9.75 | M/s Tripiurari Prasad Singh | 2017-03-31 | 15.06.2017 | 40% | 1936 | 390
117 | Feroz Gandhi Road, Lajpat Nagar | 1.05 | _do_ | _do_ | 15.06.2017 | 30% | 208 | 50
118 | Vir Savarkar Marg, Lajpat Nagar | 1.05 | _do_ | _do_ | 15.06.2017 | 30% | 208 | 50
119 | Shiv Mandir Marg from Zonal Office to Ring Road | 0.85 | _do_ | _do_ | 15.06.2017 | 40% | 169 | 30
120 | Bhisma Pitamah Road | 2.6 | _do_ | _do_ | 15.06.2017 | 30% | 516 | 60
121 | Road from B.P.Marg to Round about Defence Colony | 0.156 | _do_ | _do_ | 15.06.2017 | 40% | 31 | 20
122 | Josef Brass Titoo Marg (B.R.T.) (Lajpat Nagar Metro Station to Ambedkar Nagar) | 6.25 | _do_ | _do_ | 15.06.2017 | 30% | 1241 | 500
123 | 2nd Entry (Sarai Kale Khan Red Light to Nizamuddin Railway Station) | 0.6 | _do_ | _do_ | 15.06.2017 | 30% | 119 | 50
124 | Bhairon Road | 0.98 | _do_ | _do_ | 15.06.2017 | 40% | 195 | 40
125 | Mathura Roads from DPS ro Ashram Chowk | 2.65 | Sh. Chander Pal | 15.04.2017 | 15.06.2017 | 12% | 650 | 40
126 | Hospital Road, Bhogal | 0.56 | Sh. Chander Pal | 15.04.2017 | 15.06.2017 | 5% | 75 | 5
127 | East Nixzamuddin Peripheral Road from Mathura Road to Railway Station, East Nizamudin | 0.7 | Sh. Chander Pal | 15.04.2017 | 15.06.2017 | 5% | 85 | 5
128 | Rajdoot Hotal to Preet Place, Jangpura, Extn | 0.2 | Sh. Chander Pal | 15.04.2017 | 15.06.2017 | 5% | 30 | 5
129 | Preet Place to Nizamuddin Railway Station, Jangura | 0.7 | Sh. Chander Pal | 15.04.2017 | 15.06.2017 | 5% | 85 | 3
130 | School Road, Jangpura Extn. | 0.38 | Sh. Chander Pal | 15.04.2017 | 15.06.2017 | 5% | 45 | 5
131 | Neela Gumbad to Lodhi Flyover, Nizamudin Basti | 0.2 | Sh. Chander Pal | 15.04.2017 | 15.06.2017 | 15% | 85 | 7
132 | Maharani Bagh from Manokarma Mandir to Sunlight Colony | 0.55 | Sh. Chander Pal | 15.04.2017 | 15.06.2017 | 50% | 125 | 35
133 | IV th Avenue Road, Lodhi Colony | 1.22 | Sh. Chander Pal | 15.04.2017 | 15.06.2017 | 15% | 350 | 28
134 | V th Avenue Road, Lodhi Colony | 1 | Sh. Chander Pal | 15.04.2017 | 15.06.2017 | 5% | 120 | 3
135 | X Road between Block No. 18 & 14 Lodhi Colony | 0.16 | Sh. Chander Pal | 15.04.2017 | 15.06.2017 | 0% | 30 | -
136 | Lodhi Road Indian Habitat Centre to Lodhi Flyover | 1.76 | Sh. Chander Pal | 15.04.2017 | 15.06.2017 | 5% | 475 | 14
137 | X Road between D-1 & C-2 (F-24) Lodhi Colony | 0.16 | Sh. Chander Pal | 15.04.2017 | 15.06.2017 | 0% | 30 | -
138 | X Road btween Block No. C-2 (176) & C-2 (177) Lodhi Colony | 0.16 | Sh. Chander Pal | 15.04.2017 | 15.06.2017 | 0% | 30 | -
139 | B.P.Marg to Coffee House Lodhi Colony | 0.35 | Sh. Chander Pal | 15.04.2017 | 15.06.2017 | 5% | 75 | 5
140 | F-1 Lodhi Colony to B.P. Flyover, Lodhi Colony | 0.24 | Sh. Chander Pal | 15.04.2017 | 15.06.2017 | 5% | 25 | 5
141 | Verdhman Marg from IV-th Avenue Road, B.P.Marg , Lodhi Colony | 0.35 | Sh. Chander Pal | 15.04.2017 | 15.06.2017 | 0% | 90 | -
142 | Kushak Nallah to Sewa Nagar flyover , Sewa Nagar | 0.7 | Sh. Chander Pal | 15.04.2017 | 15.06.2017 | 60% | 200 | 100
143 | Kushak Nallah to CPWD Enquiry (Near O Block), Sewa Nagar | 0.3 | Sh. Chander Pal | 15.04.2017 | 15.06.2017 | 60% | 125 | 65
144 | Hanuman Mandir to Sewa Nagar Flyover, Sewa Nagar | 0.46 | Sh. Chander Pal | 15.04.2017 | 15.06.2017 | 60% | 125 | 65
145 | Railway Phatak to Subhasg Bazar, Sewa Nagar | 0.258 | Sh. Chander Pal | 15.04.2017 | 15.06.2017 | 5% | 35 | 5
146 | BRT from Bhairon Road T- Point to Defence Colony Flyover | 3 | Sh. Chander Pal | 15.04.2017 | 15.06.2017 | 25% | 285 | 75
147 | Sunder Nagar Peripherial Road, Sunder Nagar | 1.1 | Sh. Chander Pal | 15.04.2017 | 15.06.2017 | 10% | 150 | 9
148 | Ratan Lal Sahdev Marg, Defence Colony | 0.978 | Sh. Chander Pal | 15.04.2017 | 15.06.2017 | 60% | 225 | 110
149 | Gang Nath Marg, Safdurjunf Flyover to round about near Khushak Nallah | 0.625 | Sh. Chander Pal | 15.04.2017 | 15.06.2017 | 5% | 150 | 5
South-East Road Division-2
150 | SA Road | 5.46 Km | Sh. Suresh | 27.03.2017 | 15.06.2017 | 30% | 2400 | 480 | Er. R.S. Garg, 9818656184
151 | Maharaja Agarsen Marg | 0.50 Km | Sh. Suresh | 27.03.2017 | 15.06.2017 | 40% | 2400 | 540
152 | Baba Fateh Singh Marg | 1.00 Km | Sh. Suresh | 27.03.2017 | 15.06.2017 | 0% | 380 | 0
153 | Hans Raj Sethi Marg | 1.70 Km | Sh. Suresh | 27.03.2017 | 15.06.2017 | 10% | 350 | 50
154 | A Block Double Storey (EPDP to Hans Raj Sethi Marg) | 0.45 Km | Sh. Suresh | 27.03.2017 | 15.06.2017 | 0% | 50 | 0
155 | Jaitpur Road | 1.25 Km | Sh. Naresh Kumar | 04.12.2016 | 15.06.2017 | 90% | 800 | 100 cum
156 | Jaitpur Road -Meethapur Chowk to Gurudwara | 1.21 Km | Sh. Naresh Kumar | 04.12.2016 | 15.06.2017 | 85% |  | 100 cum
157 | Higher Secondary School Meethapur | 0.87 Km | Sh. Naresh Kumar | 04.12.2016 | 15.06.2017 | 95% |  | 500 cum
158 | Maharaja Agarsen marg | 0.80 Km | M/s R.N. Construction Co | 30.03.2017 | 15.06.2017 | 95% | 700 | 550 cum
159 | Madanpur Khadar Road | 1.20 Km | M/s R.N. Construction Co | 30.03.17 | 15.06.2017 | 40% | 400 | 150 cum
160 | Sarita Vihar Road | 1.10 Km | M/s R.N. Construction Co | 30.03.17 | 15.06.2017 | 60% | 550 | 310 cum
161 | Road No. 13 A | 2.50 Km | M/s R.N. Construction Co | 30.03.17 | 15.06.2017 | 60% | 2000 | 700 cum
162 | Mathura Road | 5.50 Km | M/s R.N. Construction Co | 30.03.17 | 15.06.2017 | 40% | 3200 | 800 cum
163 | Lala Lajpat Rai Marg to Raja Dheer Sen Marg | 0.30 Km | M/s Gaurav Construction Co. | 30.03.17 | 15.06.2017 | 50% | 170 | 20
164 | Guru Nanak Market to lala Lajpat Rai Marg | 0.57 Km | M/s Gaurav Construction Co. | 2017-03-30 | 15.06.2017 | 50% | 180 | 90
165 | Nandi Vithi Marg | 0.73 Km | M/s Gaurav Construction Co. | 30.03.17 | 15.06.2017 | 25% | 150 | 40
166 | Link Road | 0.58 Km | M/s Gaurav Construction Co. | - | 15.06.2017 | 55% | 250 | 100 cum
167 | Road from BRT to Hans Raj Gupta Marg | 0.34 Km | M/s Gaurav Construction Co. | 30.3.17 | 15.06.2017 | 50% | 50 | 25
168 | Hans Raj Gupta Marg | 2.65 Km | M/s Gaurav Construction Co. | - | 15.06.2017 | 30% | 700 | 150 cum
169 | Lala Lajpat Rai Marg | 2.4 Km | M/s Gaurav Construction Co. | - | 15.06.2017 | 20% | 180 | 50 cum
170 | Guru Harkishan Public School to Nehru Place | 0.27 Km | M/s Gaurav Construction Co. | 2017-03-30 | 15.06.2017 | 90% | 100 | 90
171 | R Block GK-1 signal to Outer Ring Road | 0.58 Km | M/s Gaurav Construction Co. | 2017-03-30 | 15.06.2017 | 80% | 96 | 77
172 | Outer Ring Road | 2.10 Km | M/s Gaurav Construction Co. | 2017-03-30 | 15.06.2017 | 50% | 1240 | 620
173 | Road from Vipin Chander Pal Marg to Police Station CR Park | 0.37 Km | M/s Gaurav Construction Co. | 30.03.17 | 15.06.2017 | 15% | 96 | 16
174 | Savitri Cinema Road | 3.10 Km | M/s Gaurav Construction Co. | 2017-03-30 | 15.06.2017 | 60% | 1300 | 705
175 | Surya Sen Marg | 0.75 Km | M/s Gaurav Construction Co. | 30.03.17 | 15.06.2017 | 95% | 225 | 202
176 | MB Road | 5.25 Km | M/s Buland Construction | 28.03.17 | 15.06.2017 | 5% | 2000 | 70 cum
177 | Guru Ravi Dass Marg | 3.75 Km | M/s Buland Construction | 28.03.17 | 15.06.2017 | 85% | 3300 | 1550 cum
178 | DDA Market Road | 0.43 Km | M/s Buland Construction | 28.03.17 | 15.06.2017 | 10% | 200 | 22 cum
179 | KPS Road | 0.64 KM | M/s Buland Construction | 28.03.17 | 15.06.2017 | 30% | 150 | 55 cum | Er. R.S. Garg, 9818656184
180 | Suraj Kund Road | 0.60 Km | M/s Buland Construction | 28.03.17 | 15.06.2017 | 5% | 300 | 15 cum
181 | Road No13 | 2.7 Km | M/s Buland Construction | 10.4.2017 | 15.06.2017 | 80% | 2450 | 1450 cum
182 | EPDP Road | 1.80 km | M/s Buland Construction | 10.04.2017 | 15.06.2017 | 0% | 800 | 0
183 | Outer Ring Road | 3.2 Km | M/s Buland Construction | 10.04.2017 | 15.06.2017 | 35% | 1500 | 100 cum
184 | Gurudwara Road GK-II | 1.70 Km | M/s Buland Construction | 10.04.2017 | 15.06.2017 | 90% | 208 | 0
185 | Vipin Chander Pal Marg | 1.50 Km | M/s Buland Construction | 10.04.2017 | 15.06.2017 | 0% | 720 | 0
South Road Division-1
186 | M.B. Road | 5.25 | Nasir Ali | 16.03.2017 | 15.06.2017 | 70% | 2150 | 880 | Sh. Narender Mahajan 9933331859
187 | Devli Road | 2 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 15.06.2017 | 20%
188 | IGNOU Road | 2.9 | M/s RichCon Engineering Company | 16.03.2017 | 15.06.2017 | 100%
189 | Maharishi Balmiki Marg | 1.8 | Nasir Ali | 16.03.2017 | 15.06.2017 | 90%
190 | Durbal Nath Marg | 1.09 | Nasir Ali | 16.03.2017 | 15.06.2017 | 70%
191 | Raja Ram Marg | 0.89 | Nasir Ali | 16.03.2017 | 15.06.2017 | 85%
192 | H Block Dakshin Puri Road | 0.4 | Nasir Ali | 16.03.2017 | 15.06.2017 | 40%
193 | Firni Road | 1 | Nasir Ali | 16.03.2017 | 15.06.2017 | 60%
194 | West End Marg | 0.8 | Nasir Ali | 16.03.2017 | 15.06.2017 | 65%
195 | Old MB Road | 1 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 15.06.2017 | 95%
196 | 100 Foota Road Chattarpur | 1.4 | Ravi Tanwar | 16.03.2017 | 15.06.2017 | 40% | 840 | 350
197 | 60 Foota Road | 0.9 | Ravi Tanwar | 16.03.2017 | 15.06.2017 | 40%
198 | SSN Marg | 10.5 | Ravi Tanwar | 16.03.2017 | 15.06.2017 | 40%
199 | Gadai Pur Band Road | 3 | Ravi Tanwar | 16.03.2017 | 15.06.2017 | 40% | 765 | 335
200 | Mandi Road | 8 | Ravi Tanwar | 16.03.2017 | 15.06.2017 | 45%
201 | Dera Bhati Road | 5.76 | Ravi Tanwar | 16.03.2017 | 15.06.2017 | 35%
202 | M.G. Road | 7.5 | Ravi Tanwar | 16.03.2017 | 15.06.2017 | 25%
203 | Aya Nagr Road | 0.6 | Ravi Tanwar | 16.03.2017 | 15.06.2017 | 80%
204 | Press Enclave (BRT to Saket Court) | 4 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 15.06.2017 | 50% | 3200 | 1545
205 | Family Court Road | 0.9 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 15.06.2017 | 55%
206 | Pushp Vihar (Internal Road) | 4 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 15.06.2017 | 52%
207 | H. Block Road | 1 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 15.06.2017 | 55%
208 | Road in front of H.No. C-11 to C-20 Malviya Nagar | 0.11 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 15.06.2017 | 50%
209 | Appjay School Road | 1.3 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 15.06.2017 | 50%
210 | Shekh Sarai Phase-1 | 0.3 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 15.06.2017 | 50%
211 | Khirki Road | 0.85 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 15.06.2017 | 50%
212 | NBCC Plaza Road | 1.1 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 15.06.2017 | 50%
213 | Birla Vidya Niketan | 1 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 15.06.2017 | 55% |  |  | Sh. Narender Mahajan 9933331859
214 | Mandir Marg | 1.2 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 15.06.2017 | 55%
215 | Pramod Mahajan Marg | 0.89 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 15.06.2017 | 50%
216 | Main Road Sector-1, Pushp Vihar | 0.75 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 15.06.2017 | 100%
217 | Pankaj Jewel Marg, Pushp Vihar | 1.1 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 15.06.2017 | 100%
218 | Asian Market Road in Pushp Vihar | 0.45 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 15.06.2017 | 55%
219 | Metro Enclave Road in Pushp Vihar | 0.45 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 15.06.2017 | 55%
220 | Road between DDA Flat Masjid Moth Ph-II and Jahapanah Forest | 0.5 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 15.06.2017 | 55%
221 | Road in front of Mother International School | 0.54 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 15.06.2017 | 55%
222 | J Block Saket | 0.89 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 15.06.2017 | 55%
223 | Apeejay School Road (Gurudwara to J Block Road). | 0.3 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 15.06.2017 | 55%
South Road-2 Division
224 | August Kranti Marg. | 3.24 | M/s Vision Constructions | 02.03.2017 | 15.06.2017 | 68% | 3064 | 2089 | Sh. Jagdish Prasad 9560207879
225 | Balbir Saxena Marg | 0.8
226 | Ch. Dilip Singh Marg, P.S. Hauz Khas | 0.6
227 | Mahinder Singh Jain Marg Road / Gautam Nagar Road | 1.2
228 | P-Block Road from August Kranti Marg via jain Mandir & Dustbin to August Kranti Marg. | 0.34
229 | Sudarshan Cinema Road. | 0.72
230 | Gautam Nagar Road | 0.5
231 | Road form Balbir Sxsena Marg to Ch. Dalip SinghMarg (NIFT Road), Hauz Khas | 0.6
232 | Road form August Kranti marg to Aurobindo Marg (Subash Chopra Road), Hauz Khas | 0.79
233 | Asiad Village peripheral road | 3
234 | Siri Fort Road | 1.2
235 | Sri Aurobindo Marg | 5 | M/s Samridhi Construction, | 02.03.2017 | 15.06.2017 | 90% | 5768 | 5191
236 | Outer Ring Road ( IIT Flyover to Africa Avenue Junction) | 1.8
237 | Ch. Jhandu Singh Marg | 1.53
238 | Ch. Harsukh Marg | 1.83
239 | Ch. Hukum Chand Marg | 0.6
240 | Green Park Market Road | 1
241 | Narender Kumar Pandey Marg | 1.16
242 | Hauz Khas Village Road | 0.9
243 | Ring Road (Safdarjung to Hyatt) | 2.1
244 | Anuvart Marg | 2.5 | Sh. Jagdish Prasad Meena | 02.03.2017 | 15.06.2017 | 83.33% | 4212 | 3510
245 | Aruna Asaf Ali Road | 3.5
246 | Vedant Deshika Marg | 0.7 | [6 empty] | Sh. Jagdish Prasad 9560207879
247 | B-1 Telephone Exchange Road,Vasant Kunj (Mahipalpur Road to B-5 & B-6 Road) | 0.6
248 | DAV School Road Vasant Kunj | 0.55
249 | Shiv Mandir to B-5 & B-6 Road) | 0.3
250 | D-1 & D-2 Road, Vasant Kunj | 0.24
251 | Sports Complex Road D-2,Vasant Kunj | 0.7
252 | Shaheed Jeet Singh | 2.1
253 | Road from B 15/7 to BSES Office,Q.I.A. | 0.3
254 | Peripheral Road of A Block of Q.I.A. | 0.41
255 | Peripheral Road of C and B Block of Q.I.A. | 1.57
256 | Outer Ring Road (Panchsheel to IIT Gate) | 1 | Sh. Narendra Singh Yadav | 02.03.2017 | 15.06.2017 | 85% | 1085 | 922
257 | Outer Ring Road (Chirag Delhi to Panchsheel) | 3.7
258 | A-1 Block, Panchsheel Enclave Road | 0.5
259 | S-Bend Road (Maharishi Dayanand Marg) | 1.8 | Sh. Narendra Singh Yadav | 02.03.2017 | 15.06.2017 | 77% | 1680 | 1288
260 | Shivalik Road (Basant Kaur Marg) | 1.86
261 | Guru Govind Singh Marg | 1.2