## South Zone
PWD Desilting Report (Preparedness for Monsoon)
DESILTING UNDER PWD MAINTENANCE SOUTH ZONE AS ON 19.06.2017
Sl. No. | Name of Road / Drain | Length of Road (Km) | Contractor | Date of Start of De-silting | Date of completion (Ist Cycle) | % Drain cleaned (Lengthwise) | Estimate Qty. of silt (cum) | Qty. of silt lifted and disposed off (cum) | EE in charge / Mobile No.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
South-East Road-I
1 | Raja Dheer Sain marg | 2.38 | Sh. Jagdish Prasad Meena | 01.05.2017 | 30.06.2017 | 90% | 511.7 | 460 | Er. Virendra Singh 9868284746
2 | Kalka Devi Marg | 1.12 |  | 01.05.2017 | 30.06.2017 | 90% | 346.21 | 310
3 | Gaptain Gaur Marg | 2.15 |  | 01.05.2017 | 30.06.2017 | 90% | 1272.15 | 826.9
4 | Road No. 3 Andrews Ganj | 0.75 |  | 01.05.2017 | 30.06.2017 | 5% | 18.48 | 0.92
5 | Road No. 7 Andrews Ganj | 0.24 |  | 01.05.2017 | 30.06.2017 | 5% | 5.96 | 0.3
6 | Road No. 5 Andrews Ganj | 0.13 |  | 01.05.2017 | 30.06.2017 | 5% | 13.28 | 0.66
7 | Road No. 2 Andrews Ganj | 0.4 |  | 01.05.2017 | 30.06.2017 | 5% | 6.76 | 0.33
8 | Road No. 6 Andrews Ganj | 0.24 |  | 01.05.2017 | 30.06.2017 | 5% | 12.48 | 0.62
9 | Kalka Devi Marg to Banglow Road | 0.47 |  | 01.05.2017 | 30.06.2017 | 5% | 166.99 | 8.35
10 | Central Road to Back Ring Road to Lajpat Nagar-IV | 0.35 |  | 01.05.2017 | 30.06.2017 | 5% | 158.19 | 7.91
11 | Dr. Moti Lal Jotwani Road to Lajpat Nagar-IV | 0.49 |  | 01.05.2017 | 30.06.2017 | 5% | 195.28 | 9.76
12 | Theka Road S.N. Puri | 0.25 |  | 01.05.2017 | 30.06.2017 | 5% | 89.74 | 4.49
13 | Shri Niwas Puri internal Road MCD Store Round about via Maternity Home. | 0.91 |  | 01.05.2017 | 30.06.2017 | 5% | 279.98 | 14
14 | S.N. Puri internal Road opposite Police Post S.N. Puri | 0.15 |  | 01.05.2017 | 30.06.2017 | 5% | 11.23 | 0.56
15 | S.N. Puri internal Road Post office to CPWD Via Jal Board | 0.54 |  | 01.05.2017 | 30.06.2017 | 5% | 216.92 | 10.85
16 | Banglow Road to Gidwani Marg Lajpat | 0.12 |  | 01.05.2017 | 30.06.2017 | 5% | 39.74 | 1.98
17 | S.N. Puri Main Road from Cambridge School to CTC | 1.4 |  | 01.05.2017 | 30.06.2017 | 5% | 370.94 | 18.55
18 | Mathura Road | 2 | M/s TripurariPrasad Singh | 2017-04-20 | 30.06.2017 | 40% | 900 | 90
19 | C.V. Raman Marg | 2 |  | 2017-05-01 | 30.06.2017 | 30% | 750 | 38
20 | M.P. Road | 1 |  | 2017-05-10 | 30.06.2017 | 30% | 320 | 32
21 | Gurudwara Road | 1.2 |  | 2017-05-10 | 30.06.2017 | 30% | 260 | 5
22 | MMA Road | 3 |  | 2017-05-12 | 30.06.2017 | 20% | 360 | 7
23 | Sukhdev Vihar | 1 |  | 2017-05-12 | 30.06.2017 | 10% | 280 | 0
24 | Mata Mandir Road | 0.6 |  | 2017-05-15 | 30.06.2017 | 30% | 180 | 0
25 | Ring Road from AIIMS to Bhairon Road 'T' Point | 9.75 |  | 31.03.2017 | 30.06.2017 | 40% | 1935.67 | 390
26 | Feroz Gandhi Road, Lajpat Nagar | 1.05 |  | 31.03.2017 | 30.06.2017 | 30% | 208.46 | 50
27 | Vir Savarkar Marg, Lajpat Nagar | 1.05 |  | 31.03.2017 | 30.06.2017 | 30% | 208.46 | 50
28 | Shiv Mandir Marg from Zonal Office to Ring Road | 0.85 |  | 31.03.2017 | 30.06.2017 | 40% | 168.75 | 30
29 | Bhisma Pitamah Road | 2.6 |  | 31.03.2017 | 30.06.2017 | 30% | 516.18 | 60
30 | Road from B.P.Marg to Round about Defence Colony | 0.156 | M/s Tripiurari Prasad Singh | 31.03.2017 | 30.06.2017 | 40% | 30.97 | 20 | Er. Virendra Singh 9868284746
31 | Josef Brass Titoo Marg (B.R.T.) (Lajpat Nagar Metro Station to Ambedkar Nagar) | 6.25 |  | 31.03.2017 | 30.06.2017 | 30% | 1240.81 | 500
32 | 2nd Entry (Sarai Kale Khan Red Light to Nizamuddin Railway Station) | 0.6 |  | 31.03.2017 | 30.06.2017 | 30% | 119.12 | 50
33 | Bhairon Road | 0.98 |  | 31.03.2017 | 30.06.2017 | 40% | 194.56 | 40
34 | Mathura Roads from DPS ro Ashram Chowk | 2.65 | Sh. Chander Pal | 31.03.2017 | 30.06.2017 | 75% | 650 | 380
35 | Hospital Road, Bhogal | 0.56 |  | 15.04.2017 | 30.06.2017 | 5% | 75 | 5
36 | East Nixzamuddin Peripheral Road from Mathura Road to Railway Station, East Nizamudin | 0.7 |  | 15.04.2017 | 30.06.2017 | 40% | 85 | 5
37 | Rajdoot Hotal to Preet Place, Jangpura, Extn | 0.2 |  | 15.04.2017 | 30.06.2017 | 5% | 30 | 10
38 | Preet Place to Nizamuddin Railway Station, Jangura | 0.7 |  | 15.04.2017 | 30.06.2017 | 5% | 85 | 3
39 | School Road, Jangpura Extn. | 0.38 |  | 15.04.2017 | 30.06.2017 | 5% | 45 | 5
40 | Neela Gumbad to Lodhi Flyover, Nizamudin Basti | 0.2 |  | 15.04.2017 | 30.06.2017 | 60% | 85 | 40
41 | Maharani Bagh from Manokarma Mandir to Sunlight Colony | 0.55 |  | 15.04.2017 | 30.06.2017 | 60% | 125 | 40
42 | IV th Avenue Road, Lodhi Colony | 1.22 |  | 15.04.2017 | 30.06.2017 | 30% | 350 | 100
43 | V th Avenue Road, Lodhi Colony | 1 |  | 15.04.2017 | 30.06.2017 | 5% | 120 | 3
44 | X Road between Block No. 18 & 14 Lodhi Colony | 0.16 |  | 15.04.2017 | 30.06.2017 | 5% | 30 | 3
45 | Lodhi Road Indian Habitat Centre to Lodhi Flyover | 1.76 |  | 15.04.2017 | 30.06.2017 | 60% | 475 | 150
46 | X Road between D-1 & C-2 (F-24) Lodhi Colony | 0.16 |  | 15.04.2017 | 30.06.2017 | 5% | 30 | 3
47 | X Road btween Block No. C-2 (176) & C-2 (177) Lodhi Colony | 0.16 |  | 15.04.2017 | 30.06.2017 | 5% | 30 | 3
48 | B.P.Marg to Coffee House Lodhi Colony | 0.35 |  | 15.04.2017 | 30.06.2017 | 5% | 75 | 5
49 | F-1 Lodhi Colony to B.P. Flyover, Lodhi Colony | 0.24 |  | 15.04.2017 | 30.06.2017 | 5% | 25 | 5
50 | Verdhman Marg from IV-th Avenue Road, B.P.Marg , Lodhi Colony | 0.35 |  | 15.04.2017 | 30.06.2017 | 5% | 90 | 5
51 | Kushak Nallah to Sewa Nagar flyover , Sewa Nagar | 0.7 |  | 15.04.2017 | 30.06.2017 | 65% | 200 | 110
52 | Kushak Nallah to CPWD Enquiry (Near O Block), Sewa Nagar | 0.3 |  | 15.04.2017 | 30.06.2017 | 65% | 125 | 70
53 | Hanuman Mandir to Sewa Nagar Flyover, Sewa Nagar | 0.46 |  | 15.04.2017 | 30.06.2017 | 70% | 125 | 75
54 | Railway Phatak to Subhasg Bazar, Sewa Nagar | 0.258 |  | 15.04.2017 | 30.06.2017 | 5% | 35 | 5
55 | BRT from Bhairon Road T- Point to Defence Colony Flyover | 3 |  | 15.04.2017 | 30.06.2017 | 25% | 285 | 75
56 | Sunder Nagar Peripherial Road, Sunder Nagar | 1.1 | Sh. Chander Pal | 15.04.2017 | 30.06.2017 | 60% | 150 | 18 | Er. Virendra Singh 9868284746
57 | Ratan Lal Sahdev Marg, Defence Colony | 0.978 |  | 15.04.2017 | 30.06.2017 | 60% | 225 | 110
58 | Gang Nath Marg, Safdurjunf Flyover to round about near Khushak Nallah | 0.625 |  | 15.04.2017 | 30.06.2017 | 5% | 150 | 5
South-East Road-II
59 | SA Road | 5.46 | Sh. Suresh | 27.03.2017 | 30.06.2017 | 45% | 2400 | 960 | Er. R.K. Sharma 9818615817
60 | Maharaja Agarsen Marg | 0.5 |  | 27.03.2017 | 30.06.2017 | 30% | 100 | 30
61 | Baba Fateh Singh Marg | 1 |  | 27.03.2017 | 30.06.2017 | 30% | 380 | 76
62 | Hans Raj Sethi Marg | 1.7 |  | 27.03.2017 | 30.06.2017 | 45% | 350 | 140
63 | A Block Double Storey (EPDP to Hans Raj Sethi Marg) | 0.45 |  | 27.03.2017 | 30.06.2017 | 20% | 50 | 7.5
64 | Jaitpur Road | 1.25 | Sh. Naresh Kumar | 04.12.2016 | 30.06.2017 | 90% | 800 | 100
65 | Jaitpur Road -Meethapur Chowk to Gurudwara | 1.21 |  | 04.12.2016 | 30.06.2017 | 85% |  | 100
66 | Higher Secondary School Meethapur | 0.87 |  | 04.12.2016 | 30.06.2017 | 95% |  | 520
67 | Maharaja Agarsen marg | 0.8 | M/s R.N. Construction Co | 30.03.2017 | 30.06.2017 | 95% | 700 | 560
68 | Madanpur Khadar Road | 1.2 |  | 30.03.2017 | 30.06.2017 | 50% | 400 | 200
69 | Sarita Vihar Road | 1.1 |  | 30.03.2017 | 30.06.2017 | 60% | 550 | 310
70 | Road No. 13 A | 2.5 |  | 30.03.2017 | 30.06.2017 | 75% | 2000 | 1400
71 | Mathura Road | 5.5 |  | 30.03.2017 | 30.06.2017 | 60% | 3200 | 1760
72 | Lala Lajpat Rai Marg to Raja Dheer Sen Marg | 0.3 | M/s Gaurav Construction Co. | 30.03.2017 | 30.06.2017 | 80% | 170 | 136
73 | Guru Nanak Market to lala Lajpat Rai Marg | 0.57 |  | 30.03.2017 | 30.06.2017 | 75% | 180 | 135
74 | Nandi Vithi Marg | 0.73 |  | 30.03.2017 | 30.06.2017 | 65% | 150 | 90
75 | Link Road | 0.58 |  | - | 30.06.2017 | 85% | 250 | 200
76 | Road from BRT to Hans Raj Gupta Marg | 0.34 |  | 30.03.2017 | 30.06.2017 | 75% | 50 | 35
77 | Hans Raj Gupta Marg | 2.65 |  | - | 30.06.2017 | 72% | 700 | 504
78 | Lala Lajpat Rai Marg | 2.4 |  | - | 30.06.2017 | 90% | 180 | 162
79 | Guru Harkishan Public School to Nehru Place | 0.27 |  | 30.03.2017 | 30.06.2017 | 95% | 100 | 90
80 | R Block GK-1 signal to Outer Ring Road | 0.58 |  | 30.03.2017 | 30.06.2017 | 90% | 96 | 86
81 | Outer Ring Road | 2.1 |  | 30.03.2017 | 30.06.2017 | 70% | 1240 | 868
82 | Road from Vipin Chander Pal Marg to Police Station CR Park | 0.37 |  | 30.03.2017 | 30.06.2017 | 60% | 96 | 55
83 | Savitri Cinema Road | 3.1 |  | 30.03.2017 | 30.06.2017 | 85% | 1300 | 1040
84 | Surya Sen Marg | 0.75 |  | 30.03.2017 | 30.06.2017 | 95% | 225 | 202
85 | MB Road | 5.25 | M/s Buland Construction | 28.03.2017 | 30.06.2017 | 30% | 2000 | 400
86 | Guru Ravi Dass Marg | 3.75 |  | 28.03.2017 | 30.06.2017 | 90% | 3300 | 2980
87 | DDA Market Road | 0.43 |  | 28.03.2017 | 30.06.2017 | 70% | 200 | 140
88 | KPS Road | 0.64 |  | 28.03.2017 | 30.06.2017 | 45% | 150 | 68
89 | Suraj Kund Road | 0.6 |  | 28.03.2017 | 30.06.2017 | 15% | 300 | 15
90 | Road No13 | 2.7 |  | 10.04.2017 | 30.06.2017 | 80% | 2450 | 1450
91 | EPDP Road | 1.8 |  | 10.04.2017 | 30.06.2017 | 30% | 800 | 120
92 | Outer Ring Road | 3.2 |  | 10.04.2017 | 30.06.2017 | 60% | 1500 | 525
93 | Gurudwara Road GK-II | 1.7 | M/s Buland Construction | 10.04.2017 | 30.06.2017 | 90% | 208 | 140 | Er. R.K. Sharma 9818615817
94 | Vipin Chander Pal Marg | 1.5 |  | 10.04.2017 | 30.06.2017 | 20% | 720 | 105
South West Road -I
95 | B.J. Marg | 1.3 | M/s Amocon | 15.05.2017 | 15.06.2017 | 70% | 650 | 300 | Sh. S K Sinha 9958469778
96 | Rao Tula Ram Marg (RTR Marg) | 1.7 |  | 15.04.2017 | 15.06.2017 | 85% | 425 | 400
97 | Baba Balak Nath Marg | 1.1 |  | 01.06.2017 | 15.06.2017 | 70% | 580 | 150
98 | Nelson Mandela Marg | 4.01 | Sh. Vinay Shankar | 15.04.2017 | 15.06.2017 | 70% | 900 | 500
99 | Baba Gang Nath marg | 1.17 |  | 15.05.2017 | 15.06.2017 | 60% | 400 | 300
100 | Outer Ring Road | 4.8 |  | 15.05.2017 | 15.06.2017 | 55% | 1050 | 450
101 | Africa Avenue (Road No.9) | 2.2 | M/s Amocon | 18.05.2017 | 15.06.2017 | 80% | 600 | 450
102 | Babu Genu Marg, R.K.Puram | 0.6 |  | 18.05.2017 | 15.06.2017 | 85% | - | -
103 | Kama Koti Marg | 1.75 |  | 18.05.2017 | 15.06.2017 | 75% | - | -
104 | Venketeshwar Marg | 1.1 |  | 18.05.2017 | 15.06.2017 | 95% | 200 | 200
105 | Major Som Nath Marg | 0.9 |  | 18.05.2017 | 15.06.2017 | 95% | 324 | 300
106 | Amar Shaheed Babu Genu Marg | 0.9 |  | 18.05.2017 | 15.06.2017 | 95% | 324 | 300
107 | Tamil Sangam Marg | 0.5 |  | 18.05.2017 | 15.06.2017 | 60% | 180 | 100
108 | Kaifi Azmi Marg | 1.3 |  | 18.05.2017 | 15.06.2017 | 90% | 468 | 400
109 | Swami Vivekanand Marg | 2 |  | 18.05.2017 | 15.06.2017 | 65% | 576 | 300
110 | Church Road | 1.6 |  | 18.05.2017 | 15.06.2017 | 60% | 180 | 100
111 | Munirka Marg | 0.5 |  | 18.05.2017 | 15.06.2017 | 90% | 180 | 150
112 | Poorvi Marg | 0.5 |  | 18.05.2017 | 15.06.2017 | 80% | 200 | 100
113 | Dr. Prem Nath Dogra Marg | 0.6 |  | 18.05.2017 | 15.06.2017 | 70% | 200 | 100
114 | Basant Marg | 0.9 |  | 18.05.2017 | 15.06.2017 | 65% | 150 | -
115 | Paschimi Marg | 1.25 |  | 18.05.2017 | 15.06.2017 | 80% | 150 | -
116 | Ganga Ram Hospital Road | 1.08 | Sh. Bishwa Mohan Jha | 03.04.2017 | 02.11.2017 | 70% | 250 | 60
117 | Shankar Road | 1.64 |  | 03.04.2017 | 15.06.2017 | 70% | 350 | -
118 | Dr. K.S. Krishanan Marg | 0.92 |  | 03.04.2017 | 15.06.2017 | 90% | 250 | -
119 | PUSA Institute (IARI) Internal Road | 0.7 |  | 03.04.2017 | 15.06.2017 | 50% | 200 | -
120 | Dev Prakash Shastri marg (Road No. 25) | 4.45 |  | 03.04.2017 | 15.06.2017 | 65% | 1200 | 450
121 | Girdhari Lal Goswami Marg (Road No. 89) | 3.65 |  | 03.04.2017 | 15.06.2017 | 70% | 1000 | 100
122 | O.P. Bharti Marg 1 | 0.76 |  | 03.04.2017 | 15.06.2017 | 80% | 200 | -
123 | O.P. Bharti Marg 2 | 0.18 |  | 03.04.2017 | 15.06.2017 | 80% | 50 | -
124 | O.P. Bharti Marg 3 | 0.181 |  | 03.04.2017 | 15.06.2017 | 80% | 50 | -
125 | O.P. Bharti Marg 4 | 0.42 |  | 03.04.2017 | 15.06.2017 | 80% | 50 | -
126 | Mahatma gandhi Marg (Ring Road) (both side) | 8.6 |  | 04.04.2017 | 15.06.2017 | 70% | 1850 | 650
127 | NH-8 (both side) | 2.9 |  | 04.04.2017 | 15.06.2017 | 70% | 400 | 300
128 | Road No. 36(Sat Guru Ram Singh Marg) (both side) | 3.4 | Sh. Rajnish Yadav | 25.03.2017 | 15.06.2017 | 60% | 1400 | 550
129 | MM Road | 6.8 | M/s R.R. construction | 10.05.2017 | 15.06.2017 | 90% | 1630 | -
South-West Road-II
130 | 60 futa Road | 0.45 | M/s Ram Charan Bansal | 21.03.2017 | 20.06.2017 | 80% | work to be executed by super sucker machine. NIL | The drain is being cleaned by super sucker machines hence quanitity cannot be ascertained. However approx. Silt disposed out by S/S till date is 180 MT | Sh. J. P. Vashist 9971396164
131 | A Block Road | 0.2 |  | 21.03.2017 | 20.06.2017 | 90%
132 | Central School Road | 0.29 |  | 21.03.2017 | 20.06.2017 | 80%
133 | Dabri Road | 0.9 |  | 21.03.2017 | 20.06.2017 | 60%
134 | Fire Station Road | 0.4 |  | 21.03.2017 | 20.06.2017 | 80%
135 | Lal Sai Marg to Pankha Road | 0.65 |  | 21.03.2017 | 20.06.2017 | 60%
136 | Lal Sai Road | 2.5 |  | 21.03.2017 | 20.06.2017 | 50%
137 | Mall Road | 0.65 |  | 21.03.2017 | 20.06.2017 | 70%
138 | Old Pankha Road | 0.5 |  | 21.03.2017 | 20.06.2017 | 40%
139 | Pankha Road | 6.6 |  | 21.03.2017 | 20.06.2017 | 40%
140 | Ram Mandir Marg | 0.86 |  | 21.03.2017 | 20.06.2017 | -
141 | Road C-2/22 C-2/274 Road Janakpuri | 0.76 |  | 21.03.2017 | 20.06.2017 | 80%
142 | Road from Ram Mandir Marg to Mall Road (Connecting Road) | 0.3 |  | 21.03.2017 | 20.06.2017 | -
143 | Road From Shani Bazar to Ram Mandir Marg (Connecting Road) | 0.3 |  | 21.03.2017 | 20.06.2017 | -
144 | Shani Bazar Road | 0.65 |  | 21.03.2017 | 20.06.2017 | 60%
145 | Vidya Marg | 1.6 |  | 21.03.2017 | 20.06.2017 | 60%
146 | Nasir Pur Road | 0.34 |  | 21.03.2017 | 20.06.2017 | 80% | 750 MT | The drain is being cleaned by super sucker machines hence quanitity cannot be ascertained. However approx. Silt disposed out by S/S till date is 300 MT
147 | Internal Road C-1 to C-1A Block | 0.3 |  | 21.03.2017 | 20.06.2017 | 60%
148 | Palam Dabri Road | 1.39 |  | 21.03.2017 | 20.06.2017 | 80%
149 | Paras Public schol to L-103 Pocket-4 Chankya Puri Binda Pur | 0.24 |  | 21.03.2017 | 20.06.2017 | 70%
150 | Peer Baba Road | 0.6 |  | 21.03.2017 | 20.06.2017 | 90%
151 | Police Station Road | 0.37 |  | 21.03.2017 | 20.06.2017 | 80%
152 | Pt. Vishnu Dutt Marg | 0.75 |  | 21.03.2017 | 20.06.2017 | 75%
153 | Sagar Pur Road | 2.54 |  | 21.03.2017 | 20.06.2017 | 80%
154 | Satguru Ram Singh Marg | 0.9 |  | 21.03.2017 | 20.06.2017 | 75%
155 | Link Road (Pt. Vishnu Dutt Marg to Satguru Ram Singh Marg) | 0.3 |  | 21.03.2017 | 20.06.2017 | 75%
156 | Najafgarh Nagloi Road | 2.6 | Sh. Surender Singh | 21.03.2017 | 20.06.2017 | 60% | 382 MT | The drain is being cleaned by super sucker machines hence quanitity cannot be ascertained. However approx. Silt disposed out by S/S till date is 250 MT
157 | Najafgarh Phirni | 2.2 |  | 21.03.2017 | 20.06.2017 | 60%
158 | Najafgarh Dhansa Road | 16.25 |  | 21.03.2017 | 20.06.2017 | 80%
(Section-II)
159 | Najafgarh Dechaun Road | 4.55 | M/s Anmol Infratech Pvt Ltd. | 21.03.2017 | 20.06.2017 | 60% | work to be executed by super sucker machine. NIL | The drain is being cleaned by super sucker machines hence quanitity cannot be ascertained. However approx. Silt disposed out by S/S till date is 125 MT | Sh. J. P. Vashist 9971396164
160 | Najafgarh Jaroda Road | 7.2 |  | 21.03.2017 | 20.06.2017 | 60%
162 | Najafgarh Kakrola Road | 4 |  | 21.03.2017 | 20.06.2017 | 90%
163 | Laxmi Chand Marg | 11.3 | Sh. Surender Singh | 21.03.2017 | 20.06.2017 | 75% | 1090 MT | The drain is being cleaned by super sucker machines hence quanitity cannot be ascertained. However approx. Silt disposed out by S/S till date is 400 MT
164 | Prithvi Singh Dagar Marg | 11.2 |  | 21.03.2017 | 20.06.2017 | 75%
165 | Jhatikara Morh to Jhatikara | 8.55 |  | 21.03.2017 | 20.06.2017 | 95% | 890 MT | The drain is being cleaned by super sucker machines hence quanitity cannot be ascertained. However approx. Silt disposed out by S/S till date is 330 MT
166 | Najafgarh Bijwasan Road | 11.25 |  | 21.03.2017 | 20.06.2017 | 70%
167 | Bhartal Road | 3.48 | M/s Anmol Infratech Pvt Ltd. | 21.03.2017 | 20.06.2017 | 90% |  | The drain is being cleaned by super sucker machines hence quanitity cannot be ascertained. However approx. Silt disposed out by S/S till date is 550 MT
168 | Goyla Deenpur Road | 4.2 |  | 21.03.2017 | 20.06.2017 | 50%
169 | Kapashera Bijwasan Road | 3.8 |  | 21.03.2017 | 20.06.2017 | 70% | 1470 MT
170 | Link Road | 1.7 |  | 21.03.2017 | 20.06.2017 | 80%
171 | Old DG Road | 2.5 |  | 21.03.2017 | 20.06.2017 | 50%
South Road-I
171 | M.B. Road | 5.25 | Nasir Ali | 16.03.2017 | 25.06.2017 | 85% | 2150 | 880 | Sh. Narender Mahajan 9933331859
172 | Devli Road | 2 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 25.06.2017 | 40%
173 | IGNOU Road | 2.9 | M/s RichCon Engineering Company | 16.03.2017 | 25.06.2017 | 100%
174 | Maharishi Balmiki Marg | 1.8 | Nasir Ali | 16.03.2017 | 25.06.2017 | 95%
175 | Durbal Nath Marg | 1.09 |  | 16.03.2017 | 25.06.2017 | 85%
176 | Raja Ram Marg | 0.89 |  | 16.03.2017 | 25.06.2017 | 92%
177 | H Block Dakshin Puri Road | 0.4 |  | 16.03.2017 | 25.06.2017 | 60%
178 | Firni Road | 1 |  | 16.03.2017 | 25.06.2017 | 70%
179 | West End Marg | 0.8 |  | 16.03.2017 | 25.06.2017 | 75%
180 | Old MB Road | 1 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 25.06.2017 | 95%
181 | 100 Foota Road Chattarpur | 1.4 | Ravi Tanwar | 16.03.2017 | 25.06.2017 | 65% | 840 | 350
182 | 60 Foota Road | 0.9 |  | 16.03.2017 | 25.06.2017 | 65%
183 | SSN Marg | 10.5 |  | 16.03.2017 | 25.06.2017 | 60%
184 | Gadai Pur Band Road | 3 |  | 16.03.2017 | 25.06.2017 | 65% | 855 | 635
185 | Mandi Road | 8 |  | 16.03.2017 | 25.06.2017 | 65%
186 | Dera Bhati Road | 5.76 |  | 16.03.2017 | 25.06.2017 | 55%
187 | M.G. Road | 7.5 |  | 16.03.2017 | 25.06.2017 | 45%
188 | Aya Nagr Road | 0.6 |  | 16.03.2017 | 25.06.2017 | 90%
189 | Ghitorni Road to CPWD Land | 0.54 |  | 16.03.2017 | 25.06.2017 | 70%
190 | Ghitorni Village Road | 1.04 |  | 16.03.2017 | 25.06.2017 | 65%
191 | MG Road to Ghitorni Village | 0.3 |  | 16.03.2017 | 25.06.2017 | 75%
192 | Press Enclave (BRT to Saket Court) | 4 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 25.06.2017 | 65% | 3200 | 1545
193 | Family Court Road | 0.9 |  | 16.03.2017 | 25.06.2017 | 70%
194 | Pushp Vihar (Internal Road) | 4 |  | 16.03.2017 | 25.06.2017 | 65%
195 | H. Block Road | 1 |  | 16.03.2017 | 25.06.2017 | 65%
196 | Road in front of H.No. C-11 to C-20 Malviya Nagar | 0.11 |  | 16.03.2017 | 25.06.2017 | 65%
197 | Appjay School Road | 1.3 |  | 16.03.2017 | 25.06.2017 | 70%
198 | Shekh Sarai Phase-1 | 0.3 |  | 16.03.2017 | 25.06.2017 | 60%
199 | Khirki Road | 0.85 |  | 16.03.2017 | 25.06.2017 | 70%
200 | NBCC Plaza Road | 1.1 |  | 16.03.2017 | 25.06.2017 | 100%
201 | Birla Vidya Niketan | 1 |  | 16.03.2017 | 25.06.2017 | 70%
202 | Mandir Marg | 1.2 |  | 16.03.2017 | 25.06.2017 | 95%
203 | Pramod Mahajan Marg | 0.89 |  | 16.03.2017 | 25.06.2017 | 100%
204 | Main Road Sector-1, Pushp Vihar | 0.75 |  | 16.03.2017 | 25.06.2017 | 100%
205 | Pankaj Jewel Marg, Pushp Vihar | 1.1 |  | 16.03.2017 | 25.06.2017 | 100%
206 | Asian Market Road in Pushp Vihar | 0.45 |  | 16.03.2017 | 25.06.2017 | 70%
207 | Metro Enclave Road in Pushp Vihar | 0.45 |  | 16.03.2017 | 25.06.2017 | 65%
208 | Road between DDA Flat Masjid Moth Ph-II and Jahapanah Forest | 0.5 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 25.06.2017 | 65% | --do-- | --do-- | Sh. Narender Mahajan 9933331859
209 | Road in front of Mother International School | 0.54 |  | 16.03.2017 | 25.06.2017 | 60%
210 | J Block Saket | 0.89 |  | 16.03.2017 | 25.06.2017 | 65%
211 | Apeejay School Road (Gurudwara to J Block Road). | 0.3 |  | 16.03.2017 | 25.06.2017 | 60%
South Road-II
212 | August Kranti Marg. | 3.24 | M/s Vision Constructions | 02.03.2017 | 25.06.2017 | 98% | 3064 | 2089 | Sh. Jagdish Prasad 9560207879
213 | Balbir Saxena Marg | 0.8
214 | Ch. Dilip Singh Marg, P.S. Hauz Khas | 0.6
215 | Mahinder Singh Jain Marg Road / Gautam Nagar Road | 1.2
216 | P-Block Road from August Kranti Marg via jain Mandir & Dustbin to August Kranti Marg. | 0.34
217 | Sudarshan Cinema Road. | 0.72
218 | Gautam Nagar Road | 0.5
219 | Road form Balbir Sxsena Marg to Ch. Dalip SinghMarg (NIFT Road), Hauz Khas | 0.6
220 | Road form August Kranti marg to Aurobindo Marg (Subash Chopra Road), Hauz Khas | 0.79
221 | Asiad Village peripheral road | 3
222 | Siri Fort Road | 1.2
223 | Sri Aurobindo Marg | 5 | M/s Samridhi Construction | 02.03.2017 | 25.06.2017 | 90% | 5768 | 5191
224 | Outer Ring Road ( IIT Flyover to Africa Avenue Junction) | 1.8
225 | Ch. Jhandu Singh Marg | 1.53
226 | Ch. Harsukh Marg | 1.83
227 | Ch. Hukum Chand Marg | 0.6
228 | Green Park Market Road | 1
229 | Narender Kumar Pandey Marg | 1.16
230 | Hauz Khas Village Road | 0.9
231 | Ring Road (Safdarjung to Hyatt) | 2.1
232 | Anuvart Marg | 2.5 | Sh. Jagdish Prasad Meena | 02.03.2017 | 25.06.2017 | 92% | 4212 | 3510
233 | Aruna Asaf Ali Road | 3.5
234 | Vedant Deshika Marg | 0.7
235 | B-1 Telephone Exchange Road,Vasant Kunj (Mahipalpur Road to B-5 & B-6 Road) | 0.6
236 | DAV School Road Vasant Kunj | 0.55
237 | Shiv Mandir to B-5 & B-6 Road) | 0.3
238 | D-1 & D-2 Road, Vasant Kunj | 0.24
239 | Sports Complex Road D-2,Vasant Kunj | 0.7
240 | Shaheed Jeet Singh | 2.1
241 | Road from B 15/7 to BSES Office,Q.I.A. | 0.3
242 | Peripheral Road of A Block of Q.I.A. | 0.41
243 | Peripheral Road of C and B Block of Q.I.A. | 1.57
244 | Outer Ring Road (Panchsheel to IIT Gate) | 1 | Sh. Narendra Singh Yadav | 02.03.2017 | 25.06.2017 | 90% | 1085 | 922 | Sh. Jagdish Prasad 9560207879
245 | Outer Ring Road (Chirag Delhi to Panchsheel) | 3.7
246 | A-1 Block, Panchsheel Enclave Road | 0.5
247 | S-Bend Road (Maharishi Dayanand Marg) | 1.8 |  | 02.03.2017 | 25.06.2017 | 78% | 1680 | 1288
248 | Shivalik Road (Basant Kaur Marg) | 1.86
249 | Guru Govind Singh Marg | 1.2