## 21.07.17
Details of Desilting of Drain
Under North Zone (M)
(As on 21-07-2017)
Sl. No. | Name of Road / Drain | Length of Road (Km) | Contractor | Date of Start | Revised date of completion (Ist Cycle) | Estimate Qty. of silt (cum) | % Drain cleaned (Lengthwise) | Qty. of silt lifted and disposed off (cum) | EE in charge / Mobile No.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Circle:- North West
Division:- NW R-1
1 | Shyamji Krishan Verma Marg (Road No.44) | 2 | Sh. Jitender Singh | 2017-04-28 | 2017-07-27 | 2000 | 90% | 1520 | Sh. R.K. Khanna / 8826818787
2 | Kabir Das Road | 1.59 | ..do... | 2017-04-28 | 2017-07-27 | 800 | 95% | 570 | ..do...
3 | Maharishi Parshu Ram Marg | 0.75 | ..do... | 2017-04-28 | 2017-07-27 | 180 | 90% | 120 | ..do...
4 | Main Road of G-Block & H-Block | 0.33 | ..do... | 2017-04-28 | 2017-07-27 | 100 | 80% | 65 | ..do...
5 | Valmiki Road | 0.6 | ..do... | 2017-04-28 | 2017-07-27 | 200 | 85% | 130 | ..do...
6 | Triwalubar Marg | 0.29 | ..do... | 2017-04-28 | 2017-07-27 | 140 | 90% | 85 | ..do...
7 | Lala Lajpat Rai Marg | 0.37 | ..do... | 2017-04-28 | 2017-07-27 | 150 | 95% | 85 | ..do...
8 | Eklavya Marg | 0.37 | ..do... | 2017-04-28 | 2017-07-27 | 120 | 95% | 85 | ..do...
9 | Balbhir singh sidhu marg | 0.99 | ..do... | 2017-04-28 | 2017-07-27 | 300 | 90% | 270 | ..do...
10 | Guru Harikishan Marg (Road No. 43) (From RD 0m to RD 1745m) | 1.46 | ..do... | 2017-04-28 | 2017-07-27 | 1200 | 90% | 460 | ..do...
11 | Veer Hemu Marg | 1.09 | ..do... | 2017-04-28 | 2017-07-27 | 300 | 80% | 150 | ..do...
12 | Abdul Hameed Marg | 0.78 | ..do... | 2017-04-28 | 2017-07-27 | 250 | 90% | 170 | ..do...
13 | Phirni Road | 0.53 | ..do... | 2017-04-28 | 2017-07-27 | 200 | 95% | 150 | ..do...
14 | Lawrence Road | 0.6 | ..do... | 2017-04-28 | 2017-07-27 | 200 | 85% | 120 | ..do...
15 | Rampura Main Road | 1.2 | ..do... | 2017-04-28 | 2017-07-27 | 300 | 65% | 90 | ..do...
16 | Parwana road | 0.375 | ..do... | 2017-04-28 | 2017-07-27 | 150 | 95% | 130 | ..do...
17 | Padeshwar Dham Mandir Marg | 1.1 | M/s Aditya Construction Company | 2017-05-17 | 2017-07-27 | 310 | 90 | 235 | ..do...
18 | KC Goel Marg | 1.43 | ..do... | 2017-04-24 | 2017-07-27 | 360 | 80 | 185 | ..do...
19 | Gulab Singh Marg | 3.1 | ..do... | 2017-05-08 | 2017-07-27 | 360 | 80 | 180 | ..do...
20 | Bharat Nagar Road | 2.09 | ..do... | 2017-05-17 | 2017-07-27 | 320 | 90 | 210 | ..do...
21 | Nimri Colony H.NO. 623 to Gurudwara | 0.3 | ..do... | 2017-05-17 | 2017-05-30 | 45 | 100 | 40 | ..do...
22 | Tewatia Marg | 1.03 | ..do... | 2017-04-28 | 2017-05-30 | 120 | 100 | 120 | ..do...
23 | Ch. Mange Ram Marg | 0.371 | ..do... | 2017-04-22 | 2017-07-27 | 110 | 95 | 95 | ..do...
24 | Madhav Marg | 1.6 | ..do... | 2017-04-22 | 2017-07-27 | 210 | 80 | 120 | ..do...
25 | Sh. Guru Nanak Dev Ji Marg | 0.482 | ..do... | 2017-04-22 | 2017-06-15 | 55 | 100 | 50 | ..do...
26 | Front of Keshavpuram Police Station | 0.45 | ..do... | 2017-04-22 | 2017-07-27 | 55 | 80 | 40 | ..do...
27 | Maharishi Dayanand Saraswati Marg | 0.455 | ..do... | 2017-04-22 | 2017-06-15 | 55 | 100 | 45 | ..do...
28 | Shri Ram Krishan Mandir Marg | 0.551 | ..do... | 2017-04-22 | 2017-06-15 | 70 | 100 | 70 | ..do...
29 | Kulachi Hans Raj School Marg | 0.23 | ..do... | 2017-04-22 | 2017-07-27 | 50 | 90 | 45 | ..do...
30 | F-Block Market | 0.38 | ..do... | 2017-04-22 | 2017-06-15 | 70 | 100 | 62 | ..do...
31 | B-Block Market | 0.27 | ..do... | 2017-04-22 | 2017-07-27 | 70 | 90 | 55 | ..do...
32 | Deep Chand Central Market | 1 | ..do... | 2017-04-22 | 2017-07-27 | 150 | 90 | 120 | ..do...
33 | Road No. 37 (Maharaja Nahar Singh Marg) | 3 | ..do... | 2017-04-22 | 2017-07-27 | 200 | 70 | 105 | ..do...
34 | Jhule Lal Marg | 0.363 | M/s Aditya Construction Company | 2017-04-22 | 2017-07-27 | 120 | 80 | 112 | Sh. R.K. Khanna / 8826818787
35 | Shiv Ram Mandir Marg | 0.3 | ..do... | 2017-04-22 | 2017-07-27 | 60 | 90 | 62 | ..do...
36 | Road No. 38 | 0.7 | ..do... | 2017-04-22 | 2017-06-30 | 100 | 100 | 80 | ..do...
37 | Mata Jai Kaur Road | 0.29 | ..do... | 2017-04-22 | 2017-07-27 | 45 | 90 | 40 | ..do...
38 | Sunder Lal Jain Road | 0.55 | ..do... | 2017-04-22 | 2017-07-27 | 45 | 90 | 40 | ..do...
39 | Bunkar Colony Road | 0.224 | ..do... | 2017-04-22 | 2017-07-15 | 35 | 100 | 35 | ..do...
40 | Kakaji Lane | 0.32 | ..do... | 2017-04-22 | 2017-06-15 | 25 | 100 | 25 | ..do...
41 | Laxmi Bai College Road | 0.385 | ..do... | 2017-04-22 | 2017-06-15 | 25 | 100 | 25 | ..do...
42 | Swamy Narayan underpass road | 0.5 | ..do... | 2017-04-22 | 2017-07-27 | 45 | 90 | 40 | ..do...
43 | Nimri Colony (House No. 623 to Gurudwara) | 0.3 | ..do... | 2017-04-22 | 2017-05-30 | 45 | 100 | 40 | ..do...
44 | Nimri Colony Road | 0.175 | ..do... | 2017-04-22 | 2017-05-30 | 30 | 100 | 28 | ..do...
45 | Nimri Colony Road | 0.175 | ..do... | 2017-04-22 | 2017-05-30 | 30 | 100 | 34 | ..do...
46 | Nimri Colony Road | 0.35 | ..do... | 2017-04-22 | 2017-05-30 | 35 | 100 | 32 | ..do...
47 | Nimri Colony Road | 0.095 | ..do... | 2017-04-22 | 2017-06-15 | 20 | 100 | 17 | ..do...
48 | Nimri Colony Road | 0.773 | ..do... | 2017-04-22 | 2017-06-15 | 60 | 100 | 50 | ..do...
49 | Nimri Colony Road | 0.328 | ..do... | 2017-04-22 | 2017-06-15 | 35 | 100 | 32 | ..do...
50 | Road No. 40 (Bir Bandha Bairagi Marg) | 3.45 | ..do... | 2017-04-22 | 2017-06-15 | 1500 | 100% | 1500 | ..do...
51 | Swamy Narayan Marg | 2.94 | ..do... | 2017-04-22 | 2017-07-27 | 1200 | 90% | 1080 | ..do...
52 | Old Rohtak Road (Zakhira RUB to Road No.40 near Metro Pillar No.100 ) | 3 | ..do... | 2017-04-22 | 2017-07-27 | 1600 | 90% | 1440 | ..do...
53 | Kalidass marg (sarai rohilla flyover) | 0.7 | ..do... | 2017-04-22 | 2017-06-15 | 20 | 100% | 7 | ..do...
54 | Nand Lal Marg | 1.11 | ..do... | 2017-04-22 | 2017-05-30 | 250 | 100% | 290 | ..do...
55 | Azad Road | 1.485 | ..do... | 2017-04-22 | 2017-05-30 | 100 | 100% | 100 | ..do...
56 | Haji Abdul Salam Quareshi Marg | 0.48 | ..do... | 2017-04-22 | 2017-05-30 | 250 | 100% | 220 | ..do...
57 | Mata Jai Kaur Road | 0.165 | ..do... | 2017-04-22 | 2017-06-15 | 45 | 100% | 48 | ..do...
58 | Swamy Narayan underpass road | 0.445 | ..do... | 2017-04-22 | 2017-06-15 | 300 | 100% | 280 | ..do...
59 | Patap Nagar Road | 0.75 | ..do... | 2017-04-22 | 2017-05-30 | 300 | 100% | 250 | ..do...
60 | Bhagat Singh Road | 0.31 | ..do... | 2017-04-22 | 2017-05-30 | 150 | 100% | 165 | ..do...
61 | Link Road (east Moti Bagh) | 0.165 | ..do... | 2017-04-22 | 2017-05-30 | 50 | 100% | 35 | ..do...
62 | Rana Pratap Bagh | 0.26 | ..do... | 2017-04-22 | 2017-06-15 | 50 | 100% | 20 | ..do...
63 | BDFD Marg | 0.54 | Sh. Sahil Goyal | 2017-05-17 | 2017-06-15 | 50 | 100% | 150 | ..do...
64 | Power House Road | 1.3 | ..do... | 2017-04-21 | 2017-07-15 | 350 | 100% | 350 | ..do...
65 | Muni Maya Ram Marg | 1.738 | ..do... | 2017-04-21 | 2017-07-15 | 650 | 100% | 620 | ..do...
66 | Outer Ring Road | 3.8 | ..do... | 2017-05-17 | 2017-07-15 | 950 | 100% | 1050 | ..do...
67 | RUB Shalimar Bagh Road | 0.6 | ..do... | 2017-04-22 | 2017-07-27 | 75 | 95% | 71 | ..do...
68 | Jhule Lal Mandir Marg Shalimar Bagh | 1.25 | ..do... | 2017-04-22 | 2017-07-27 | 160 | 90% | 144 | ..do...
69 | Dividing Road | 0.26 | ..do... | 2017-04-22 | 2017-07-27 | 300 | 85% | 250 | ..do...
70 | Abhinav model School | 0.4 | ..do... | 2017-04-22 | 2017-07-27 | 200 | 85% | 170 | ..do...
71 | Ahinsa path Road | 0.4 | ..do... | 2017-04-22 | 2017-07-27 | 100 | 90% | 90 | ..do...
72 | NP - MP Road | 0.46 | ..do... | 2017-04-22 | 2017-07-27 | 200 | 96% | 192 | ..do...
73 | SP School Road | 0.65 | ..do... | 2017-04-22 | 2017-07-27 | 270 | 90% | 243 | ..do...
74 | Shaheed Udham Singh Marg | 1.6 | Sh. Sahil Goyal | 2017-04-22 | 2017-07-27 | 180 | 90% | 162 | Sh. R.K. Khanna / 8826818787
75 | Swami Shardanand Saraswati Marg | 1.2 | ..do... | 2017-04-22 | 2017-07-27 | 150 | 80% | 120 | ..do...
76 | Maharaja Agarsen Road | 2.84 | ..do... | 2017-04-22 | 2017-07-27 | 425 | 92% | 391 | ..do...
77 | Gopal Mandir Road | 1.105 | ..do... | 2017-04-22 | 2017-07-27 | 300 | 85% | 255 | ..do...
78 | Gurudwara Road | 0.6 | ..do... | 2017-04-22 | 2017-07-27 | 150 | 90% | 135 | ..do...
79 | Gyan Shakti Mandir Marg | 1.25 | ..do... | 2017-04-22 | 2017-07-27 | 100 | 90% | 90 | ..do...
80 | Maharishi Dayanand Marg | 0.4 | ..do... | 2017-04-22 | 2017-07-27 | 200 | 90% | 180 | ..do...
81 | Bhagwan Mahavir Marg | 0.54 | ..do... | 2017-04-22 | 2017-07-27 | 230 | 90% | 207 | ..do... | 297.5
82 | Club Road | 0.6 | ..do... | 2017-04-22 | 2017-07-27 | 400 | 85% | 340 | ..do...
83 | K.L. Bagga Marg | 0.6 | ..do... | 2017-04-22 | 2017-07-27 | 125 | 80% | 100 | ..do...
84 | Haiderpur Main Road | 0.9 | ..do... | 2017-04-22 | 2017-07-27 | 350 | 96% | 336 | ..do...
85 | Canal Road | 0.88 | ..do... | 2017-04-22 | 2017-07-27 | 155 | 90% | 140 | ..do...
86 | Ram Leela Ground Road | 0.88 | ..do... | 2017-04-22 | 2017-07-27 | 200 | 90% | 180 | ..do...
87 | Ring Road | 3.2 | ..do... | 2017-04-22 | 2017-07-27 | 1060 | 95% | 1007 | ..do...
88 | Road No. 41 | 3 | ..do... | 2017-04-22 | 2017-07-27 | 1100 | 90% | 990 | ..do...
89 | Road No. 37 extn. | 0.32 | ..do... | 2017-04-22 | 2017-07-27 | 400 | 90% | 360 | ..do...
90 | Elevated portion | 1.78 | ..do... | 2017-04-22 | 2017-07-27 | 500 | 90% | 450 | ..do...
91 | T.V Tower Road | 0.66 | ..do... | 2017-04-15 | 2017-07-15 | 100 | 100% | 150 | ..do...
Division : N-W R-2
M-3121
92 | Road No. 316 | 1.4 | ..do... | 14.04.2017 | 10.07.2017 | 2277 | 100% | 2250 | Sh. Baljeet Singh 9811621849
93 | Road No. 317 | 0.35 | ..do... | 14.04.2017 | 05.07.2017 | 110 | 100% | 100 | ..do...
94 | Road No. 318 | 0.85 | ..do... | 14.04.2017 | 05.07.2017 | 178 | 100% | 170 | ..do...
95 | Road No. 319 | 0.35 | ..do... | 14.04.2017 | 10.07.2017 | 110 | 100% | 100 | ..do...
96 | S.N. Hardiker Marg (Road No. A-1) | 1.19 | ..do... | 14.04.2017 | 15.06.2017 | 374 | 100% | 370 | ..do...
97 | Sir Chotu Ram Marg (road No. A-3) | 1 | ..do... | 14.04.2017 | 15.06.2017 | 400 | 100% | By Super Sucker | ..do...
98 | Pradeep Bhatia Marg (Road No. A-5) | 1 | ..do... | 14.04.2017 | 15.06.2017 | 180 | 100% | By Super Sucker | ..do...
99 | Maharaja Aggarsen Marg (Road No. 42-A) | 2.3 | ..do... | 14.04.2017 | 15.06.2017 | 900 | 100% | By Super Sucker | ..do...
MCD ROADS
100 | Nangloi Rly.Stn to Sultanpuri Bus Terminal via Jalebi Chowk | 2.1 | Sh. Sahil Goyal | 14.04.2017 | 05.07.2017 | 900 | 100% | By Super Sucker | Sh. Baljeet Singh 9811621849
101 | Sultanpuri Bus Terminal to Flood Control Drain. | 1 | ..do... | 14.04.2017 | 15.06.2017 | 500 | 100% | By Super Sucker | ..do...
102 | Sanjay Gandhi Hospital Road from Road No.316 to J Block Survodya Vidhyalya to Kanjhawla Road. | 1.6 | ..do... | 14.04.2017 | 05.07.2017 | 360 | 100% | By Super Sucker | ..do...
103 | Police Station Road from Road No.3 i.e. Kanjhawla Road to Sanjay Gandhi Hospital Road. | 1.3 | ..do... | 14.04.2017 | 05.07.2017 | 520 | 100% | By Super Sucker | ..do...
104 | Sultanpuri Main Road | 0.6 | ..do... | 14.04.2017 | 05.07.2017 | 200 | 100% | By Super Sucker | ..do...
105 | Shani Bazar Road | 0.6 | ..do... | 14.04.2017 | 05.07.2017 | 200 | 100% | By Super Sucker | ..do...
106 | H Block Road | 0.32 | ..do... | 14.04.2017 | 25.07.2017 | 130 | 94% | By Super Sucker | ..do...
107 | Jagdamba Road | 0.38 | ..do... | 14.04.2017 | 05.07.2017 | 160 | 100% | By Super Sucker | ..do...
108 | Bhalla Factory road | 0.38 | ..do... | 14.04.2017 | 05.07.2017 | 750 | 100% | 740 | ..do... | 450
109 | Kala Mandir Cinema Road in Mangolpuri | 0.8 | ..do... | 14.04.2017 | 05.07.2017 | 280 | 100% | By Super Sucker | ..do...
110 | LP Road (Tank Road) Mangolpuri | 1.2 | ..do... | 14.04.2017 | 05.07.2017 | 2480 | 100% | 2450 | ..do...
111 | B-Block Road Mangolpuri | 1.4 | ..do... | 14.04.2017 | 05.07.2017 | 500 | 100% | By Super Sucker | ..do...
112 | G-Block Road | 0.15 | ..do... | 14.04.2017 | 05.07.2017 | 60 | 100% | By Super Sucker | ..do...
113 | 70 ft Road Kirari | 1.25 | ..do... | 14.04.2017 | 10.07.2017 | 600 | 100% | By Super Sucker | ..do...
114 | Katran Road (Durbal Nath Marg) Mangolpuri | 0.55 | ..do... | 14.04.2017 | 05.07.2017 | 200 | 100% | By Super Sucker | ..do...
ROHINI SECTOR-2
115 | Road No.A-2 From Pole Star to CSC-II, Sec.1/2, Rohini. | 0.54 | ..do... | 14.04.2017 | 15.06.2017 | 160 | 100% | By Super Sucker | ..do...
116 | Road from New Bal Bharti Public School to Road No.3 Sec.2 | 0.4 | ..do... | 14.04.2017 | 15.06.2017 | 130 | 100% | By Super Sucker | ..do...
117 | Road from CSC Market Pkt.4 to Mangolpur Kalan Phirni Road Sec.2 | 0.3 | ..do... | 14.04.2017 | 15.06.2017 | 110 | 100% | By Super Sucker | ..do...
| ROHINI SECTOR-4 | [7 empty] | ..do...
118 | Roadfrom PocketA-1 to Pocket A-2 in Sec.4 Rohini | 0.225 | ..do... | 14.04.2017 | 15.06.2017 | 70 | 100% | 65 | ..do...
119 | Roadfrom Pocket B-5to Pocket B-9 in Sec.4 Rohini MC Pry. School | 0.31 | ..do... | 14.04.2017 | 15.06.2017 | 100 | 100% | By Super Sucker | ..do...
M-3122
PWD roads
120 | Deen Bandhu Sir Chotu Ram Marg (Road No. A-4) | 1 | ..do... | 14.04.2017 | 15.06.2017 | 240 | 100% | 230 | ..do...
121 | Road No. 41-A Bhagwan mahavir Marg. | 3.995 | ..do... | 14.04.2017 | 15.06.2017 | 950 | 100% | By Super Sucker | ..do...
122 | Road No. B-1 | 0.96 | Sh. Sahil Goyal | 14.04.2017 | 15.06.2017 | 240 | 100% | 90/ Super Sucker | Sh. Baljeet Singh 9811621849
123 | Road No. B-3 | 1.55 | ..do... | 14.04.2017 | 15.06.2017 | 450 | 100% | By Super Sucker | ..do...
ROHINI SECTOR-3
124 | Road From Pocket A-2 to Pkt.C-13 in Sec.3 Rohini | 1 | ..do... | 14.04.2017 | 15.06.2017 | 240 | 100% | 235 | ..do...
125 | Road from Pocket F-22 to Pocket H-34 in Sec-3 Rohini | 1 | ..do... | 14.04.2017 | 15.06.2017 | 240 | 100% | 230 | ..do...
126 | Road from MC Pry. School 3A to Sarvodaya School in Sec.3, Rohini | 0.325 | ..do... | 14.04.2017 | 15.06.2017 | 80 | 100% | 70 | ..do...
127 | Road from DDA Shopping Centre to Kendriya Vidyalaya in Sec.3, Rohini. | 0.325 | ..do... | 14.04.2017 | 15.06.2017 | 80 | 100% | 70 | ..do...
128 | Jaipur Golden Hospital Road Sec.3 | 1 | ..do... | 14.04.2017 | 15.06.2017 | 240 | 100% | 225 | ..do...
ROHINI SECTOR-5
129 | MTNL Godown to C6/137 Sec.5, Rohini | 0.533 | ..do... | 14.04.2017 | 15.06.2017 | 140 | 100% | 135 | ..do...
130 | Som Bazar Road, Sec.5, Rohini | 0.71 | ..do... | 14.04.2017 | 15.06.2017 | 170 | 100% | 160 | ..do...
ROHINI SECTOR-6
131 | Shiva Road from Ring Road to Dividing Road of Sec.5 & 6, Rohini. | 2.217 | Sh. Sahil Goyal | 14.04.2017 | 05.07.2017 | 120 | 100% | 110 | Sh. Baljeet Singh 9811621849
132 | Vidya Jain Public School, Se.6, Rohini | 0.477 | ..do... | 14.04.2017 | 15.06.2017 | 120 | 100% | 115 | ..do...
133 | C-4/253 toC5/253, Sec.6, Rohini | 0.33 | ..do... | 14.04.2017 | 15.06.2017 | 80 | 100% | 75 | ..do...
134 | D-6 and A-1 Road sec.6,Rohini | 0.33 | ..do... | 14.04.2017 | 15.06.2017 | 80 | 100% | 75 | ..do...
ROHINI SECTOR-7
135 | G-23/30 to E4/15 Sec.7 | 0.396 | ..do... | 14.04.2017 | 15.06.2017 | 85 | 100% | 80 | ..do...
136 | B-6/159 to Naharpur DAV School back side Sec.7 | 0.296 | ..do... | 14.04.2017 | 15.06.2017 | 70 | 100% | 70 | ..do...
137 | B-22/279 to G-21/222 Sec.7 | 0.321 | ..do... | 14.04.2017 | 15.06.2017 | 75 | 100% | 70 | ..do...
138 | B-4/30 to CGHS Dispensary Sec.7 | 0.172 | ..do... | 14.04.2017 | 15.06.2017 | 50 | 100% | 45 | ..do...
139 | H18 to F-25 Sec.6 & 7 dividing road (Bhagwan Parshu Ram marg) | 1.3 | ..do... | 14.04.2017 | 15.06.2017 | 200 | 100% | 180 | ..do...
ROHINI SECTOR-8
140 | Rama Road Sec.8, Rohini | 0.73 | ..do... | 14.04.2017 | 15.06.2017 | 175 | 100% | 160 | ..do...
141 | Road from Road No. 41-A to Rama Road in Sec.8, Rohini | 1.05 | ..do... | 14.04.2017 | 18.06.2017 | 250 | 100% | 245 | ..do...
142 | Road from Road No. 42-A to Rama Road in Sec.8, Rohini | 0.55 | ..do... | 14.04.2017 | 21.06.2017 | 130 | 100% | 120 | ..do...
ROHINI SECTOR-9
143 | Sawran Jayanti Park Road, Sec.9 &13 | 1.68 | ..do... | 14.04.2017 | 15.06.2017 | 400 | 100% | Manual/Super Sucker | ..do...
ROHINI SECTOR-11
144 | Road from F-3 block to H-4 in Sec.11, Rohini | 0.7 | ..do... | 14.04.2017 | 15.06.2017 | 170 | 100% | 160 | ..do...
145 | From A-1 to F-3 Block near NDPL office Sec.11, Rohini. | 1.5 | ..do... | 14.04.2017 | 15.06.2017 | 360 | 100% | 355 | ..do...
146 | From Block H-1 to H-5 Block Sec.11, Rohini | 0.65 | ..do... | 14.04.2017 | 04.06.2017 | 80 | 100% | By Super Sucker | ..do...
147 | From F-1 to H-2 Block near NDPL office Sec.11, Rohini. | 0.65 | ..do... | 14.04.2017 | 10.07.2017 | 80 | 100% | By Super Sucker | ..do...
148 | From C-4 to A-3 Block near NDPL office Sec.11, Rohini. | 0.65 | ..do... | 14.04.2017 | 15.06.2017 | 160 | 100% | 150 | ..do...
149 | From F-1 to F-3 Block near NDPL office Sec.11, Rohini. | 0.375 | ..do... | 14.04.2017 | 10.06.2017 | 50 | 100% | By Super Sucker | ..do...
150 | From A-1 to A-3 Block near NDPL office Sec.11, Rohini. | 0.375 | ..do... | 14.04.2017 | 10.07.2017 | 50 | 100% | By Super Sucker | ..do...
151 | From C-1 to C-5 Block near NDPL office Sec.11, Rohini. | 0.375 | ..do... | 14.04.2017 | 05.07.2017 | 50 | 100% | By Super Sucker | ..do...
152 | From Community Centre to NDMC Colony, Sec.11, Rohini. | 0.69 | ..do... | 14.04.2017 | 10.07.2017 | 100 | 100% | 95 | ..do...
ROHINI SECTOR - 16
153 | D-1 TO I-3 (Length 0.463 KM) | 0.463 | ..do... | 14.04.2017 | 15.06.2017 | 110 | 100% | 105 | ..do...
154 | G-1 TO E-5 (Length 0.650 KM) | 0.65 | ..do... | 14.04.2017 | 10.07.2017 | 160 | 100% | 150 | ..do...
155 | G-7 TO G-1 (Length 1.000 KM) | 1 | ..do... | 14.04.2017 | 25.07.2017 | 240 | 75% | 190 | ..do...
156 | H-3 TO H-1 (Length 0.400 KM) | 0.4 | ..do... | 14.04.2017 | 10.07.2017 | 100 | 100% | 95 | ..do...
157 | A-2 TO E-3 (Length 0.650 KM) | 0.65 | ..do... | 14.04.2017 | 15.06.2017 | 95 | 100% | 90 | ..do...
158 | C-1 TO I-11 (Length 0.600 KM) | 0.6 | ..do... | 14.04.2017 | 15.06.2017 | 150 | 100% | 140 | ..do...
159 | District Park TO C-1 (Length 0.438 KM) | 0.438 | ..do... | 14.04.2017 | 15.06.2017 | 100 | 100% | 90 | ..do...
160 | F-2 TO F-6 (Length 0.338 KM) | 0.338 | ..do... | 14.04.2017 | 05.07.2017 | 70 | 100% | 60 | ..do...
161 | A-6 TO A-8 (Length 0.263 KM) | 0.263 | ..do... | 14.04.2017 | 10.07.2017 | 50 | 100% | 50 | ..do...
162 | F-3 TO F-5 (Length 0.338 KM) | 0.338 | ..do... | 14.04.2017 | 05.06.2017 | 70 | 100% | 65 | ..do...
163 | I-1 TO Police Station (Length 0.538 KM) | 0.538 | ..do... | 14.04.2017 | 15.06.2017 | 130 | 100% | 120 | ..do...
ROHINI SECTOR - 17
164 | B-2 TO B-6 (Length 0.210 KM) | 0.21 | ..do... | 14.04.2017 | 15.06.2017 | 50 | 100% | 45 | ..do...
165 | A-8 TO B-6 (Length 0.600 KM) | 0.6 | ..do... | 14.04.2017 | 15.06.2017 | 150 | 100% | 140 | ..do...
166 | B-1 TO C-1 (Length 0.475 KM) | 0.475 | ..do... | 14.04.2017 | 10.07.2017 | 120 | 100% | 115 | ..do...
167 | A-8 TO B-1 ROAD (Length 0.445 KM) | 0.445 | ..do... | 14.04.2017 | 15.06.2017 | 110 | 100% | 90 | ..do...
M-3123
168 | Dr. K.N. Katju Marg(45m wide road) | 3.77 | Sh. Inderjit Singh | 21.04.2017 | 10.07.2017 | 800 | 100% | 750 | ..do... | 90
169 | Road No. B-2 (Ram murthi Passi Marg) | 1.652 | ..do... | 21.04.2017 | 05.07.2017 | 200 | 100% | By Super Sucker | ..do...
170 | Road No. B-4 | 1.4 | ..do... | 21.04.2017 | 25.07.2017 | 200 | 70% | By Super Sucker | ..do...
171 | Road No. B-5 | 1.64 | ..do... | 21.04.2017 | 2017-06-30 | 200 | 100% | By Super Sucker | ..do...
172 | Road No. B-6 | 1 | ..do... | 21.04.2017 | 10.07.2017 | 300 | 100% | 295 | ..do...
173 | Road No. B-7 | 1.25 | ..do... | 21.04.2017 | 25.07.2017 | 400 | 85% | 300 | ..do...
174 | Road No. B-8 | 1.18 | Sh. Inderjit Singh | 21.04.2017 | 10.07.2017 | 300 | 100% | 295 | Sh. Baljeet Singh 9811621849
MCD ROADS
ROHINI SECTOR-9
175 | Col. Sarna Marg Sec.9 & 13 | 1.02 | ..do... | 21.04.2017 | 25.07.2017 | 100 | 85% | 80 | ..do...
176 | Internal Road of Sec.9 Rohini | 0.325 | ..do... | 21.04.2017 | 2017-06-20 | 200 | 100% | 195 | ..do... | 20
177 | Internal Road of Sec.9 Rohini | 0.33 | ..do... | 21.04.2017 | 2017-06-20 | 200 | 100% | 195 | ..do...
178 | R.N. Gujral Marg Sec.9 | 0.265 | ..do... | 21.04.2017 | 2017-06-25 | 200 | 100% | 190 | ..do...
179 | Chetak Apartment to New Modern Apartment Sec.9 | 0.319 | ..do... | 21.04.2017 | 10.07.2017 | 100 | 100% | 90 | ..do...
180 | Vidhya Vihar to Neelgiri Apt. Sec.9 | 0.33 | ..do... | 21.04.2017 | 10.07.2017 | 100 | 100% | 90 | ..do...
181 | Captain Dahiya Marg Sec.9 & 13 | 1.68 | ..do... | 21.04.2017 | 25.07.2017 | 500 | 90% | 470 | ..do...
182 | Ahinsha Marg Sec.9 & 13 | 1.68 | ..do... | 21.04.2017 | 25.07.2017 | 450% | 90% | 400 | ..do...
ROHINI SECTOR - 13 Extn.
183 | Sunrise Appartment (K. N. Katzu Marg) to Neelkanth Appartment (K. N. Katzu Marg) | 0.975 | ..do... | 21.04.2017 | 10.07.2017 | 200 | 100% | 190 cum | ..do...
184 | Kawal Kunj Soceity to K.N. Katzu Marg (Length 0.265 KM) | 0.265 | ..do... | 21.04.2017 | 10.07.2017 | 100 | 100% | 90cum | ..do...
ROHINI SECTOR-14
185 | Fire Station to CRPF School Corner Sec.14 Rohini (Ram Prasad Bismil Marg) | 0.72 | ..do... | 21.04.2017 | 2017-06-15 | 250% | 100% | 250 cum | ..do...
186 | Babosa Chowk to Tulsi Apartment Sec.14, Rohini. | 0.55 | ..do... | 21.04.2017 | 10.07.2017 | 200 | 100% | 190 cum | ..do...
187 | PWD Ring Road to Maheswari Apt. Sec.14 toward Sec.13. | 0.845 | ..do... | 21.04.2017 | 2017-06-20 | 200 | 100% | 190 | ..do...
188 | Rukmani Devi Institute to Rohini Court Sec.14 | 0.45 | ..do... | 21.04.2017 | 10.07.2017 | 200 | 100% | 195 | ..do...
189 | Connecting road from ORR to Road No.B-5 passing through CRPF School, Sec.14, Rohini | 0.86 | ..do... | 21.04.2017 | 2017-06-15 | 500 | 100% | 500 cum | ..do...
ROHINI SECTOR - 15
190 | A-1/1 to G-18/1 (Length 0.600 KM) | 0.6 | ..do... | 21.04.2017 | 25.07.2017 | 200 | 65% | 120 | ..do...
191 | G-17/1 to Western Yamuna Canal (Length 0.750 KM) | 0.75 | ..do... | 21.04.2017 | 25.07.2017 | 200 | 60% | 110 | ..do... | 150
192 | Western Yamuna Canal to Arya Appartment (Length 0.590 KM) | 0.59 | ..do... | 21.04.2017 | 25.07.2017 | 200 | 54% | 100 | ..do...
ROHINI SECTOR - 18
193 | Western Yamuna Canal to A-11/87 (Length 0.300 KM) | 0.3 | ..do... | 21.04.2017 | 25.07.2017 | 100 | 75% | By Super Sucker | ..do...
194 | PWD Road (B-7) to Corner of E-II Ashtha Kunj (Length 0.245 KM) | 0.245 | ..do... | 21.04.2017 | 25.07.2017 | 200 | 95% | By Super Sucker | ..do...
195 | Corner of Data Ram Society to CEPT (Length 0.390 KM) | 0.39 | ..do... | 21.04.2017 | 25.07.2017 | 200 | 95% | By Super Sucker | ..do...
196 | Behind Data Ram Society to Corner of Mt. Abu School (Length 0.390 KM) | 0.39 | Sh. Inderjit Singh | 21.04.2017 | 25.07.2017 | 200 | 80% | By Super Sucker | Sh. Baljeet Singh 9811621849
197 | PWD Road (B-7) to CEPT (Length 0.580 KM) | 0.58 | ..do... | 21.04.2017 | 2017-06-15 | 200 | 100% | By Super Sucker | ..do...
198 | H-3/53 to DDA Park (Length 0.145 KM) | 0.145 | ..do... | 21.04.2017 | 25.07.2017 | 50 | 75% | By Super Sucker | ..do...
ROHINI SECTOR - 19
199 | PWD Road to DJB Booster Pump (Length 0.270 KM) | 0.27 | ..do... | 21.04.2017 | 25.07.2017 | 200 | 75% | 120 cum | ..do...
200 | PWD Road to Baba wala Park (Corner of Booster Pump) (Length 0.590 KM) | 0.59 | ..do... | 21.04.2017 | 2017-06-20 | 300 | 100% | 300 | ..do...
201 | Western Yamuna Canal to Badli Chowk (Length 0.310 KM) | 0.31 | ..do... | 21.04.2017 | 25.07.2017 | 200 | 75% | 150 | ..do...
ROHINI SECTOR-20
202 | Road from Pkt-10 to Pkt-D-4, Sec-20,Rohini | 0.505 | ..do... | 21.04.2017 | 2017-06-15 | 1500 | 100% | 1350 cum | ..do...
203 | Road from Pkt-14 to Pkt-C-1,Sec-20,Rohini | 1 | ..do... | 21.04.2017 | 2017-06-15 | 2000 | 100% | 1800 cum | ..do... | 180
ROHINI SECTOR-21
204 | Road from Pkt-8 to Pkt.-9,Sec-21, Rohini | 0.505 | ..do... | 21.04.2017 | 2017-06-10 | 800 | 100% | By Super Sucker | ..do...
205 | Road from Pkt-B to Park, Sec-21, Rohini | 0.187 | ..do... | 21.04.2017 | 2017-06-10 | 400 | 100% | By Super Sucker | ..do...
206 | Road from Pkt-13 to Pkt-9,Sec-21, Rohini | 0.448 | ..do... | 21.04.2017 | 2017-06-10 | 600 | 100% | By Super Sucker | ..do...
207 | Road from Pkt-5 to Pkt-6, Sec-21, Rohini | 0.115 | ..do... | 21.04.2017 | 2017-06-10 | 300 | 100% | By Super Sucker | ..do...
M-3124
208 | Chandra Shekhar Azad Marg (Road No. 42) | 1.23 | Sh. Rajnish Yadav | 14.04.2017 | 10.07.2017 | 490 | 100% | 485 | ..do...
209 | Guru Harkishan Marg (road No. 43) | 3.545 | ..do... | 14.04.2017 | 25.07.2017 | 1600 | 95% | 1450 | ..do...
210 | Road No.30 | 2 | ..do... | 14.04.2017 | 25.07.2017 | 1000 | 95% | 900 | ..do...
MCD ROADS
SARSWATI VIHAR/Paschim Vihar
211 | Mahatma Hans Raj Marg | 1.4 | ..do... | 14.04.2017 | 25.07.2017 | 490 | 90% | 450 | ..do...
212 | Guru Birja Nand Marg (a) | 0.8 | ..do... | 14.04.2017 | 25.07.2017 | 400 | 85% | 330 | ..do...
| Guru Birja Nand Marg (b)... | 0.6 | ..do... | 14.04.2017 | 25.07.2017 | 210 | 95% | 180 | ..do...
213 | Sant Nagar M2K Road | 0.47 | ..do... | 14.04.2017 | 25.07.2017 | 170 | 60% | 90 | ..do...
214 | Amar Shaheed Bismil Marg | 0.94 | ..do... | 14.04.2017 | 25.07.2017 | 400 | 95% | By Super Sucker | ..do...
215 | Police Line Road | 0.62 | ..do... | 14.04.2017 | 15/06/2017 | 240 | 100% | By Super Sucker | ..do...
216 | Parwana Road, Saraswati Vihar | 2.8 | ..do... | 14.04.2017 | 25.07.2017 | 1000 | 80% | 800 | ..do...
217 | Major Ashwani Kanva Marg | 1 | ..do... | 14.04.2017 | 15/06/2017 | 200 | 100% | 185 | ..do...
218 | Balbir Singh Marg | 1.1 | ..do... | 14.04.2017 | 15/06/2017 | 700 | 100% | 690 | ..do...
219 | Bhao Rao Dev Ras Marg | 1.4 | ..do... | 14.04.2017 | 15/06/2017 | 300 | 100% | 280 | ..do...
220 | Deen Dayal Upadhayay Marg | 0.6 | ..do... | 14.04.2017 | 25.07.2017 | 320 | 65% | By Super Sucker | ..do...
221 | Road between B-4 & B-5 Block Paschim Vihar | 0.35 | ..do... | 14.04.2017 | 15/06/2017 | 150 | 100% | 100 | ..do...
M-3125
222 | Road No.3 - Guru Gowalkar Marg | 5.8 | Sh. Vinay Shankar | 27.04.2017 | 25.07.2017 | 367 | 95% | 350 | ..do...
223 | Kanjhawala Link road | 0.4 | ..do... | 27.04.2017
PWD Road
224 | Outer Ring Road 26 (a) | 4.22 | Sh. Abhilekh Yadav | 27.04.2017 | 25.07.2017 | 930 | 95% | 880 | ..do...
225 | Elevated corridor with RE wall (b) | 2.66 | ..do... | 27.04.2017 |  |  |  |  | ..do...
Circle:- North
Division:- North Road
Sub Division NR-11
226 | Kushal Cinema Road Starting from Raseela Paint Shop to T Point Pryas Road in Jahangirpuri-I, W.No. 16 Civil Line Zone | 1.102 | Inderjit Singh | 25-03-17 | 10.07.17 | 3200 | 100% | 1600 | Sh. Vikram Pal 9717916732
227 | Dhobhi Ghat Road Starting from Kushal Cinema Chowk to Shah Alam Bandh Road | 0.45 | ..do... | 25-03-17 | 10.07.17 |  | 100% |  | ..do...
228 | Malik Ram Tandon Marg from Road No. 51 to Shah Alam Bandh Road | 0.89 | ..do... | 25-03-17 | 10.07.17 |  | 100% |  | ..do...
229 | Shah Alam Bandh Road from Burari Road to 80" Road (ROW) at Malik Ram Tondon Road upto Road No. 51 | 1.55 | ..do... | 25-03-17 | 10.07.17 |  | 100% |  | ..do...
230 | Shah Alam Bandh Road from Main G.T. Road to Malik Ram Tandon Marg | 1.4 | ..do... | 25-03-17 | 10.07.17 |  | 100% |  | ..do...
231 | Mangal Bazar Road starting from Kushal Road Green Belt to Shah Alam Bandh Road | 0.4 | ..do... | 25-03-17 | 10.07.17 |  | 100% |  | ..do...
232 | Prayas Road (from Shah Alam Bandh Road to Dhalao, Jahangirpuri) | 0.7 | ..do... | 25-03-17 | 10.07.17 |  | 100% |  | ..do...
233 | Fire Station to Pump House | 0.55 | ..do... | 25-03-17 | 10.07.17 |  | 100% |  | ..do...
Sub Division NR-12
234 | Mall Road Extension from Azadpur Flyover to Mukarba Chowk | 3.5 | Anumol Infratech Pvt Ltd | 26-03-17 | 10.07.17 | 3060 | 100% | 1450 (Dispose off of the above is in progress) | ..do...
235 | Indra Park Road | 0.38 | ..do... | 26-03-17 | 30-06-17 |  | 100% |  | ..do...
236 | Princess Road from Mall road to Road No.51 | 3.1 | ..do... | 26-03-17 | 25-07-17 |  | 98% |  | ..do...
237 | Road No. 51 from Azadpur Flyover to Outer Ring Road | 2.5 | ..do... | 26-03-17 | 10.07.17 |  | 100% |  | ..do...
238 | Model Town-III Road from Mall Road to Arya Samaj Mandir | 0.727 | Sanjay Kaura | 26-03-17 | 10.07.17 | 3090 | 100% | 1900 | ..do...
239 | Mahatma Gandhi road (Ring Road) from Camp Chowk to Azadpur Flyover | 3.5 | ..do... | 26-03-17 | 10.07.17 |  | 100% |  | ..do...
240 | Lala Auchint Ram Road from Stadium Road to Pambari Road | 0.95 | ..do... | 26-03-17 | 10.07.17 |  | 100% |  | ..do...
241 | Stadium Road from Chattrashal Stadium Mall Road to GT Road | 0.68 | Sanjay Kaura | 26-03-17 | 10.07.17 |  | 100% |  | Sh. Vikram Pal 9717916732
242 | Brahamkumari Marg from Mall Road to G.T. Road | 0.65 | ..do... | 26-03-17 | 10.07.17 |  | 100% |  | ..do...
243 | Model Town II Road from Mall Road to F-14/56 Model Town | 0.495 | ..do... | 26-03-17 | 10.07.17 |  | 100% |  | ..do...
244 | G.T Road from Gurudwara Nanakpiao to Azadpur Round about | 2 | ..do... | 26-03-17 | 25-07-17 |  | 85% |  | ..do...
Sub Division NR-13
245 | Old G.T. Karnal Road | 3 | V.V Associates | 20-03-17 | 15.07.17 | 5270 | 100% | 2600 | ..do...
246 | Narela Alipur Road from Shahpur Grahi to Old GTK Road Alipur | 5.02 | ..do... | 20-03-17 | 15.07.17 |  | 100% |  | ..do...
247 | Ramdev Chowk Narela to Kanya Gurukul | 1.9 | ..do... | 20-03-17 | 15.07.17 |  | 100% |  | ..do...
248 | Narela Alipur Road from Narela Y section to Shahpur Garhi | 3.4 | ..do... | 20-03-17 | 15.07.17 |  | 100% |  | ..do...
249 | Narela Safiabad Road from Narela to Safiabad Border | 2.9 | ..do... | 20-03-17 | 15.07.17 |  | 100% |  | ..do...
250 | Narela Lampur Road from Narela to Lampur Border | 3.8 | ..do... | 20-03-17 | 15.07.17 |  | 100% |  | ..do...
251 | Nangli Puna Underpass to Khera Kalan Railway X-ing. | 3 | ..do... | 20-03-17 | 15.07.17 |  | 100% |  | ..do...
252 | Holambi Khurd Crossing to Metro Vihar | 3 | ..do... | 20-03-17 | 15.07.17 |  | 80% (Desilting of remaining portion is not possible as Repair of Drain is in Progress) |  | ..do...
253 | Bawana Narela Road From CRPF to Singhu Border | 10.4 | ..do... | 20-03-17 | 15.07.17 |  | 100% |  | ..do...
254 | New GT Road to Old GT Road (via PHC Alipur) from New GTk Road to Old GTK Road | 0.38 | ..do... | 20-03-17 | 15.07.17 | 5470 | 100% | 3000 | ..do...
255 | Holambi Khurd Crossing to Shahpur Garhi turn | 1.9 | ..do... | 20-03-17 | 15.07.17 |  | 100% |  | ..do...
256 | Railway Crossing to Holambi Khurd | 0.7 | ..do... | 20-03-17 | 15.07.17 |  | 100% |  | ..do...
257 | Khera Kalan to Holambi Kalan via Naya bans | 7 | ..do... | 20-03-17 | 15.07.17 |  | 100% |  | ..do...
258 | Subhash Chowk Bhakhtawar Pur to Palla | 3.2 | ..do... | 20-03-17 | 15.07.17 |  | 95% (Drain cannot be completely de-silted due to partly katcha drain exists). |  | ..do...
259 | Subhash Chowk Bhakhtawar Pur to Hiranki Bandh | 4.2 | ..do... | 20-03-17 | 15.07.17 |  | 100% |  | ..do...
260 | NH-44 to Bakhtawar Pur | 3.5 | ..do... | 20-03-17 | 15.07.17 |  | 100% |  | ..do...
261 | NH-44 from Nangli Puna to Singhu Border alongwith Service Road (LHS & RHS) | 10 | ..do... | 06-06-17 | 15.07.17 |  | 100%
Sub Division NR-14
262 | Swaroop Nagar Road | 2 | Rahul Builders | 26-03-17 | 15.07.17 | 9056 | 100% | 3667 | ..do...
263 | Railway Road from NH-44 to Badli Railway Station | 1.25 | ..do... | 26-03-17 | 15.07.17 |  | 100% |  | ..do...
264 | ORR Mukarba Chowk Flyover | 6.8 | ..do... | 26-03-17 | 15.07.17 |  | 100% |  | ..do...
265 | Libaspur to Siraspur Road | 0.5 | ..do... | 26-03-17 | 15.07.17 |  | 100% |  | ..do...
266 | G.T. Karnal Road to Libaspur Road | 1.6 | ..do... | 26-03-17 | 15.07.17 |  | 100% |  | ..do...
267 | 66 Ft. Road Libaspur to Gurudwara Road | 1.7 | ..do... | 26-03-17 | 15.07.17 |  | 100% |  | ..do...
268 | G.T. Karnal Road to Siraspur Village | 2 | ..do... | 26-03-17 | 15.07.17 |  | 100% |  | ..do...
269 | Mamchand Dhania Marg | 2.7 | ..do... | 26-03-17 | 15.07.17 |  | 100% |  | ..do...
270 | ITI Road from Main Jahangirpuri Road to Metro App. | 0.324 | ..do... | 26-03-17 | 15.07.17 |  | 100% |  | ..do...
271 | Back side K Block Road from Metro App. to dividing road K Block | 0.17 | ..do... | 26-03-17 | 15.07.17 |  | 100% |  | ..do...
272 | Lucky Park Road from J-51 to J-1951 | 0.5 | ..do... | 26-03-17 | 15.07.17 |  | 100% |  | ..do...
273 | Lucky Park Road to I-2000 (Back Side Road) | 0.35 | ..do... | 26-03-17 | 15.07.17 |  | 100% |  | ..do...
274 | Mangal Bazar Road B Block | 0.55 | ..do... | 26-03-17 | 15.07.17 |  | 100% |  | ..do...
275 | Zonal Park Road C Block | 0.55 | ..do... | 26-03-17 | 15.07.17 |  | 100% |  | ..do...
276 | Jahangirpuri Main Road from G.T. Road Red Light to Fire Station | 1.395 | ..do... | 26-03-17 | 15.07.17 |  | 100% |  | ..do...
277 | Bhalswa Dairy Road from Flood Road to C Block along Bhalswa Lake via Shani Bazar | 1.83 | ..do... | 26-03-17 | 15.07.17 |  | 100% |  | ..do...
278 | G.T Road to Western Yamuna Canal | 2.77 | ..do... | 26-03-17 | 15.07.17 |  | 100% |  | ..do...
279 | NH-44 with service Lane | 3 | ..do... | 26-03-17 | 15.07.17 |  | 100% |  | ..do...
Sub Division NR-15
280 | From Western Yamuna Canal to Auchandi Border | 18.5 | Pawan Kumar Gupta | 20-03-17 | 15.07.17 | 6000 | 100% | 1975 | ..do...
281 | Auchandi Border to Tatesar Village | 9.3 | ..do... | 20-03-17 | 15.07.17 | 7604 | 100% | 1875 | ..do...
282 | Majra Dabbas to Sannoth Mor | 8 | ..do... | 20-03-17 | 15.07.17 |  | 100% |  | ..do...
Circle: West
Division: West Road-1
Sub Division:- WR-11
283 | Goswami Tulsi Dass Marg i.e. Road No. 32 | 3.2 | M/s Shree Vishnu Steel Works | 26.05.17 | 25.07.17 | 6774 | 69% | 4929 | D.R.Yadav 99718738289
284 | Dr. Kundan Lal Marg | 0.84 | ..do... | 26.05.17 | 25.07.17 |  | 62% |  | ..do...
285 | Rajouri Appartment Road | 6 | ..do... | 26.05.17 | 25.07.17 |  | 77% |  | ..do...
286 | H.No. 14/35 to 13/101 Subash Nagar (Near Shandley School) | 0.91 | ..do... | 26.05.17 | 25.07.17 |  | 65% |  | ..do...
287 | Shanti Devi Marg | 0.75 | ..do... | 26.05.17 | 25.07.17 |  | 72% |  | ..do...
288 | Ayodhya Prasad Chopra Marg | 0.9 | ..do... | 26.05.17 | 25.07.17 |  | 70% |  | ..do...
289 | Road No. 32 to 17/117 Subash Nagar | 0.7 | ..do... | 26.05.17 | 25.07.17 |  | 75% |  | ..do...
290 | H.No. 6/1 to 3/200 Subhash Nagar | 1.36 | ..do... | 26.05.17 | 25.07.17 |  | 64% |  | ..do...
291 | Vedic Marg | 2.7 | ..do... | 26.05.17 | 25.07.17 |  | 90% |  | ..do...
292 | H.No. 11/76 to 11/85 Subhash Nagar | 0.1 | ..do... | 26.05.17 | 25.07.17 |  | 60% |  | ..do...
293 | H.No. 8/1 to 14/149 Subhash Nagar | 0.7 | ..do... | 26.05.17 | 25.07.17 |  | 62% |  | ..do...
294 | H.No. 10/1 to 14/97 Subhash Nagar | 0.58 | ..do... | 26.05.17 | 25.07.17 |  | 55% |  | ..do...
295 | Sardar Kulwant Singh Sethi Marg | 2.09 | ..do... | 26.05.17 | 25.07.17 |  | 52% |  | ..do...
296 | DA-1, Hari Nagar to DB-1 Hari Nagar | 0.85 | ..do... | 26.05.17 | 25.07.17 |  | 55% |  | ..do...
297 | Shaheed Bhagat Singh Mrg. (Jail Rd) | 4.56 | ..do... | 26.05.17 | 25.07.17 |  | 65% |  | ..do...
298 | Shaheed Bhagat Singh Mrg. (Jail Rd) | 2.8 | ..do... | 26.05.17 | 25.07.17 |  | 69% |  | ..do...
299 | B-2/Dharam Marg | 2.76 | ..do... | 26.05.17 | 25.07.17 |  | 80% |  | ..do...
300 | Capt. Anuj Nayyar Marg. | 1.34 | ..do... | 26.05.17 | 25.07.17 |  | 67% |  | ..do...
301 | B1- B2 Connecting Road. | 1.18 | ..do... | 26.05.17 | 25.07.17 |  | 62% |  | ..do...
302 | Gurudwara Road | 1.26 | ..do... | 26.05.17 | 25.07.17 |  | 60% |  | ..do...
303 | BA-BB Block Road | 0.76 | ..do... | 26.05.17 | 25.07.17 |  | 57% |  | ..do...
304 | B2 Block Sabzi Mandi Road | 0.8 | ..do... | 26.05.17 | 25.07.17 |  | 60% |  | ..do...
305 | Prem Nagar Gurudwara Rd. | 1.04 | ..do... | 26.05.17 | 25.07.17 |  | 68% |  | ..do...
306 | Major Rajeev Laul Marg | 1.76 | ..do... | 26.05.17 | 25.07.17 |  | 80% |  | ..do...
307 | Shaheed Mangal Pandey Marg | 1.48 | ..do... | 26.05.17 | 25.07.17 |  | 91% |  | ..do...
308 | Bhai Kanheya Ji Marg (ITI Road) | 1.34 | ..do... | 26.05.17 | 25.07.17 |  | 65% |  | ..do...
309 | Mangal Pandey Marg (Hari Nagar Clock Tower to Maya Puri) | 1.7 | ..do... | 26.05.17 | 25.07.17 |  | 95% |  | ..do...
Sub Division:- WR-12
310 | Prof. Joginder Singh Marg (In front of Janakpuri Distt. Centre) | 2.16 | ..do... | 27.05.17 | 25.07.17 | 2405 | 60% | 2210 | ..do...
311 | Authority Road (Janak Puri) | 1.3 | ..do... | 27.05.17 | 25.07.17 |  | 90% |  | ..do...
312 | Mota Singh Road | 1.96 | ..do... | 27.05.17 | 25.07.17 |  | 70% |  | ..do...
313 | Possangi Pur Road | 0.8 | ..do... | 27.05.17 | 25.07.17 |  | 20% |  | ..do...
314 | Major Deepak Tyagi Marg | 1.94 | ..do... | 27.05.17 | 25.07.17 |  | 90% |  | ..do...
315 | A-1 Block Main Road | 1.24 | ..do... | 27.05.17 | 27.06.17 |  | 100% |  | ..do...
316 | Road Opp. A1B Block Janak Puri | 0.56 | ..do... | 27.05.17 | 27.06.17 |  | 100% |  | ..do...
317 | Asalatpur Road | 0.32 | ..do... | 27.05.17 | 10.07.17 |  | 100% |  | ..do...
318 | Asalatpur Road-II | 1.58 | ..do... | 27.05.17 | 25.07.17 |  | 85% |  | ..do...
319 | Najafgarh Road (Shivaji Marg) (Dhauli Piao to Pankha Road Red Light) | 2.5 | ..do... | 27.05.17 | 25.07.17 |  | 60% |  | ..do...
Sub Division:- WR-13
320 | Lala Ganesh Dass Marg | 2.54 | Sh. Ramesh Chander | 14.05.17 | 25.07.17 | 6205 | 80% | 4015 | D.R.Yadav 99718738289
321 | Road between Two Blocks of G- Block Vikas Puri | 0.48 | ..do... | 14.05.17 | 25.07.17 |  | 72% |  | ..do...
322 | From G-1 Block Vikas Puri to Palican Road VikasPuri | 1.04 | ..do... | 14.05.17 | 27.06.17 |  | Handed over to MCD |  | ..do...
323 | Keshopur Sabzi Mandi Red Light (Outer Ring Road) to Subhash Nagar Drain | 0.77 | ..do... | 14.05.17 | 25.07.17 |  | 41% |  | ..do...
324 | Road No. 235 | 0.7 | ..do... | 14.05.17 | 25.07.17 |  | 66% |  | ..do...
325 | Road No. 235 extension | 1.52 | ..do... | 14.05.17 | 25.07.17 |  | 55% |  | ..do...
326 | Chowkhandi Road | 0.44 | ..do... | 14.05.17 | 25.07.17 |  | 90% |  | ..do...
327 | Najafgarh road from Subhash Nagar Crossing to Dhauli Piao | 8.4 | ..do... | 14.05.17 | 25.07.17 |  | 59% |  | ..do...
328 | Tilak Nagar To 20 Block Tilak Vihar | 1 | ..do... | 14.05.17 | 25.07.17 |  | 69% |  | ..do...
329 | Road from H-Block To H-3 Block | 1.08 | ..do... | 14.05.17 | 25.07.17 |  | 87% |  | ..do...
330 | Road from Guruvirjanand Marg to Distt. Park,Vikas Puri | 0.28 | ..do... | 14.05.17 | 25.07.17 |  | 61% |  | ..do...
331 | Shaheed Raj Guru Marg Vikas Puri | 2.56 | ..do... | 14.05.17 | 25.07.17 |  | 75% |  | ..do...
332 | Tilak Vihar Main Road | 1.08 | ..do... | 14.05.17 | 25.07.17 |  | 61% |  | ..do...
333 | Road Adjcent to PVR Complex Vikas Puri | 0.3 | ..do... | 14.05.17 | 25.07.17 |  | 73% |  | ..do...
334 | Pelicon Road from Guru Virzanand Marg to Road No. 235 Extension | 1.82 | ..do... | 14.05.17 | 25.07.17 |  | 69% |  | ..do...
335 | Tilak Nagar Main Market Road | 0.14 | ..do... | 14.05.17 | 25.07.17 |  | 83% |  | ..do...
336 | Brain Public School Road | 1.5 | ..do... | 14.05.17 | 25.07.17 |  | 51% |  | ..do...
337 | K. R. Manglam | 1.08 | ..do... | 14.05.17 | 25.07.17 |  | 75% |  | ..do...
338 | H- Block to Vikas Puri | 0.39 | ..do... | 14.05.17 | 25.07.17 |  | 49% |  | ..do...
339 | 70 Block Park Ashok Nagar to Tihar No. 2 School | 1.04 | ..do... | 14.05.17 | 25.07.17 |  | 88% |  | ..do...
340 | 2/1 to 2/10 Ashok Nagar | 1.2 | ..do... | 14.05.17 | 25.07.17 |  | 38% |  | ..do... | 447
341 | Ashok Nagar Road | 0.64 | ..do... | 14.05.17 | 25.07.17 |  | 60% |  | ..do...
342 | Guruvirja Nanad Marg | 1.7 | ..do... | 14.05.17 | 25.07.17 |  | 80% |  | ..do...
Sub Division:- WR-14
343 | Road No. 236 | 3.6 | ..do... | 03.05.17 | 25.07.17 | 9881 | 98% | 8396 | ..do...
344 | Road No. 237 | 0.9 | ..do... | 03.05.17 | 25.07.17 |  | 98% |  | ..do...
345 | Road between Krishi Appt. to DAV school (PWD Road) | 0.59 | ..do... | 03.05.17 | 25.07.17 |  | 75% |  | ..do...
346 | Road between Devdoot Appt. to Parmarth Appt. PWD Road Vikas Puri | 0.56 | ..do... | 03.05.17 | 25.07.17 |  | 60% |  | ..do...
347 | Road between Jupiter Appt. to Priya Appt. PWD Road Vikas Puri | 0.78 | ..do... | 03.05.17 | 25.07.17 |  | 68% |  | ..do...
348 | Road Between Nalanda Appt. To Nightingale Appt. Vikas Puri | 1.08 | ..do... | 03.05.17 | 25.07.17 |  | 66% |  | ..do...
349 | Road Sunrise Appt. to DAV School (PWD Road) Vikas Puri | 0.87 | ..do... | 03.05.17 | 25.07.17 |  | 66% |  | ..do...
350 | Road from F-234 to IFC drain (Over head tank) Vikas Puri | 0.5 | ..do... | 03.05.17 | 25.07.17 |  | 85% |  | ..do...
351 | Road from ITI Corner (Flat No. 58) to Central School Corner (Flat No. 391) LIG Flat Hastsal | 0.48 | ..do... | 03.05.17 | 25.07.17 |  | 65% |  | ..do...
352 | Road from Navyug Appt. to IFC drain (Brotherhood Appt.) Vikas Puri | 0.54 | ..do... | 03.05.17 | 25.07.17 |  | 98% |  | ..do...
353 | Guruvirja Nanad Marg | 5.4 | ..do... | 03.05.17 | 25.07.17 |  | 90% |  | ..do...
354 | Road starting from Oxford School to Airport Appt. (PWD Road) Vikas Puri | 1.76 | M/s Rajnish Yadav | 03.05.17 | 25.07.17 |  | 90% |  | D.R.Yadav 99718738289
355 | Road between Lok Vihar Appt. (PWD Road) to Fblock Market Vikas Puri | 1.35 | ..do... | 03.05.17 | 25.07.17 |  | 90% |  | ..do...
356 | Nangloi - Najafgarh Road | 11 | ..do... | 03.05.17 | 25.07.17 |  | 90% |  | ..do...
357 | Najafgarh Road (Shivaji Marg) (Pankha Road Red Light to Kakrolla Mor) | 8 | ..do... | 03.05.17 | 25.07.17 |  | 76% |  | ..do...
Sub Division:- WR-15
358 | Keshav Marg | 1.2 | M/s Richcon Engg. Co. | 27.03.17 | 25.07.17 | 6206 | 37% | 2380 | D.R.Yadav 99718738289
359 | Ring road to A-31 rajori garden | 0.09 | ..do... | 27.03.17 | 25.07.17 |  | 50% |  | ..do...
360 | Najafgarh Road to A-71 Rajouri Garden | 0.08 | ..do... | 27.03.17 | 25.07.17 |  | 10% |  | ..do...
361 | Sakti Mandir Marg | 0.4 | ..do... | 27.03.17 | 27.06.17 |  | 100% |  | ..do...
362 | Najafgarh Road | 3.9 | ..do... | 27.03.17 | 25.07.17 |  | 30% |  | ..do...
363 | Major Sudesh Gadok Marg (J 12/1 to NG Road) | 1.24 | ..do... | 27.03.17 | 25.07.17 |  | 3% |  | ..do...
364 | Major Sudesh Marg (NG Road to Ring Road) | 3.8 | ..do... | 27.03.17 | 25.07.17 |  | 28% |  | ..do...
365 | 100' Road (Patel Chowk to Subhash Nagar Drain (Patel Chowk Road) | 1.6 | ..do... | 27.03.17 | 25.07.17 |  | 45% |  | ..do...
366 | 100' Road New Khayala Road | 1.4 | ..do... | 27.03.17 | 25.07.17 |  | 15% |  | ..do...
367 | 80' Road Chowkhandi Road | 2 | ..do... | 27.03.17 | 25.07.17 |  | 45% |  | ..do...
368 | Arya Samaj Marg | 0.24 | ..do... | 27.03.17 | 25.07.17 |  | 40% |  | ..do...
369 | J.Krishnatrey Marg | 0.22 | ..do... | 27.03.17 | 25.07.17 |  | 96% |  | ..do...
370 | AD-1 to BF- 31 (Tagore Garden) | 1.2 | ..do... | 27.03.17 | 25.07.17 |  | 90% |  | ..do...
371 | DE-131 to Community Hall | 0.44 | ..do... | 27.03.17 | 25.07.17 |  | 90% |  | ..do...
372 | Devki Nandan Marg | 1.56 | ..do... | 27.03.17 | 25.07.17 |  | 25% |  | ..do...
373 | Tanki Wala Marg | 0.4 | ..do... | 27.03.17 | 25.07.17 |  | 90% |  | ..do...
374 | Sant Berwa Marg with Titar Pur drain | 1.2 | ..do... | 27.03.17 | 25.07.17 |  | 30% |  | ..do...
375 | Road No. 28 | 1 | ..do... | 27.03.17 | 25.07.17 |  | 85% |  | ..do...
Division: West Road -2
Sub Division WR-21
376 | Najafgarh Road from Zakhira Round about to Moti Nagar | 2.24 | M/s Para Builders | 18/05/2017 | 25/07/2017 | 400 | 85% | 287 | Sh. Manish Kaushik 9650167297
377 | Najafgarh Road from Moti Nagar to Raja Garden | 2.2 | ..do... | 18/05/2017 | 25/07/2017 | 400 | 70% | 190 | ..do...
378 | Shivdass Puri Marg | 2 | ..do... | 18/05/2017 | 25/07/2017 | 250 | 55% | 30 | ..do...
379 | Hemvati Nandan Bahnguma Marg | 0.8 | ..do... | 18/05/2017 | 30/06/2017 | 100 | 100% | 50 | ..do...
380 | Road from Milan Cinema to H. No. 19/289 | 0.42 | ..do... | 18/05/2017 | 30/06/2017 | 50 | 100% | 20 | ..do...
381 | Road from House No. H-1 to I-47 near Milan Cinema Karmapura | 0.4 | ..do... | 18/05/2017 | 30/06/2017 | 50 | 100% | 20 | ..do...
382 | Road from HIL to Bus Terminal of 234, Karampura | 0.412 | ..do... | 18/05/2017 | 30/06/2017 | 50 | 100% | 20 | ..do...
383 | Punjab Garden Road | 0.21 | ..do... | 18/05/2017 | 30/06/2017 | 50 | 100% | 20 | ..do...
384 | Smt. Ginni Devi Road | 0.75 | ..do... | 18/05/2017 | 30/06/2017 | 50 | 100% | 20 | ..do...
385 | Bhagwan Dass Marg (K.C. Garg Marg) | 0.3 | ..do... | 18/05/2017 | 30/06/2017 | 50 | 100% | 20 | ..do...
386 | Ring Road from Punjabi Bagh to Maya Puri | 4.81 | ..do... | 18/05/2017 | 30/06/2017 | 500 | 100% | 420 | ..do...
387 | Rohtak Road from Zakhira to Punjabi Bagh | 2.1 | ..do... | 18/05/2017 | 30/06/2017 | 500 | 100% | 200 | ..do...
388 | Road from Road No. 36 (Sat Guru Ram Singh Marg (Maya Puri Chowk to SD Public School) | 2 | ..do... | 18/05/2017 | 25/07/2017 | 300 | 85% | 100 | ..do...
389 | Rama Road (Satguru Ram Singh Marg) | 1.2 | ..do... | 18/05/2017 | 30/06/2017 | 200 | 100% | 90 | ..do...
390 | Rama Road (Satguru Ram Singh Marg) | 1.695 | ..do... | 18/05/2017 | 25/07/2017 | 200 | 80% | 90 | ..do...
391 | Road from Bus Route B-14 Tagore Market to G-82 Kirti Nagar | 0.91 | ..do... | 18/05/2017 | 25/07/2017 | 200 | 71% | 25 | ..do...
392 | Major Rajive Bhasin Marg D/Story | 0.78 | M/s Para Builders | 18/05/2017 | 25/07/2017 | 100 | 41% | 10 | Sh. Manish Kaushik 9650167297
393 | Pankaj Batra Marg | 0.77 | ..do... | 18/05/2017 | 25/07/2017 | 100 | 80% | 40 | ..do...
394 | Lai Sai Mandir Marg D/Story | 0.325 | ..do... | 18/05/2017 | 25/07/2017 | 100 | 80% | 82 | ..do...
395 | 80' wide Road MS Garden Road | 2.49 | ..do... | 18/05/2017 | 25/07/2017 | 300 | 76% | 96 | ..do...
396 | Patel Road | 2.93 | ..do... | 18/05/2017 | 25/07/2017 | 300 | 51% | 30 | ..do...
397 | Vishwakarma Marg | 1 | ..do... | 18/05/2017 | 25/07/2017 | 100 | 82% | 25 | ..do...
398 | T-Sohan Lal Marg | 0.9 | ..do... | 18/05/2017 | 25/07/2017 | 100 | 52% | 12 | ..do...
399 | Link Road No. 2 | 0.18 | ..do... | 18/05/2017 | 25/07/2017 | 100 | 61% | 25 | ..do...
400 | Suman Lata Badola Marg | 0.243 | ..do... | 18/05/2017 | 09/06/2017 | 100 | 100% | 100 | ..do...
401 | Madhav Setu Marg | 0.605 | ..do... | 18/05/2017 | 30/06/2017 | 100 | 100% | 100 | ..do...
Sub Division WR-22 | [8 empty] | ..do...
402 | Hiran Kudna Road (NH-10) | 3.95 | Sh. Inderjit Singh | 22/04/2017 | 09/06/2017 | 3200 | 100% | 150 | ..do...
403 | Road from Ghevra More to Kanjhawala | 7.9 | ..do... | 22/04/2017 | 25/07/2017 | 4500 | 88% | 170 | ..do...
404 | Guru Golwalkar Marg (Road No. 3) | 9.8 | ..do... | 22/04/2017 | 25/07/2017 | 5173 | 88% | 90 | ..do...
405 | NH-10 (Delhi Rohtak Road) From Metro Pillar No. 410 to Tikri Border | 9.573 | Sh. Sanjay Kaura | 22/04/2017 | 25/07/2017 | 945 | 71% | 75 | ..do...
Sub Division WR-23
406 | NH-10 (Delhi Rohtak Road) road from Peeragarhi Chowk to Metro Pillar No. 410 | 3.627 | M/s Rahul Builders | 23/03/2017 | 30/06/2017 | 600 | 100% | 550 | ..do... | 240
407 | Road from Outer Ring Road Meera Bagh to GH-8 Fire station Paschim Vihar | 1.251 | ..do... | 23/03/2017 | 30/06/2017 | 350 | 100% | 330 | ..do...
408 | Road from GH-6 Chowk to GH-5 and 7 Paschim Vihar | 0.292 | ..do... | 23/03/2017 | 09/06/2017 | 250 | 100% | 250 | ..do...
409 | Road from Garg Plaza to L.I.C. Colony Paschim Vihar | 1.322 | ..do... | 23/03/2017 | 30/06/2017 | 250 | 100% | 245 | ..do...
410 | Road from Sai Baba Mandir GH-12 to GH-8 Fire station Paschim Vihar | 0.963 | ..do... | 23/03/2017 | 09/06/2017 | 250 | 100% | 250 | ..do...
411 | Road from Outer Ring Road Bhera Enclave to Sai Baba Mandir Paschim Vihar | 1.251 | ..do... | 23/03/2017 | 30/06/2017 | 800 | 100% | 780 | ..do...
412 | Road from GH-13 to Sayed Nangloi Village Chowk Paschim Vihar | 0.902 | ..do... | 23/03/2017 | 30/06/2017 | 400 | 100% | 380 | ..do...
413 | Road from Sant Mar'ks School to DDA Mkt. GH-5&7 Paschim Vihar | 0.435 | ..do... | 23/03/2017 | 09/06/2017 | 300 | 100% | 300 | ..do...
414 | Laxmi Narain Marg (N.S. Road) | 0.7 | ..do... | 23/03/2017 | 09/06/2017 | 350 | 100% | 350 | ..do...
415 | Ch. Prem Sukh Road | 1.292 | ..do... | 23/03/2017 | 30/06/2017 | 800 | 100% | 780 | ..do...
416 | 60' road in Jawala Puri | 1.15 | ..do... | 23/03/2017 | 30/06/2017 | 500 | 100% | 450 | ..do...
417 | Road from Capital Plaza Market to Jhaj Aptt. Mianwali Nagar | 0.35 | ..do... | 23/03/2017 | 09/06/2017 | 200 | 100% | 200 | ..do...
418 | Road from Vindhachal Aptt. To Viral Co. Op. Society Mianwali Nagar | 0.35 | ..do... | 23/03/2017 | 09/06/2017 | 300 | 100% | 300 | ..do...
419 | Road from Rblock jwalapuri to Sai mandir Guru Harkishan Nagar | 0.36 | ..do... | 23/03/2017 | 09/06/2017 | 350 | 100% | 350 | ..do... | 7.5
420 | Outer Ring Road No. 26 | 2.08 | ..do... | 23/03/2017 | 30/06/2017 | 800 | 100% | 720 | ..do...
421 | Nangloi- Najafgarah Road | 2.5 | ..do... | 23/03/2017 | 30/06/2017 | 1900 | 100% | 1800 | ..do...
Sub Division WR-24
422 | Road No./ 33 from 48 NWA Ch. Balbir Singh Marg to Road No. 32 | 0.39 | M/s Park Infrastructure Ltd. | 23/03/2017 | 25/07/2017 | 30 | 86% | 18 | Sh. Manish Kaushik 9650167297
423 | Vashisth Kumar Gulla Marg | 1.39 | ..do... | 23/03/2017 | 09/06/2017 | 60 | 100% | 60 | ..do...
424 | N.A. Road | 1 | ..do... | 23/03/2017 | 10/05/2017 | 20 | 100% | 20 | ..do...
425 | Ch. Balbir Singh Marg (Club Road) | 1.41 | ..do... | 23/03/2017 | 30/06/2017 | 60 | 100% | 50 | ..do...
426 | Road from Sant Bairwa Marg to Road No. 28 | 0.39 | ..do... | 23/03/2017 | 10/05/2017 | 25 | 100% | 25 | ..do...
427 | Road from R-17 to D-335 Raghubir Nagar | 0.192 | ..do... | 23/03/2017 | 25/07/2017 | 10 | 84% | 6 | ..do...
428 | Road from C-1 to C-494 Raghubir Nagar | 0.188 | ..do... | 23/03/2017 | 25/07/2017 | 10 | 84% | 10 | ..do...
429 | Road from Road no. 29 to R Block "T" Hart | 1.18 | ..do... | 23/03/2017 | 25/07/2017 | 75 | 85% | 40 | ..do...
430 | Road from front of Ambedkar Market from Shop No. 1 to 130, Raghubir Nagar | 0.305 | ..do... | 23/03/2017 | 25/07/2017 | 30 | 70% | 18 | ..do...
431 | Road from Najafgarh Road to Flat No. 13, Four Storey Qtrs. Tagore Garden Extension | 0.19 | ..do... | 23/03/2017 | 09/06/2017 | 40 | 100% | 40 | ..do... | 31.5
432 | Road from A-23 Vishal Enclave (NG Road) to B-33 Vishal Enclave (PWD Road No. 28) (Vishal Cinema Road) | 0.7 | ..do... | 23/03/2017 | 09/06/2017 | 40 | 100% | 40 | ..do...
433 | Road from Flat No. 157 Four Story to Vishal Road (opp. Police Station Rajouri Garden) | 0.47 | ..do... | 23/03/2017 | 25/07/2017 | 50 | 83% | 41.5 | ..do...
434 | Road from Bhagat Singh Colony (opp. Plot No. 66 Shivaji Enclave) to FA-33 Shivaji Enclave (On PWD Road No. 28) | 0.6 | ..do... | 23/03/2017 | 25/07/2017 | 70 | 83% | 45 | ..do...
435 | Shri Krishan Gyan Mandir Marg | 0.66 | ..do... | 23/03/2017 | 25/07/2017 | 80 | 38% | 20 | ..do...
436 | Road from Shivaji College (PWD Road No. 28) to Bhagat Singh Colony | 0.71 | ..do... | 23/03/2017 | 25/07/2017 | 80 | 83% | 64 | ..do...
437 | NH-10 (Delhi Rohtak Road) road from Punjabi Bagh to Peeragarhi Chowk | 4.5 | ..do... | 23/03/2017 | 25/07/2017 | 1100 | 45% | 495 | ..do...
438 | Road from Paschim Puri Chowk to New Slum Qtrs. | 0.45 | ..do... | 23/03/2017 | 20/06/2017 | 25 | 100% | 25 | ..do...
439 | Road from Shiv Mndir Road (Rohtak Road) to shiv Mandir Madipur Village | 0.7 | ..do... | 23/03/2017 | 10/05/2017 | 60 | 100% | 60 | ..do...
440 | Road from Madipur Main Road from Rohtak Road to Paschim Puri Chowk | 1 | ..do... | 23/03/2017 | 25/07/2017 | 70 | 81% | 46 | ..do...
441 | Maharishi Road from B-1 to C-17 | 0.475 | ..do... | 23/03/2017 | 10/05/2017 | 0 | 100% | 0 | ..do...
442 | Road No. 77 from Hans Raj Model School to Punjabi Bagh DTC Depot | 1.51 | ..do... | 23/03/2017 | 25/07/2017 | 300 | 84% | 252 | ..do... | 6
443 | Road from H.No. A-250 to Shiv Mandir Road in C-103 Punjabi Bagh | 0.48 | ..do... | 23/03/2017 | 10/05/2017 | 10 | 100% | 10 | ..do...
444 | Road No. 4 from H. No. 11 and North West Avenue Road to 23/4 in Punjabi Bagh Extn. | 0.15 | ..do... | 23/03/2017 | 10/05/2017 | 10 | 100% | 10 | ..do...
445 | Road No. 28 | 1.93 | ..do... | 23/03/2017 | 25/07/2017 | 70 | 85% | 35 | ..do...
446 | Road No. 29 | 2.8 | ..do... | 23/03/2017 | 25/07/2017 | 150 | 85% | 90 | ..do...
447 | Road from Road No. 41 from H.No. 1 to 81 in West Punjabi Bagh | 1.715 | ..do... | 23/03/2017 | 25/07/2017 | 150 | 30% | 38 | ..do...
448 | Major Sunil Bakshi Marg Road from H-1 Bali Nagar (NG Road) to ESI Hospital (Ring Road) | 0.52 | ..do... | 23/03/2017 | 30/06/2017 | 30 | 100% | 26 | ..do...
449 | Road from Najafgarh Road to WZ-494, Basai Darapur (Sheo Nath Tyagi Marg) | 0.675 | ..do... | 23/03/2017 | 25/07/2017 | 30 | 87% | 26 | ..do...