## All sub diviison (hidden)
DETAILS OF DESILTING OF DRAIN UNDER SOUTH WEST ROAD - I AS ON DATED 22.05.2017
Sl. No. | Name of drain | Contractor | Length of drain | Date of start | Revised date of completion | Estimated Qty. of silt | % drain cleaned lengthwise | Qty. of silt lifted and disposed off.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Sub division -1
1 | B.J. Marg | M/s Amocon | 1800 Mtr. | 15.05.2017 | 15.06.2017 | - | 5% | -
2 | Rao Tula Ram Marg (RTR Marg) | M/s Amocon | 3200 Mtr. | 15.04.2017 | 15.06.2017 | - | 75% | -
3 | Zonal road No. 2 (Baba Balak Nath Marg) | M/s Amocon | 1750 Mtr. | 01.06.2017 | 15.06.2017 | - | - | -
4 | Zonal Road No. 6 (Hare Krishna Mehto Marg) | M/s Amocon | 700 Mtr. | 01.06.2017 | 15.06.2017 | - | - | -
5 | M.M.Road | Sh. T.P. Singh | 4250 Mtr. | 15.04.2017 | 15.06.2017 | - | 50% | -
6 | Ullan Buttor Marg | Sh. Vinay Shankar | 550 Mtr. | 01.06.2017 | 15.06.2017 | - | - | -
7 | Nelson Mandela Marg | Sh. T.P. Singh | 5200 Mtr. | 15.04.2017 | 15.06.2017 | - | 25% | -
8 | Baba Gang Nath marg | Sh. T.P. Singh | 2150 Mtr. | 15.05.2017 | 15.06.2017 | - | 20% | -
9 | Outer Ring Road | Sh. Vinay Shankar | 6160 Mtr. | 15.05.2017 | 15.06.2017 | - | 2% | -
10 | Vatika Road (DPS Vasant Kunj to MM road) | Sh. Vinay Shankar | 2150 Mtr. | 15.04.2017 | 15.06.2017 | - | 10% | -
Sub division - 2
11 | Africa Avenue (Road No.9) | Sh. Brijpal Singh | 4400 Mtr. | 18.05.2017 | 15.06.2017 | - | 15% | -
12 | Tamil Sangam Marg | - | - | - | - | - | - | -
13 | Major Som nath marg | - | - | - | - | - | - | -
14 | Kafi Azami Marg | - | - | - | - | - | - | -
15 | Church Road, R.K.Puram | - | - | - | - | - | - | -
16 | Babu Genu Marg, R.K.Puram | - | - | - | - | - | - | -
17 | Prem nath Dogra marg, R.K.Puram | - | - | - | - | - | - | -
18 | Kama Koti Marg | - | - | - | - | - | - | -
19 | Vivekanand Marg | - | - | - | - | - | - | -
20 | Venketeshwar Marg | Sh. Brijpal Singh | 2200 Mtr. | 18.05.2017 | 15.06.2017 | - | 10% | -
21 | Ring Road (Under DMRC) | - | - | - | - | - | - | -
22 | Basant marg-I | - | - | - | - | - | - | -
23 | Basant Marg-II | - | - | - | - | - | - | -
24 | Poorvi Marg | - | - | - | - | - | - | -
25 | Paschimi Marg | - | - | - | - | - | - | -
26 | Munirka marg | - | - | - | - | - | - | -
27 | A-9 Street Road | - | - | - | - | - | - | -
Sub division - 3
28 | Ganga Ram Hospital Road | Sh. Bishwa Mohan Jha | 1.08 | 03.04.2017 | 02.11.2017 | - | - | -
29 | PUSA Road | Sh. Bishwa Mohan Jha | 1.50 actual 2.00 KM | 03.04.2017 | 02.11.2017 | - | - | -
30 | Shankar Road | Sh. Bishwa Mohan Jha | 1.64 | 03.04.2017 | 02.11.2017 | - | - | -
31 | Dr. K.S. Krishanan Marg | Sh. Bishwa Mohan Jha | 0.92 | 03.04.2017 | 02.11.2017 | - | 60% | -
32 | PUSA Institute (IARI) Internal Road | Sh. Bishwa Mohan Jha | 0.7 | 03.04.2017 | 02.11.2017 | - | 10% | -
33 | Dev Prakash Shastri marg (Road No. 25) | Sh. Bishwa Mohan Jha | 4.45 | 03.04.2017 | 02.11.2017 | - | 25% | -
34 | Girdhari Lal Goswami Marg (Road No. 89) | Sh. Bishwa Mohan Jha | 3.65 | 03.04.2017 | 02.11.2017 | - | 25% | -
35 | Ram Nath Vij Marg | Sh. Bishwa Mohan Jha | 1.19 | 03.04.2017 | 02.11.2017 | - | - | -
36 | O.P. Bharti Marg 1 | Sh. Bishwa Mohan Jha | 0.54 | 03.04.2017 | 02.11.2017 | - | - | -
37 | O.P. Bharti Marg 2 | Sh. Bishwa Mohan Jha | 0.76 | 03.04.2017 | 02.11.2017 | - | 5% | -
38 | O.P. Bharti Marg 3 | Sh. Bishwa Mohan Jha | 0.18 | 03.04.2017 | 02.11.2017 | - | 50% | -
39 | O.P. Bharti Marg 4 | Sh. Bishwa Mohan Jha | 0.42 | 03.04.2017 | 02.11.2017 | - | - | -
Sub Division - 4
40 | Mahatma gandhi Marg (Ring Road) | Sh. Bishwa Mohan Jha | 8.6 | 04.04.2017 | 03.08.2017 | - | 55% | -
41 | NH-8 | Sh. Bishwa Mohan Jha | 2.9 | 04.04.2017 | 03.08.2017 | - | 40% | -
42 | Upper Ridge Road (Vande Martram Marg) | No Drainage exit
43 | Road No. 36(Sat Guru Ram Singh Marg) | Sh. Rajnish Yadav | 3.4 | 25.03.2017 | 17.07.2017 | - | 30% | -
Sub Division - 5
44 | MM Road | M/s R.R. construction | 6800 Mtr. | 10.05.2017 | 15.06.2017 | - | 15% | -
Certificate
It is certified that the above mentioned information are correct
Junior Engineer |  | Assistant Engineer |  | Executive Engineer

## Modified dated 23.05.2017 (hidden)
DETAILS OF DESILTING OF DRAIN UNDER SOUTH WEST ROAD - I AS ON DATED 23.05.2017
Sl. No. | Name of drain | Contractor | Length of drain | Date of start | Revised date of completion | Estimated Qty. of silt (appx.) | % drain cleaned lengthwise | Qty. of silt lifted and disposed off. (appx.)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Sub division -1
1 | B.J. Marg | M/s Amocon | 1800 | 15.05.2017 | 15.06.2017 | 500 | 5% | 25
2 | Rao Tula Ram Marg (RTR Marg) | M/s Amocon | 3200 | 15.04.2017 | 15.06.2017 | 400 | 75% | 400
3 | Zonal road No. 2 (Baba Balak Nath Marg) | M/s Amocon | 1750 | 01.06.2017 | 15.06.2017 | 504 | - | -
4 | Zonal Road No. 6 (Hare Krishna Mehto Marg) | M/s Amocon | 700 | 01.06.2017 | 15.06.2017 | 201.6 | - | -
3 | M.M.Road | Sh. T.P. Singh | 4250 | 15.04.2017 | 15.06.2017 | 850 | 50% | 400
6 | Ullan Buttor Marg | Sh. Vinay Shankar | 5500 | 01.06.2017 | 15.06.2017 | 1584 | - | -
4 | Nelson Mandela Marg | Sh. T.P. Singh | 5200 | 15.04.2017 | 15.06.2017 | 700 | 25% | 175
5 | Baba Gang Nath marg | Sh. T.P. Singh | 2150 | 15.05.2017 | 15.06.2017 | 400 | 20% | 80
6 | Outer Ring Road | Sh. Vinay Shankar | 6160 | 15.05.2017 | 15.06.2017 | 950 | 2% | 20
7 | Vatika Road (DPS Vasant Kunj to MM road) | Sh. Vinay Shankar | 2150 | 15.04.2017 | 15.06.2017 | 350 | 10% | 35
Sub division - 2
8 | Africa Avenue (Road No.9) | Sh. Brijpal Singh | 4400 | 18.05.2017 | 15.06.2017 | 600 | 15% | 90
12 | Tamil Sangam Marg | - | - | - | - | #VALUE! | - | #VALUE!
13 | Major Som nath marg | - | - | - | - | #VALUE! | - | #VALUE!
14 | Kafi Azami Marg | - | - | - | - | #VALUE! | - | #VALUE!
15 | Church Road, R.K.Puram | - | - | - | - | #VALUE! | - | #VALUE!
16 | Babu Genu Marg, R.K.Puram | - | - | - | - | #VALUE! | - | #VALUE!
17 | Prem nath Dogra marg, R.K.Puram | - | - | - | - | #VALUE! | - | #VALUE!
18 | Kama Koti Marg | - | - | - | - | #VALUE! | - | #VALUE!
19 | Vivekanand Marg | - | - | - | - | #VALUE! | - | #VALUE!
9 | Venketeshwar Marg | Sh. Brijpal Singh | 2200 | 18.05.2017 | 15.06.2017 | 200 | 10% | 20
21 | Ring Road (Under DMRC) | - | - | - | - | - | - | -
22 | Basant marg-I | - | - | - | - | - | - | -
23 | Basant Marg-II | - | - | - | - | - | - | -
24 | Poorvi Marg | - | - | - | - | - | - | -
25 | Paschimi Marg | - | - | - | - | - | - | -
26 | Munirka marg | - | - | - | - | - | - | -
27 | A-9 Street Road | - | - | - | - | - | - | -
Sub division - 3
13 | Ganga Ram Hospital Road | Sh. Bishwa Mohan Jha | 1080 | 03.04.2017 | 02.11.2017 | 311.04 | - | -
14 | PUSA Road | Sh. Bishwa Mohan Jha | 1500 | 03.04.2017 | 02.11.2017 | 432 | - | -
15 | Shankar Road | Sh. Bishwa Mohan Jha | 1640 | 03.04.2017 | 02.11.2017 | 472.32 | - | -
10 | Dr. K.S. Krishanan Marg | Sh. Bishwa Mohan Jha | 920 | 03.04.2017 | 15.06.2017 | 250 | 60% | 160
11 | PUSA Institute (IARI) Internal Road | Sh. Bishwa Mohan Jha | 700 | 03.04.2017 | 15.06.2017 | 200 | 10% | 20
12 | Dev Prakash Shastri marg (Road No. 25) | Sh. Bishwa Mohan Jha | 4450 | 03.04.2017 | 15.06.2017 | 1200 | 25% | 300
13 | Girdhari Lal Goswami Marg (Road No. 89) | Sh. Bishwa Mohan Jha | 3650 | 03.04.2017 | 15.06.2017 | 1000 | 25% | 250
20 | Ram Nath Vij Marg | Sh. Bishwa Mohan Jha | 1190 | 03.04.2017 | 02.11.2017 | 342.72 | - | -
21 | O.P. Bharti Marg 1 | Sh. Bishwa Mohan Jha | 540 | 03.04.2017 | 02.11.2017 | 155.52 | - | -
14 | O.P. Bharti Marg 2 | Sh. Bishwa Mohan Jha | 760 | 03.04.2017 | 15.06.2017 | 200 | 5% | 10
15 | O.P. Bharti Marg 3 | Sh. Bishwa Mohan Jha | 180 | 03.04.2017 | 15.06.2017 | 50 | 50% | 25
24 | O.P. Bharti Marg 4 | Sh. Bishwa Mohan Jha | 420 | 03.04.2017 | 02.11.2017 | 120.96 | - | -
Sub Division - 4
16 | Mahatma gandhi Marg (Ring Road) (both side) | Sh. Bishwa Mohan Jha | 12700 | 04.04.2017 | 15.06.2017 | 1850 | 55% | 600
17 | NH-8 (both side) | Sh. Bishwa Mohan Jha | 2300 | 04.04.2017 | 15.06.2017 | 400 | 40% | 250
42 | Upper Ridge Road (Vande Martram Marg) | No Drainage exit
18 | Road No. 36(Sat Guru Ram Singh Marg) (both side) | Sh. Rajnish Yadav | 6400 | 25.03.2017 | 15.06.2017 | 1400 | 30% | 300
Sub Division - 5
19 | MM Road | M/s R.R. construction | 6800 | 10.05.2017 | 15.06.2017 | 1000 | 15% | 150
Note: Lifted silt yet to be disposed
Certificate
It is certified that the above mentioned information are correct
Junior Engineer |  | Assistant Engineer |  | Executive Engineer

## Modified dated 05.06.2017 (hidden)
DETAILS OF DESILTING OF DRAINS UNDER SOUTH WEST ROAD - I AS ON DATED 05.06.2017
Sl. No. | Name of Road/ drain | Length of Road (Km) | Contractor | Date of start of De-silting | Date of completion (1st Cycle) | % drain cleaned (Lengthwise) | Estimate Qty. of silt (cum) | Qty. of silt lifted and disposed off. (appx.) | EE in Charge/ Mobile No.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Sub division -1
1 | B.J. Marg | 1.3 | M/s Amocon | 15.05.2017 | 15.06.2017 | 50% | 500 | 220 | Sh. S K Sinha 9958469778
2 | Rao Tula Ram Marg (RTR Marg) | 1.7 |  | 15.04.2017 | 15.06.2017 | 80% | 400 | 400
3 | Zonal road No. 2 (Baba Balak Nath Marg) | 1750 |  | 01.06.2017 | 15.06.2017 | - | #VALUE! | -
4 | Zonal Road No. 6 (Hare Krishna Mehto Marg) | 700 |  | 01.06.2017 | 15.06.2017 | - | #VALUE! | -
3 | Baba Balak Nath Marg | 1.1 |  | 01.06.2017 | 15.06.2017 | 25% | 265 | 45
4 | M.M.Road | 3 | Sh. T.P. Singh | 15.04.2017 | 15.06.2017 | 55% | 850 | 510
6 | Ullan Buttor Marg | 5500 |  | 01.06.2017 | 15.06.2017 | - | #VALUE! | -
5 | Nelson Mandela Marg | 4.01 |  | 15.04.2017 | 15.06.2017 | 35% | 700 | 265
6 | Baba Gang Nath marg | 1.17 |  | 15.05.2017 | 15.06.2017 | 30% | 400 | 165
7 | Outer Ring Road | 4.8 | Sh. Vinay Shankar | 15.05.2017 | 15.06.2017 | 12% | 950 | 160
8 | Vatika Road (DPS Vasant Kunj to MM road) | 1.7 |  | 15.04.2017 | 15.06.2017 | 10% | 350 | 95
Sub division - 2
9 | Africa Avenue (Road No.9) | 2.2 | M/s Amocon | 18.05.2017 | 15.06.2017 | 65% | 600 | 390
12 | Tamil Sangam Marg | 1.1 |  | - | - | - | #VALUE! | #VALUE!
13 | Major Som nath marg |  |  | - | - | - | #VALUE! | #VALUE!
14 | Kafi Azami Marg |  |  | - | - | - | #VALUE! | #VALUE!
15 | Church Road, R.K.Puram |  |  | - | - | - | #VALUE! | #VALUE!
16 | Babu Genu Marg, R.K.Puram |  |  | - | - | - | #VALUE! | #VALUE!
17 | Prem nath Dogra marg, R.K.Puram |  |  | - | - | - | #VALUE! | #VALUE!
18 | Kama Koti Marg |  |  | - | - | - | #VALUE! | #VALUE!
19 | Vivekanand Marg |  |  | - | - | - | #VALUE! | #VALUE!
10 | Venketeshwar Marg | 1.1 |  | 18.05.2017 | 15.06.2017 | 95% | 200 | 190
11 | Major Som Nath Marg | 0.9 |  | 18.05.2017 | 15.06.2017 | 85% | 324 | 275.4
12 | Amar Shaheed Babu Genu Marg | 0.9 |  | 18.05.2017 | 15.06.2017 | 80% | 324 | 259.2
13 | Tamil Sangam Marg | 0.5 |  | 18.05.2017 | 15.06.2017 | 30% | 180 | 54
14 | Kaifi Azmi Marg | 1.3 |  | 18.05.2017 | 15.06.2017 | 85% | 468 | 397.8
15 | Swami Vivekanand Marg | 2 |  | 18.05.2017 | 15.06.2017 | 30% | 576 | 172.8
16 | Church Road | 1.6 |  | 18.05.2017 | 15.06.2017 | 30% | 180 | 54
17 | Munirka Marg | 0.5 |  | 18.05.2017 | 15.06.2017 | 85% | 180 | 153
18 | Poorvi Marg | 0.5 |  | 18.05.2017 | 15.06.2017 | 15% | 200 | 30
19 | Dr. Prem Nath Dogra Marg | 0.6 |  | 18.05.2017 | 15.06.2017 | 10% | 200 | 20
21 | Ring Road (Under DMRC) | - | - | - | - | - | - | -
22 | Basant marg-I | - | - | - | - | - | - | -
23 | Basant Marg-II | - | - | - | - | - | - | -
24 | Poorvi Marg | - | - | - | - | - | - | -
25 | Paschimi Marg | - | - | - | - | - | - | -
26 | Munirka marg | - | - | - | - | - | - | -
27 | A-9 Street Road | - | - | - | - | - | - | -
Sub division - 3
13 | Ganga Ram Hospital Road | Sh. Bishwa Mohan Jha | 1080 | 03.04.2017 | 02.11.2017 | 311.04 | - | -
14 | PUSA Road | Sh. Bishwa Mohan Jha | 1500 | 03.04.2017 | 02.11.2017 | 432 | - | -
15 | Shankar Road | Sh. Bishwa Mohan Jha | 1640 | 03.04.2017 | 02.11.2017 | 472.32 | - | -
20 | Ganga Ram Hospital Road | 1.08 | Sh. Bishwa Mohan Jha | 03.04.2017 | 15.06.2017 | 70% | 250
21 | Shankar Road | 1.64 |  | 03.04.2017 | 15.06.2017 | 60% | 350
22 | Dr. K.S. Krishanan Marg | 0.92 |  | 03.04.2017 | 15.06.2017 | 85% | 250 | 200
23 | PUSA Institute (IARI) Internal Road | 0.7 |  | 03.04.2017 | 15.06.2017 | 40% | 200 | 20
24 | Dev Prakash Shastri marg (Road No. 25) | 4.45 |  | 03.04.2017 | 15.06.2017 | 40% | 1200 | 420
25 | Girdhari Lal Goswami Marg (Road No. 89) | 3.65 |  | 03.04.2017 | 15.06.2017 | 60% | 1000 | 400
20 | Ram Nath Vij Marg | 0.76 |  | 03.04.2017 | 02.11.2017 | - | #VALUE! | #VALUE!
21 | O.P. Bharti Marg 1 | 0.18 |  | 03.04.2017 | 02.11.2017 | - | #VALUE! | #VALUE!
26 | O.P. Bharti Marg 2 | 0.76 |  | 03.04.2017 | 15.06.2017 | 50% | 200 | 20
27 | O.P. Bharti Marg 3 | 0.18 |  | 03.04.2017 | 15.06.2017 | 80% | 50 | 30
24 | O.P. Bharti Marg 4 | Sh. Bishwa Mohan Jha | 420 | 03.04.2017 | 02.11.2017 | 120.96 | - | -
Sub Division - 4
28 | Mahatma gandhi Marg (Ring Road) (both side) | 5.5 | Sh. Bishwa Mohan Jha | 04.04.2017 | 15.06.2017 | 62% | 1850 | 650
29 | NH-8 (both side) | 2.9 |  | 04.04.2017 | 15.06.2017 | 57% | 400 | 300
42 | Upper Ridge Road (Vande Martram Marg) | No Drainage exit
30 | Road No. 36(Sat Guru Ram Singh Marg) (both side) | 3.4 | Sh. Bishwa Mohan Jha | 25.03.2017 | 15.06.2017 | 42% | 1400 | 550
Sub Division - 5
31 | MM Road | 6.8 | M/s R.R. construction | 10.05.2017 | 15.06.2017 | 55% | 1000 | 510
Note: Lifted silt yet to be disposed
Certificate
It is certified that the above mentioned information are correct
Junior Engineer |  | Assistant Engineer |  | Executive Engineer

## Desilting as on 18.08.2017
PWD CHIEF ENIGNEER (SOUTH M)
PWD Desilting Report (Preparedness for Monsoon)
DESILTING UNDER PWD MAINTENANCE SOUTH EAST CIRCLE AS ON 18.08.2017
Sl. No. | Name of Road / Drain | Length of Road (Km) | Contractor | Date of start of De-silting | Date of completion (2nd Cycle) | % drain cleaned (Lengthwise) (2nd Cycle) | Estimate Qty. of silt (cum) | Qty. of silt lifted and disposed off. (appx.) (M.T) | EE in Charge/ Mobile No.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
South-East Circle
EE/SER-I/R-11
1 | Raja Dheer Sain marg | 2.38 | Sh. Jagdish Prasad Meena | 15.04.2017 | 31.08.2017 | 60% | 511.7 | 307.02 | Er. Sheel Rajneesh, 8527021144
2 | Kalka Devi Marg | 1.12 |  | 15.04.2017 | 31.08.2017 | 60% | 346.21 | 207.726
3 | Gaptain Gaur Marg | 2.15 |  | 15.04.2017 | 31.08.2017 | 60% | 1272.15 | 763.29
4 | Road No. 3 Andrews Ganj | 0.75 |  | 15.04.2017 | 31.08.2017 | 80% | 18.48 | 11.088
5 | Road No. 7 Andrews Ganj | 0.24 |  | 15.04.2017 | 31.08.2017 | 80% | 5.96 | 3.576
6 | Road No. 5 Andrews Ganj | 0.13 |  | 15.04.2017 | 31.08.2017 | 80% | 13.28 | 7.968
7 | Road No. 2 Andrews Ganj | 0.4 |  | 15.04.2017 | 31.08.2017 | 80% | 6.76 | 4.056
8 | Road No. 6 Andrews Ganj | 0.24 |  | 15.04.2017 | 31.08.2017 | 80% | 12.48 | 7.488
9 | Kalka Devi Marg to Banglow Road | 0.47 |  | 15.04.2017 | 31.08.2017 | 80% | 166.99 | 100.194
10 | Central Road to Back Ring Road to Lajpat Nagar-IV | 0.35 |  | 15.04.2017 | 31.08.2017 | 80% | 158.19 | 94.914
11 | Dr. Moti Lal Jotwani Road to Lajpat Nagar-IV | 0.49 |  | 15.04.2017 | 31.08.2017 | 80% | 195.28 | x
12 | Theka Road S.N. Puri | 0.25 |  | 15.04.2017 | 31.08.2017 | 60% | 89.74 | 53.844
13 | Shri Niwas Puri internal Road MCD Store Round about via Maternity Home. | 0.91 |  | 15.04.2017 | 31.08.2017 | 60% | 279.98 | 167.988
14 | S.N. Puri internal Road opposite Police Post S.N. Puri | 0.15 |  | 15.04.2017 | 31.08.2017 | 60% | 11.23 | 6.738
15 | S.N. Puri internal Road Post office to CPWD Via Jal Board | 0.54 |  | 15.04.2017 | 31.08.2017 | 60% | 216.92 | 130.152
16 | Banglow Road to Gidwani Marg Lajpat | 0.12 |  | 15.04.2017 | 31.08.2017 | 80% | 39.74 | 23.844
17 | S.N. Puri Main Road from Cambridge School to CTC | 1.4 |  | 15.04.2017 | 31.08.2017 | 60% | 370.94 | 222.564
18 | Mathura Road | 2 | M/s Tripiurari Prasad Singh | 31.03.2017 | 31.08.2017 | 98% | 900 | 540
19 | C.V. Raman Marg | 2 |  | 31.03.2017 | 31.08.2017 | 99% | 750 | 450
20 | M.P. Road | 1 |  | 31.03.2017 | 31.08.2017 | 99% | 320 | 192
21 | Gurudwara Road | 1.2 |  | 31.03.2017 | 31.08.2017 | 98% | 260 | 156
22 | MMA Road | 3 |  | 31.03.2017 | 31.08.2017 | 98% | 360 | 216
23 | Sukhdev Vihar | 1 |  | 31.03.2017 | 31.08.2017 | 99% | 280 | 168
24 | Mata Mandir Road | 0.6 |  | 31.03.2017 | 25.07.2017 | 100% | 180 | 108
25 | Ring Road from AIIMS to Bhairon Road 'T' Point | 9.75 |  | 31.03.2017 | 15.08.2017 | 98% | 1935.67 | 950
26 | Feroz Gandhi Road, Lajpat Nagar | 1.05 |  | 31.03.2017 | 15.07.2017 | 100% | 208.46 | 150
27 | Vir Savarkar Marg, Lajpat Nagar | 1.05 |  | 31.03.2017 | 15.07.2017 | 100% | 208.46 | 120
28 | Shiv Mandir Marg from Zonal Office to Ring Road | 0.85 |  | 31.03.2017 | 15.07.2017 | 100% | 168.75 | 100
29 | Bhisma Pitamah Road | 2.6 |  | 31.03.2017 | 15.08.2017 | 98% | 516.18 | 260
30 | Road from B.P.Marg to Round about Defence Colony | 0.156 |  | 31.03.2017 | 15.07.2017 | 100% | 30.97 | 28
31 | Josef Brass Titoo Marg (B.R.T.) (Lajpat Nagar Metro Station to Ambedkar Nagar) | 6.25 |  | 31.03.2017 | 15.08.2017 | 98% | 1240.81 | 650
32 | 2nd Entry (Sarai Kale Khan Red Light to Nizamuddin Railway Station) | 0.6 |  | 31.03.2017 | 15.07.2017 | 100% | 119.12 | 75
33 | Bhairon Road | 0.98 |  | 31.03.2017 | 15.07.2017 | 100% | 194.56 | 90
34 | Mathura Roads from DPS ro Ashram Chowk | 2.65 | Sh. Chander Pal | 15.04.2017 | 30.06.2017 | 100% | 650 | 400 | Er. Sheel Rajneesh, 8527021144
35 | Hospital Road, Bhogal | 0.56 |  | 15.04.2017 | 30.06.2017 | 100% | 75 | 50
36 | East Nixzamuddin Peripheral Road from Mathura Road to Railway Station, East Nizamudin | 0.7 |  | 15.04.2017 | 30.06.2017 | 100% | 85 | 50
37 | Rajdoot Hotal to Preet Place, Jangpura, Extn | 0.2 |  | 15.04.2017 | 30.06.2017 | 100% | 30 | 20
38 | Preet Place to Nizamuddin Railway Station, Jangura | 0.7 |  | 15.04.2017 | 30.06.2017 | 100% | 85 | 45
39 | School Road, Jangpura Extn. | 0.38 |  | 15.04.2017 | 30.06.2017 | 100% | 45 | 35
40 | Neela Gumbad to Lodhi Flyover, Nizamudin Basti | 0.2 |  | 15.04.2017 | 30.06.2017 | 100% | 85 | 60
41 | Maharani Bagh from Manokarma Mandir to Sunlight Colony | 0.55 |  | 15.04.2017 | 30.06.2017 | 100% | 125 | 75
42 | IV th Avenue Road, Lodhi Colony | 1.22 |  | 15.04.2017 | 30.06.2017 | 100% | 350 | 180
43 | V th Avenue Road, Lodhi Colony | 1 |  | 15.04.2017 | 30.06.2017 | 100% | 120 | 90
44 | X Road between Block No. 18 & 14 Lodhi Colony | 0.16 |  | 15.04.2017 | 30.06.2017 | 100% | 30 | 20
45 | Lodhi Road Indian Habitat Centre to Lodhi Flyover | 1.76 |  | 15.04.2017 | 30.06.2017 | 100% | 475 | 250
46 | X Road between D-1 & C-2 (F-24) Lodhi Colony | 0.16 |  | 15.04.2017 | 30.06.2017 | 100% | 30 | 20
47 | X Road btween Block No. C-2 (176) & C-2 (177) Lodhi Colony | 0.16 |  | 15.04.2017 | 30.06.2017 | 100% | 30 | 20
48 | B.P.Marg to Coffee House Lodhi Colony | 0.35 |  | 15.04.2017 | 30.06.2017 | 100% | 75 | 45
49 | F-1 Lodhi Colony to B.P. Flyover, Lodhi Colony | 0.24 |  | 15.04.2017 | 30.06.2017 | 100% | 25 | 20
50 | Verdhman Marg from IV-th Avenue Road, B.P.Marg , Lodhi Colony | 0.35 |  | 15.04.2017 | 30.06.2017 | 100% | 90 | 55
51 | Kushak Nallah to Sewa Nagar flyover , Sewa Nagar | 0.7 |  | 15.04.2017 | 30.06.2017 | 100% | 200 | 130
52 | Kushak Nallah to CPWD Enquiry (Near O Block), Sewa Nagar | 0.3 |  | 15.04.2017 | 30.06.2017 | 100% | 125 | 90
53 | Hanuman Mandir to Sewa Nagar Flyover, Sewa Nagar | 0.46 |  | 15.04.2017 | 30.06.2017 | 100% | 125 | 85
54 | Railway Phatak to Subhasg Bazar, Sewa Nagar | 0.258 |  | 15.04.2017 | 30.06.2017 | 100% | 35 | 20
55 | BRT from Bhairon Road T- Point to Defence Colony Flyover | 3 |  | 15.04.2017 | 30.06.2017 | 100% | 285 | 135
56 | Sunder Nagar Peripherial Road, Sunder Nagar | 1.1 |  | 15.04.2017 | 30.06.2017 | 100% | 150 | 75
57 | Ratan Lal Sahdev Marg, Defence Colony | 0.978 |  | 15.04.2017 | 30.06.2017 | 100% | 225 | 130
58 | Gang Nath Marg, Safdurjunf Flyover to round about near Khushak Nallah | 0.625 |  | 15.04.2017 | 30.06.2017 | 100% | 150 | 75
EE/SER-II/R-21
59 | SA Road | 5.46 | Sh. Suresh | 27.03.2017 | 30.08.2017 | 20% | 240 | 48 | Er. R.K. Sharma, 9818615817
60 | Maharaja Agarsen Marg | 0.5 |  | 27.03.2017 | 30.08.2017 | 25% | 10 | 2.5
61 | Baba Fateh Singh Marg | 1 |  | 27.03.2017 | 30.08.2017 | 22% | 38 | 8.36
62 | Hans Raj Sethi Marg | 1.7 |  | 27.03.2017 | 30.08.2017 | 20% | 35 | 7
63 | A Block Double Storey (EPDP to Hans Raj Sethi Marg) | 0.45 |  | 27.03.2017 | 30.08.2017 | 30% | 5 | 1.5
64 | Jaitpur Road | 1.25 | Sh. Naresh Kumar | 04.12.2016 | 30.08.2017 | 20% | 80 | 16
65 | Jaitpur Road -Meethapur Chowk to Gurudwara | 1.21 |  | 04.12.2016 | 30.08.2017 | 23% |  | 0
66 | Higher Secondary School Meethapur | 0.87 |  | 04.12.2016 | 30.08.2017 | 24% |  | 0
67 | Maharaja Agarsen marg | 0.8 | M/s R.N. Construction Co | 30.03.2017 | 30.08.2017 | 25% | 70 | 17.5
68 | Madanpur Khadar Road | 1.2 |  | 30.03.17 | 30.08.2017 | 23% | 40 | 9.2
69 | Sarita Vihar Road | 1.1 | M/s R.N. Construction Co | 30.03.17 | 30.08.2017 | 21% | 55 | 11.55 | Er. R.K. Sharma, 9818615817
70 | Road No. 13 A | 2.5 |  | 30.03.17 | 30.08.2017 | 20% | 200 | 40
71 | Mathura Road | 5.5 |  | 30.03.17 | 30.08.2017 | 18% | 320 | 57.6
72 | Lala Lajpat Rai Marg to Raja Dheer Sen Marg | 0.3 | M/s Gaurav Construction Co. | 30.03.17 | 30.08.2017 | 25% | 17 | 4.25
73 | Guru Nanak Market to lala Lajpat Rai Marg | 0.57 |  | 2017-03-30 | 30.08.2017 | 30% | 18 | 5.4
74 | Nandi Vithi Marg | 0.73 |  | 30.03.17 | 30.08.2017 | 25% | 15 | 3.75
75 | Link Road | 0.58 |  | - | 30.08.2017 | 20% | 25 | 5
76 | Road from BRT to Hans Raj Gupta Marg | 0.34 |  | 30.3.17 | 30.08.2017 | 18% | 5 | 0.9
77 | Hans Raj Gupta Marg | 2.65 |  | - | 30.08.2017 | 19% | 70 | 13.3
78 | Lala Lajpat Rai Marg | 2.4 |  | - | 30.08.2017 | 20% | 18 | 3.6
79 | Guru Harkishan Public School to Nehru Place | 0.27 |  | 2017-03-30 | 30.08.2017 | 10% | 10 | 1
80 | R Block GK-1 signal to Outer Ring Road | 0.58 |  | 2017-03-30 | 30.08.2017 | 15% | 9.6 | 1.44
81 | Outer Ring Road | 2.1 |  | 2017-03-30 | 30.08.2017 | 20% | 124 | 24.8
82 | Road from Vipin Chander Pal Marg to Police Station CR Park | 0.37 |  | 30.03.17 | 30.08.2017 | 10% | 9.6 | 0.96
83 | Savitri Cinema Road | 3.1 |  | 2017-03-30 | 30.08.2017 | 20% | 130 | 26
84 | Surya Sen Marg | 0.75 |  | 30.03.17 | 30.08.2017 | 30% | 22.5 | 6.75
85 | MB Road | 5.25 | M/s Buland Construction | 28.03.17 | 30.08.2017 | 20% | 200 | 40
86 | Guru Ravi Dass Marg | 3.75 |  | 28.03.17 | 30.08.2017 | 15% | 330 | 49.5
87 | DDA Market Road | 0.43 |  | 28.03.17 | 30.08.2017 | 22% | 20 | 4.4
88 | KPS Road | 0.64 |  | 28.03.17 | 30.08.2017 | 24% | 15 | 145
89 | Suraj Kund Road | 0.6 |  | 28.03.17 | 30.08.2017 | 25% | 30 | 7.5
90 | Road No13 | 2.7 |  | 10.4.2017 | 30.08.2017 | 24% | 245 | 58.8
91 | EPDP Road | 1.8 |  | 10.04.2017 | 30.08.2017 | 21% | 80 | 16.8
92 | Outer Ring Road | 3.2 |  | 10.04.2017 | 30.08.2017 | 23% | 150 | 34.5
93 | Gurudwara Road GK-II | 1.7 |  | 10.04.2017 | 30.08.2017 | 15% | 20.8 | 3.12
94 | Vipin Chander Pal Marg | 1.5 |  | 10.04.2017 | 30.08.2017 | 18% | 72 | 12.96
South Circle
Sub-Divn.-SR-11
1 | M.B. Road | 5.25 | Nasir Ali | 16.03.2017 | 01.09.2017 | 80% | 2150 | 880 | Sh. Narender Mahajan 9933331859
2 | Devli Road | 2 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 01.09.2017 | 20%
3 | IGNOU Road | 2.9 | M/s RichCon Engineering Company | 16.03.2017 | 01.09.2017 | 70%
4 | Maharishi Balmiki Marg | 1.8 | Nasir Ali | 16.03.2017 | 01.09.2017 | 30%
5 | Durbal Nath Marg | 1.09 |  | 16.03.2017 | 01.09.2017 | 30%
6 | Raja Ram Marg | 0.89 |  | 16.03.2017 | 01.09.2017 | 50%
7 | H Block Dakshin Puri Road | 0.4 |  | 16.03.2017 | 01.09.2017 | 40%
8 | Firni Road | 1 |  | 16.03.2017 | 01.09.2017 | 55%
9 | West End Marg | 0.8 |  | 16.03.2017 | 01.09.2017 | 100%
10 | Old MB Road | 1 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 01.09.2017 | 80%
| Total | 17.13
Sub-Divn.-SR-12
11 | 100 Foota Road Chattarpur | 1.4 | Ravi Tanwar | 16.03.2017 | 01.09.2017 | 70% | 840 | 350
12 | 60 Foota Road | 0.9 |  | 16.03.2017 | 01.09.2017 | 70%
13 | SSN Marg | 10.5 |  | 16.03.2017 | 01.09.2017 | 70%
| Total | 12.8
Sub-Divn.-SR-13 & 15
14 | Gadai Pur Band Road | 3 | Ravi Tanwar | 16.03.2017 | 01.09.2017 | 80% | 855 | 635
15 | Mandi Road | 8 |  | 16.03.2017 | 01.09.2017 | 80%
16 | Dera Bhati Road | 5.76 |  | 16.03.2017 | 01.09.2017 | 80%
17 | M.G. Road | 7.5 |  | 16.03.2017 | 01.09.2017 | 80%
18 | Aya Nagr Road | 0.6 |  | 16.03.2017 | 01.09.2017 | 95%
19 | Ghitorni Road to CPWD Land | 0.54 |  | 16.03.2017 | 01.09.2017 | 95%
20 | Ghitorni Village Road | 1.04 |  | 16.03.2017 | 01.09.2017 | 95%
21 | MG Road to Ghitorni Village | 0.3 |  | 16.03.2017 | 01.09.2017 | 95%
| Total | 26.74
Sub-Divn.-SR-14
22 | Press Enclave (BRT to Saket Court) | 4 | M/S BULAND CONSTRUCTIONS | 16.03.2017 | 01.09.2017 | 30% | 3200 | 1545 | Sh. Narender Mahajan 9933331859
23 | Family Court Road | 0.9 |  | 16.03.2017 | 01.09.2017 | 60%
24 | Pushp Vihar (Internal Road) | 4 |  | 16.03.2017 | 01.09.2017 | 40%
25 | H. Block Road | 1 |  | 16.03.2017 | 01.09.2017 | 40%
26 | Road in front of H.No. C-11 to C-20 Malviya Nagar | 0.11 |  | 16.03.2017 | 01.09.2017 | 40%
27 | Appjay School Road | 1.3 |  | 16.03.2017 | 01.09.2017 | 40%
28 | Shekh Sarai Phase-1 | 0.3 |  | 16.03.2017 | 01.09.2017 | 65%
29 | Khirki Road | 0.85 |  | 16.03.2017 | 01.09.2017 | 40%
30 | NBCC Plaza Road | 1.1 |  | 16.03.2017 | 01.09.2017 | 50%
31 | Birla Vidya Niketan | 1 |  | 16.03.2017 | 01.09.2017 | 45%
32 | Mandir Marg | 1.2 |  | 16.03.2017 | 01.09.2017 | 40%
33 | Pramod Mahajan Marg | 0.89 |  | 16.03.2017 | 01.09.2017 | 50%
34 | Main Road Sector-1, Pushp Vihar | 0.75 |  | 16.03.2017 | 01.09.2017 | 45%
35 | Pankaj Jewel Marg, Pushp Vihar | 1.1 |  | 16.03.2017 | 01.09.2017 | 45%
36 | Asian Market Road in Pushp Vihar | 0.45 |  | 16.03.2017 | 01.09.2017 | 10%
37 | Metro Enclave Road in Pushp Vihar | 0.45 |  | 16.03.2017 | 01.09.2017 | 45%
38 | Road between DDA Flat Masjid Moth Ph-II and Jahapanah Forest | 0.5 |  | 16.03.2017 | 01.09.2017 | 10%
39 | Road in front of Mother International School | 0.54 |  | 16.03.2017 | 01.09.2017 | 60%
40 | J Block Saket | 0.89 |  | 16.03.2017 | 01.09.2017 | 60%
41 | Apeejay School Road (Gurudwara to J Block Road). | 0.3 |  | 16.03.2017 | 01.09.2017 | 60%
| Total | 21.63
South Road-2 Division
Sub Division - I
42 | August Kranti Marg. | 3.24 | M/s Vision Constructions | 02.03.2017 | 01.09.2017 | 60% | 3064 | 2500 | Sh. Jagdish Prasad 9560207879
43 | Balbir Saxena Marg | 0.8 |  |  |  | 60%
44 | Ch. Dilip Singh Marg, P.S. Hauz Khas | 0.6 |  |  |  | 50%
45 | Mahinder Singh Jain Marg Road / Gautam Nagar Road | 1.2 |  |  |  | 60%
46 | P-Block Road from August Kranti Marg via jain Mandir & Dustbin to August Kranti Marg. | 0.34 |  |  |  | 60%
47 | Sudarshan Cinema Road. | 0.72 |  |  |  | 50%
48 | Gautam Nagar Road | 0.5 |  |  |  | 50%
49 | Road form Balbir Sxsena Marg to Ch. Dalip SinghMarg (NIFT Road), Hauz Khas | 0.6 |  |  |  | 60%
50 | Road form August Kranti marg to Aurobindo Marg (Subash Chopra Road), Hauz Khas | 0.79 |  |  |  | 60%
51 | Asiad Village peripheral road | 3 |  |  |  | 70%
52 | Siri Fort Road | 1.2 |  |  |  | 80%
| Total | 12.99
Sub Division - II
53 | Sri Aurobindo Marg | 5 | M/s Samridhi Construction, | 02.03.2017 | 01.09.2017 | 40% | 5768 | 5300 | Sh. Jagdish Prasad 9560207879
54 | Outer Ring Road ( IIT Flyover to Africa Avenue Junction) | 1.8 |  |  |  | 50%
55 | Ch. Jhandu Singh Marg | 1.53 |  |  |  | 70%
56 | Ch. Harsukh Marg | 1.83 |  |  |  | 70%
57 | Ch. Hukum Chand Marg | 0.6 |  |  |  | 60%
58 | Green Park Market Road | 1 |  |  |  | 60%
59 | Narender Kumar Pandey Marg | 1.16 |  |  |  | 60%
60 | Hauz Khas Village Road | 0.9 |  |  |  | 60%
61 | Ring Road (Safdarjung to Hyatt) | 2.1 |  |  |  | 60%
| Total | 15.92
Sub Division - III
62 | Anuvart Marg | 2.5 | Sh. Jagdish Prasad Meena | 02.03.2017 | 01.09.2017 | 60% | 4212 | 3900 | Sh. Jagdish Prasad 9560207879
63 | Aruna Asaf Ali Road | 3.5 |  |  |  | 70%
64 | Vedant Deshika Marg | 0.7 |  |  |  | 60%
65 | B-1 Telephone Exchange Road,Vasant Kunj (Mahipalpur Road to B-5 & B-6 Road) | 0.6 |  |  |  | 60%
66 | DAV School Road Vasant Kunj | 0.55 |  |  |  | 50%
67 | Shiv Mandir to B-5 & B-6 Road) | 0.3 |  |  |  | 50%
68 | D-1 & D-2 Road, Vasant Kunj | 0.24 |  |  |  | 50%
69 | Sports Complex Road D-2,Vasant Kunj | 0.7 |  |  |  | 50%
70 | Shaheed Jeet Singh | 2.1 |  |  |  | 50%
71 | Road from B 15/7 to BSES Office,Q.I.A. | 0.3 |  |  |  | 60%
72 | Peripheral Road of A Block of Q.I.A. | 0.41 |  |  |  | 50%
73 | Peripheral Road of C and B Block of Q.I.A. | 1.57 |  |  |  | 60%
| Total | 13.47
Sub Division - IV
74 | Outer Ring Road (Panchsheel to IIT Gate) | 1 | Sh. Narendra Singh Yadav | 02.03.2017 | 01.09.2017 | 60% | 1085 | 950 | Sh. Jagdish Prasad 9560207879
75 | Outer Ring Road (Chirag Delhi to Panchsheel) | 3.7 |  |  |  | 60%
76 | A-1 Block, Panchsheel Enclave Road | 0.5 |  |  |  | 60%
| Total | 5.2
Sub Division - V
77 | S-Bend Road (Maharishi Dayanand Marg) | 1.8 | Sh. Narendra Singh Yadav | 02.03.2017 | 01.09.2017 | 50% | 1680 | 1350 | Sh. Jagdish Prasad 9560207879
78 | Shivalik Road (Basant Kaur Marg) | 1.86 |  |  |  | 40%
79 | Guru Govind Singh Marg | 1.2 |  |  |  | 40%
| Total | 4.86
DETAILS OF DESILTING OF DRAINS UNDER SOUTH WEST CIRCLE/ SOUTH ZONE
South West Road-I
Sub Division -1
1 | B.J. Marg | 1.3 | M/s Amocon M/s Sai Tube Well | 15.05.2017 | 31.08.17 | 45% | 650 | 300 | Sh. S K Sinha 9958469778
2 | Rao Tula Ram Marg (RTR Marg) | 1.7 |  | 15.04.2017 | 31.08.17 | 50% | 425 | 400
3 | Zonal road No. 2 (Baba Balak Nath Marg) | 1750 |  | 01.06.2017 | 31.08.17 |  | 0 | -
4 | Zonal Road No. 6 (Hare Krishna Mehto Marg) | 700 |  | 01.06.2017 | 31.08.17 |  | 0 | -
3 | Baba Balak Nath Marg | 1.1 |  | 01.06.2017 | 31.08.17 | 45% | 580 | 150
6 | Ullan Buttor Marg | 5500 |  | 01.06.2017 | 31.08.17 |  | 0 | -
4 | Nelson Mandela Marg | 4.01 |  | 15.04.2017 | 31.08.17 | 45% | 900 | 500
5 | Baba Gang Nath marg | 1.17 |  | 15.05.2017 | 31.08.17 | 45% | 400 | 300
6 | Outer Ring Road | 4.8 | Sh. Vinay Shankar | 15.05.2017 | 31.08.17 | 50% | 1050 | 480
Sub Division - 2
7 | Africa Avenue (Road No.9) | 2.2 | M/s Amocon M/s Sai Tube Well | 18.05.2017 | 31.08.17 | 45% | 600 | 500
12 | Tamil Sangam Marg | 1.1 |  | 18.05.2017 | 31.08.17 |  | 0 | #VALUE!
13 | Major Som nath marg |  |  | 18.05.2017 | 31.08.17 |  | 0 | #VALUE!
14 | Kafi Azami Marg |  |  | 18.05.2017 | 31.08.17 |  | 0 | #VALUE!
15 | Church Road, R.K.Puram |  |  | 18.05.2017 | 31.08.17 |  | 0 | #VALUE!
8 | venketeshwar marg | 0.6 |  | 18.05.2017 | 31.08.17 | 50% | 200 | 200
17 |  |  |  | 18.05.2017 | 31.08.17 |  | 0 | #VALUE!
9 | Major Som nath marg | 1.75 |  | 18.05.2017 | 31.08.17 | 50% | 324 | 300
19 |  |  |  | - | 31.08.17 |  | 0 | #VALUE!
10 | amar shaheed babu genu marg | 1.1 |  | 18.05.2017 | 31.08.17 | 45% | 324 | 300
11 | Tamil Sangam Marg | 0.9 |  | 18.05.2017 | 31.08.17 | 50% | 180 | 10
12 | Kafi Azami Marg | 0.9 |  | 18.05.2017 | 31.08.17 | 45% | 468 | 400
13 | swami vivekanand marg | 0.5 |  | 18.05.2017 | 31.08.17 | 45% | 576 | 320
14 | Church Road, R.K.Puram | 1.3 |  | 18.05.2017 | 31.08.17 | 45% | 180 | 125
15 | munirka marg | 2 |  | 18.05.2017 | 31.08.17 | 45% | 180 | 150
16 | poorvi marg | 1.6 |  | 18.05.2017 | 31.08.17 | 50% | 200 | 125
17 | Dr. Prem nath dogra marg | 0.5 |  | 18.05.2017 | 31.08.17 | 50% | 200 | 125
18 | basant marg | 0.5 |  | 18.05.2017 | 31.08.17 | 45% | 150 | -
19 | paschimi marg | 0.6 |  | 18.05.2017 | 31.08.17 | 45% | 150 | -
21 |  | - |  | - |  |  | - | -
22 |  | - |  | - |  |  | - | -
23 |  | - |  | - |  |  | - | -
24 |  | - |  | - |  |  | - | -
25 |  | - |  | - |  |  | - | -
26 |  | - |  | - |  |  | - | -
27 |  | - |  | - |  |  | - | -
Sub Division - 3
13 | Ganga Ram Hospital Road | Sh. Bishwa Mohan Jha | 1080 | 03.04.2017 |  |  | - | -
14 | PUSA Road | Sh. Bishwa Mohan Jha | 1500 | 03.04.2017 |  |  | - | -
15 | Shankar Road | Sh. Bishwa Mohan Jha | 1640 | 03.04.2017 |  |  | - | -
20 | Ganga Ram Hospital Road | 1.08 | Sh. Bishwa Mohan Jha M/s Sai Tube Well | 03.04.2017 | 31.08.17 | 50% | 250 | 200
21 | Shankar Road | 1.64 |  | 03.04.2017 | 31.08.17 | 50% | 350 | 200
22 | Dr. K.S. Krishanan Marg | 0.92 |  | 03.04.2017 | 31.08.17 | 45% | 250 | 250
23 | PUSA Institute (IARI) Internal Road | 0.7 |  | 03.04.2017 | 31.08.17 | 45% | 200 | 100
24 | Dev Prakash Shastri marg (Road No. 25) | 4.45 |  | 03.04.2017 | 31.08.17 | 45% | 1200 | 800
25 | Girdhari Lal Goswami Marg (Road No. 89) | 3.65 |  | 03.04.2017 | 31.08.17 | 50% | 1000 | 700
20 | Ram Nath Vij Marg | 0.76 |  | 03.04.2017 | 31.08.17 |  | 0
21 | O.P. Bharti Marg 1 | 0.18 |  | 03.04.2017 | 31.08.17 |  | 0
26 | O.P. Bharti Marg 1 | 0.76 |  | 03.04.2017 | 31.08.17 | 50% | 200 | 100
27 | O.P. Bharti Marg 2 | 0.18 |  | 03.04.2017 | 31.08.17 | 50% | 50 | 50
24 | O.P. Bharti Marg 4 | Sh. Bishwa Mohan Jha |  | 03.04.2017 | 31.08.17 |  | 50 | -
28 | O.P. Bharti Marg 3 | 0.181 |  | 03.04.2017 | 31.08.17 | 50% | 50 | 50
29 | O.P. Bharti Marg 4 | 0.42 |  | 03.04.2017 | 31.08.17 | 45% | 50 | 50
Sub Division - 4
30 | Mahatma gandhi Marg (Ring Road) (both side) | 8.6 | Sh. Bishwa Mohan Jha | 04.04.2017 | 31.08.17 | 50% | 1850 | 1350
31 | NH-8 (both side) | 2.9 |  | 04.04.2017 | 31.08.17 | 45% | 400 | 325
42 | Upper Ridge Road (Vande Martram Marg) | No Drainage exit
32 | Road No. 36(Sat Guru Ram Singh Marg) (both side) | 3.4 | Sh. Rajnish Yadav | 25.03.2017 | 31.08.17 | 45% | 1400 | 900
Sub Division - 5
33 | MM Road | 6.8 | M/s R.R. construction | 10.05.2017 | 31.08.17 | 45% | 1630 | -
South West Road-II
EE (C) (South West) Road 2 / R-21
(Section-I)
34 | 60 futa Road | 0.45 | Sh Surender Singh Agmt No.:- 14/EE/ SWR-II/ PWD/2017-18/00457 | 21.03.2017 | 31.08.2017 | Yet to be start | Desilting done by super sucker machine | Desilting done by super sucker machine | Sh.J.P.Vashist 9917396164
35 | A Block Road | 0.2 | M/s Ram Charan Bansal Agmt No :- 103/EE/ SWR-II/ PWD/2016-17 | 21.03.2017 | 31.08.2017 | 20%
36 | Central School Road | 0.29 |  | 21.03.2017 | 31.08.2017 | 20%
37 | Dabri Road | 0.9 |  | 21.03.2017 | 31.08.2017 | 10%
38 | Fire Station Road | 0.4 |  | 21.03.2017 | 31.08.2017 | 20%
39 | Lal Sai Marg to Pankha Road | 0.65 |  | 21.03.2017 | 31.08.2017 | 20%
40 | Ram Mandir Marg | 0.86 |  | 21.03.2017 | 31.08.2017 | 20%
41 | Road C-2/22 C-2/274 Road Janakpuri | 0.76 |  | 21.03.2017 | 31.08.2017 | 30%
42 | Road from Ram Mandir Marg to Mall Road (Connecting Road) | 0.3 |  | 21.03.2017 | 31.08.2017 | 30%
43 | Road From Shani Bazar to Ram Mandir Marg (Connecting Road) | 0.3 |  | 21.03.2017 | 31.08.2017 | 20%
44 | Shani Bazar Road | 0.65 |  | 21.03.2017 | 31.08.2017 | 20%
45 | Vidya Marg | 1.6 |  | 21.03.2017 | 31.08.2017 | 20%
46 | Mall Road | 0.65 |  | 21.03.2017 | 31.08.2017 | 30%
47 | Lal Sai Road | 2.5 | Sh Surender Singh Agmt No.:- 14/EE/ SWR-II/ PWD/2017-18/00457 | 09.06.2017 | 31.08.2017 | Yet to be start
48 | Old Pankha Road | 0.5 |  | 09.06.2017 | 31.08.2017
49 | Pankha Road | 6.6 |  | 09.06.2017 | 31.08.2017
(Section-II)
50 | Nasir Pur Road | 2.3 | M/s Ram Charan Bansal Agmt No :- 102/EE/ SWR-II/ PWD/2016-17 | 21.03.2017 | 31.08.2017 | 20%
51 | Internal Road C-1 to C-1A Block | 0.3 |  | 21.03.2017 | 31.08.2017 | 20%
52 | Palam Dabri Road | 2.5 |  | 21.03.2017 | 31.08.2017 | 10%
53 | Paras Public schol to L-103 Pocket-4 Chankya Puri Binda Pur | 0.24 |  | 21.03.2017 | 31.08.2017 | 20%
54 | Peer Baba Road | 0.6 |  | 21.03.2017 | 31.08.2017 | 20%
55 | Police Station Road | 0.37 |  | 21.03.2017 | 31.08.2017 | 10%
56 | Pt. Vishnu Dutt Marg | 0.75 |  | 21.03.2017 | 31.08.2017 | 10%
57 | Sagar Pur Road | 3 |  | 21.03.2017 | 31.08.2017 | 20%
58 | Satguru Ram Singh Marg | 0.9 |  | 21.03.2017 | 31.08.2017 | 20%
59 | Link Road (Pt. Vishnu Dutt Marg to Satguru Ram Singh Marg) | 0.3 |  | 21.03.2017 | 31.08.2017 | 10%
60 | EE (C) (South West) Road 2 / R-22
61 | (Section-I)
62 | Najafgarh Nagloi Road | 2.6 | Sh. Surender Singh, Agmt No:- 105/EE/ SWR-II/ PWD/2016-17 | 21.03.2017 | 31.08.2017 | 50% | 382 MT | The drain is being cleaned by super sucker machines hence quanitity cannot be ascertained. However approx. Silt disposed out by S/S till date is 400 MT
63 | Najafgarh Phirni | 2.2 |  | 21.03.2017 | 31.08.2017 | 45%
64 | Najafgarh Dhansa Road | 16.25 |  | 21.03.2017 | 31.08.2017 | 50%
(Section-II)
65 | Najafgarh Dechaun Road | 4.55 | M/s Anmol Infratech Pvt Ltd. Agmt No:- 104/EE/ SWR-II/ PWD/2016-17 | 21.03.2017 | 31.08.2017 | 50% | Work to be executed by super sucker machine NIL | The drain is being cleaned by super sucker machines hence quanitity cannot be ascertained. However approx. Silt disposed out by S/S till date is 280 MT
66 | Najafgarh Jaroda Road | 7.2 |  | 21.03.2017 | 31.08.2017 | 50%
67 | Najafgarh Kakrola Road | 4 |  | 21.03.2017 | 31.08.2017 | 50%
EE (C) (South West) Road 2 / R-23
68 | (Section-I)
69 | Laxmi Chand Marg | 11.3 | Sh. Surender Singh, Agmt NO.;- 108/EE/ SWR-II/ PWD/2016-17 | 21.03.2017 | 31.08.2017 | 45% | 1090 MT | 500 MT
| Prithvi Singh Dagar Marg | 11.2 |  | 21.03.2017 | 31.08.2017 | 50% |  | Not yet disposed
70 | (Section-II)
71 | Jhatikara Morh to Jhatikara | 8.55 | Sh. Surender Singh, Agmt NO.;- 106/EE/ SWR-II/ PWD/2016-17 | 21.03.2017 | 31.08.2017 | 50% | 890 MT | Not yet disposed
72 | Najafgarh Bijwasan Road | 11.25 |  | 21.03.2017 | 31.08.2017 | 45% |  | 100 MT
73 | EE (C) (South West) Road 2 / R-24
74 | Bhartal Road | 3.48 | M/s Anmol Infratech Pvt Ltd. Agmt No:- 105/EE/ SWR-II/ PWD/2016-17 | 21.03.2017 | 31.08.2017 | 35% |  | Yet to be informed by the agency
75 | Goyla Deenpur Road | 4.2 |  | 21.03.2017 | 31.08.2017 | 30%
76 | Kapashera Bijwasan Road | 3.8 |  | 21.03.2017 | 31.08.2017 | 30% | 1470 MT
77 | Link Road | 1.7 |  | 21.03.2017 | 31.08.2017 | 35%
78 | Old DG Road | 2.5 |  | 21.03.2017 | 31.08.2017 | 30%

## sub division -I (hidden)
Details of desilting of drains under South West Road - I, sub division - I
Sl. No. | Name of drain | Contractor | Length of drain | Date of start | Revised date of completion | Estimated Qty. of silt | % drain cleaned lengthwise | Qty. of silt lifted and disposed off.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Sub division -1
1 | B.J. Marg | M/s Amocon | 1800 Mtr. | 15.05.2017 | 15.06.2017 | - | 5% | -
2 | Rao Tula Ram Marg (RTR Marg) | M/s Amocon | 3200 Mtr. | 15.04.2017 | 15.06.2017 | - | 75% | -
3 | Zonal road No. 2 (Baba Balak Nath Marg) | M/s Amocon | 1750 Mtr. | 01.06.2017 | 15.06.2017 | - | - | -
4 | Zonal Road No. 6 (Hare Krishna Mehto Marg) | M/s Amocon | 700 Mtr. | 01.06.2017 | 15.06.2017 | - | - | -
5 | M.M.Road | Sh. T.P. Singh | 4250 Mtr. | 15.04.2017 | 15.06.2017 | - | 50% | -
6 | Ullan Buttor Marg | Sh. Vinay Shankar | 550 Mtr. | 01.06.2017 | 15.06.2017 | - | - | -
7 | Nelson Mandela Marg | Sh. T.P. Singh | 5200 Mtr. | 15.04.2017 | 15.06.2017 | - | 25% | -
8 | Baba Gang Nath marg | Sh. T.P. Singh | 2150 Mtr. | 15.05.2017 | 15.06.2017 | - | 20% | -
9 | Outer Ring Road | Sh. Vinay Shankar | 6160 Mtr. | 15.05.2017 | 15.06.2017 | - | 2% | -
10 | Vatika Road (DPS Vasant Kunj to MM road) | Sh. Vinay Shankar | 2150 Mtr. | 15.04.2017 | 15.06.2017 | - | 10% | -
Certificate
It is certified that the above mentioned information are correct.
Junior Engineer |  | Assistant Engineer |  | Executive Engineer