## East Zone
PWD Desilting Report (Preparedness for Monsoon)
DESILTING REPORT UNDER PWD MAINTENANCE EAST ZONE
As on 18.08.2017
DESILTING UNDER PWD MAINTENANCE ………. ZONE AS ON 19.05.2017
Sl. No. | Name of Road / Drain | Length of Road (Km) | Contractor | Date of Start of De-silting | Date of completion (Ist Cycle) | % Drain cleaned (Lengthwise) | Estimate Qty. of silt (cum) | Qty. of silt lifted and disposed off (cum) | EE in charge / Mobile No.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Circle/ Divn. :- Shahdara (Road)
1 | Road No- 56 | 5.6 | M/s T.K.N. Developers | 25.02.2017 | 20.07.2017 | 100% | 1100 | 1100 | Sh Vijay Singh 8802028700
2 | Road No- 71 A | 0.6 |  | 25.02.2017 | 20.07.2017
3 | Road No- 71 | 1.6 |  | 25.02.2017 | 20.07.2017
4 | Road No. 56-A. | 1 |  | 25.02.2017 | 20.07.2017
5 | G.T Road Mansarover Park to Apsara Border | 2.6 |  | 16.05.2017 | 20.07.2017 | 100% | 1685 | 1685
6 | Road No 72 | 0.91 |  | 25.02.2017 | 31.08.2017 | 97% | 1500 | 1600
7 | Road No 72 Extn. | 1 |  | 25.02.2017 | 31.08.2017
8 | Zonal office Road. | 1.03 |  | 25.02.2017 | 31.08.2017
9 | Surajmal Vihar Market | 1.2 |  | 25.02.2017 | 31.08.2017
10 | Shrestha Vihar | 1.25 |  | 25.02.2017 | 31.08.2017
11 | Road No 58 | 2.84 | Sh. Ram Kumar Sharma | 12.06.2017 | 31.08.2017 | 92% | 2544 | 2100
12 | Road No 58 A | 2 |  | 12.06.2017 | 31.08.2017
13 | Shiva Khand Road | 0.9 |  | 16.05.2017 | 31.08.2017 | 98% | 2227 | 2100
14 | ITI Vivek Vihar | 1.4 |  | 16.05.2017 | 31.08.2017
15 | C-Block, Jhilmil | 0.45 |  | 16.05.2017 | 31.08.2017
16 | Vivek Vihar | 0.617 |  | 16.05.2017 | 31.08.2017
17 | Ram Mandir via ITI Vivek Vihar | 1.35 |  | 16.05.2017 | 31.08.2017
18 | Road along A-Block Jhilmil Colony | 0.188 |  | 16.05.2017 | 31.08.2017
19 | DJB opp. B-Block | 0.3 |  | 16.05.2017 | 31.08.2017
20 | B-Block, Jhilmil, Shaheed Bhagat Singh Marg | 0.355 |  | 16.05.2017 | 31.08.2017
21 | Link Road GT Road to Vivek Vihar ITI | 0.6 |  | 16.05.2017 | 31.08.2017
22 | Road No. 57 (Jagat Puri to Telco X-ing) | 2.52 | M/s T.K.N. Developers | 25.02.2017 | 20.07.2017 | 100% | 1920 | 1920
23 | Road No. 57 from G.T. Road Azad Nagar | 1.5 |  | 25.02.2017 | 20.07.2017
24 | Road No. 57 Azad Nagar to Jagat Puri | 1.25 |  | 25.02.2017 | 20.07.2017
25 | Bhartendu Harish Chander Marg (75-B Extension) | 2.13 |  | 25.02.2017 | 20.07.2017
26 | Bhola Nath Nagar | 0.6 |  | 25.02.2017 | 20.07.2017
27 | 60' feet Road | 1.17 |  | 25.02.2017 | 20.07.2017
28 | Shahdara Road | 0.6 |  | 25.02.2017 | 20.07.2017
29 | DCP Office | 0.112 |  | 25.02.2017 | 20.07.2017
30 | G.T Road Shyam lal Collage to Mansarover Park | 2 |  | 25.02.2017 | 31.08.2017 | 99% | 750 | 750
31 | G.T Road Railway under bridge near Metro Station Shahdara | 0.176 |  | 25.02.2017 | 31.08.2017
32 | G.T Road Railway under bridge near Railway Station Shahdara | 0.214 |  | 25.02.2017 | 31.08.2017
33 | G.T Road Shyam lal Collage to Dharmapura | 1.75 |  | 25.02.2017 | 31.08.2017
34 | Kabool Nagar Gurdwara Road | 0.132 |  | 25.02.2017 | 31.08.2017 | 99% | 900 | 891.33
35 | Gandhi Nagar Road | 1.5 |  | 25.02.2017 | 31.08.2017
36 | Road No. 62 (Road No. 70 to Apsara Border) | 1.2 | M/s T.K.N. Developers | 09.03.2017 | 31.08.2017 | 70% | 14842 | 5200 | Sh Vijay Singh 802028700
37 | Road No. 70 (Seemapuri to Tahir Pur T-Point) | 1.2 |  | 09.03.2017 | 31.08.2017
38 | Seemapuri Road from Road No. 62 to 64 | 1.06 |  | 09.03.2017 | 31.08.2017
39 | LIC Road (from Malaria office MCD to GT Road) | 0.3 |  | 09.03.2017 | 31.08.2017
40 | Road along Divider road to pummy sweet at Gurudwara road | 0.36 |  | 09.03.2017 | 31.08.2017
41 | Gurudwara Road from DTC bus depot Road No. 70 to GTB Hospital road | 1.75 |  | 09.03.2017 | 31.08.2017
42 | Road infront of Hans Raj Public School (Divider Road to Gurudwara road) | 0.36 |  | 09.03.2017 | 31.08.2017
43 | Road from T-point, L-pocket to R Block small rotary | 0.86 |  | 09.03.2017 | 31.08.2017
44 | GTB Hospital Road (From GT Road to Aggarwal Sweet Dilshad Garden) | 0.6 |  | 09.03.2017 | 31.08.2017
45 | R-Block Road (From Divider road Agarwal sweet to GT Road) | 0.5 |  | 09.03.2017 | 31.08.2017
46 | Road No. 62 (J & K pocket) to petrol pump GT Road (infront of Red Crosss society). | 0.33 |  | 09.03.2017 | 31.08.2017
47 | Road from Gurudwara road (T-point of Kalander Colony) to Gauri Shankar Mandir | 0.31 |  | 09.03.2017 | 31.08.2017
48 | Road from Divider Road (Mukherjee Public School to Sant Ram Public School at Gurudwara road) | 0.36 |  | 09.03.2017 | 31.08.2017
49 | New Seemapuri Road from Road No. 64 (Mother Dairy) to Road No. 62 near maszid | 1.16 |  | 09.03.2017 | 31.08.2017
50 | Road from LIC Colony (T-Point to rotary at Telephone Exchange) | 0.93 |  | 09.03.2017 | 31.08.2017
51 | Road No. 64 Swami Dayanand Hospital to DLF More (U.P. Border) | 3 |  | 09.03.2017 | 31.08.2017
52 | Divider Road from Seemapuri road to Road No. 64 (near SDN Hospital) | 2.4 |  | 09.03.2017 | 31.08.2017
53 | CNG Petrol Pump to deer park (Divider road) west side | 0.2 |  | 09.03.2017 | 31.08.2017
54 | CNG Petrol Pump to deer park (Divider road) east side | 0.19 |  | 09.03.2017 | 31.08.2017
55 | GTB Hospital road from Red light to Agarwal sweet (Divider road) | 0.19 | M/s Sai Tube Well | 09.03.2017 | 31.08.2017
56 | Road from GT Road to Road No. 64 via Telephone exchange | 0.41 |  | 09.03.2017 | 31.08.2017
57 | Road from General Hospital (Road No. 64 to Shahdara Flyover) | 0.26 |  | 09.03.2017 | 31.08.2017
58 | Road No. 68 (Road No. 69 to Road No. 66) | 3.4 |  | 09.03.2017 | 31.08.2017
59 | Loni Road G.T. Road to Loni Gole Chakkar | 2.894 |  | 09.03.2017 | 31.08.2017
60 | Road No. 69 | 1.25 |  | 09.03.2017 | 31.08.2017
61 | Tanga Stand Road from road no. 68 to Wazirabad Road. | 1.35 |  | 09.03.2017 | 31.08.2017
62 | Main Road LIG Flats, East of Loni Road from Loni Road to community centre Ashok Nagar. | 0.375 |  | 09.03.2017 | 31.08.2017
63 | Captain javed Ali Marg | 0.84 |  | 09.03.2017 | 31.08.2017
64 | Main Road LIG flats, Loni Road to Govt. S.S. School Ashok Nagar. | 0.275 | M/s Sai Tube Well | 09.03.2017 | 31.08.2017 | --do-- | --do-- | --do-- | Sh Vijay Singh 802028700
65 | GTB Road (From Road No. 64 to Road No. 68) | 0.91 |  | 09.03.2017 | 31.08.2017
66 | Mandoli Road (From Loni Road to Nand Nagri Railway crossing) | 1.94 |  | 09.03.2017 | 31.08.2017
67 | From Rajiv Gandhi super hospital specialty hospital to GTB hospital road | 0.95 |  | 09.03.2017 | 31.08.2017
68 | From Road No. 68 (petrol pump) to E-pocket GTB enclave police booth near Nutan Vidya Mandir public school | 0.37 |  | 09.03.2017 | 31.08.2017
69 | From Road No. 69 MIG Flat to GTB Hospital Road Via Nutan Vidya Mandir public school | 0.9 |  | 09.03.2017 | 31.08.2017
70 | Road along khel parisor from NVM school to Green field public school. | 0.25 |  | 09.03.2017 | 31.08.2017
71 | Road No-65 (GT Road to Road no.-66) | 1.2 |  | 09.03.2017 | 31.08.2017
72 | Babarpur Road (GT Road to Road no.-66 | 2 |  | 09.03.2017 | 31.08.2017
Circle / Divn. :- East-M / East Road (M-212)
Name of MLA :- Sh. Manoj Kumar
Name of Constituency :- Kondli AC (56)
73 | Road from Live stock market to Gali No. 7 Block - C in Ghazipur Dairy Farm. | 0.8 | M/s Shiva Construction Co. | 15.03.2017 | Continuous process to remove the gober from Drain by JCB |  | 15570 | 17000 | Sh. Iqbal Singh 9910925748
74 | NH-24 Ghazipur to Kondli Bridge. | 1.5 |  | 15.03.2017
75 | Road from NH-24 to Hindon cut near Ghazipur Slaughter House. | 0.5 |  | 15.03.2017 | 14.08.2017 | 98% | 50
76 | Dharamshilla Road | 0.6 |  | 15.03.2017 | 30.06.2017 | 100% | 256
77 | Saheed Budh Singh Marg | 0.28 |  | 15.03.2017 | 14.08.2017 | 90% | 100
78 | Dallupura Road | 1.25 |  | 15.03.2017 | 14.08.2017 | 85% | 530
79 | M.P. Road No. 102 | 2.2 |  | 15.03.2017 | 30.06.2017 | 100% | 500
80 | M.P Road No. 108 | 1.33 |  | 15.03.2017 | 30.06.2017 | 100% | 720
81 | M.P Road 109 | 0.81 |  | 15.03.2017 | 14.08.2017 | 95% | 550
82 | Road from Kondli Village up Gharoli Village X-ing. | 0.75 |  | 15.03.2017 | 14.08.2017 | 95% | 400
83 | Road along Shiv Mandir in Gharoli Dairy Farm 'B' Block. | 0.66 |  | 15.03.2017 | 30.06.2017 | 100% | 250
84 | EWS Flats to DDA Market Mayur Vihar Ph.-III X-ing upto Agarwal Sweet Shop. | 0.66 |  | 15.03.2017 | 30.06.2017 | 100% | 250
85 | Main road between A & B Block New Kondli. | 0.35 |  | 15.03.2017 | 30.06.2017 | 100% | 150
86 | Road from High land Apptt. To Soochna Apptt. In Vasundhara Enclave. | 0.4 |  | 15.03.2017 | 30.06.2017 | 100% | 150
87 | Road from Manav Ashray Apptt. To Hindon Apptt. In Vasundhara Enclave | 0.48 |  | 15.03.2017 | 30.06.2017 | 100% | 180
88 | Road from Dashmesh Public School to Delux Apptt. Via Mahesh Apptt. In Vasundhara Enclave. | 0.75 |  | 15.03.2017 | 30.06.2017 | 100% | 315
89 | Bhagvan Mahavir Swami Marg. | 0.8 | M/s Shiva Construction Co. | 15.03.2017 | 14.08.2017 | 95% | 350 | --do-- | Sh. Iqbal Singh 9910925748
90 | Sameer Bhan Marg | 0.825 |  | 15.03.2017 | 30.06.2017 | 100% | 300
91 | Road from Cell Apartment to Angel Public School in Vasundhara Enclave. | 0.2 |  | 15.03.2017 | 30.06.2017 | 100% | 80
92 | Road from Dainik Janyug Apartment to Hindon Apartment (Budh Singh Marg). | 0.5 |  | 15.03.2017 | 30.06.2017 | 100% | 180
93 | From Kondli Bridge to Porta Cabin MCD Primary School. | 0.85 |  | 15.03.2017 | 30.06.2017 | 100% | 200
94 | Road between Pocket A-1 & A-2 Mayur Vihar Ph-III (Gurudwara Road) | 0.26 |  | 15.03.2017 | 14.08.2017 | 95% | 70
95 | Road between Block No. 12 and 13 from Khichripur Chowk to Kalyanvas Road. | 0.75 |  | 15.03.2017 | 30.06.2017 | 100% | 100
96 | Road between Block No. 11-15 from Block-15 to LBS Hospital through Jalebi Chowk, Kalyanpuri. | 0.67 |  | 15.03.2017 | 30.06.2017 | 100% | 300
97 | Road from between Block No. 2 & 3 upto Khichripur Main Road. | 0.3 |  | 15.03.2017 | 14.08.2017 | 95% | 50
98 | Khichripur road from Kondli Bridge to Mother Dairy. | 1 |  | 15.03.2017 | 30.06.2017 | 100% | 250
Name of MLA :- Sh. Raju Dhingan
Name of Constituency :- Trilokpuri AC (55)
99 | Kotla Road from Trilok Puri Police Station to Khichirpur Bus Stand. | 3 | M/s Shiva Construction Co. | 15.03.2017 | 14.08.2017 | 95% | 1760 | 1672
100 | East end apartment road. | 0.84 | M/s Anmol Infrastructure Pvt. Ltd. | 15.03.2017 | 30.06.2017 | 100% | 330 | 330
101 | Road along Ghazipur Drain | 3.6 |  | 15.03.2017 | 14.08.2017 | 95% | 2900 | 2755
102 | Peripherial road from Chilla Chowk to kotla Village. | 1.25 |  | 15.03.2017 | 30.06.2017 | 100% | 360 | 360
103 | Road from Block No. 35 to 17 Trilokpuri (Mahrishi Balmiki Marg) | 1.07 |  | 15.03.2017 | 30.06.2017 | 100% | 175 | 175
104 | Road from Block No. 19 to Block No. 13 Trilokpuri | 1.54 |  | 15.03.2017 | 30.06.2017 | 100% | 780 | 780
105 | Main road from Block No. 33 to Block No. 19. Trilokpuri | 0.52 |  | 15.03.2017 | 30.06.2017 | 100% | 60 | 60
106 | Road from Block No. 36 to Block No. 31 Trilokpuri. | 0.99 |  | 15.03.2017 | 30.06.2017 | 100% | 560 | 560
107 | Ambedkar Marg from Block No. 18 Trilokpuri to Kotla Road. | 0.95 |  | 15.03.2017 | 30.06.2017 | 100% | 200 | 200
108 | Subhash Mkt. from Chand Cinema Turn to Balvikas School | 0.6 |  | 15.03.2017 | 30.06.2017 | 100% | 245 | 245
109 | Road from Block No. (1) to (11) of Trilokpuri | 0.98 |  | 15.03.2017 | 14.08.2017 | 97% | 210 | 203.7
110 | Chilla road from Chilla chowk to Chilla Village. | 0.9 |  | 15.03.2017 | 30.06.2017 | 100% | 1045 | 1045
Name of MLA :- Sh. Manish Sisodia
Name of Constituency :- Patparganj (57)
111 | Sadhabhawana Marg (111) | 0.75 | M/s Anmol Infrastructure Pvt. Ltd. | 15.03.2017 | 14.08.2017 | 98% | 90 | 88.2
112 | Club Avenue Marg (112) | 0.45 |  | 15.03.2017 | 14.08.2017 | 95% | 175 | 166.25
113 | Sehkarita Marg (113) | 0.65 |  | 15.03.2017 | 30.06.2017 | 100% | 340 | 340
114 | ASN School to Parwana Apartment to Kala Apartment upto LSC. | 0.8 |  | 15.03.2017 | 30.06.2017 | 100% | 400 | 400
115 | Samachar Apartment Road (Link Road) Samachar Apartment to Glaxo Apartment. | 0.35 |  | 15.03.2017 | 30.06.2017 | 100% | 300 | 300
116 | Road from Block No. 1 Khichripur to NH-24. | 0.85 | M/s Shiva Construction Co. | 15.03.2017 | 14.08.2017 | 96% | 460 | 441.6 | Sh. Iqbal Singh 9910925748
117 | Khichripur Main Road from NH-24 to Mother Dairy. | 0.8 |  | 15.03.2017 | 14.08.2017 | 96% | 350 | 336
118 | Patparganj Main Road from NH-24 to Patparganj Village. | 0.3 |  | 15.03.2017 | 14.08.2017 | 96% | 95 | 91.2
119 | Road between Pocket E & F Mayur Vihar Ph-II. | 0.6 |  | 15.03.2017 | 14.08.2017 | 96% | 110 | 105.6
120 | Road from NH-24 to DJB Office,Mayur Vihar Ph2 | 0.9 |  | 15.03.2017 | 14.08.2017 | 96% | 200 | 192
121 | Road from T-point Mayur vihar ph2 to chand Cinema crossing,kalyanvas road | 1.7 |  | 15.03.2017 | 14.08.2017 | 96% | - | 500
122 | Road infront of LBS Hospital (from Kalyanvas road to main market khichripur road) | 0.5 |  | 15.03.2017 | 14.08.2017 | 96% | - | -
Name of Constituency :- Patparganj (57)
123 | Sai Chowk | 0.67 | M/s Sai Tube Well | 15.03.2017 | 14.08.2017 | 85% | 684.33 | 3412
124 | Kailash Apartment. | 0.354 |  | 15.03.2017 | 14.08.2017 | 85% | 333.65
125 | Bathla Apartment | 0.328 |  | 15.03.2017 | 14.08.2017 | 85% | 300
126 | Gagan Vihar. | 0.4 |  | 15.03.2017 | 14.08.2017 | 70% | 90
127 | Agarsain Apartment | 0.61 |  | 15.03.2017 | 14.08.2017 | 85% | 300
128 | Mother Dairy Road (Narwana Road) | 2.5 |  | 15.03.2017 | 14.08.2017 | 80% | 1214
129 | Mother Dairy Road | 1.5 |  | 15.03.2017 | 14.08.2017 | 70% | 874.65
130 | Madhu Vihar Road | 1.6 |  | 15.03.2017 | 14.08.2017 | 85% | 1578.67
131 | Balco Market | 0.63 |  | 15.03.2017 | 14.08.2017 | 90% | 153.45
132 | Prince Apartment | 0.59 |  | 15.03.2017 | 14.08.2017 | 95% | 567.88
133 | Oriental Apartment | 0.334 |  | 15.03.2017 | 14.08.2017 | 85% | 222.11
134 | Narwana Apartment | 0.46 |  | 15.03.2017 | 14.08.2017 | 85% | 262.2
135 | Trilokia Apartment | 0.38 |  | 15.03.2017 | 14.08.2017 | 85% | 216.6
136 | Rama Krishna Apartment | 0.27 |  | 15.03.2017 | 14.08.2017 | 80% | 99.9
137 | Disused canal road (Main Drain with EDMC) | 2.9 |  | 15.03.2017 | 14.08.2017 | 75% | 870
138 | New Rajdhani Road | 0.79 |  | 15.03.2017 | 14.08.2017 | 70% | 537.2
139 | Chitra Vihar Road | 0.69 |  | 15.03.2017 | 14.08.2017 | 85% | 393.3
140 | Patparganj Road | 2.89 |  | 15.03.2017 | 14.08.2017 | 75% | 2691.67
141 | Vikas Marg (Road No. 75 A & 75 B | 3.14 |  | 15.03.2017 | 14.08.2017 | 70% | 494.55
142 | Patpargunj Road (Preet Vihar) | 1.47 |  | 15.03.2017 | 14.08.2017 | 70% | 1651.86
(North-East) Road Division / M-213
143 | Road No. 66 (Seelampur Red Light on G.T. Road to Moujpur Red Light) | 2.1 | M/s Sai Tube Well | 25.04.2017 | 31.08.2017 | 85% | 1121 | 952 | Sh. K.P.Singh 9810438957
144 | Main Road Maujpur (Ghonda Chowk to Red Light on Road No.-66) | 0.999 |  | 25.04.2017 | 31.08.2017 | 85% | 605 | 605
145 | Road No. 59 ( Part of Wazirabad Road) Loni Gole Chakkar to Khajuri Chowk) | 3.45 |  | 26.03.2017 | 31.08.2017 | 90% | 2484 | 2335
146 | Tanki Road (DTC Depot dividing road to Tikona park Subhash Vihar Water Tank) | 0.65 |  | 04.06.2017 | 31.08.2017 | 95% | 760 | 740
147 | Yamuna Vihar Road (C-1 to C-4) | 1.1 |  | 01.05.2017 | 31.08.2017 | 95% | 1056 | 980
148 | Yamuna Vihar Road C block Service Road (From gokalpuri Flyover to Bhajanpura Petrol Pump) | 1.7 | M/s Sai Tube Well | 30.04.2017 | 31.08.2017 | 95% | 340 | 340 | Sh. K.P.Singh 9810438957
149 | Yamuna Vihar Dividing road (Wazirabad Road Yamuna Vihar Red Light to DTC Depot near H. No. B-5/18, Yamuna Vihar, Delhi) | 0.5 |  | 05.06.2017 | 31.08.2017 | 95% | 360 | 355
150 | Road No. 66 (Moujpur Red Light to Gokalpuri Flyover) | 1.5 |  | 05.06.2017 | 31.08.2017 | 80% | 856 | 770
151 | Main Road Noor –E-Illahi Road (DTC Depot Yamuna Vihar to Ghonda Chowk) | 0.98 |  | 28.05.2017 | 31.08.2017 | 90% | 470 | 423
152 | Road No. 63 ( Part of Wazirabad Road) Bhopura Border (U.P.) to Loni Flyover near Loni Gole Chakkar | 3.18 |  | 20.03.2017 | 31.08.2017 | 90% | 2160 | 1940
153 | Sewadham Road ( Nand Nagri Red Light on Road No. 63 to U.P. Border) | 2.45 |  | 15.05.2017 | 31.08.2017 | 80% | 1960 | 1365
154 | Loni Road G.T. Road to U.P. Border (Loni gole Chakkar to U.P. Border (Loni)) | 0.5 |  | 10.05.2017 | 31.08.2017 | 95% | 90 | 95
155 | Gokulpuri Main Road (Wazirabad Road H. No. A-1 to Gokulpuri H. No. B-22) | 0.246 |  | 09.04.2017 | 31.08.2017 | 95% | 177 | 120
156 | Bank Colony Road along western Side of Mandoli Jail Complex (Mandoli Bank Colony to Harsh Vihar Colony.) | 0.337 |  | 30.04.2017 | 31.08.2017 | 95% | 122 | 90
157 | Main Brahmpuri Road (Ghonda Chowk to Brahampuri Dhalav) | 1.84 |  | 20.05.2017 | 31.08.2017 | 82% | 1484 | 1400
158 | Old G.T. Road (Old Yamuna bridge to Darampura Y- Point) | 0.9 | Sh. Vinod Kumar | 01.05.2017 | 31.08.2017 | 95% | 510 | 450
159 | Zero Pusta (Zero Pusta to Bharampuri culvert) | 0.99 |  | 15.03.2017 | 31.08.2017 | 95% | 1090 | 690
160 | Seelmapur Road (Road No. 66 to Dhalav) | 0.517 |  | 07.04.2017 | 31.08.2017 | 95% | 480 | 370
161 | E.A. Road (Dharam Pura T-Point to ISBT) (Service road Hotel de aqua) | 4.2 |  | 07.04.2017 | 31.08.2017 | 95% | 330 | 430
162 | Grudwara Road (G. T. Road to Seelampur main Road) | 0.3 |  | 07.04.2017 | 31.08.2017 | 95% | 325 | 250
163 | MB Road (Shastri Park To Khajuri Chowk) | 3.75 |  | 10.04.2017 | 31.08.2017 | 95% | 415 | 350
164 | Gamri Road (5th Pusta to Ghonda Chowk) | 1.85 |  | 15.03.2017 | 31.08.2017 | 92% | 1435 | 990
Circle / Divn. : SRD Project Circle / SRD Project Division-I
Name of MLA :- Sh. Asim Ahmed Khan
Name of Constituency & Constituency No.:- Matia Mahal AC 21
165 | Barron Road | 0.28 | M/s Shiva Costruction Co. | 24.03.2017 | Completed | 100% | 2000 cum | 1700cum | Er. Rajeev Lochan (Mob. 9911058852)
166 | Thomson Road | 0.75 |  | 24.03.2017 | 20.08.2017 | 90%
167 | Mir Dard Road | 0.55 |  | 24.03.2017 | Completed | 100%
168 | DDU Marg | 1.98 |  | 24.03.2017 | Completed | 100%
169 | Mahawat Khan Road | 1.1 |  | 24.03.2017 | Completed | 100%
170 | Vishnu Dignamber Marg | 0.32 |  | 24.03.2017 | Completed | 100%
171 | Ranjit Singh Road | 0.45 |  | 24.03.2017 | 20.08.2017 | 85%
172 | Minto Road | 0.7 |  | 24.03.2017 | Completed | 100%
173 | Mata Sundri Road | 1.1 |  | 24.03.2017 | 20.08.2017 | 90%
174 | Turkman Road | 0.6 |  | 24.03.2017 | Completed | 100%
175 | JLN Marg | 1.86 |  | 24.03.2017 | 20.08.2017 | 80%
176 | Kotla Road | 1.48 |  | 24.03.2017 | Completed | 100%
177 | N S Marg (Delhi Gate to Urdu Bazar Chowk) | 2.22 | M/s Shiva Costruction Co. | 24.03.2017 | 20.08.2017 | 90% | --do-- | --do-- | Er. Rajeev Lochan (Mob. 9911058852)
178 | Asaf Ali Marg | 1.9 |  | 24.03.2017 | 20.08.2017 | 85%
179 | Chaman Lal Marg | 0.18 |  | 24.03.2017 | Completed | 100%
Name of MLA :- Ms. Alka lamba | [8 empty] | Er. Rajeev Lochan (Mob. 9911058852)
Name of Constituency & Constituency No.:- Chandni Chowk AC 20
180 | S.P.M. Marg | 1.48 | M/s Shiva Costruction Co. | 24.03.2017 | 20.08.2017 | 95% | 1800 | 1700 cum
181 | HC Sen Road | 0.4 |  | 24.03.2017 | Completed | 100%
182 | Khari Bawali Road | 0.427 |  | 24.03.2017 | 20.08.2017 | 95%
183 | Esplanade Road | 0.43 |  | 24.03.2017 | Completed | 100%
184 | Naya Bazar Road | 0.58 |  | 24.03.2017 | 20.08.2017 | 90%
185 | Zorawar Singh Marg | 1.32 |  | 24.03.2017 | Completed | 100%
186 | Mori Gate Road | 0.38 |  | 24.03.2017 | Completed | 100%
187 | Kela Ghat | 0.175 |  | 24.03.2017 | Completed | 100%
188 | Dewan Hall Road | 0.27 |  | 24.03.2017 | Completed | 100%
189 | Jama Masjid Road | 1.45 |  | 24.03.2017 | Completed | 100%
190 | Chandni Chowk Road | 1.29 |  | 24.03.2017 | 20.08.2017 | 90%
191 | Road No.- 47 (Boulevard Road) | 1.04 |  | 24.03.2017 | Completed | 100%
192 | Rajpur Road | 2.565 |  | 24.03.2017 | Completed | 100%
193 | Approach Road | 0.25 |  | 24.03.2017 | Completed | 100%
194 | Approach Road | 0.215 |  | 24.03.2017 | 20.08.2017 | 90%
195 | Hamilton Road | 0.24 |  | 24.03.2017 | Completed | 100%
196 | Gokhle Road | 0.876 |  | 24.03.2017 | 20.08.2017 | 90%
197 | Sarai Phose Road | 0.71 |  | 24.03.2017 | Completed | 100%
198 | NS Marg (Urdu Bazar Chowk to Lothian Bridge) | 1.4 |  | 24.03.2017 | 20.08.2017 | 90%
199 | Lothein Road | 0.925 |  | 24.03.2017 | Completed | 100%
Karol Bagh, Constituency
200 | Panchkuiya Road | 1.28 | M/s S.K. Associates | 10-04-2017 | 20.08.2017 | 95% | 5098 | 936.37 | Er. Hari Singh (Mob. 9999566267)
201 | Nehru Bazar Road | 0.45 |  | 23-05-2017 | 20.08.2017 | 87%
202 | DAV Aram Bagh Road | 0.46 |  | 10-04-2017 | 20.08.2017 | 95%
203 | Basant Road | 0.77 |  | 24-05-2017 | 20.08.2017 | 82%
204 | Main Bazar Road | 0.95 |  | 24-05-2017 | 20.08.2017 | 90%
205 | Chitra Gupta Road | 0.68 |  | 22-05-2017 | 20.08.2017 | 95%
206 | C.G.H.S. Dispansary Road | 0.23 |  | 25-05-2017 | 20.08.2017 | 96%
207 | Desh Bandu Gupta Road | 2.4 |  | 25-05-2017 | 20.08.2017 | 90%
208 | New Rohtak Road | 2.2 |  | 15-03-2017 | 10.08.2017 | 91%
209 | Faiz Road | 1.41 |  | 25-05-2017 | 10.08.2017 | 91%
210 | Rani Jhansi Road | 1.71 |  | 25-05-2017 | 20.08.2017 | 95%
211 | Vallabacharya marg | 0.25 |  | 10-05-2017 | 20.08.2017 | 95%
212 | Ajmal Khan Road | 1.6 |  | 25-05-2017 | 20.08.2017 | 85%
213 | Road No. 3 | 0.5 |  | 15-03-2017 | 20.08.2017 | 95%
214 | Dyanand Saraswati Marg (Road No. 4) | 0.5 |  | 17-03-2017 | 20.08.2017 | 90%
215 | Guru Nanak Road (Road No. 5) | 0.9 |  | 23-05-2017 | 20.08.2017 | 90%
216 | Military Road | 1.4 |  | 15-03-2017 | Completed | 100%
217 | Pyare Lal Road | 2 |  | 18-03-2017 | 20.08.2017 | 95%
218 | Hardhyan Singh Road | 1.8 |  | 20-04-2017 | 20.08.2017 | 85%
219 | Padam Singh Road | 1.5 |  | 25-05-2017 | 20.08.2017 | 90%
220 | Tank Road | 1 |  | 25-05-2017 | 20.08.2017 | 87%
221 | Guru Ravi Das Marg | 2 | M/s S.K. Associates | 24-03-2017 | 20.08.2017 | 90% | --do-- | --do-- | Er. Hari Singh (Mob. 9999566267)
222 | East Park Road | 0.99 |  | 25-05-2017 | 20.08.2017 | 85%
223 | S.K. Dass Road | 1 |  | 20-05-2017 | 20.08.2017 | 85%
224 | Abdul Rehman Road | 0.715 |  | 25-05-2017 | 20.08.2017 | 90%
225 | Abdul Aziz Road | 0.85 |  | 25-05-2017 | 20.08.2017 | 85%
226 | Elahi Bux Road | 0.415 |  | 25-05-2017 | 20.08.2017 | 90%
227 | Gurudara Road | 1 |  | 20-05-2017 | 20.08.2017 | 90%
228 | Saraswati Marg | 1 |  | 25-03-2017 | 20.08.2017 | 95%
229 | Gangeshwar Dham Marg | 0.375 |  | 25-05-2017 | 20.08.2017 | 85%
230 | D.B Gupta Road | 2 |  | 01-05-2017 | 20.08.2017 | 90%
231 | Arya Samaj Road | 1.8 |  | 25-05-2017 | 20.08.2017 | 88%
232 | Khajoor Road | 0.32 |  | 22-05-2017 | 20.08.2017 | 85%
233 | Ganga Mandir Marg | 1.5 |  | 10-05-2017 | 20.08.2017 | 85%
234 | Vishnu Mandir Marg | 1.5 |  | 20-05-2017 | 20.08.2017 | 85%
Ballimaran Constituency
235 | Chelmsford Road | 0.39 | M/s Sakur Ahmad & Sons | 10-05-2017 | 20.08.2017 | 95% | 2310 | 1700
236 | Sadar Thana Road | 0.5 |  | 25-05-2017 | 20.08.2017 | 95%
237 | Desh Raj Bhatiya Marg | 0.83 |  | 25-05-2017 | 20.08.2017 | 95%
238 | Ram Kumar Marg | 0.45 |  | 25-05-2017 | 20.08.2017 | 82%
239 | Idgah Road | 1.09 |  | 25-05-2017 | 20.08.2017 | 82%
240 | G.B. Road | 0.5 |  | 26-05-2017 | 20.08.2017 | 82%
241 | S.N. Marg | 0.95 |  | 26-05-2017 | 20.08.2017 | 85%
242 | Qutub Road | 1.85 |  | 10-05-2017 | 20.08.2017 | 90%
Sadar Bazar Constituency
243 | Azad Market Road | 0.79 |  | 20-05-2017 | 20.08.2017 | 90%
244 | Bahadur Garth Road | 0.91 |  | 20-05-2017 | 20.08.2017 | 80%
245 | Pahari Dheeraj Road | 1.2 |  | 20-05-2017 | 20.08.2017 | 80%
246 | Foota Road | 0.25 |  | 25-05-2017 | 20.08.2017 | 95%
247 | New Rohtak Road | 1 |  | 25-05-2017 | 20.08.2017 | 95%
248 | Gali No. 10 | 0.8 |  | 01-06-2017 | 20.08.2017 | 90%
C&ND Road Division (M-413)
249 | Main Burari Road | 14.2 | Sh. Sher Singh | 27.01.2017 | 18.08.2017 | 95% | 8000 | 7600 | Sh. Anil Trehan 8447001861
250 | BBM Road from Hakikat Nagar, Red Light to Mukherjee Nagar Bandh | 4.8 | Sh. Mangat Ram Gupta | 10.03.2017 | 18.08.2017 | 96%
251 | 60ft Road from Aggarwal Sweets to Nulife Hospital between BBM Road and Burari Road | 0.7 |  | 10.03.2017 | 18.08.2017 | 95%
252 | Sant Parmanand Colony Road | 1.8 |  | 10.03.2017 | 18.08.2017 | 93%
253 | Burari Road from Kingsway Camp to Road No. 50 | 7 |  | 10.03.2017 | 18.08.2017 | 95%
254 | Wazirabad Flyover | No Drain |  | 10.03.2017 | - | No Drain
255 | Munshi Ram Road | 1 |  | 10.03.2017 | 18.08.2017 | 96%
256 | Parmanand School Road | 0.66 |  | 10.03.2017 | 18.08.2017 | 96%
257 | Swaroop Nagar Road | 4.4 |  | 10.03.2017 | 18.08.2017 | 92%
258 | Police Chowki to Mandir Ortram Lane | 0.88 |  | 10.03.2017 | 18.08.2017 | 93%
259 | Tagore Park Main road | 1.8 |  | 10.03.2017 | 18.08.2017 | 95%
260 | Avtar Singh Marg (Nirankari colony) (Nirankari Colony Gate to culvert Burari Road towards Nirankari Sr. Sec. School) | 3.8 | Sh. Mangat Ram Gupta | 10.03.2017 | 18.08.2017 | 95% | --do-- | --do-- | Sh. Anil Trehan 8447001861
261 | BBM Road to Jahangirpuri Drain | 0.8 |  | 10.03.2017 | 18.08.2017 | 92%
262 | Gandhi Vihar | 1.34 |  | 10.03.2017 | 18.08.2017 | 95%
263 | Road in Tagore Park from H. No. 213 to Gole Chakkar | 0.9 |  | 10.03.2017 | 18.08.2017 | 92%
264 | Road in tagore Park from H. No. 37 to H. No. 64 | 3.1 |  | 10.03.2017 | 18.08.2017 | 94%
265 | Magazine Road | 2.7 |  | 10.03.2017 | 18.08.2017 | 92%
266 | Road No. -46 | 0.3 |  | 10.03.2017 | 18.08.2017 | 96%
267 | Road No. -45 | 5 |  | 10.03.2017 | 18.08.2017 | 98%
268 | Parallel CC Road | 14.48 | Sh. Jitender Kumar | 10.03.2017 | - | No Drain | 4350 | 4850
269 | University Road from Mall Road to Petrol Pump Ward-10 | 3.16 |  | 04.03.2017 | 14.08.2017 | 100%
270 | Khalsa College road from Mall Road to Roop Nagar (Gurutegh Bahadur Road) | 2.6 |  | 04.03.2017 | 14.08.2017 | 100%
271 | Chhatra Marg Road from Mall Road to Malka Gunj Chowk | 3.3 |  | 04.03.2017 | 14.08.2017 | 100%
272 | Shiriya Mishra marg from Jai Jawan Tea Stall to Moris Nagar Thana | 0.84 |  | 04.03.2017 | 14.08.2017 | 100%
273 | Sudhir Bose Marg from chouburjja chowk to ACP Office | 2.5 |  | 04.03.2017 | 14.08.2017 | 100%
274 | Mahatma Gandhii Road (Ring Road) | 3.2 |  | 04.03.2017 | 14.08.2017 | 100%
275 | Road No. 48 | 3.84 |  | 04.03.2017 | 14.08.2017 | 100%
276 | Vijay Nagar main road from Royal Palace to E-11 Vijay Nagar | 1.5 |  | 04.03.2017 | 14.08.2017 | 100%
277 | Surjit Singh Marg Camp Chowk to Najafgarh Drain | 1.6 |  | 04.03.2017 | 14.08.2017 | 100%
278 | Bunglow Road from Roop Nagar round about to Hansraj College T-point on Chattra Marg | 1.3 |  | 04.03.2017 | 14.08.2017 | 100%
279 | Mandelia Road from GT Road to Bunglow Road | 1.4 |  | 04.03.2017 | 14.08.2017 | 100%
280 | Polo Road from Bhama Shah Road to Shani Mandir (Vijay Nagar) | 1.68 |  | 04.03.2017 | 14.08.2017 | 100%
281 | Polo Road from Jahanara Marg to shani Mandir Vijay Nagar | 0.6 |  | 04.03.2017 | 14.08.2017 | 100%
282 | Kalyan Vihar Road from 25 Kalyan Vihar to 1 No. Priyadarshni Vihar | 1.8 |  | 04.03.2017 | 14.08.2017 | 100%
283 | Gurmandi Road from Tripolia gate GT Road to H. NO. 264 Kalyan Vihar | 0.85 |  | 04.03.2017 | 14.08.2017 | 100%
284 | Jahanara Road from Bhamashah Marg to vijay Nagar | 1.66 |  | 04.03.2017 | 30.06.2017 | 100%
285 | Satyawati Marg from Police Station Roop Nagar to Shakti Nagar Chowk | 1.04 |  | 04.03.2017 | 30.06.2017 | 100%
286 | Bhama Shah Road from Mall Road to GT Road Nanak Piao Gurudwara | 1.45 |  | 04.03.2017 | 30.06.2017 | 100%
287 | G.T. Road from Baraf Khana chowk to Clock Tower | 2.4 |  | 04.03.2017 | 14.08.2017 | 100%
288 | Roshnara Road from Pulbanash Metro Station to Hans Raj College. | 5.4 | Sh. Jitender Kumar | 04.03.2017 | 14.08.2017 | 100% | --do-- | --do-- | Sh. Anil Trehan 8447001861
289 | GT Road | 1.95 |  | 04.03.2017 | 14.08.2017 | 100%
290 | Inderchand Shastri Marg from Shakti Nagar Chowk to Swami Narayan Marg | 1.8 |  | 04.03.2017 | 14.08.2017 | 100%
291 | Timarpur road from Mall Road crossing to Wazirabad Crossing | 3.8 |  | 04.03.2017 | 14.08.2017 | 100%
292 | Lucknow Road from Mall Road to P.S. Timarpur | 3.4 | M/s Satyam Construction Co. | 04.03.2017 | 14.08.2017 | 100% | 7300 | 7150
293 | Ring Road By-pass | 5.8 |  | 07.03.2017 | 30.06.2017 | 100%
294 | Sachivalya Road | 3.2 |  | 07.03.2017 | 30.06.2017 | 100%
295 | IP Marg | 1 |  | 07.03.2017 | 30.06.2017 | 100%
296 | IG Slip Road | 1.16 |  | 07.03.2017 | 22.07.2017 | 98%
297 | Velodrome Road | 0.57 |  | 07.03.2017 | 22.07.2017 | 96%
298 | Vikas Marg | 1 |  | 07.03.2017 | 30.06.2017 | 100%
299 | Satyagrah Marg | 1 |  | 07.03.2017 | 30.06.2017 | 100%
300 | Azad Bhawan Road | 1 |  | 07.03.2017 | 15.07.2017 | 100%
301 | Ring Road Bhairon Road T-Jn. to Shanti Van Crossing | 8.4 |  | 07.03.2017 | 18.08.2017 | 96% | --do-- | --do--
302 | JLN Marg (Delhi Gate) | 1.12 |  | 07.03.2017 | 18.08.2017 | 96%
303 | Ghata Masjid Road | 0.52 |  | 07.03.2017 | 18.08.2017 | 96%
304 | Mathura Road | 1.5 |  | 07.03.2017 | 18.08.2017 | 95%
305 | Bahadur Shah Zafar Marg | 4 |  | 07.03.2017 | 18.08.2017 | 98%
306 | Ring Road By-pass | 5.3 |  | 07.03.2017 | 30.06.2017 | 100%
307 | Court Road | 3.5 |  | 07.03.2017 | 30.06.2017 | 100%
308 | Club Road | 3.5 |  | 07.03.2017 | 18.08.2017 | 95%
309 | Under Hill Road | 1.38 |  | 07.03.2017 | 18.08.2017 | 95%
310 | Flag Staff Road | 0.85 |  | 07.03.2017 | 30.06.2017 | 100%
311 | Shamnath Marg | 1.3 |  | 07.03.2017 | 18.08.2017 | 98%
312 | Rajniwas Marg | 1.852 |  | 07.03.2017 | 18.08.2017 | 95%
313 | CNG Crematorium Road | 0.5 |  | 07.03.2017 | 30.06.2017 | 100%
314 | Ring Road | 4 |  | 07.03.2017 | 18.08.2017 | 95%
315 | Mahatma Gandhi Road | 8 |  | 07.03.2017 | 18.08.2017 | 98%
316 | Nishad Raj Marg | 1.1 |  | 07.03.2017 | 18.08.2017 | 98%