## East Zone as on 25.05.18
PWD Desilting Report (Preparedness for Monsoon)
DESILTING UNDER PWD MAINTENANCE OF EAST ZONE AS ON 25.05.2018
Sl. No. | Name of Road / Drain | Length of Road (Km) | Contractor | Date of Start of De-silting | Date of completion (Ist Cycle) | % Drain cleaned (Lengthwise) | Estimate Qty. of silt (cum) | Qty. of silt lifted and disposed off (cum) | EE in charge / Mobile No.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Project Circle
Name of MLA :- Sh. Asim Ahmed Khan
Name of Constituency & Constituency No.:-Matia Mahal AC 21
SRDP-I
1 | Barron Road | 0.28 | M/s Shiva Construction Co. | 30.03.2018 | 20.06.2018 | - | 618 | NIL | Er. Suresh Pal (Mob. 9871997722)
2 | Thomson Road | 0.75 |  | 30.03.2018 | 20.06.2018 | -
3 | Mir Dard Road | 0.55 |  | 30.03.2018 | 27.05.2018 | 20%
4 | DDU Marg | 1.98 |  | 30.03.2018 | 08.06.2018 | -
5 | Mahawat Khan Road | 1.1 |  | 30.03.2018 | 08.06.2018 | -
6 | Vishnu Dignamber Marg | 0.32 |  | 30.03.2018 | 08.06.2018 | -
7 | Ranjit Singh Road | 0.45 |  | 30.03.2018 | 08.06.2018 | 10%
8 | Minto Road | 0.7 |  | 30.03.2018 | 08.06.2018 | -
9 | Mata Sundri Road | 1.1 |  | 30.03.2018 | 27.05.2018 | 25%
10 | Turkman Road | 0.6 |  | 30.03.2018 | 20.06.2018 | -
11 | JLN Marg | 1.86 |  | 30.03.2018 | 27.05.2018 | 20%
12 | Kotla Road | 1.48 |  | 30.03.2018 | 27.05.2018 | -
13 | N S Marg (Delhi Gate to Urdu Bazar Chowk) | 2.22 |  | 30.03.2018 | 20.06.2018 | -
14 | Asaf Ali Marg | 1.9 |  | 30.03.2018 | 20.06.2018 | -
15 | Chaman Lal Marg | 0.18 |  | 30.03.2018 | 27.05.2018 | -
Name of MLA :- Ms. Alka lamba
Name of Constituency & Constituency No.:- Chandni Chowk AC 20
16 | S.P.M. Marg | 1.48 | M/s Shiva Construction Co. | Nil |  |  |  |  | Er. Suresh Pal (Mob. 9871997722)
17 | HC Sen Road | 0.4
18 | Khari Bawali Road | 0.427
19 | Esplanade Road | 0.43
20 | Naya Bazar Road | 0.58
21 | Zorawar Singh Marg | 1.32
22 | Mori Gate Road | 0.38
23 | Kela Ghat | 0.175
24 | Dewan Hall Road | 0.27
25 | Jama Masjid Road | 1.45
26 | Chandni Chowk Road | 1.29
27 | Road No.- 47 (Boulevard Road) | 1.04 | M/s Shiva Construction Co. | Nil |  |  |  |  | Er. Suresh Pal (Mob. 9871997722)
28 | Rajpur Road | 2.565
29 | Approach Road | 0.25
30 | Approach Road | 0.215
31 | Hamilton Road | 0.24
32 | Gokhle Road | 0.876
33 | Sarai Phose Road | 0.71
34 | NS Marg (Urdu Bazar Chowk to Lothian Bridge) | 1.4
35 | Lothein Road | 0.925
SRD-II
Karol Bagh, Constituency
36 | Panchkuiya Road | 1.28 | Tender recalled & to be opened on dt. 25.05.2018 | - | - | - | - | - | Er. G.L. Sharma (Mob.: 7836975727)
37 | Nehru Bazar Road | 0.45 |  | - | - | - | - | -
38 | DAV Aram Bagh Road | 0.46 |  | - | - | - | - | -
39 | Basant Road | 0.77 |  | - | - | - | - | -
40 | Main Bazar Road | 0.95 |  | - | - | - | - | -
41 | Chitra Gupta Road | 0.68 |  | - | - | - | - | -
42 | C.G.H.S. Dispansary Road | 0.23 |  | - | - | - | - | -
43 | Desh Bandu Gupta Road | 2.4 |  | - | - | - | - | -
44 | New Rohtak Road | 2.2 |  | - | - | - | - | -
45 | Faiz Road | 1.41 |  | - | - | - | - | -
46 | Rani Jhansi Road | 1.71 |  | - | - | - | - | -
47 | Vallabacharya marg | 0.25 |  | - | - | - | - | -
| Ballimaran Constituency |  |  | - | - | - | - | -
48 | Chelmsford Road | 0.39 | Tender recalled & to be opened on 25.05.2018 | - | - | - | - | -
49 | Sadar Thana Road | 0.5 |  | - | - | - | - | -
50 | Desh Raj Bhatiya Marg | 0.83 |  | - | - | - | - | -
51 | Ram Kumar Marg | 0.45 |  | - | - | - | - | -
52 | Idgah Road | 1.09 |  | - | - | - | - | -
53 | G.B. Road | 0.5 |  | - | - | - | - | -
54 | S.N. Marg | 0.95 |  | - | - | - | - | -
55 | Qutub Road | 1.85 |  | - | - | - | - | -
Sadar Bazar Constituency
56 | Azad Market Road | 0.79 | Tender recalled & to be opened on 25.05.2018 | - | - | - | - | - | Er. G.L. Sharma (Mob.: 7836975727)
57 | Bahadur Garth Road | 0.91 |  | - | - | - | - | -
58 | Pahari Dheeraj Road | 1.2 |  | - | - | - | - | -
59 | Foota Road | 0.25 |  | - | - | - | - | -
60 | New Rohtak Road | 1 |  | - | - | - | - | -
61 | Gali No. 10 | 0.8 |  | - | - | - | - | -
62 | Ajmal Khan Road | 1.6 |  | - | - | - | - | -
63 | Road No. 3 | 0.5 |  | - | - | - | - | -
64 | Dyanand Saraswati Marg (Road No. 4) | 0.5 |  | - | - | - | - | -
65 | Guru Nanak Road (Road No. 5) | 0.9 |  | - | - | - | - | -
66 | Military Road | 1.4 |  | - | - | - | - | -
67 | Pyare Lal Road | 2 |  | - | - | - | - | -
68 | Hardhyan Singh Road | 1.8 |  | - | - | - | - | -
69 | Padam Singh Road | 1.5 |  | - | - | - | - | -
70 | Tank Road | 1 |  | - | - | - | - | -
71 | Guru Ravi Das Marg | 2 |  | - | - | - | - | -
72 | East Park Road | 0.99 |  | - | - | - | - | -
73 | S.K. Dass Road | 1 |  | - | - | - | - | -
74 | Abdul Rehman Road | 0.715 |  | - | - | - | - | -
75 | Abdul Aziz Road | 0.85 |  | - | - | - | - | - | Er. G.L. Sharma (Mob.: 7836975727)
76 | Elahi Bux Road | 0.415 |  | - | - | - | - | -
77 | Gurudara Road | 1 |  | - | - | - | - | -
78 | Saraswati Marg | 1 |  | - | - | - | - | -
79 | Gangeshwar Dham Marg | 0.375 |  | - | - | - | - | -
80 | D.B Gupta Road | 2 |  | - | - | - | - | -
81 | Arya Samaj Road | 1.8 |  | - | - | - | - | -
82 | Khajoor Road | 0.32 |  | - | - | - | - | -
83 | Ganga Mandir Marg | 1.5 |  | - | - | - | - | -
84 | Vishnu Mandir Marg | 1.5 |  | - | - | - | - | -
C&ND Circle /C&ND Road Divn. (M-413)
85 | Main Burari Road | 14.2 | M/s Rajat Construction Co. Agmt. No. 144/EE/C&ND-R/M413/2017-18 | 19.03.2018 | 18.10.2018 | 35% | 15042 | 1800 | Sh. Yadvinder Singh / 9717754877
86 | BBM Road from Hakikat Nagar, Red Light to Mukherjee Nagar Bandh | 4.8 |  | 19.03.2018 | 18.10.2018 | 0%
87 | 60ft Road from Aggarwal Sweets to Nulife Hospital between BBM Road and Burari Road | 0.7 |  | 19.03.2018 | 18.10.2018 | 0%
88 | Sant Parmanand Colony Road | 1.8 |  | 19.03.2018 | 18.10.2018 | 30%
89 | Burari Road from Kingsway Camp to Road No. 50 | 7 |  | 19.03.2018 | 18.10.2018 | 50% |  |  |  | 8460
90 | Wazirabad Flyover | No Drain |  | 19.03.2018 | 18.10.2018 | 0% |  |  |  | 9640
91 | Munshi Ram Road | 1 |  | 19.03.2018 | 18.10.2018 | 70% |  |  |  | 6042.8571
92 | Parmanand School Road | 0.66 |  | 19.03.2018 | 18.10.2018 | 0%
93 | Swaroop Nagar Road | 4.4 |  | 19.03.2018 | 18.10.2018 | 45%
94 | Police Chowki to Mandir Ortram Lane | 0.88 |  | 19.03.2018 | 18.10.2018 | 0%
95 | Tagore Park Main road | 1.8 |  | 19.03.2018 | 18.10.2018 | 20% |  |  |  |  | 6885.7143
96 | Avtar Singh Marg (Nirankari colony) (Nirankari Colony Gate to culvert Burari Road towards Nirankari Sr. Sec. School) | 3.8 |  | 19.03.2018 | 18.10.2018 | 95%
97 | BBM Road to Jahangirpuri Drain | 0.8 |  | 19.03.2018 | 18.10.2018 | 0%
98 | Gandhi Vihar | 1.34 |  | 19.03.2018 | 18.10.2018 | 40%
99 | Road in Tagore Park from H. No. 213 to Gole Chakkar | 0.9 |  | 19.03.2018 | 18.10.2018 | 0%
100 | Road in tagore Park from H. No. 37 to H. No. 64 | 3.1 |  | 19.03.2018 | 18.10.2018 | 0%
101 | Magazine Road | 2.7 |  | 19.03.2018 | 18.10.2018 | 0%
102 | Road No. -46 | 0.3 |  | 19.03.2018 | 18.10.2018 | 0%
103 | Road No. -45 | 5 |  | 19.03.2018 | 18.10.2018 | 40%
104 | University Road from Mall Road to Petrol Pump Ward-10 | 3.16 | M/s K.P. Singh & Co. Agmt. No. 146/EE/C&ND-R/M413/2017-18 | 19.03.2018 | 18.10.2018 | 0% | 5400 | 1998 | Sh. Yadvinder Singh / 9717754877
105 | Khalsa College road from Mall Road to Roop Nagar (Gurutegh Bahadur Road) | 2.6 |  | 19.03.2018 | 18.10.2018 | 0%
106 | Chhatra Marg Road from Mall Road to Malka Gunj Chowk | 3.3 |  | 19.03.2018 | 18.10.2018 | 0%
107 | Shiriya Mishra marg from Jai Jawan Tea Stall to Moris Nagar Thana | 0.84 |  | 19.03.2018 | 18.10.2018 | 0%
108 | Sudhir Bose Marg from chouburjja chowk to ACP Office | 2.5 |  | 19.03.2018 | 18.10.2018 | 0%
109 | Mahatma Gandhii Road (Ring Road) | 3.2 |  | 19.03.2018 | 18.10.2018 | 0%
110 | Road No. 48 | 3.84 |  | 19.03.2018 | 18.10.2018 | 0%
111 | Vijay Nagar main road from Royal Palace to E-11 Vijay Nagar | 1.5 |  | 19.03.2018 | 18.10.2018 | 0%
112 | Surjit Singh Marg Camp Chowk to Najafgarh Drain | 1.6 |  | 19.03.2018 | 18.10.2018 | 0%
113 | Bunglow Road from Roop Nagar round about to Hansraj College T-point on Chattra Marg | 1.3 |  | 19.03.2018 | 18.10.2018 | 0%
114 | Mandelia Road from GT Road to Bunglow Road | 1.4 |  | 19.03.2018 | 18.10.2018 | 0%
115 | Polo Road from Bhama Shah Road to Shani Mandir (Vijay Nagar) | 1.68 |  | 19.03.2018 | 18.10.2018 | 90%
116 | Polo Road from Jahanara Marg to shani Mandir Vijay Nagar | 0.6 |  | 19.03.2018 | 18.10.2018 | 90%
117 | Kalyan Vihar Road from 25 Kalyan Vihar to 1 No. Priyadarshni Vihar | 1.8 |  | 19.03.2018 | 18.10.2018 | 90%
118 | Gurmandi Road from Tripolia gate GT Road to H. NO. 264 Kalyan Vihar | 0.85 | M/s K.P. Singh & Co. Agmt. No. 146/EE/C&ND-R/M413/2017-18 | 19.03.2018 | 18.10.2018 | 90% | -do- | -do- | Sh. Yadvinder Singh / 9717754877
119 | Jahanara Road from Bhamashah Marg to vijay Nagar | 1.66 |  | 19.03.2018 | 18.10.2018 | 0%
120 | Satyawati Marg from Police Station Roop Nagar to Shakti Nagar Chowk | 1.04 |  | 19.03.2018 | 18.10.2018 | 0%
121 | Bhama Shah Road from Mall Road to GT Road Nanak Piao Gurudwara | 1.45 |  | 19.03.2018 | 18.10.2018 | 90%
122 | G.T. Road from Baraf Khana chowk to Clock Tower | 2.4 |  | 19.03.2018 | 18.10.2018 | 50%
123 | Roshnara Road from Pulbanash Metro Station to Hans Raj College. | 5.4 |  | 19.03.2018 | 18.10.2018 | 60%
124 | GT Road | 1.95 |  | 19.03.2018 | 18.10.2018 | 0%
125 | Inderchand Shastri Marg from Shakti Nagar Chowk to Swami Narayan Marg | 1.8 |  | 19.03.2018 | 18.10.2018 | 0%
126 | Timarpur road from Mall Road crossing to Wazirabad Crossing | 3.8 |  | 19.03.2018 | 18.10.2018 | 85%
127 | Lucknow Road from Mall Road to P.S. Timarpur | 3.4 |  | 19.03.2018 | 18.10.2018 | 80%
128 | Ring Road By-pass | 5.8 | M/s Satyam Construction Co. Agmt. No. 04/EE/C&ND-R/M413/2017-18 | 15.04.2018 | 20.06.2018 | 30% | 8021 | 1750 | Sh. Yadvinder Singh / 9717754877
129 | Sachivalya Road | 3.2 |  |  |  | 40%
130 | IP Marg | 1 |  |  |  | 25%
131 | IG Slip Road | 1.16 |  |  |  | 30%
132 | Velodrome Road | 0.57 |  |  |  | 20%
133 | Vikas Marg | 1 |  |  |  | 30%
134 | Satyagrah Marg | 1 |  |  |  | 35%
135 | Azad Bhawan Road | 1 |  |  |  | 60%
136 | Ring Road Bhairon Road T-Jn. to Shanti Van Crossing | 8.4 | M/s Satyam Construction Co. Agmt. No. 04/EE/C&ND-R/M413/2017-18 | 15.04.2018 | 20.06.2018 | 50% | -do- | -do- | Sh. Yadvinder Singh / 9717754877
137 | JLN Marg (Delhi Gate) | 1.12 |  |  |  | 0%
138 | Ghata Masjid Road | 0.52 |  |  |  | 20%
139 | Bahadur Shah Zafar Marg | 4 |  | 20.04.2018 | 25.06.2018 | 10%
140 | Ring Road By-pass | 5.3 |  |  |  | 15%
141 | Court Road | 3.5 |  |  |  | 25%
142 | Club Road | 3.5 |  |  |  | 40%
143 | Under Hill Road | 1.38 |  |  |  | 40%
144 | Flag Staff Road | 0.85 |  |  |  | 45%
145 | Shamnath Marg | 1.3 |  |  |  | 25%
146 | Rajniwas Marg | 1.852 |  |  |  | 25%
147 | CNG Crematorium Road | 0.5 |  |  |  | 0%
148 | Ring Road | 4 |  | 07.04.2018 | 20.05.2018 | 35%
149 | Mahatma Gandhi Road | 8 |  |  |  | 40%
150 | Nishad Raj Marg | 1.1 |  |  |  | 0%
Shahdara Circle /Shahdara Road Divn. (M-211)
151 | Road No 56 | 5.6 | Sh. Devender Singh Malik | 10.04.2018 | 07.06.2018 | 6% | 2200 | 0 | Er. Prakash Rawat Mobile no- 9446515711
152 | Road No. 71 | 1.6 |  | 10.04.2018 | 20.05.2018 | 4%
153 | Road No. 71 A | 0.6 |  | 10.04.2018 | 31.05.2018 | 0%
154 | Road No. 56 A | 1 |  | 10.04.2018 | 31.05.2018 | 10%
155 | G.T Road | 6.35 | M/s Maan builders | 09.04.2018 | 07.06.2018 | 5% | 2400 | 0
a) | G.T Road Railway under bridge near Metro Station Shahdara | 0.176 |  | 09.04.2018 | 20.05.2018 | 0%
b) | G.T Road Railway under bridge near Railway Station Shahdara | 0.214 |  | 09.04.2018 | 25.05.2018 | 0%
156 | Gandhi Nagar Road | 1.5 |  | 09.04.2018 | 20.05.2018 | 0%
157 | Road No 58 | 2.84 | M/s Sharma Construction Co. | 10.06.2018 | 22.06.2018 | 0% | 6300 | 0
158 | Road No 58 A | 1.6 |  | 10.06.2018 | 22.06.2018 | 0%
159 | Shaheed Bhagat Singh Marg | 1.4 |  | 20.05.2018 | 25.05.2018 | 0%
160 | Peripherial Road | 1.35 |  | 20.05.2018 | 25.05.2018 | 0%
161 | Shrestha Vihar Road | 1.25 |  | 20.05.2018 | 25.05.2018 | 0%
162 | Surajmal Vihar Market Road | 1.2 |  | 20.05.2018 | 25.05.2018 | 0%
163 | Zonal office Road. | 1.03 | M/s Sharma Construction Co. | 20.05.2018 | 25.05.2018 | 55% | -do- | -do- | Er. Prakash Rawat mobile no- 9446515711
164 | Road No 72 Extn. | 1 |  | 05.04.2018 | 31.05.2018 | 10%
165 | Road No 72 | 0.91 |  | 05.04.2018 | 31.05.2018 | 0%
166 | Shiva Khand Road | 0.9 |  | 20.05.2018 | 25.05.2018 | 0%
167 | Rishabh Vihar Road | 0.65 |  | 20.05.2018 | 25.05.2018 | 0%
168 | Sant Lal Gupta Marg | 0.617 |  | 20.05.2018 | 25.05.2018 | 0%
169 | Link Road (GT Road to Vivek Vihar ITI) | 0.6 |  | 20.05.2018 | 25.05.2018 | 0%
170 | E.S.I. Hospital Road | 0.45 |  | 20.05.2018 | 25.05.2018 | 0%
171 | Road along B-Block Jhilmil | 0.355 |  | 20.05.2018 | 25.05.2018 | 0%
172 | Road from Booster pumping station DJB opp. B-Block to A-Block market | 0.3 |  | 20.05.2018 | 25.05.2018 | 0%
173 | Road along A-Block Jhilmil Colony | 0.188 |  | 20.05.2018 | 25.05.2018 | 0%
174 | Road No. 57 (Jagatpuri Chowk to Telco-xing) | 3 | M/s Shiva Construction | 20.04.2018 | 30.05.2018 | 15% | 2250 | 0
175 | Road No. 57 (Jagatpuri Chowk to Bihari Colony) | 2.52 |  | 10.05.2018 | 25.05.2018 | 10%
176 | Road No. 75B (Karkari more to Road No. 58A) | 2.13 |  | 20.05.2018 | 25.05.2018 | 5%
177 | Vishwas Nagar 60' Road | 1.17 |  | 28.05.2018 | 07.06.2018 | 0%
178 | Shahdara Road from Drain No.1 to Dhalao Snatan Dharam School, Bhola Nath Nagar | 0.6 |  | 28.05.2018 | 07.06.2018 | 0%
179 | Bhola Nath Nagar (Railway line to Baburam School | 0.6 |  | 28.05.2018 | 07.06.2018 | 0%
180 | Shalimar park extension road (Shahdara road to H. N. 4/29830 | 0.2 |  | 28.05.2018 | 07.06.2018 | 0%
181 | DCP Office Road ( DCP office to Shahdara road) | 0.112 |  | 28.05.2018 | 07.06.2018 | 0%
182 | Road No. 68 (Road No. 69 to Railway Line Nand Nagri) | 2.2 |  | 20.04.2018 | 30.05.2018 | 10% | 4968 | 0
183 | Loni Road G.T. Road to Loni Gole Chakkar | 2.894 |  | 10.05.2018 | 30.05.2018 | 20%
184 | Main Road LIG Flats, East of Loni Road from Loni Road to community centre Ashok Nagar. | 0.375 | M/s Shiva Construction | 10.05.2018 | 25.05.2018 | 12% | -do- | -do- | Er. Prakash Rawat mobile no- 9446515711
185 | Main Road LIG flats, Loni Road to Govt. S.S. School Ashok Nagar. | 0.275 |  | 10.05.2018 | 17.05.2018 | 10%
186 | Mandoli Road | 1.942 |  | 10.05.2018 | 30.05.2018 | 0%
187 | Road No. 65 (Keshav Chowk to Road No.66 T) | 1.2 |  | 10.05.2018 | 30.05.2018 | 5%
188 | Babarpur Road (From Road No.66 to G.T. Road) | 2 |  | 10.05.2018 | 30.05.2018 | 10%
189 | Divider Road from Seemapuri road to Road No. 64 (near SDN Hospital) | 2.4 | Vinod Kumar | 21.05.2018 | 07.06.2018 | 0% | 6200 | 0
190 | Gurudwara Road from DTC bus depot Road No. 70 to GTB Hospital road | 1.75 |  | 16.05.2018 | 30.05.2018 | 85%
191 | Road No. 62 (Road No. 70 to Apsara Border) | 1.2 |  | 01.05.2018 | 30.05.2018 | 30%
192 | Road No. 70 (Seemapuri to Tahir Pur T-Point) | 1.2 |  | 01.05.2018 | 30.05.2018 | 10%
193 | New Seemapuri Road from Road No. 64 (Mother Dairy) to Road No. 62 near maszid | 1.16 |  | 21.05.2018 | 07.06.2018 | 20%
194 | Seemapuri Road from Road No. 62 to 64 | 1.065 |  | 16.04.2018 | 30.05.2018 | 75%
195 | Road from LIC Colony (T-Point to rotary at Telephone Exchange) | 0.935 |  | 21.05.2018 | 07.06.2018 | 0%
196 | Road from T-point, L-pocket to R Block small rotary | 0.86 |  | 16.05.2018 | 30.05.2018 | 30%
197 | GTB Hospital Road (From GT Road to Aggarwal Sweet Dilshad Garden) | 0.6 |  | 10.05.2018 | 25.05.2018 | 0%
198 | R-Block Road (From Divider road Agarwal sweet to GT Road) | 0.5 |  | 10.05.2018 | 25.05.2018 | 0%
199 | Road from GT Road to Road No. 64 via Telephone exchange | 0.415 |  | 21.05.2018 | 30.05.2018 | 0%
200 | Road infront of Hans Raj Public School (Divider Road to Gurudwara road) | 0.365 | Vinod Kumar | 09.04.2018 | 31.05.2018 | 25% | -do- | -do- | Er. Prakash Rawat mobile no- 9446515711
201 | Road along Divider road to pummy sweet at Gurudwara road) | 0.36 |  | 09.04.2018 | 31.05.2018 | 70%
202 | Road from Divider Road (Mukherjee Public School to Sant Ram Public School at Gurudwara road) | 0.36 |  | 09.04.2018 | 31.05.2018 | 85%
203 | LIC Road (from Malaria office MCD to GT Road) | 0.33 |  | 09.04.2018 | 31.05.2018 | 95%
204 | Road No. 62 (J & K pocket) to petrol pump GT Road (infront of Red Crosss society). | 0.33 |  | 10.05.2018 | 17.05.2018 | 0%
205 | Road from Gurudwara road (T-point of Kalander Colony) to Gauri Shankar Mandir | 0.31 |  | 09.04.2018 | 31.05.2018 | 80%
206 | Road from General Hospital (Road No. 64 to Shahdara Flyover) | 0.26 |  | 21.05.2018 | 25.05.2018 | 0%
207 | CNG Petrol Pump to deer park (Divider road) west side | 0.2 |  | 16.04.2018 | 10.05.2018 | 0%
208 | CNG Petrol Pump to deer park (Divider road) east side | 0.197 |  | 21.05.2018 | 25.05.2018 | 0%
209 | GTB Hospital road from Red light to Agarwal sweet (Divider road) | 0.195 |  | 21.05.2018 | 25.05.2018 | 0%
210 | Road No. 64 (Swami Dayanand Hospital to DLF More (U.P. Border) | 3 |  | 1.05.2018 | 15.06.2018 | 0% | 5778 | 0
211 | Road No. 68 (Road No. 69 to Railway Line Nand Nagri) | 1.4 |  | 1.05.2018 | 31.05.2018 | 0%
212 | Tanga Stand Road from road no. 68 to Wazirabad Road. | 1.25 |  | 1.05.2018 | 31.05.2018 | 25%
213 | Road No. 69 (Road No. 63 to Road No. 64 (T-point)) | 1.2 | Vinod Kumar | 1.05.2018 | 31.05.2018 | 0% | -do- | -do- | Er. Prakash Rawat mobile no- 9446515711
214 | From Rajiv Gandhi super hospital speciality hospital to GTB hospital road | 0.95 |  | 1.05.2018 | 25.05.2018 | 0%
215 | GTB Road (From Road No. 64 to Road No. 68) | 0.91 |  | 1.05.2018 | 25.05.2018 | 60%
216 | From Road No. 69 MIG Flat to GTB Hospital Road Via Nutan Vidya Mandir public school | 0.9 |  | 1.05.2018 | 20.05.2018 | 80%
217 | Captain Javed Ali Marg | 0.84 |  | 1.05.2018 | 25.05.2018 | 0%
218 | From Road No. 68 (petrol pump) to E-pocket GTB enclave police booth near Nutan Vidya Mandir public school | 0.375 |  | 1.05.2018 | 31.05.2018 | 95%
219 | Road along khel parisor from NVM school to Green field public school. | 0.25 |  | 1.05.2018 | 31.05.2018 | 0%
East Circle/ East Road (M-212)
Name of MLA :- Sh. Manoj Kumar
Name of Constituency :- Kondli AC (56)
0.5 | Road from Live stock market to Gali No. 7 Block - C in Ghazipur Dairy Farm. | 0.8 | M/s Shiva Construction Co. | 18.05.2018 | 15.06.2018 | - | - | - | Sh. Iqbal Singh 9910925748
221 | NH-24 Ghazipur to Kondli Bridge. | 1.5 |  | 18.05.2018 | 15.06.2018 | - | - | -
222 | Road from NH-24 to Hindon cut near Ghazipur Slaughter House. | 0.5 |  | 18.05.2018 | 15.06.2018 | - | - | -
223 | Dharamshilla Road | 0.6 |  | 18.05.2018 | 15.06.2018 | - | - | -
224 | Saheed Budh Singh Marg | 0.28 |  | 18.05.2018 | 15.06.2018 | - | - | -
225 | Dallupura Road | 1.25 |  | 18.05.2018 | 15.06.2018 | - | - | -
226 | M.P. Road No. 102 | 2.2 |  | 18.05.2018 | 15.06.2018 | 40% | - | -
227 | M.P Road No. 108 | 1.33 |  | 18.05.2018 | 15.06.2018 | - | - | -
228 | M.P Road 109 | 0.81 |  | 18.05.2018 | 15.06.2018 | - | - | -
229 | Road from Kondli Village up Gharoli Village X-ing. | 0.75 |  | 18.05.2018 | 15.06.2018 | 40% | - | -
230 | Road along Shiv Mandir in Gharoli Dairy Farm 'B' Block. | 0.66 |  | 18.05.2018 | 15.06.2018 | - | - | -
231 | EWS Flats to DDA Market Mayur Vihar Ph.-III X-ing upto Agarwal Sweet Shop. | 0.66 | M/s Shiva Construction Co. | 18.05.2018 | 15.06.2018 | - | - | - | Sh. Iqbal Singh 9910925748
232 | Main road between A & B Block New Kondli. | 0.35 |  | 18.05.2018 | 15.06.2018 | - | - | -
233 | Road from High land Apptt. To Soochna Apptt. In Vasundhara Enclave. | 0.4 |  | 18.05.2018 | 15.06.2018 | - | - | -
234 | Road from Manav Ashray Apptt. To Hindon Apptt. In Vasundhara Enclave | 0.48 |  | 18.05.2018 | 15.06.2018 | - | - | -
235 | Road from Dashmesh Public School to Delux Apptt. Via Mahesh Apptt. In Vasundhara Enclave. | 0.75 |  | 18.05.2018 | 15.06.2018 | - | - | -
236 | Bhagvan Mahavir Swami Marg. | 0.8 |  | 18.05.2018 | 15.06.2018 | - | - | -
237 | Sameer Bhan Marg | 0.825 |  | 18.05.2018 | 15.06.2018 | - | - | -
238 | Road from Cell Apartment to Angel Public School in Vasundhara Enclave. | 0.2 |  | 18.05.2018 | 15.06.2018 | - | - | -
239 | Road from Dainik Janyug Apartment to Hindon Apartment (Budh Singh Marg). | 0.5 |  | 18.05.2018 | 15.06.2018 | - | - | -
240 | From Kondli Bridge to Porta Cabin MCD Primary School. | 0.85 |  | 18.05.2018 | 15.06.2018 | - | - | -
241 | Road between Pocket A-1 & A-2 Mayur Vihar Ph-III (Gurudwara Road) | 0.26 |  | 18.05.2018 | 15.06.2018 | - | - | -
242 | Road between Block No. 12 and 13 from Khichripur Chowk to Kalyanvas Road. | 0.75 |  | 18.05.2018 | 15.06.2018 | - | - | -
243 | Road between Block No. 11-15 from Block-15 to LBS Hospital through Jalebi Chowk, Kalyanpuri. | 0.67 |  | 18.05.2018 | 15.06.2018 | - | - | -
244 | Road from between Block No. 2 & 3 upto Khichripur Main Road. | 0.3 |  | 18.05.2018 | 15.06.2018 | - | - | -
245 | Khichripur road from Kondli Bridge to Mother Dairy. | 1 |  | 18.05.2018 | 15.06.2018 | - | - | -
Name of MLA :- Sh. Raju Dhingan
Name of Constituency :- Trilokpuri AC (55)
246 | Kotla Road from Trilok Puri Police Station to Khichirpur Bus Stand. | 3 | M/s Shiva Construction Co. | 18.05.2018 | 15.06.2018 | - | - | - | Sh. Iqbal Singh 9910925748
247 | East end apartment road. | 0.84 |  | 18.05.2018 | 15.06.2018 | - | - | -
248 | Road along Ghazipur Drain | 3.6 |  | 18.05.2018 | 15.06.2018 | - | - | -
249 | Peripherial road from Chilla Chowk to kotla Village. | 1.25 |  | 18.05.2018 | 15.06.2018 | - | - | -
250 | Road from Block No. 35 to 17 Trilokpuri (Mahrishi Balmiki Marg) | 1.07 |  | 18.05.2018 | 15.06.2018 | - | - | -
251 | Road from Block No. 19 to Block No. 13 Trilokpuri | 1.54 |  | 18.05.2018 | 15.06.2018 | - | - | -
252 | Main road from Block No. 33 to Block No. 19. Trilokpuri | 0.52 |  | 18.05.2018 | 15.06.2018 | - | - | -
253 | Road from Block No. 36 to Block No. 31 Trilokpuri. | 0.99 |  | 18.05.2018 | 15.06.2018 | - | - | -
254 | Ambedkar Marg from Block No. 18 Trilokpuri to Kotla Road. | 0.95 |  | 18.05.2018 | 15.06.2018 | - | - | -
255 | Subhash Mkt. from Chand Cinema Turn to Balvikas School | 0.6 |  | 18.05.2018 | 15.06.2018 | 10% | - | -
256 | Road from Block No. (1) to (11) of Trilokpuri | 0.98 |  | 18.05.2018 | 15.06.2018 | 10% | - | -
257 | Chilla road from Chilla chowk to Chilla Village. | 0.9 |  | 18.05.2018 | 15.06.2018 | - | - | -
Name of MLA :- Sh. Manish Sisodia
Name of Constituency :- Patparganj (57)
258 | Sadhabhawana Marg (111) | 0.75 | M/s Shiva Construction Co. | 18.05.2018 | 15.06.2018 | - | - | - | Sh. Iqbal Singh 9910925748
259 | Club Avenue Marg (112) | 0.45 |  | 18.05.2018 | 15.06.2018 | - | - | -
260 | Sehkarita Marg (113) | 0.65 |  | 18.05.2018 | 15.06.2018 | - | - | -
261 | ASN School to Parwana Apartment to Kala Apartment upto LSC. | 0.8 |  | 18.05.2018 | 15.06.2018 | - | - | -
262 | Samachar Apartment Road (Link Road) Samachar Apartment to Glaxo Apartment. | 0.35 |  | 18.05.2018 | 15.06.2018 | - | - | -
263 | Road from Block No. 1 Khichripur to NH-24. | 0.85 |  | 18.05.2018 | 15.06.2018 | - | - | -
264 | Khichripur Main Road from NH-24 to Mother Dairy. | 0.8 |  | 18.05.2018 | 15.06.2018 | - | - | -
265 | Patparganj Main Road from NH-24 to Patparganj Village. | 0.3 |  | 18.05.2018 | 15.06.2018 | - | - | -
266 | Road between Pocket E & F Mayur Vihar Ph-II. | 0.6 |  | 18.05.2018 | 15.06.2018 | - | - | -
267 | Road from NH-24 to DJB Office,Mayur Vihar Ph2 | 0.9 |  | 18.05.2018 | 15.06.2018 | - | - | -
268 | Road from T-point Mayur vihar ph2 to chand Cinema crossing,kalyanvas road | 1.7 |  | 18.05.2018 | 15.06.2018 | - | - | -
269 | Road infront of LBS Hospital (from Kalyanvas road to main market khichripur road) | 0.5 |  | 18.05.2018 | 15.06.2018 | - | - | -
Name of Constituency :- Patparganj (57)
270 | Sai Chowk | 0.67 | M/s Shiva Construction Co. | 23.04.2018 | 30.06.2018 | - | 11582 | 130 | Sh. Iqbal Singh 9910925748
271 | Kailash Apartment | 0.354 |  | 23.04.2018 | 30.06.2018 | -
272 | Bathla Apartment | 0.328 |  | 23.04.2018 | 30.06.2018 | -
273 | Gagan Vihar | 0.4 |  | 23.04.2018 | 30.06.2018 | 40%
274 | Agarsain Apartment | 0.61 |  | 23.04.2018 | 30.06.2018 | -
275 | Mother Dairy Road (Narwana Road) | 2.5 |  | 23.04.2018 | 30.06.2018 | -
276 | Mother Dairy Road | 1.5 | M/s Shiva Construction Co. | 23.04.2018 | 30.06.2018 | - | -do- | -do- | Sh. Iqbal Singh 9910925748
277 | Madhu Vihar Road | 1.6 |  | 23.04.2018 | 30.06.2018 | - | -
278 | Balco Market | 0.63 |  | 23.04.2018 | 30.06.2018 | - | -
279 | Prince Apartment | 0.59 |  | 23.04.2018 | 30.06.2018 | - | -
280 | Oriental Apartment | 0.334 |  | 23.04.2018 | 30.06.2018 | - | -
281 | Narwana Apartment | 0.46 |  | 23.04.2018 | 30.06.2018 | 10% | -
282 | Trilokia Apartment | 0.38 |  | 23.04.2018 | 30.06.2018 | - | -
283 | Rama Krishna Apartment | 0.27 |  | 23.04.2018 | 30.06.2018 | - | -
284 | Disused canal road (Main Drain with EDMC) | 2.9 |  | 23.04.2018 | 30.06.2018 | 10% | -
285 | New Rajdhani Road | 0.79 |  | 23.04.2018 | 30.06.2018 | - | -
286 | Chitra Vihar Road | 0.69 |  | 23.04.2018 | 30.06.2018 | - | -
287 | Patparganj Road | 2.89 |  | 23.04.2018 | 30.06.2018 | 30% | -
288 | Vikas Marg (Road No. 75 A & 75 B | 3.14 |  | 23.04.2018 | 30.06.2018 | 2% | -
288 | Preet Vihar | 1.47 |  | 23.04.2018 | 30.06.2018 | - | -
290 | ROB -36 | 1.3 |  | 23.04.2018 | 30.06.2018 | - | -
North East Circle/NE Road Divn. (M-213)
291 | Road No. 66 (Seelampur Red Light on G.T. Road to Moujpur Red Light) | 2.1 | Sh. Rajneesh 08/EE/CRMD/ M-213/2018-19 | 13.05.2018 | 31.05.2018 | 10% | 365 | - | Sh. Pratap Singh 9910435151
292 | Main Road Maujpur (Ghonda Chowk to Red Light on Road No.-66) | 0.999 |  |  |  | 10% | 400 | -
293 | Road No. 66 (Moujpur Red Light to Gokalpuri Flyover) | 1.5 |  |  |  | 10% | 450 | -
294 | Sewadham Road ( Nand Nagri Red Light on Road No. 63 to U.P. Border) | 2.45 |  |  |  | 10% | 735 | -
295 | Main Brahmpuri Road (Ghonda Chowk to Brahampuri Dhalav) | 1.84 |  |  |  | 10% | 1380 | -
296 | Road No. 59 ( Part of Wazirabad Road) Loni Gole Chakkar to Khajuri Chowk) | 3.45 |  |  |  | 10% | 2480 | -
297 | Tanki Road (DTC Depot dividing road to Tikona park Subhash Vihar Water Tank) | 0.65 | Sh. Jitender Kumar 05/EE/CRMD/M-213/2018-19 | 20.04.2018 | 31.05.2018 | 10% | 528 | - | Sh. Pratap Singh 9910435151
298 | Yamuna Vihar Road (C-1 to C-4) | 1.1 |  |  |  | 9% | 891 | -
299 | Yamuna Vihar Road C block Service Road (From gokalpuri Flyover to Bhajanpura Petrol Pump) | 1.7 |  |  |  | 10% | 21 | -
300 | Yamuna Vihar Dividing road (Wazirabad Road Yamuna Vihar Red Light to DTC Depot near H. No. B-5/18, Yamuna Vihar, Delhi) | 0.5 |  |  |  | 10% | 405 | -
301 | Main Road Noor –E-Illahi Road (DTC Depot Yamuna Vihar to Ghonda Chowk) | 0.98 |  |  |  | 25% | 720 | -
302 | Road No. 63 ( Part of Wazirabad Road) Bhopura Border (U.P.) to Loni Flyover near Loni Gole Chakkar | 3.18 |  |  |  | 35% | 2290 | -
303 | Loni Road G.T. Road to U.P. Border (Loni gole Chakkar to U.P. Border (Loni)) | 0.5 |  |  |  | 35% | 75 | -
304 | Gokulpuri Main Road (Wazirabad Road H. No. A-1 to Gokulpuri H. No. B-22) | 0.246 |  |  |  | 9% | 265 | -
305 | Bank Colony Road along western Side of Mandoli Jail Complex (Mandoli Bank Colony to Harsh Vihar Colony.) | 0.337 |  |  |  | 10% | 50 | -
306 | Shastri Park To Khajuri Chowk | 3.75 | M/s. Maan Builders 06/EE/CRMD/ M-213/2018-19 | 24.04.2018 | 31.05.2018 | 15% | 710 | - | Sh. Pratap Singh 9910435151
307 | Gamri Road | 1.05 |  |  |  | 15% | 1800 | -
308 | E.A. Road | 3.3 |  |  |  | 10% | 400 | -
309 | Seelmapur Road from Road No. 66 to Dhalav. | 0.517 |  |  |  | 10% | 580 | -
310 | G.T. Road Old Yamuna bridge to Y Point | 0.9 |  |  |  | 5% | 620 | -
311 | Gurudwara Road | 0.3 |  |  |  | 5% | 400 | -
312 | Zero Pusta to Bharampuri culvert | 0.99 |  |  |  | 5% | 1320 | -