## 01-06-18
Details of Desilting of Drain
Under North Zone (M)
(As on 01-06-18)
Sl. No. | Name of Road / Drain | Length of Road (Km) | Contractor | Date of Start | Revised date of completion (Ist Cycle) | Estimate Qty. of silt (cum) | % Drain cleaned (Lengthwise) | Qty. of silt lifted and disposed off (cum) | EE in charge / Mobile No.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
NORTH WEST CIRCLE
NORTH WEST ROAD-1
1 | Shyamji Krishan Verma Marg (Road No.44) | 2 | Sh.Sanjay Kaura | 2018-04-28 | 2018-07-26 | 2507 | 45 |  | Sh. R.K. Khanna / 8826818787
2 | Kabir Das Road | 1.59 | ----Do--- | 2018-04-28 | 2018-07-26 |  | 20 |  | -do-
3 | Maharishi Parshu Ram Marg | 0.75 | ----Do--- | 2018-04-28 | 2018-07-26 |  | 0 |  | -do-
4 | Main Road of G-Block & H-Block | 0.33 | ----Do--- | 2018-04-28 | 2018-07-26 |  | 15 |  | -do-
5 | Valmiki Road | 0.6 | ----Do--- | 2018-04-28 | 2018-07-26 |  | 0 |  | -do-
6 | Triwalubar Marg | 0.29 | ----Do--- | 2018-04-28 | 2018-07-26 |  | 35 |  | -do-
7 | Lala Lajpat Rai Marg | 0.37 | ----Do--- | 2018-04-28 | 2018-07-26 |  | 0 |  | -do-
8 | Eklavya Marg | 0.37 | ----Do--- | 2018-04-28 | 2018-07-26 |  | 0 |  | -do-
9 | Balbhir singh sidhu marg | 0.99 | ----Do--- | 2018-04-28 | 2018-07-26 |  | 10 |  | -do-
10 | Guru Harikishan Marg (Road No. 43) (From RD 0m to RD 1745m) | 1.46 | ----Do--- | 2018-04-28 | 2018-07-26 |  | 65 |  | -do-
11 | Veer Hemu Marg | 1.09 | ----Do--- | 2018-04-28 | 2018-07-26 |  | 0 |  | -do-
12 | Abdul Hameed Marg | 0.78 | ----Do--- | 2018-04-28 | 2018-07-26 |  | 0 |  | -do-
13 | Phirni Road | 0.53 | ----Do--- | 2018-04-28 | 2018-07-26 |  | 0 |  | -do-
14 | Lawrence Road | 0.6 | ----Do--- | 2018-04-28 | 2018-07-26 |  | 0 |  | -do-
15 | Rampura Main Road | 1.2 | ----Do--- | 2018-04-28 | 2018-07-26 |  | 0 |  | -do-
16 | Parwana road | 0.375 | ----Do--- | 2018-04-28 | 2018-07-26 |  | 0 |  | -do-
17 | Padeshwar Dham Mandir Marg | 1.8 | M/s Shiv Shakti Enterprises | 2018-04-05 | 2018-07-03 | 727 | 75 | 0 | -do-
18 | KC Goel Marg | 2 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 0 |  | -do-
19 | Gulab Singh Marg | 5.4 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 0 |  | -do-
20 | Bharat Nagar Road | 4.18 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 65 |  | -do-
21 | Nimri Colony H.NO. 623 to Gurudwara | 0.7 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 90 |  | -do-
22 | Tewatia Marg | 2.2 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 0 |  | -do-
23 | Ch. Mange Ram Marg | 0.35 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 85 |  | -do-
24 | Madhav Marg | 2 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 75 |  | -do-
25 | Sh. Guru Nanak Dev Ji Marg | 0.8 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 90 |  | -do-
26 | Front of Keshavpuram Police Station | 0.7 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 90 |  | -do-
27 | Maharishi Dayanand Saraswati Marg | 0.9 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 50 |  | -do-
28 | Shri Ram Krishan Mandir Marg | 0.8 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 0 |  | -do-
29 | Kulachi Hans Raj School Marg | 0.4 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 25 |  | -do-
30 | F-Block Market | 0.2 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 0 |  | -do-
31 | B-Block Market | 0.875 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 0 |  | -do-
32 | Deep Chand Central Market | 1.6 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 0 |  | -do-
33 | Road No. 37 (Maharaja Nahar Singh Marg) | 0.9 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 0 |  | Sh. R.K. Khanna / 8826818787
34 | Jhule Lal Marg | 0.7 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 0 |  | -do-
35 | Shiv Ram Mandir Marg | 0.6 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 50 |  | -do-
36 | Road No. 38 | 1.62 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 20 |  | -do-
37 | Mata Jai Kaur Road | 0.58 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 0 |  | -do-
38 | Sunder Lal Jain Road | 1.1 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 0 |  | -do-
39 | Bunkar Colony Road | 0.448 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 90 |  | -do-
40 | Kakaji Lane | 0.64 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 0 |  | -do-
41 | Laxmi Bai College Road | 0.77 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 0 |  | -do-
42 | Swamy Narayan underpass road | 1 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 0 |  | -do-
43 | Nimri Colony Road (H.No. 215 Nimri colony to Staff Quarters) | 0.6 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 85 |  | -do-
44 | Nimri Colony Road (H.No. 411 to H.No. 397) | 0.35 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 85 |  | -do-
45 | Nimri Colony Road (H.No. 23 to H.No. 123) | 0.35 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 85 |  | -do-
46 | Nimri Colony Road (K-Block JJ Colony Dhalao to Nahjafgarh Drain) | 0.19 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 75 |  | -do-
47 | Nimri Colony Road (H.No. 1to H.No. 423) | 0.644 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 80 |  | -do-
48 | Nimri Colony Road (H.No. 227 to Gulab Singh Mag Opp. Murga Market). | 1.546 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 85 |  | -do-
49 | Nimri Colony Road (H.No. 413 to Little Fairy Public School) | 0.656 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 85 |  | -do-
50 | Road No. 40 (Bir Bandha Bairagi Marg) | 6.305 | ----Do--- | 2018-04-05 | 2018-07-03 | 2781 | 15 | 0 | -do-
51 | Swamy Narayan Marg | 4.95 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 0 |  | -do-
52 | Old Rohtak Road (Zakhira RUB to Road No.40 near Metro Pillar No.100 ) | 5.25 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 15 |  | -do-
53 | Nand Lal Marg | 1.52 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 50 |  | -do-
54 | Azad Road | 1.45 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 75 |  | -do-
55 | Haji Abdul Salam Quareshi Marg | 0.86 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 50 |  | -do-
56 | Swamy Narayan underpass road | 1.85 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 90 |  | -do-
57 | Partap Nagar Road | 1.25 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 75 |  | -do-
58 | Bhagat Singh Road | 0.47 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 90 |  | -do-
59 | Link Road (East Moti Bagh) | 0.18 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 90 |  | -do-
60 | Link Road (Lellawati School Road) | 0.29 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 90 |  | -do-
61 | Rana Pratap Bagh | 0.4 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 75 |  | -do-
62 | Roshanara Underpass Road | 0.15 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 50 |  | -do-
63 | Zakhira Underpass | 0.325 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 10 |  | -do-
64 | Outer Ring Road (Madhuban Chowk to Haiderpur Metro Station) | 5.6 | Sh. Sanjay Kaura | 2018-04-05 | 2018-07-03 | 1633 | 95 | 0 | -do-
65 | BDFD Marg | 0.54 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 5 |  | -do-
66 | T.V. Tower Road | 0.66 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 10 |  | -do-
67 | Power House Road | 1.3 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 55 |  | -do-
68 | Muni Maya Ram Marg | 1.738 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 60 |  | -do-
69 | Ring Road (Punjabi Bagh Flyover to Prembari Underpass) | 3.2 | M/s Shiv Shakti Enterprises | 2018-04-05 | 2018-07-03 | 2668 | 60 | 0 | Sh. R.K. Khanna / 8826818787
70 | RUB Shalimar Bagh Road | 0.6 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 90 |  | -do-
71 | Jhule Lal Mandir Marg Shalimar Bagh | 1.25 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 35 |  | -do-
72 | Dividing Road | 0.26 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 20 |  | -do-
73 | Abhinav model School | 0.4 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 15 |  | -do-
74 | Ahinsa path Road | 0.4 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 15 |  | -do-
75 | NP - MP Road | 0.46 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 60 |  | -do-
76 | SP School Road | 0.65 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 35 |  | -do-
77 | Shaheed Udham Singh Marg | 1.6 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 30 |  | -do-
78 | Swami Shardanand Saraswati Marg | 1.2 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 40 |  | -do-
79 | Maharaja Agarsen Road | 2.84 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 50 |  | -do-
80 | Gopal Mandir Road | 1.105 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 70 |  | -do-
81 | Gurudwara Road | 0.6 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 50 |  | -do-
82 | Gyan Shakti Mandir Marg | 1.25 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 30 |  | -do-
83 | Maharishi Dayanand Marg | 0.4 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 5 |  | -do-
84 | Club Road | 0.6 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 0 |  | -do-
85 | K.L. Bagga Marg | 0.6 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 0 |  | -do-
86 | Haiderpur Main Road | 0.9 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 70 |  | -do-
87 | Canal Road | 0.88 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 20 |  | -do-
88 | Ram Leela Ground Road | 0.88 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 80 |  | -do-
89 | Ring Road (Prembari to ROB Azadpur) | 2 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 25 |  | -do-
90 | Road No. 41 | 3 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 35 |  | -do-
91 | Road No. 37 extn. | 0.32 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 60 |  | -do-
92 | Ring Road (Britannia Crossing to Data Dev Temple) | 0.35 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 40 |  | -do-
93 | Ring Road (Punjab Kesri to Railway Track) | 0.35 | ----Do--- | 2018-04-05 | 2018-07-03 |  | 40 |  | -do-
NORTH WEST ROAD-2 DIVISION
94 | Road No. 316 | 1.4 | Sh. Rajnish Yadav | 04.05.2018 | 30.06.2018 | By Super Sucker | 70 | 0 | Baljit Singh/ 9811621849
95 | Road No. 317 | 0.35 | .........DO........ | 04.05.2018 | 30.06.2018 |  | 0 | 0
96 | Road No. 318 | 0.85 | .........DO........ | 04.05.2018 | 30.06.2018 |  | 0 | 0
97 | Road No. 319 | 0.35 | .........DO........ | 04.05.2018 | 30.06.2018 |  | 0 | 0
98 | S.N. Hardiker Marg (Road No. A-1) | 1.19 | .........DO........ | 04.05.2018 | 30.06.2018 |  | 0 | 0
99 | Sir Chotu Ram Marg (road No. A-3) | 1 | .........DO........ | 04.05.2018 | 30.06.2018 |  | 0 | 0
100 | Pradeep Bhatia Marg (Road No. A-5) | 1 | .........DO........ | 04.05.2018 | 30.06.2018 |  | 0 | 0
101 | Maharaja Aggarsen Marg (Road No. 42-A) | 2.3 | .........DO........ | 04.05.2018 | 30.06.2018 |  | 0 | 0
102 | Nangloi Rly.Stn to Sultanpuri Bus Terminal via Jalebi Chowk | 2.1 | .........DO........ | 04.05.2018 | 30.06.2018 |  | 40 | 0
103 | Sultanpuri Bus Terminal to Flood Control Drain. | 1 | .........DO........ | 04.05.2018 | 30.06.2018 |  | 20 | 0
104 | Sanjay Gandhi Hospital Road from Road No.316 to J Block Survodya Vidhyalya to Kanjhawla Road. | 1.6 | .........DO........ | 04.05.2018 | 30.06.2018 |  | 30 | 0
105 | Police Station Road from Road No.3 i.e. Kanjhawla Road to Sanjay Gandhi Hospital Road. | 1.3 | .........DO........ | 04.05.2018 | 30.06.2018 |  | 40 | 0
106 | Sultanpuri Main Road | 0.6 | .........DO........ | 04.05.2018 | 30.06.2018 |  | 0 | 0
107 | Shani Bazar Road | 0.6 | .........DO........ | 04.05.2018 | 30.06.2018 |  | 50 | 0
108 | H Block Road | 0.32 | .........DO........ | 04.05.2018 | 30.06.2018 |  | 30 | 0
109 | Jagdamba Road | 0.38 | .........DO........ | 04.05.2018 | 30.06.2018 |  | 20 | 0
110 | Bhalla Factory road | 0.38 | .........DO........ | 04.05.2018 | 30.06.2018 |  | 80 | 0
111 | Kala Mandir Cinema Road in Mangolpuri | 0.8 | .........DO........ | 04.05.2018 | 30.06.2018 |  | 0 | 0
112 | LP Road (Tank Road) Mangolpuri | 1.2 | .........DO........ | 04.05.2018 | 30.06.2018 |  | 0 | 0
113 | B-Block Road Mangolpuri | 1.4 | .........DO........ | 04.05.2018 | 30.06.2018 |  | 0 | 0
114 | G-Block Road | 0.15 | .........DO........ | 04.05.2018 | 30.06.2018 |  | 0 | 0
115 | 70 ft Road Kirari | 1.25 | .........DO........ | 04.05.2018 | 30.06.2018 |  | 70 | 0
116 | Katran Road (Durbal Nath Marg) Mangolpuri | 0.55 | .........DO........ | 04.05.2018 | 30.06.2018 |  | 80 | 0
117 | Road No.A-2 From Pole Star to CSC-II, Sec.1/2, Rohini. | 0.54 | .........DO........ | 04.05.2018 | 30.06.2018 |  | 0 | 0
118 | Road from New Bal Bharti Public School to Road No.3 Sec.2 | 0.4 | .........DO........ | 04.05.2018 | 30.06.2018 |  | 0 | 0
119 | Road from CSC Market Pkt.4 to Mangolpur Kalan Phirni Road Sec.2 | 0.3 | .........DO........ | 04.05.2018 | 30.06.2018 |  | 0 | 0
120 | Roadfrom PocketA-1 to Pocket A-2 in Sec.4 Rohini | 0.225 | .........DO........ | 04.05.2018 | 30.06.2018 |  | 0 | 0
121 | Roadfrom Pocket B-5to Pocket B-9 in Sec.4 Rohini MC Pry. School | 0.31 | .........DO........ | 04.05.2018 | 30.06.2018 |  | 0 | 0
M-3122
122 | Deen Bandhu Sir Chotu Ram Marg (Road No. A-4) | 1 | M/s work Cee | 31.03.2018 | 30.06.2018 | By Super Sucker | 80 | 0 | Baljit Singh / 9811621849
123 | Road No. 41-A Bhagwan mahavir Marg. | 3.995 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 27 | 0
124 | Road No. B-1 | 0.96 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
125 | Road No. B-3 | 1.55 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
126 | Road From Pocket A-2 to Pkt.C-13 in Sec.3 Rohini | 1 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
127 | Road from Pocket F-22 to Pocket H-34 in Sec-3 Rohini | 1 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 50 | 0
128 | Road from MC Pry. School 3A to Sarvodaya School in Sec.3, Rohini | 0.325 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
129 | Road from DDA Shopping Centre to Kendriya Vidyalaya in Sec.3, Rohini. | 0.325 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 40 | 0
130 | Jaipur Golden Hospital Road Sec.3 | 1 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
131 | MTNL Godown to C6/137 Sec.5, Rohini | 0.533 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 90 | 0
132 | Som Bazar Road, Sec.5, Rohini | 0.71 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 90 | 0
ROHINI SECTOR-6
133 | Shiva Road from Ring Road to Dividing Road of Sec.5 & 6, Rohini. | 2.217 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
134 | Vidya Jain Public School, Se.6, Rohini | 0.477 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 25 | 0
135 | C-4/253 toC5/253, Sec.6, Rohini | 0.33 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
136 | D-6 and A-1 Road sec.6,Rohini | 0.33 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 80 | 0
ROHINI SECTOR-7
137 | G-23/30 to E4/15 Sec.7 | 0.396 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 30 | 0
138 | B-6/159 to Naharpur DAV School back side Sec.7 | 0.296 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 90 | 0
139 | B-22/279 to G-21/222 Sec.7 | 0.321 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 5 | 0
140 | B-4/30 to CGHS Dispensary Sec.7 | 0.172 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
141 | H18 to F-25 Sec.6 & 7 dividing road(Bhagwan Parshu Ram Marg) | 1.3 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 50 | 0
ROHINI SECTOR-8
142 | Rama Road Sec.8, Rohini | 0.73 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
143 | Road from Road No. 41-A to Rama Road in Sec.8, Rohini | 1.05 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
144 | Road from Road No. 42-A to Rama Road in Sec.8, Rohini | 0.55 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
ROHINI SECTOR-9
145 | Sawran Jayanti Park Road, Sec.9 &13 | 1.68 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
ROHINI SECTOR-11
146 | Road from F-3 block to H-4 in Sec.11, Rohini | 0.7 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
147 | From A-1 to F-3 Block near NDPL office Sec.11, Rohini. | 1.5 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 5 | 0
148 | From Block H-1 to H-5 Block Sec.11, Rohini | 0.65 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
149 | From F-1 to H-2 Block near NDPL office Sec.11, Rohini. | 0.65 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
150 | From C-4 to A-3 Block near NDPL office Sec.11, Rohini. | 0.65 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 20 | 0
151 | From F-1 to F-3 Block near NDPL office Sec.11, Rohini. | 0.375 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
152 | From A-1 to A-3 Block near NDPL office Sec.11, Rohini. | 0.375 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
153 | From C-1 to C-5 Block near NDPL office Sec.11, Rohini. | 0.375 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 7 | 0
154 | From Community Centre to NDMC Colony, Sec.11, Rohini. | 0.69 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
ROHINI SECTOR - 16
155 | D-1 TO I-3 (Length 0.463 KM) | 0.463 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
156 | G-1 TO E-5 (Length 0.650 KM) | 0.65 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
157 | G-7 TO G-1 (Length 1.000 KM) | 1 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
158 | H-3 TO H-1 (Length 0.400 KM) | 0.4 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
159 | A-2 TO E-3 (Length 0.650 KM) | 0.65 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
160 | C-1 TO I-11 (Length 0.600 KM) | 0.6 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
161 | District Park TO C-1 (Length 0.438 KM) | 0.438 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
162 | F-2 TO F-6 (Length 0.338 KM) | 0.338 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
163 | A-6 TO A-8 (Length 0.263 KM) | 0.263 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
164 | F-3 TO F-5 (Length 0.338 KM) | 0.338 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
165 | I-1 TO Police Station (Length 0.538 KM) | 0.538 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
ROHINI SECTOR - 17
166 | B-2 TO B-6 (Length 0.210 KM) | 0.21 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 20 | 0
167 | A-8 TO B-6 (Length 0.600 KM) | 0.6 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
168 | B-1 TO C-1 (Length 0.475 KM) | 0.475 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
169 | A-8 TO B-1 ROAD (Length 0.445 KM) | 0.445 | .........DO........ | 31.03.2018 | 30.06.2018 |  | 0 | 0
M-3123
170 | Dr. K.N. Katju Marg(45m wide road) | 3.77 | M/S Workcee | 29.03.2018 | 30.06.2018 | By Super Sucker | 30 | 0 | Baljit Singh/ 9811621849
171 | Road No. B-2 (Ram murthi Passi Marg) | 1.652 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 8 | 0
172 | Road No. B-4 | 1.4 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 8 | 0
173 | Road No. B-5 | 1.64 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 10 | 0
174 | Road No. B-6 | 1 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 10 | 0
175 | Road No. B-7 | 1.25 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 10 | 0
176 | Road No. B-8 | 1.18 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 10 | 0
ROHINI SECTOR-9
177 | Col. Sarna Marg Sec.9 & 13 | 1.02 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 15 | 0
178 | Internal Road of Sec.9 Rohini | 0.325 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 15 | 0
179 | Internal Road of Sec.9 Rohini | 0.33 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 15 | 0
180 | R.N. Gujral Marg Sec.9 | 0.265 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 20 | 0
181 | Chetak Apartment to New Modern Apartment Sec.9 | 0.319 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 15 | 0
182 | Vidhya Vihar to Neelgiri Apt. Sec.9 | 0.33 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 20 | 0
183 | Captain Dahiya Marg Sec.9 & 13 | 1.68 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 20 | 0
184 | Ahinsha Marg Sec.9 & 13 | 1.68 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 10 | 0
ROHINI SECTOR - 13 Extn.
185 | Sunrise Appartment (K. N. Katzu Marg) to Neelkanth Appartment (K. N. Katzu Marg) | 0.975 | .............DO..... | 29.03.2018 | 30.06.2018 |  | 15 | 0
186 | Kawal Kunj Soceity to K.N. Katzu Marg (Length 0.265 KM) | 0.265 | .............DO..... | 29.03.2018 | 30.06.2018 |  | 15 | 0
ROHINI SECTOR-14
187 | Fire Station to CRPF School Corner Sec.14 Rohini (Ram Prasad Bismil Marg) | 0.72 | .............DO..... | 29.03.2018 | 30.06.2018 |  | 50 | 0
188 | Babosa Chowk to Tulsi Apartment Sec.14, Rohini. | 0.55 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 15 | 0
189 | PWD Ring Road to Maheswari Apt. Sec.14 toward Sec.13. | 0.845 | .............DO..... | 29.03.2018 | 30.06.2018 |  | 12 | 0
190 | Rukmani Devi Institute to Rohini Court Sec.14 | 0.45 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 15 | 0
191 | Connecting road from ORR to Road No.B-5 passing through CRPF School, Sec.14, Rohini | 0.86 | .............DO..... | 29.03.2018 | 30.06.2018 |  | 15 | 0
ROHINI SECTOR - 15
192 | A-1/1 to G-18/1 (Length 0.600 KM) | 0.6 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 8 | 0
193 | G-17/1 to Western Yamuna Canal | 0.75 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 8 | 0
194 | Western Yamuna Canal to Arya Appartment | 0.59 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 8 | 0
ROHINI SECTOR - 18
195 | Western Yamuna Canal to A-11/87 | 0.3 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 15 | 0
196 | PWD Road (B-7) to Corner of E-II Ashtha Kunj | 0.245 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 20 | 0
197 | Corner of Data Ram Society to CEPT | 0.39 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 10 | 0
198 | Behind Data Ram Society to Corner of Mt. Abu School | 0.39 | .............DO..... | 29.03.2018 | 30.06.2018 |  | 10 | 0
199 | PWD Road (B-7) to CEPT | 0.58 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 10 | 0
200 | H-3/53 to DDA Park | 0.145 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 10 | 0
ROHINI SECTOR - 19
201 | PWD Road to DJB Booster Pump | 0.27 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 15 | 0
202 | PWD Road to Baba wala Park (Corner of Booster Pump) | 0.59 | .............DO..... | 29.03.2018 | 30.06.2018 |  | 15 | 0
203 | Western Yamuna Canal to Badli Chowk | 0.31 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 15 | 0
ROHINI SECTOR-20-21
204 | Road from Pkt-10 to Pkt-D-4, Sec-20,Rohini | 0.505 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 60 | 0
205 | Road from Pkt-14 to Pkt-C-1,Sec-20,Rohini | 1 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 60 | 0
206 | Road from Pkt-8 to Pkt.-9,Sec-21, Rohini | 0.505 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 60 | 0
207 | Road from Pkt-B to Park, Sec-21, Rohini | 0.187 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 60 | 0
208 | Road from Pkt-13 to Pkt-9,Sec-21, Rohini | 0.448 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 60 | 0
209 | Road from Pkt-5 to Pkt-6, Sec-21, Rohini | 0.115 | .............DO.......... | 29.03.2018 | 30.06.2018 |  | 60 | 0
M-3124
210 | Chandra Shekhar Azad Marg (Road No. 42) | 1.23 | Sh. Rajnish Yadav | 19.03.2018 | 30.06.2018 | By Super Sucker | 0 | 0 | Baljit Singh/ 9811621849
211 | Guru Harkishan Marg (road No. 43) | 3.545 | .............DO.......... | 19.03.2018 | 30.06.2018 |  | 5 | 0
212 | Road No.30 | 2 | .............DO.......... | 19.03.2018 | 30.06.2018 |  | 20 | 0
213 | Mahatma Hans Raj Marg | 1.4 | .............DO.......... | 19.03.2018 | 30.06.2018 |  | 0 | 0
214 | Guru Birja Nand Marg (a) | 0.8 | .............DO.......... | 19.03.2018 | 30.06.2018 |  | 30 | 0
215 | (b)... | 0.6 | .............DO.......... | 19.03.2018 | 30.06.2018 |  | 0 | 0
216 | Sant Nagar M2K Road | 0.47 | .............DO.......... | 19.03.2018 | 30.06.2018 |  | 0 | 0
217 | Amar Shaheed Bismil Marg | 0.94 | .............DO.......... | 19.03.2018 | 30.06.2018 |  | 0 | 0
218 | Police Line Road | 0.62 | .............DO.......... | 19.03.2018 | 30.06.2018 |  | 0 | 0
219 | Parwana Road, Saraswati Vihar | 2.8 | .............DO.......... | 19.03.2018 | 30.06.2018 |  | 10 | 0
220 | Major Ashwani Kanva Marg | 1 | .............DO.......... | 19.03.2018 | 30.06.2018 |  | 0 | 0
221 | Balbir Singh Marg | 1.1 | .............DO.......... | 19.03.2018 | 30.06.2018 |  | 0 | 0
222 | Bhao Rao Dev Ras Marg | 1.4 | .............DO.......... | 19.03.2018 | 30.06.2018 |  | 30 | 0
223 | Deen Dayal Upadhayay Marg | 0.6 | .............DO.......... | 19.03.2018 | 30.06.2018 |  | 20 | 0
224 | Road between B-4 & B-5 Block Paschim Vihar | 0.35 | .............DO.......... | 19.03.2018 | 30.06.2018 |  | 0 | 0
M-3125
225 | Road No.3 - Guru Gowalkar Marg | 5.8 | Jitendra Singh | 27.05.2018 | 30.06.2018 |  | 25 | 0
226 | Kanjhawala Link road | 0.4 | Jitendra Singh | 27.05.2018 | 30.06.2018 |  | 90 | 0
227 | Outer Ring Road 26 | 4.52 | Jitender Singh | 27.05.2018 | 30.06.2018 |  | 10 | 0
NORTH CIRCLE
NORTH ROAD DIVISION
1 | Kushal Cinema Road Starting from Raseela Paint Shop to T Point Pryas Road in Jahangirpuri-I, W.No. 16 Civil Line Zone | 1.102 | Anmol Infratech Pvt Ltd | 03-04-18 | 30-06-18 | 5694 | 10% | Full fledged desilting could not be started due to non availability of Dumping ground Permission from MCD which is still awaited | Sh. Vikram Pal 9717916732
2 | Dhobhi Ghat Road Starting from Kushal Cinema Chowk to Shah Alam Bandh Road | 0.45 |  | 03-04-18 | 30-06-18 |  | 2% |  | ..do...
3 | Malik Ram Tandon Marg from Road No. 51 to Shah Alam Bandh Road | 0.89 |  | 03-04-18 | 30-06-18 |  | 9% |  | ..do...
4 | Shah Alam Bandh Road from Burari Road to 80" Road (ROW) at Malik Ram Tondon Road upto Road No. 51 | 1.55 |  | 03-04-18 | 30-06-18 |  | 5% |  | ..do...
5 | Shah Alam Bandh Road from Main G.T. Road to Malik Ram Tandon Marg | 1.4 |  | 03-04-18 | 30-06-18 |  | 0% |  | ..do...
6 | Mangal Bazar Road starting from Kushal Road Green Belt to Shah Alam Bandh Road | 0.4 |  | 03-04-18 | 30-06-18 |  | 2% |  | ..do...
7 | Prayas Road (from Shah Alam Bandh Road to Dhalao, Jahangirpuri) | 0.7 |  | 03-04-18 | 30-06-18 |  | 2% |  | ..do...
8 | Fire Station to Pump House | 0.55 |  | 03-04-18 | 30-06-18 |  | 0% |  | ..do...
9 | Mall Road Extension from Azadpur Flyover to Mukarba Chowk | 3.5 | Anmol Infratech Pvt Ltd | 03-04-18 | 30-06-18 | 3486 | 0% |  | ..do...
10 | Indra Park Road | 0.38 |  | 03-04-18 | 30-06-18 |  | 0% |  | ..do...
11 | Princess Road from Mall road to Road No.51 | 3.1 |  | 03-04-18 | 30-06-18 |  | 5% |  | ..do...
12 | Road No. 51 from Azadpur Flyover to Outer Ring Road | 2.5 |  | 03-04-18 | 30-06-18 |  | 20% |  | ..do...
13 | Model Town-III Road from Mall Road to Arya Samaj Mandir | 0.727 | Anmol Infratech Pvt Ltd | 03-04-18 | 30-06-18 | 3453 | 0% |  | ..do...
14 | Mahatma Gandhi road (Ring Road) from Camp Chowk to Azadpur Flyover | 3.5 |  | 03-04-18 | 30-06-18 |  | 15% |  | ..do...
15 | Lala Auchint Ram Road from Stadium Road to Pambari Road | 0.95 |  | 03-04-18 | 30-06-18 |  | 2% |  | ..do...
16 | Stadium Road from Chattrashal Stadium Mall Road to GT Road | 0.68 |  | 03-04-18 | 30-06-18 |  | 0% |  | ..do...
17 | Brahmkumari Marg from Mall Road to G.T. Road | 0.65 |  | 03-04-18 | 30-06-18 |  | 0% |  | ..do...
18 | Model Town II Road from Mall Road to F-14/56 Model Town | 0.495 |  | 03-04-18 | 30-06-18 |  | 0% |  | ..do...
19 | G.T Road from Gurudwara Nanakpiao to Azadpur Round about | 2 |  | 03-04-18 | 30-06-18 |  | 0% |  | ..do...
20 | Old G.T. Karnal Road | 3 | Sanjay Kaura | 03-05-18 | 30-06-18 | 5454 | 5% |  | ..do...
21 | Narela Alipur Road from Shahpur Grahi to Old GTK Road Alipur | 5.02 |  | 03-05-18 | 30-06-18 |  | 0%
22 | Ramdev Chowk Narela to Kanya Gurukul | 1.9 |  | 03-05-18 | 30-06-18 |  | 0% |  | ..do...
23 | Narela Alipur Road from Narela Y section to Shahpur Garhi | 3.4 |  | 03-05-18 | 30-06-18 |  | 5% |  | ..do...
24 | Narela Safiabad Road from Narela to Safiabad Border | 2.9 |  | 03-05-18 | 30-06-18 |  | 25% |  | ..do...
25 | Narela Lampur Road from Narela to Lampur Border | 3.8 |  | 03-05-18 | 30-06-18 |  | 55% |  | ..do...
26 | Nangli Puna Underpass to Khera Kalan Railway X-ing. | 3 |  | 03-05-18 | 30-06-18 |  | 15% |  | ..do...
27 | Holambi Khurd Crossing to Metro Vihar | 3 |  | 03-05-18 | 30-06-18 |  | 0% |  | Sh. Vikram Pal 9717916732
28 | Bawana Narela Road From CRPF to Singhu Border | 10.4 |  | 03-05-18 | 30-06-18 |  | 15%
29 | New GT Road to Old GT Road (via PHC Alipur) from New GTk Road to Old GTK Road | 0.38 | Sanjay Kaura | 03-05-18 | 30-06-18 | 5046 | 0% |  | ..do...
30 | Holambi Khurd Crossing to Shahpur Garhi turn | 1.9 |  | 03-05-18 | 30-06-18 |  | 0% |  | ..do...
31 | Railway Crossing to Holambi Khurd | 0.7 |  | 03-05-18 | 30-06-18 |  | 45% |  | ..do...
32 | Khera Kalan to Holambi Kalan via Naya bans | 7 |  | 03-05-18 | 30-06-18 |  | 10% |  | ..do...
33 | Subhash Chowk Bhakhtawar Pur to Palla | 3.2 |  | 03-05-18 | 30-06-18 |  | 30% |  | ..do...
34 | Subhash Chowk Bhakhtawar Pur to Hiranki Bandh | 4.2 |  | 03-05-18 | 30-06-18 |  | 15% |  | ..do...
35 | NH-44 to Bakhtawar Pur | 3.5 |  | 03-05-18 | 30-06-18 |  | 5% |  | ..do...
36 | Swaroop Nagar Road | 2 | Anmol Infratech Pvt Ltd | 05-04-18 | 30-06-18 | 9056 | 25% |  | ..do...
37 | Railway Road from NH-44 to Badli Railway Station | 1.25 |  | 05-04-18 | 30-06-18 |  | 0%
38 | ORR Mukarba Chowk Flyover | 6.8 |  | 05-04-18 | 30-06-18 |  | 0% |  | ..do...
39 | Libaspur to Siraspur Road | 1.6 |  | 05-04-18 | 30-06-18 |  | 0% |  | ..do...
40 | G.T. Karnal Road to Libaspur Road | 0.5 |  | 05-04-18 | 30-06-18 |  | 40% |  | ..do...
41 | 66 Ft. Road Libaspur to Gurudwara Road | 1.7 |  | 05-04-18 | 30-06-18 |  | 5% |  | ..do...
42 | G.T. Karnal Road to Siraspur Village | 2 |  | 05-04-18 | 30-06-18 |  | 0% |  | ..do...
43 | Mamchand Dhania Marg | 2.7 |  | 05-04-18 | 30-06-18 |  | 10% |  | ..do...
44 | ITI Road from Main Jahangirpuri Road to Metro App. | 0.324 |  | 05-04-18 | 30-06-18 |  | 20% |  | ..do...
45 | Back side K Block Road from Metro App. to dividing road K Block | 0.17 |  | 05-04-18 | 30-06-18 |  | 0% |  | ..do...
46 | Lucky Park Road from J-51 to J-1951 | 0.5 |  | 05-04-18 | 30-06-18 |  | 0% |  | ..do...
47 | Lucky Park Road to I-2000 (Back Side Road) | 0.35 |  | 05-04-18 | 30-06-18 |  | 0% |  | ..do...
48 | Mangal Bazar Road B Block | 0.55 |  | 05-04-18 | 30-06-18 |  | 0% |  | ..do...
49 | Zonal Park Road C Block | 0.55 |  | 05-04-18 | 30-06-18 |  | 0% |  | ..do...
50 | Jahangirpuri Main Road from G.T. Road Red Light to Fire Station | 1.395 |  | 05-04-18 | 30-06-18 |  | 15% |  | ..do...
51 | Bhalswa Dairy Road from Flood Road to C Block along Bhalswa Lake via Shani Bazar | 1.83 |  | 05-04-18 | 30-06-18 |  | 0% |  | ..do...
52 | G.T Road to Western Yamuna Canal | 2.77 |  | 05-04-18 | 30-06-18 |  | 0% |  | ..do...
53 | From Western Yamuna Canal to Auchandi Border | 18.5 | Raj Associates | 05-06-18 | 30-06-18 | 5070 | 0% |  | ..do...
54 | Auchandi Border to Tatesar Village | 9.3 | Pawan Kumar Gupta | 05-06-18 | 30-06-18 | 4430 | 0% |  | ..do...
55 | Majra Dabbas to Sannoth Mor | 8 |  | 05-06-18 | 30-06-18 |  | 0% |  | ..do...
WEST CIRCLE
WEST ROAD-1
1 | Goswami Tulsi Dass Marg i.e. Road No. 32 | 3.2 | M/s Anmol Infratech Pvt. Ltd | 12.04.2018 | 12.06.2018 | 5737 | 35% | Nil | Er. D.R.Yadav 9971738289
2 | Dr. Kundan Lal Marg | 0.42 |  | 14.04.2018 | 12.06.2018 |  | 5% |  | ..do...
3 | Rajouri Appartment Road | 6 |  | 17.04.2018 | 14.06.2018 |  | 15% |  | ..do...
4 | H.No. 14/35 to 13/101 Subash Nagar (Near Shadley School) | 0.454 |  | 20.04.2018 | 18.06.2018 |  | 0% |  | ..do...
5 | Shanti Devi Marg | 0.75 |  | 22.04.2018 | 18.06.2018 |  | 0% |  | ..do...
6 | Ayodhya Prasad Chopra Marg | 0.9 |  | 24.04.2018 | 19.06.2018 |  | 0% |  | ..do...
7 | Road No. 32 to 17/117 Subash Nagar | 0.7 |  | 26.04.2018 | 20.06.2018 |  | 0% |  | Er. D.R.Yadav 9971738289
8 | H.No. 6/1 to 3/200 Subhash Nagar | 1.36 |  | 28.04.2018 | 20.06.2018 |  | 0% |  | ..do...
9 | Vedic Marg | 2.7 |  | 01.05.2018 | 15.06.2018 |  | 0% |  | ..do...
10 | H.No. 11/76 to 11/85 Subhash Nagar | 0.1 |  | 03.05.2018 | 10.06.2018 |  | 0% |  | ..do...
11 | H.No. 8/1 to 14/149 Subhash Nagar | 0.7 |  | 05.05.2018 | 10.06.2018 |  | 0% |  | ..do...
12 | H.No. 10/1 to 14/97 Subhash Nagar | 0.584 |  | 07.05.2018 | 10.06.2018 |  | 0% |  | ..do...
13 | Sardar Kulwant Singh Sethi Marg | 2.092 |  | 09.05.2018 | 15.06.2018 |  | 20% |  | ..do...
14 | DA-1, Hari Nagar to DB-1 Hari Nagar | 0.846 |  | 13.05.2018 | 15.06.2018 |  | 0% |  | ..do...
15 | Shaheed Bhagat Singh Mrg. (Jail Rd) | 4.56 |  | 15.05.2018 | 15.06.2018 |  | 25% |  | ..do...
16 | Shaheed Bhagat Singh Mrg. (Jail Rd) | 2.8 |  | 15.05.2018 | 15.06.2018 |  | 10% |  | ..do...
17 | B-2/Dharam Marg | 2.76 |  | 02.05.2018 | 08.06.2018 |  | 30% |  | ..do...
18 | Capt. Anuj Nayyar Marg. | 1.34 | M/s Anmol Infratech Pvt. Ltd | 04.05.2018 | 08.06.2018 |  | 25% |  | ..do...
19 | B1- B2 Connecting Road. | 1.18 |  | 06.05.2018 | 10.06.2018 |  | 0% |  | ..do...
20 | Gurudwara Road | 1.26 |  | 08.05.2018 | 10.06.2018 |  | 0% |  | ..do...
21 | BA-BB Block Road | 0.76 |  | 10.05.2018 | 05.06.2018 |  | 0% |  | ..do...
22 | B2 Block Sabzi Mandi Road | 0.8 |  | 11.05.2018 | 10.06.2018 |  | 0% |  | ..do...
23 | Prem Nagar Gurudwara Rd. | 1.04 |  | 11.05.2018 | 10.06.2018 |  | 0% |  | ..do...
24 | Major Rajeev Laul Marg | 1.76 |  | 12.05.2018 | 11.06.2018 |  | 5% |  | ..do...
25 | Shaheed Mangal Pandey Marg | 1.48 |  | 13.04.2018 | 12.06.2018 |  | 0% |  | ..do...
26 | Bhai Kanheya Ji Marg (ITI Road) | 1.34 |  | 21.04.2018 | 20.06.2018 |  | 0% |  | ..do...
27 | Mangal Pandey Marg (Hari Nagar Clock Tower to Maya Puri) | 1.7 |  | 22.04.2018 | 20.06.2018 |  | 0% |  | ..do...
28 | Prof. Joginder Singh Marg (In front of Janakpuri Distt. Centre) | 2.36 | M/s Anmol Infratech Pvt. Ltd | 12.04.2018 | 14.06.2018 | 1950 | 10% | Nil | ..do...
29 | Authority Road (Janak Puri) | 1.3 |  | 15.04.2018 | 16.06.2018 |  | 0% |  | ..do...
30 | Mota Singh Road | 1.96 |  | 17.04.2018 | 19.06.2018 |  | 0% |  | ..do...
31 | Possangi Pur Road | 0.8 |  | 20.04.2018 | 20.06.2018 |  | 0% |  | ..do...
32 | Major Deepak Tyagi Marg | 1.94 |  | 22.04.2018 | 20.06.2018 |  | 0% |  | ..do...
33 | A-1 Block Main Road | 1.24 |  | 25.04.2018 | 18.06.2018 |  | 0% |  | ..do...
34 | Road Opp. A1B Block Janak Puri | 0.56 |  | 27.04.2018 | 18.06.2018 |  | 0% |  | ..do...
35 | Asalatpur Road | 0.32 |  | 28.04.2018 | 19.06.2018 |  | 0% |  | ..do...
36 | Asalatpur Road-II | 1.58 |  | 29.04.2018 | 20.06.2018 |  | 0% |  | ..do...
37 | Najafgarh Road (From Dhauli Pio to Uttam Nagar Red Light) | 2.5 |  | 01.05.2018 | 20.06.2018 |  | 10% |  | ..do...
38 | Pankha Road | 6.5 |  | 04.05.2018 | 20.06.2018 |  | 15% |  | ..do...
39 | Old Pankha Road | 1 |  | 11.05.2018 | 18.06.2018 |  | 0% |  | ..do...
40 | Central School Road | 0.58 |  | 13.05.2018 | 18.06.2018 |  | 0% |  | ..do...
41 | Fire Station Road | 0.8 |  | 14.05.2018 | 15.06.2018 |  | 0% |  | ..do...
42 | Internal Road C-1 To C-1 A Block | 0.6 |  | 16.05.2018 | 16.06.2018 |  | 0% |  | ..do...
43 | Lal Sai Marg to Pankha Road | 1.3 |  | 17.05.2018 | 18.06.2018 |  | 0% |  | ..do...
44 | Lal Sai Marg | 5 | M/s Anmol Infratech Pvt. Ltd | 19.05.2018 | 20.06.2018 |  | 20% |  | ..do...
45 | Mall Road | 1.3 |  | 24.05.2018 | 20.06.2018 |  | 0% |  | ..do...
46 | Ram Mandir Marg | 1.72 |  | 26.05.2018 | 19.06.2018 |  | 0% |  | ..do...
47 | Road C-2/22, C-2/274 Road Janakpuri | 1.52 |  | 27.05.2018 | 15.06.2018 |  | 2% |  | Er. D.R.Yadav 9971738289
48 | Ram Mandir Marg to Mall Road (Connecting Road) | 0.6 |  | 29.05.2018 | 10.06.2018 |  | 0% |  | ..do...
49 | Shani Bazar Road | 1.3 |  | 30.05.2018 | 10.06.2018 |  | 0% |  | ..do...
50 | Road from Shani Bazar to Ram Mandir Marg (Connecting Road) | 0.6 |  | 01.06.2019 | 01.06.2018 |  | 2% |  | ..do...
51 | Vidya Marg | 3.2 |  | 02.06.2018 | 06.06.2018 |  | 15% |  | ..do...
52 | Dabri Road | 1.8 |  | 07.06.2018 | 09.06.2018 |  | 0% |  | ..do...
53 | 60 Futa Road | 0.9 |  | 10.06.2018 | 11.06.2018 |  | 0% |  | ..do...
54 | Lala Ganesh Dass Marg | 0 | Sh. Ramesh Chander | 03.05.2018 | 06.06.2018 | 4092 | 2% | Nil | ..do...
55 | Keshopur Sabzi Mandi Red Light (Outer Ring Road) to Subhash Nagar Drain | 0 |  | 09.04.2018 | 15.06.2018 |  | 0% |  | ..do...
56 | Road No. 235 extension |  |  | No Drain |  |  | 0% |  | ..do...
57 | Chowkhandi Road | 0 |  | 09.04.2018 | 15.06.2018 |  | 0% |  | ..do...
58 | Najafgarh road from Subhash Nagar Crossing to Dhauli Piao | 0 |  | 01.05.2018 | 15.06.2018 |  | 0% |  | ..do...
59 | Tilak Nagar To 20 Block Tilak Vihar | 0 |  | 18.04.2018 | 03.06.2018 |  | 0% |  | ..do...
60 | Road from Guruvirjanand Marg to Distt. Park,Vikas Puri | 0 |  | 16.04.2018 | 15.06.2018 |  | 0% |  | ..do...
61 | Tilak Vihar Main Road | 0 |  | 28.04.2018 | 17.06.2018 |  | 4% |  | ..do...
62 | Pelicon Road from Guru Virzanand Marg to Road No. 235 Extension | 0 |  | 24.04.2018 | 15.06.2018 |  | 4% |  | ..do...
63 | Tilak Nagar Main Market Road | 0 |  | 09.04.2018 | 16.06.2018 |  | 6% |  | ..do...
64 | Brain Public School Road | 0 |  | 12.04.2018 | 16.06.2018 |  | 0% |  | ..do...
65 | K. R. Manglam | 0 |  | 06.04.2018 | 17.06.2018 |  | 0% |  | ..do...
66 | H- Block to Vikas Puri | 0 |  | 08.05.2018 | 16.06.2018 |  | 0% |  | ..do...
67 | 70 Block Park Ashok Nagar to Tihar No. 2 School | 0 | Sh. Ramesh Chander | 14.05.2018 | 15.06.2018 |  | 0% |  | ..do...
68 | 2/1 to 2/10 Ashok Nagar | 0 |  | 26.05.2018 | 09.06.2018 |  | 0% |  | ..do...
69 | Ashok Nagar Road | 0 |  | 23.05.2018 | 04.06.2018 |  | 0% |  | ..do...
70 | Road between Two Blocks of G- Block Vikas Puri | 0 |  | 23.05.2018 | 07.06.2018 |  | 0% |  | ..do...
71 | Shaheed Raj Guru Marg Vikas Puri | 0 |  | 01.06.2018 | 11.06.2018 |  | 2% |  | ..do...
72 | Road Adjcent to PVR Complex Vikas Puri | 0 |  | 06.06.2018 | 12.06.2018 |  | 0% |  | ..do...
73 | Road No. 236 | 3.6 | M/s Anmol Infratech Pvt. Ltd | 12.04.2018 | 18.06.2018 | 2446 | 0% | NIL | ..do...
74 | Road No. 237 | 0.9 |  | 17.04.2018 | 18.06.2018 |  | 0% |  | ..do...
75 | Road between Krishi Appt. to DAV school (PWD Road) | 0.59 |  | 19.04.2018 | 19.06.2018 |  | 4% |  | ..do...
76 | Road between Devdoot Appt. to Parmarth Appt. PWD Road Vikas Puri | 0.56 |  | 21.04.2018 | 19.06.2018 |  | 0% |  | ..do...
77 | Road between Jupiter Appt. to Priya Appt. PWD Road Vikas Puri | 0.78 |  | 24.04.2018 | 20.06.2018 |  | 0% |  | ..do...
78 | Road Between Nalanda Appt. To Nightingale Appt. Vikas Puri | 1.08 |  | 27.04.2018 | 20.06.2018 |  | 0% |  | ..do...
79 | Road Sunrise Appt. to DAV School (PWD Road) Vikas Puri | 0.87 |  | 01.05.2018 | 20.06.2018 |  | 0% |  | ..do...
80 | Road from F-234 to IFC drain (Over head tank) Vikas Puri | 0.5 |  | 04.05.2018 | 19.06.2018 |  | 0% |  | ..do...
81 | Road from ITI Corner (Flat No. 58) to Central School Corner (Flat No. 391) LIG Flat Hastsal | 0.48 |  | 07.05.2018 | 19.06.2018 |  | 0% |  | ..do...
82 | Road from Navyug Appt. to IFC drain (Brotherhood Appt.) Vikas Puri | 0.76 |  | 10.05.2018 | 19.06.2018 |  | 0% |  | ..do...
83 | Guruvirja Nanad Marg | 4 |  | 13.05.2018 | 18.06.2018 |  | 0% |  | Er. D.R.Yadav 9971738289
84 | Road starting from Oxford School to Airport Appt. (PWD Road) Vikas Puri | 1.76 |  | 17.05.2018 | 20.06.2018 |  | 0% |  | ..do...
85 | Road between Lok Vihar Appt. (PWD Road) to Fblock Market Vikas Puri | 1.35 |  | 21.05.2018 | 20.06.2018 |  | 0% |  | ..do...
86 | Najafgarh Road (Uttam Nagar Red Light to Kakrolla Drain) | 6 |  | 24.05.2018 | 20.06.2018 |  | 3% |  | ..do...
87 | Nangloi - Najafgarh Road | 11 |  | 01.06.2018 | 09.06.2018 |  | 2% |  | ..do...
88 | Road No. 235 | 0.7 |  | 10.06.2018 | 15.06.2018 |  | 0% |  | ..do...
89 | Keshav Marg | 1.2 | Sh. Ramesh Chander | 09.04.2018 | 15.06.2018 | 2857 | 0% | NIL | ..do...
90 | Ring road to A-31 Rajouri garden | Nil |  | No Drain |  |  | 0% |  | ..do...
91 | Najafgarh Road to A-71 Rajouri Garden | Nil |  | No Drain |  |  | 0% |  | ..do...
92 | Sakti Mandir Marg | 0.4 |  | 09.04.2018 | 17.06.2018 |  | 0% |  | ..do...
93 | Najafgarh Road | 3.9 |  | 16.05.2018 | 15.06.2018 |  | 2% |  | ..do...
94 | Major Sudesh Gadok Marg (J 12/1 to NG Road) | 1.2 |  | 09.04.2018 | 17.06.2018 |  | 0% |  | ..do...
95 | Major Sudesh Marg (NG Road to Ring Road) | 4 |  | 09.04.2018 | 15.06.2018 |  | 0% |  | ..do...
96 | 100' Road (Patel Chowk to Subhash Nagar Drain) | 1.6 |  | 25.04.2018 | 15.06.2018 |  | 1% |  | ..do...
97 | 100' Road New Khayala Road | 1.4 |  | 25.04.2018 | 10.06.2018 |  | 0% |  | ..do...
98 | 80' Road Chowkhandi Road | 2 |  | 25.04.2018 | 10.06.2018 |  | 0% |  | ..do...
99 | Arya Samaj Marg | 0.24 |  | 16.05.2018 | 17.06.2018 |  | 0% |  | ..do...
100 | J.Krishnatrey Marg | 0.22 |  | 16.05.2018 | 17.06.2018 |  | 0% |  | ..do...
101 | AD-1 to BF- 31 (Tagore Garden) | 1.2 |  | 16.05.2018 | 16.06.2018 |  | 0% |  | ..do...
102 | DE-131 to Community Hall | 0.44 |  | 16.05.2018 | 16.06.2018 |  | 0% |  | ..do...
103 | Devki Nandan Marg | 1.56 |  | 16.05.2018 | 16.06.2018 |  | 0% |  | ..do...
104 | Tanki Wala Marg | 0.4 |  | 31.05.2018 | 15.06.2018 |  | 0% |  | ..do...
105 | Sant Berwa Marg with Titar Pur drain | 1.2 |  | 31.05.2018 | 15.06.2018 |  | 2% |  | ..do...
106 | Road No. 28 | 1 |  | 31.05.2018 | 15.06.2018 |  | 0% |  | ..do...
WEST ROAD-2 DIVISION
1 | Najafgarh Road from Zakhira Round about to Moti Nagar | 2.24 | Sh. Rajnish Yadav | 10.04.2018 | 28.09.2018 | 2900 | 40% | 0 | Sh. Manish Kaushik 9650167297
2 | Najafgarh Road from Moti Nagar to Raja Garden | 2.2 |  |  |  |  | 20% |  | ..do...
3 | Shivdass Puri Marg from Ring Road to Rama Road | 2 |  |  |  |  | 0% |  | ..do...
4 | Hemvati Nandan Bahnguma Marg | 0.8 |  |  |  |  | 40% |  | ..do...
5 | Road from Milan Cinema to H. No. 19/289 | 0.42 |  |  |  |  | 25% |  | ..do...
6 | Road from House No. H-1 to I-47 near Milan Cinema Karmapura | 0.4 |  |  |  |  | 10% |  | ..do...
7 | Road from HIL to Bus Terminal of 234, Karampura | 0.412 |  |  |  |  | 0% |  | ..do...
8 | Punjab Garden Road | 0.21 |  |  |  |  | 0% |  | ..do...
9 | Smt. Ginni Devi Road | 0.75 |  |  |  |  | 0% |  | ..do...
10 | Bhagwan Dass Marg (K.C. Garg Marg) | 0.3 |  |  |  |  | 0% |  | ..do...
11 | Ring Road fron Punjabi Bagh Chowk to Mayapuri Chowk | 4.81 |  |  |  |  | 75% |  | ..do...
12 | Rohtak Road from Zakhira to Punjabi Bagh | 2.1 |  |  |  |  | 0% |  | ..do...
13 | Road from Road No. 36 (Sat Guru Ram Singh Marg (Maya Puri Chowk to SD Public School) | 2 |  |  |  |  | 50% |  | Sh. Manish Kaushik 9650167297
14 | Rama Road (Satguru Ram Singh Marg) from SD Public School to Patel Road | 1.2 |  |  |  |  | 50% |  | ..do...
15 | Rama Road (Satguru Ram Singh Marg) from Patel Road to Zakhira round about | 1.695 |  |  |  |  | 50% |  | ..do...
16 | Road from Bus Route B-14 Tagore Market to G-82 Kirti Nagar | 0.91 |  |  |  |  | 25% |  | ..do...
17 | Major Rajive Bhasin Marg D/Story | 0.78 |  |  |  |  | 0% |  | ..do...
18 | Pankaj Batra Marg | 0.77 |  |  |  |  | 0% |  | ..do...
19 | Lai Sai Mandir Marg D/Story | 0.325 |  |  |  |  | 0% |  | ..do...
20 | 80' wide Road MS Garden Road | 2.49 |  |  |  |  | 0% |  | ..do...
21 | Patel Road frpm PUSA/Siddhartha Hotel Round about to Shadipur Flyover | 2.93 |  |  |  |  | 0% |  | ..do...
22 | Zakhira Flyover | 1.6 |  |  |  |  | 0% |  | ..do...
23 | Vishwakarma Marg | 1 |  |  |  |  | 60% |  | ..do...
24 | T-Sohan Lal Marg | 0.9 |  |  |  |  | 0% |  | ..do...
25 | G.L. Sikka Marg | 0.8 |  |  |  |  | 0% |  | ..do...
26 | Link Road No. 1 | 0.23 |  |  |  |  | 0% |  | ..do...
27 | Link Road No. 2 | 0.18 |  |  |  |  | 0% |  | ..do...
28 | Suman Lata Badola Marg | 0.243 |  |  |  |  | 0% |  | ..do...
29 | Madhav Setu Marg | 0.605 |  |  |  |  | 0% |  | ..do...
30 | Rohtak Road NH-10 from Pillar No. 410 to Tikri Border (Both side Mundka Area) | 9.57 | Sh. Ramesh Chander | 10.04.2018 | 28.09.2018 | 1200 | 30% | 0 | ..do...
31 | Hiran Kudna Road from Rohtak Road (NH-10) to Nirwall more | 3.95 |  |  |  |  | 40% |  | ..do...
32 | Road from Ghevra More to Chand Pur More from Ghevra More to Chand Pur More | 7.9 | Sh. Laxman | 10.04.2018 | 28.09.2018 | 2800 | 35% | 0 | ..do...
33 | Guru Golwalkar Marg (Road No. 3) from Jain Nagar to Tatesar | 9.8 |  |  |  |  | 25% |  | ..do...
34 | Najafgarh- Nangloi Road from Nangloi Chowk to Rishal Garden | 3.75 | Sh. Ramesh Chander | 10.04.2018 | 26.09.2018 | 3400 | 60% | 0 | ..do...
35 | NH-10 (Delhi Rohtak Road) from Peeragarhi Chowk to Nangloi Metro Pillar No. 410 | 3.627 |  |  |  |  | 50% |  | ..do...
36 | Road from Outer Ring Road Meera Bagh to GH-8 Fire station Paschim Vihar | 1.251 |  |  |  |  | 40% |  | ..do...
37 | Road from GH-6 Chowk to GH-5 and 7 Paschim Vihar | 0.292 |  |  |  |  | 30% |  | ..do...
38 | Road from Garg Plaza to L.I.C. Colony Paschim Vihar | 1.322 |  |  |  |  | 30% |  | ..do...
39 | Road from Sai Baba Mandir GH-12 to GH-8 Fire station Paschim Vihar | 0.963 |  |  |  |  | 40% |  | ..do...
40 | Road from Outer Ring Road Bhera Enclave to Sai Baba Mandir Paschim Vihar | 1.251 |  |  |  |  | 30% |  | ..do...
41 | Road from GH-13 to Sayed Nangloi Village Chowk Paschim Vihar | 0.902 |  |  |  |  | 30% |  | ..do...
42 | Road from Sant Mar'ks School to DDA Mkt. GH-5&7 Paschim Vihar | 0.435 |  |  |  |  | 50% |  | ..do...
43 | Laxmi Narain Marg (N.S. Road) | 0.7 |  |  |  |  | 30% |  | ..do...
44 | Ch. Prem Sukh Road | 1.292 |  |  |  |  | 30% |  | ..do...
45 | 60' road in Jawala Puri | 1.15 |  |  |  |  | 20% |  | Sh. Manish Kaushik 9650167297
46 | Road from Capital Plaza Market to Jhaj Aptt. Mianwali Nagar | 0.35 |  |  |  |  | 20% |  | ..do...
47 | Road from Vindhachal Aptt. To Viral Co. Op. Society Mianwali Nagar | 0.35 |  |  |  |  | 20% |  | ..do...
48 | Road from Rblock jwalapuri to Sai mandir Guru Harkishan Nagar | 0.36 |  |  |  |  | 20% |  | ..do...
49 | Road from Durbal Nath Vatica to NH-10 | 0.6 |  |  |  |  | 0% |  | ..do...
50 | Outer Ring Road No. 26 from Mangol Puri Railway crossing to Najafgarh drain | 2.04 |  |  |  |  | 35% |  | ..do...
51 | Road from 48 NWA Ch. Balbir Singh Marg to Road No. 32 (road no.33) | 0.39 | Sh. Ramesh Chander | 10.04.2018 | 26.09.2018 | 1800 | 5% | 0 | ..do...
52 | Vashisth Kumar Gulla Marg | 1.39 |  |  |  |  | 5% |  | ..do...
53 | N.A. Road | 1 |  |  |  |  | 5% |  | ..do...
54 | Ch. Balbir Singh Marg (Club Road) | 1.41 |  |  |  |  | 5% |  | ..do...
55 | Road from Sant Bairwa Marg to Road No. 28 (Holichild school) | 0.39 |  |  |  |  | 5% |  | ..do...
56 | Road from R-17 to D-335 Raghubir Nagar | 0.192 |  |  |  |  | 5% |  | ..do...
57 | Road from C-1 to C-494 Raghubir Nagar | 0.188 |  |  |  |  | 5% |  | ..do...
58 | Road from Road no. 29 to R Block "T" Hart | 1.18 |  |  |  |  | 5% |  | ..do...
59 | Road from front of Ambedkar Market from Shop No. 1 to 130, Raghubir Nagar | 0.305 |  |  |  |  | 5% |  | ..do...
60 | Road from Park to B-8, Vishal Enclave | 0.1 |  |  |  |  | 5% |  | ..do...
61 | Road from Najafgarh Road to Flat No. 13, Four Storey Qtrs. Tagore Garden Extension | 0.19 |  |  |  |  | 5% |  | ..do...
62 | Road from A-23 Vishal Enclave (NG Road) to B-33 Vishal Enclave (PWD Road No. 28) (Vishal Cinema Road) | 0.7 |  |  |  |  | 5% |  | ..do...
63 | Road from Flat No. 157 Four Story to Vishal Road (opp. Police Station Rajouri Garden) | 0.47 |  |  |  |  | 5% |  | ..do...
64 | Road from Bhagat Singh Colony (opp. Plot No. 66 Shivaji Enclave) to FA-33 Shivaji Enclave (On PWD Road No. 28) | 0.6 |  |  |  |  | 5% |  | ..do...
65 | Shri Krishan Gyan Mandir Marg | 0.66 |  |  |  |  | 5% |  | ..do...
66 | Road from Shivaji College (PWD Road No. 28) to Bhagat Singh Colony | 0.71 |  |  |  |  | 5% |  | ..do...
67 | NH-10 (Delhi Rohtak Road) from Punjabi Bagh underpass to Peeragarhi Chowk | 4.5 |  |  |  |  | 30% |  | ..do...
68 | Road from Paschim Puri Chowk to New Slum Qtrs. | 0.45 |  |  |  |  | 70% |  | ..do...
69 | Road from Shiv Mndir Road (Rohtak Road) to shiv Mandir Madipur Village | 0.7 |  |  |  |  | 35% |  | ..do...
70 | Road from Madipur Main Road from Rohtak Road to Paschim Puri Chowk | 0.7 |  |  |  |  | 25% |  | ..do...
71 | Maharishi Road from B-1 to C-17 | 0.475 |  |  |  |  | 5% |  | ..do...
72 | Road from Road No. 32 to Hans Raj Model School to Road No. 33 | 1.51 |  |  |  |  | 5% |  | ..do...
73 | Road from H.No. A-250 to Shiv Mandir Road in C-103 Punjabi Bagh | 0.48 |  |  |  |  | 35% |  | ..do...
74 | Road No. 4 from H. No. 11 and North West Avenue Road to 23/4 in Punjabi Bagh Extn. | 0.15 |  |  |  |  | 5% |  | ..do...
75 | Road No. 28 | 1.93 |  |  |  |  | 25% |  | ..do...
76 | Road No. 29 | 2.8 |  |  |  |  | 20% |  | Sh. Manish Kaushik 9650167297
77 | Road from Road No. 41 from H.No. 1 to 81 in West Punjabi Bagh | 1.715 |  |  |  |  | 25% |  | ..do...
78 | Major Sunil Bakshi Marg Road from H-1 Bali Nagar (NG Road) to ESI Hospital (Ring Road) | 0.52 |  |  |  |  | 45% |  | ..do...
79 | Road from Najafgarh Road to WZ-494, Basai Darapur (Sheo Nath Tyagi Marg) | 0.675 |  |  |  |  | 40% |  | ..do...