## Sheet1
PWD Desilting Report (Preparedness for Monsoon)
DESILTING REPORT UNDER PWD MAINTENANCE SOUTH ZONE UPTO 08.06.2018
As on 08.06.2018
Sl. No. | Name of Road / Drain | Length of Road (Km) | Contractor | Date of Start of De-Siliting | Date of completion | % Drain cleaned (Lengthwise) | Estimate Qty. of silt (cum) | Qty. of silt lifted and disposed off (cum) | EE in charge / Mobile No. | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
1)-South-West Circle
South West Road-1 Division
1 | B.J. Marg | 1.3 | M/s Shatrughna Construction Co M/s WORKCEE |  | 30.06.18 | 20% |  |  | Er. S.K. Sinha / 9958469778 | Work is progress.
2 | Rao Tula Ram Marg (RTR Marg) | 1.7 |  |  | 30.06.18 | 80%
3 | Zonal road No. 2 (Baba Balak Nath Marg) | 1.1 |  |  | 30.06.18
4 | Zonal Road No. 6 (Hare Krishna Mehto Marg) | 0.7 |  |  | 30.06.18 | 40%
5 | Ullan Buttor Marg | 0.7 |  |  | 30.06.18
6 | Outer Ring Road | 4.8 |  |  | 30.06.18 | 50%
7 | Babu Genu Marg, R.K.Puram | 0.6 |  |  | 30.06.18
8 | Nelson Mandela Marg | 4.04 |  |  | 30.06.18 | 75%
9 | Baba Gang Nath marg | 1.17 |  |  | 30.06.18 | 80%
10 | Major Som nath marg | 1.6 |  |  | 30.06.18 | 40%
11 | Africa Avenue (Road No.9) | 2.2 | M/s WORKCEE & M/s Samridhi Construction | 26.03.18 | Work in Progress | 75%
12 | Kafi Azami Marg | 0.9 |  |  | 30.06.18 | 67%
13 | Church Road, R.K.Puram | 0.85 |  |  | 30.06.18
14 | Vivekanand Marg | 1.1 |  | 25.04.2018 | Work in Progress | 18%
15 | Venketeshwar Marg | 1.1 |  |  | 30.06.18 | 50%
16 | Ring Road | 5 |  | 20.04.2018 | 30.06.18 | 40%
17 | Kama Koti Marg | 1.75 |  |  | 30.06.18
18 | Prem nath Dogra marg, R.K.Puram | 0.85 |  |  | 30.06.18
19 | Tamil Sangam Marg | 1.1 |  |  | 30.06.18 | 15%
20 | A-9 Street Road | 0.65 |  |  | 30.06.18
21 | Basant Marg-II | 0.5 |  |  | 30.06.18
22 | Paschimi Marg | 1.25 |  |  | 30.06.18
23 | Poorvi Marg | 1.65 |  |  | 30.06.18 | 32%
24 | Ganga Ram Hospital Road | 1.08 | M/S Sai Tube Well Shri Rajpal Sehgal | 25.03.18 | 30.06.18 | 32% | 295 |  | Er. S.K. Sinha / 9958469778 | Work is in Progress.
25 | PUSA Road | 2 |  | 25.03.18 | 30.06.18 | 32% | 540
26 | Shankar Road | 1.64 |  | 25.03.18 | 30.06.18 | 67% | 250
27 | Dr. K.S. Krishanan Marg | 0.915 |  | 25.03.18 | 30.06.18 | 37% | 250
28 | PUSA Institute (IARI) Internal Road | 0.7 |  |  | 30.06.18 | 37% | 200
29 | Dev Prakash Shastri marg (Road No. 25) | 4.45 |  |  | 30.06.18 | 38% | 1200
30 | Girdhari Lal Goswami Marg (Road No. 89) | 3.65 |  |  | 30.06.18 | 47% | 1100
31 | Ram Nath Vij Marg | 1.19 |  |  | 30.06.18 | -
32 | O.P. Bharti Marg 1 | 0.535 |  |  | 30.06.18 | 78% | 150
33 | O.P. Bharti Marg 2 | 0.762 |  |  | 30.06.18 | 78% | 205
34 | O.P. Bharti Marg 3 | 0.181 |  |  | 30.06.18 | 75% | 50
35 | O.P. Bharti Marg 4 | 0.42 |  |  | 30.06.18 | 78% | 120
36 | Guru Ravi Dass Marg | 0.8 |  | 25.03.18 | 30.06.18 | 37% | 215
37 | Ganga Mandir Marg | 0.75 |  |  | 30.06.18 | 32% | 210
38 | Vishnu Mandir Marg | 0.6 |  | 25.03.18 | 30.06.18 | 32% | 160
39 | Saraswati Marg | 0.5 |  | 25.03.18 | 30.06.18 | 33% | 150
40 | Ajmal Khan Road | 0.6 |  | 25.03.18 | 30.06.18 | 32% | 165
41 | Gurudwara Road | 0.5 |  | 25.03.18 | 30.06.18 | 66% | 135
42 | Abdul Aziz Road | 0.4 |  |  | 30.06.18 | 22% | 110
43 | S.K. Dass Road | 0.3 |  | 25.03.18 | 30.06.18 | - | 80
44 | Abdul Rehman | 0.2 |  | 25.03.18 | 30.06.18 | 46% | 55
45 | Padam Singh Road | 0.75 |  | 25.03.18 | 30.06.18 | 53% | 210
46 | Arya Samaj Road | 1 |  | 25.03.18 | 30.06.18 | 52% | 270
47 | Mahatma gandhi Marg (Ring Road) | 7.1 | M/s Shatrughna Construction Co & Shri Rajnish Yadav | 25.03.18 | 30.06.18 | 60% | nil | -
48 | Road No. 36(Sat Guru Ram Singh Marg) | 3.4 |  | 25.03.18 | 30.06.18 | 60% | nil | -
49 | Upper Ridge Road (Vande Martram Marg) | 7 |  |  | 30.06.18 | Nil | nil | Nil
51 | MM Road | 6.8 | M/s RichCon Engineering Company | 25.03.18 | 30.06.18 | 45% | 250 Cum | - | Er. S.K. Sinha / 9958469778 | Work is in progress.
52 | Vatika Road (DPS Vasant Kunj to MM road) | 0.7 |  | Not started yet | 30.06.18 | 45% | 300 Cum
53 | Munirka marg | 0.9 |  | Not started yet | 30.06.18 | nil
54 | Basant marg-I | 0.9 |  | 25.03.18 | 30.06.18 | nil
54 | Baba Gang Nath marg | 1.17 |  | 25.03.18 | 30.06.18 | nil
South West Road-2 Division
1 | A Block Road | 0.2 | ANMOL INFRATECH PRIVATE LIMITED | 2018-03-21 | 15.06.18 | 100% | Work executed by super sucker machine | The drain is being cleaned by super sucker machines hence quanitity cannot be ascertained. | Er. J. P. Vashist M- 9971396164
2 | Pankha Road | 1 |  | 2018-03-21 | 15.06.18 | 25%
3 | Nasir Pur Road | 2.3 |  | 2018-03-21 | 15.06.18 | 50%
4 | Palam Dabri Road | 2.5 |  | 2018-03-21 | 15.06.18 | 75%
5 | Paras Public schol to L-103 Pocket-4 Chankya Puri Binda Pur | 0.24 |  | 2018-03-21 | 15.06.18 | 50%
6 | Peer Baba Road | 0.6 |  | 2018-03-21 | 15.06.18 | 100%
7 | Police Station Road | 0.37 |  | 2018-03-21 | 15.06.18 | 100%
8 | Pt. Vishnu Dutt Marg | 0.75 |  | 2018-03-21 | 15.06.18 | 50%
9 | Sagar Pur Road | 3 |  | 2018-03-21 | 15.06.18 | 50%
10 | Satguru Ram Singh Marg | 0.9 |  | 2018-03-21 | 15.06.18 | 50%
11 | Link Road (Pt. Vishnu Dutt Marg to Satguru Ram Singh Marg) | 0.3 |  | 2018-03-21 | 15.06.18 | 50%
12 | Najafgarh Nagloi Road | 2.6 | Surender Singh | 2018-02-23 | 15.06.18 | 25%
13 | Najafgarh Phirni | 2.2 |  | 2018-02-23 | 15.06.18 | 100%
14 | Najafgarh Dhansa Road | 16.25 |  | 2018-03-07 | 15.06.18 | 75%
15 | Najafgarh Dechaun Road | 4.55 | Ram Charan Bansal | 2018-02-23 | 15.06.18 | 75%
16 | Najafgarh Jaroda Road | 7.2 |  | 2018-02-23 | 15.06.18 | 25%
17 | Najafgarh Kakrola Road | 4 | Surender Singh | 2018-03-07 | 15.06.18 | 25%
18 | Laxmi Chand Marg | 11.3 | Surender Singh | 2018-03-07 | 15.06.18 | 25%
19 | Prithvi Singh Dagar Marg | 11.2 |  | 2018-03-07 | 15.06.18 | 50%
20 | Jhatikara Morh to Jhatikara | 8.55 | Ram Charan Bansal | 2018-02-23 | 15.06.18 | 25%
21 | Najafgarh Bijwasan Road | 11.25 |  | 2018-02-23 | 15.06.18 | 25%
22 | Bhartal Road | 3.48 | Surender Singh | 2018-03-01 | 15.06.18 | 100% | -do- | -do- | Er. J. P. Vashist M- 9971396164
23 | Goyla Deenpur Road | 4.2 |  | 2018-03-01 | 15.06.18 | 100%
24 | Kapashera Bijwasan Road | 3.8 | ANMOL INFRATECH PRIVATE LIMITED | 2018-03-21 | 15.06.18 | 35%
25 | Link Road | 1.7 |  | 2018-03-21 | 15.06.18 | 50%
26 | Old DG Road | 2.5 |  | 2018-03-21 | 15.06.18 | 75%
2)-South Circle
South Road-1 Division
1 | M.B. Road | 5.25 | M/s Maan Builders | 09.04.2018 | 30.06.2018 | 40% | 4682 | 1640 | Er. Narender Mahajan/ 9643870385
|  |  | M/s Buland constructions | 15.04.2018 | 30.06.2018 | 40% | 3019 | 1510
2 | IGNOU Road | 1.9 | M/s Buland constructions | 15.04.2018 |  | 51% | 2725 | 1365
3 | Westend Marg | 0.6 | M/s Buland constructions | 09.04.2018 | 30.06.2018 | 26%
4 | Devli Road | 1.05 | M/s Maan Builders | 09.04.2018 | 30.062 | 90%
5 | H Block, Dakshinpuri | 0.9 |  |  |  | 95%
6 | Raja Ram Marg | 0.89 |  |  |  | 40%
7 | Durbal Nath Marg | 1.09 |  |  |  | 90%
8 | Maharishi Balmiki Marg | 1.8 |  |  |  | 26%
9 | Phirni Road | 1 |  |  |  | 26%
10 | Old MB Road | 0.6 | M/s Kleenwel Enviro Engg. Services | 09.04.2018 | 30.06.2018 | 100%
11 | 100 Foota Road | 1.4 |  | 09.04.2018 | 30.06.2018 | 26%
12 | 60 Foota Road | 0.9 |  | 09.04.2018 | 30.06.2018 | 26%
13 | SSN Marg | 10.5 | M/s Buland Constructions | 09.04.2018 | 30.06.2018 | 35% | 2162
14 | Mandi Road | 8 | M/s Buland Constructions | 09.04.2018` | 30.06.2018 | 51% | 1144 cum | 300
15 | Gadaipur Bundh Road | 3 |  | 09.04.2018 | 30.06.2018 | 51%
16 | Mandi Road | 8 | Sh. Ravi Tanwar | 28.04.2018 | 30.06.2018 | 95% | 2340 cum | 1900 Cum
17 | Gadaipur Bundh Road | 3 |  |  |  | 100%
18 | Dera Bhatti Road | 5.76 |  |  |  | 95%
19 | Pankaj Juyal Marg | 1.1 | M/s Buland Constructions | 2018-03-31 | 30.06.2018 | 80% | 6150 | 3125 | Er. Narender Mahajan / 9933331859
20 | Family Court road | 0.55 |  |  |  | 100%
21 | J-Block Road | 1.2 |  |  |  | 26%
22 | Asian Market Road | 0.45 |  |  |  | 15%
23 | Mandir marg | 1.2 |  |  |  | 26%
24 | NBCC Plaza Road | 1.1 |  |  |  | 100%
25 | Birla Vidya Niketan Marg | 0.95 |  |  |  | 100%
26 | Pramod Mahajan Marg | 0.89 |  |  |  | 76%
27 | Main Road Pushp Vihar Sector-1 | 0.75 |  |  |  | 100%
28 | Metro Enclave Road | 0.45 |  |  |  | 100%
29 | Press Enclave Road | 3.78 | M/s Buland Constructions | 2018-04-06 | 30.06.2018 | 51% | 3135 | 780
30 | Khirki Road | 0.85 |  |  |  | 51%
31 | Apeejay School Road | 1.3 |  |  |  | 30%
32 | Sheikh Sarai Phase-1 Road-1 | 0.6 |  |  |  | 15%
33 | Sheikh Sarai Phase-1 Road-2 | 0.3 |  |  |  | 20%
34 | Road in front of Mother International School | 0.54 |  |  |  | 51%
35 | Road from H.No. C-11 to C-20 Malviya Nagar | 0.11 |  |  |  | 90%
36 | Gurudwara Road Saket | 0.55 | Sh. Babu lal Gupta | 2018-04-06 | 30.06.2018 | 76% | 684 | 270
37 | Pramod Mahajan Marg | 0.89 |  |  |  | 100%
38 | M.G. Road | 7.5 | M/s Buland Constructions | 09.04.2018 | 30.06.2018 | 10% | 5265 | ---
39 | Aya Nagar | 0.6 |  |  |  | 76% |  | 240 Cum
40 | Ghitorni Road to CPWD Land | 0.54 |  |  |  | 80% |  | 260 Cum
41 | Ghitorni Village Road | 1.04 |  |  |  | 30% |  | 50 Cum
42 | MG Road to Ghitorni Village | 0.3 |  |  |  | 51% |  | ---
South Road-2 Division
43 | August Kranti Marg. | 3.24 | Sh. Yogesh Arora | 22.02.2018 | 30.06.18 | 76% | 618.75 | 470 | Sh. Jagdish Prasad 9560207879
44 | Balbir Saxena Marg | 0.8 |  |  |  | 90% | 192 | 173
45 | Ch. Dilip Singh Marg, P.S. Hauz Khas | 0.6 |  |  |  | 80% | 360 | 288
46 | Mahinder Singh Jain Marg Road / Gautam Nagar Road | 1.2 |  |  |  | 90% | 480 | 432
47 | P-Block Road from August Kranti Marg via jain Mandir & Dustbin to August Kranti Marg. | 0.34 | Sh. Yogesh Arora | 22.02.2018 | 30.06.18 | 85% | 120 | 102 | Sh. Jagdish Prasad 9560207879
48 | Sudarshan Cinema Road. | 0.72 |  |  |  | 90% | 75 | 68
49 | Gautam Nagar Road | 0.5 |  |  |  | 40% | 225 | 30
50 | Road form Balbir Sxsena Marg to Ch. Dalip SinghMarg (NIFT Road), Hauz Khas | 0.6 |  |  |  | 90% | 135 | 122
51 | Road form August Kranti marg to Aurobindo Marg (Subash Chopra Road), Hauz Khas | 0.79 |  |  |  | 85% | 99 | 84
52 | Asiad Village peripheral road | 3 |  |  |  | 90% | 375 | 338
53 | Siri Fort Road | 1.2 |  |  |  | 90% | 288 | 265
54 | Sri Krishna Chaitnya Maha Prabhu Marg | 0.7 |  |  |  | 80% | 80 | 64
55 | Sri Aurobindo Marg | 4.3 | M/s Amit Enterprises | 16.02.2018 | 30.06.18 | 95% | 2874 | 2730
56 | Ring Road | 2 |  |  |  | 92% | 2998 | 1441
57 | Outer Ring Road | 1.5 |  |  |  | 85% |  | 324
58 | Ch. Harsukh Marg | 2 |  |  |  | 85% |  | 335
59 | Ch Jhandu Singh Marg | 1.53 |  |  |  | 85% |  | 175
60 | Ch Hukum Chand Marg | 0.6 |  |  |  | 76% |  | 123
61 | Green Park Market Road | 0.8 |  |  |  | 90% |  | 153
62 | Hauz Khas Village Road | 0.9 |  |  |  | 92% |  | 67
63 | N. K. Pandey Marg | 1.17 |  |  |  | 85% |  | 74
64 | Road from B15/7 to BSES (B&C Block Qutub Inst. Area) (Both Sides) | 0.3 | M/s Nagendra & Company, | 14.02.2018 | 30.06.18 | 80% | 6060 | 100
65 | Road from B12 to IIM (B&C Block Qutub Inst. Area) (Both Sides) | 0.1 |  |  |  | 80% |  | 35
66 | Satsang Vihar Marg (A-Block Qutub Inst. Area) (Both Sides) | 0.41 |  |  |  | 76% |  | 120
67 | USO Marg (A-Block Qutub Inst. Area) (Both Sides) | 0.2 |  |  |  | 76% |  | 60
68 | Peripherial Road (B&C Block Qutub Inst. Area) (Both Sides) | 1.57 | M/s Nagendra & Company, | 14.02.2018 | 30.06.18 | 80% |  | 575 | Sh. Jagdish Prasad 9560207879
69 | Saheed Jeet Singh Marg (Both Sides) | 2.1 |  |  |  | 90% |  | 700
70 | Aruna Asaf Ali Marg (Both Sides) | 3.5 |  |  |  | 90% |  | 1350
71 | Anuvart Marg (Both Sides) | 2.5 |  |  |  | 85% |  | 1060
72 | Vedant Deshika Marg (Both Sides) | 0.9 |  |  |  | 90% |  | 420
73 | Qutub Minar Round About (Both Sides) | 1 |  |  |  | 76% |  | 320
74 | DAV School Road (Vasant Kunj) (Both Sides) | 0.55 |  |  |  | 95% |  | 230
75 | B-1 Telephone Exchange Road Vasant Kunj (Mahipalpur Road to B-5 & B-6 Road) (Both Sides) | 0.6 |  |  |  | 90% |  | 220
76 | B-2 & B-3 Road (Shiv Mandir to B-5 & B-6 Road) (Both Sides) | 0.3 |  |  |  | 90% |  | 110
77 | D-1 & D-2 Road Vasant Kunj (Both Sides) | 0.24 |  |  |  | 76% |  | 70
78 | Sports Complex Road (D-2 Vasant Kunj) (Both Sides) | 0.7 |  |  |  | 76% |  | 225
79 | Outer Ring Road | 3.2 | M/s Nagendra & Company, | 16.02.2018 | 30.06.18 | 62% | 1000 | 620
80 | A-1 Block, Panchsheel Enlcave Road | 0.5 |  |  |  | 62% | 50 | 31
81 | B,C & D Block Panchsheel Enclave Road | 0.5 |  |  |  | 6% | 50 | 3
82 | S-Bend Road (Maharishi Dayanand Marg) | 1.8 | Sh. Ram Nihor | 30.03.2018 | 30.06.18 | 80% | 446 | 357
83 | Shivalik Road (Basant Kaur Marg) | 1.86 |  |  |  | 80% | 306 | 245
84 | Guru Govind Singh Marg | 1.2 |  |  |  | 76% | 185 | 141
3)-South-East Circle
South-East Road-1 Division
1 | S. N. Puri Main Road From Cambridge School To CTC | 1.2 | M/s. Buland Construction | 13.05.2018 | 10.08.2018 | 80% | 161 |  | Sh. Sheel Rajneesh 8527021144
2 | S. N. Puri Internal Road Post Office to CPWD Via Jal Board Office | 0.54 | M/s. Buland Construction | 13.05.2018 | 10.08.2018 | 80% | 72
3 | S.N. Puri Internal Road Opp Police Post S.N. Puri | 0.15 | M/s. Buland Construction | 13.05.2018 | 10.08.2018 | 80% | 20
4 | S. N. Puri Internal Road MCD Store to round about Via Maternity Home | 0.93 | M/s. Buland Construction | 13.05.2018 | 10.08.2018 | 80% | 125
5 | Theka Road Sri Niwas Puri | 0.25 | M/s. Buland Construction | 13.05.2018 | 10.08.2018 | 80% | 134
6 | Captain Gaur Marg | 2.15 | M/s. Buland Construction | 13.05.2018 | 10.08.2018 | - | 288
7 | Banglow Road To Gidwani Marg, Lajpat Nagar-4 | 0.12 | M/s. Buland Construction | 13.05.2018 | 10.08.2018 | - | 16
8 | Dr. Moti Lal Jotwani Road, Lajpat Nagar-IV | 0.47 | M/s. Buland Construction | 13.05.2018 | 10.08.2018 | - | 63
9 | Central Road to Back of Ring Road, Lajpat Nagar-IV | 0.35 | M/s. Buland Construction | 13.05.2018 | 10.08.2018 | - | 47
10 | Kalka Devi Marg | 1.12 | M/s. Buland Construction | 13.05.2018 | 10.08.2018 | - | 150
11 | Kalka Devi Marg to Banglow Road, Lajpat Nagar-IV | 0.49 | M/s. Buland Construction | 13.05.2018 | 10.08.2018 | - | 65
12 | Road No. 2 Andrews Ganj | 0.4 | M/s. Buland Construction | 13.05.2018 | 10.08.2018 | 70% | 54
13 | Road No. 5 Andrews Ganj | 0.13 | M/s. Buland Construction | 13.05.2018 | 10.08.2018 | 70% | 17
14 | Road No. 7 Andrews Ganj | 0.24 | M/s. Buland Construction | 13.05.2018 | 10.08.2018 | 70% | 32
15 | Road No. 3 Andrews Ganj | 0.75 | M/s. Buland Construction | 13.05.2018 | 10.08.2018 | 70% | 100 |  | Sh. Sheel Rajneesh 8527021144
16 | Road No. 6 Andrews Ganj | 0.24 | M/s. Buland Construction | 13.05.2018 | 10.08.2018 | 70% | 32
17 | Garhi Village to National Heart Hospital | 0.41 | M/s. Buland Construction | 13.05.2018 | 10.08.2018 | - | 55
18 | Raja Dheer Sain Marg | 1.4 | M/s. Buland Construction | 13.05.2018 | 10.08.2018 | - | 188
19 | C.V. Raman Marg | 2 | M/s Buland Constructions | 13.05.18 | 10.08.18 | Work just started | 2830 | …..
20 | Mata Mandir Road | 0.55 | M/s Buland Constructions | 13.05.18 | 10.08.18 | do | 750 | …..
21 | M.P. Road | 1.35 | M/s Buland Constructions | 13.05.18 | 10.08.18 | 50% | 250 | …..
22 | Mathura Road (NH2) | 2.05 | M/s Buland Constructions | 13.05.18 | 10.08.18 | Nil | 2520 | …..
23 | Sukhdev Vihar Road | 1 | M/s Buland Constructions | 13.05.18 | 10.08.18 | Nil | 1680 | …..
24 | MMA Road | 3 | M/s Buland Constructions | 13.05.18 | 10.08.18 | Nil | 2280 | …..
25 | Gurudwara Road | 1.35 | M/s Buland Constructions | 13.05.18 | 10.08.18 | 60% | 580 | …..
26 | Bhishma Pitamah Road | 2.3 | Sh. Rajnish Yadav | 22.04.18 | 20.07.18 | Nil | 955 | …..
27 | Road from B.P.Marg to Round About Defence Colony | 0.16 | Sh. Rajnish Yadav | 22.04.18 | 20.07.18 | Nil | 66 | …..
28 | Feroz Gandhi Road Lajpat Nagar | 1.05 | Sh. Rajnish Yadav | 22.04.18 | 20.07.18 | Nil | 438 | …..
29 | Shiv Mandir Marg from Zonal Office to Ring Road | 0.85 | Sh. Rajnish Yadav | 22.04.18 | 20.07.18 | Nil | 353 | …..
30 | Vir Savarkar Marg, Lajapat Nagar | 1.05 | Sh. Rajnish Yadav | 22.04.18 | 20.07.18 | Nil | 436 | ….. | Sh. Sheel Rajneesh 8527021144
31 | Ring Road AIIMS to Bhairon Road 'T' Jn | 9.65 | Sh. Rajnish Yadav | 22.04.18 | 20.07.18 | 45% | 4005 | …..
32 | 2 nd Enty Road | 0.6 | Sh. Rajnish Yadav | 22.04.18 | 20.07.18 | Nil | 249 | …..
33 | Bhairon Road | 0.98 | Sh. Rajnish Yadav | 22.04.18 | 20.07.18 | Nil | 400 | …..
34 | Mathura Roads from DPS to Ashram Chowk | 2.65 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | 75% | 77 | …..
35 | Hospital Road, Bhogal | 0.56 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | Nil | 113 | …..
36 | East Nizamuddin peripheral Road from Mathura Road to Railway Station, East Nizamuddin | 0.7 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | 40% | 148 | …..
37 | Rajdoot Hotel to Preet Place, Jangpura | 0.2 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | 70% | 394 | …..
38 | Preet Place to Nizamuddin Railway Station, Jangpura | 0.7 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | 60% | 226 | …..
39 | School Road, Jangpura Extn. | 0.38 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | 15% | 84 | …..
40 | Neela Gumbad to Lodhi Flyover, Nizamuddin Basti | 0.2 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | 20% | 316 | …..
41 | Lodhi Road Indian Habitat Centre to Lodhi Flyover | 1.76 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | 75% | 122 | …..
42 | IVth- Avenue Road, Lodhi Colony | 1.22 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | 80% | 323 | …..
43 | Vth- Avenue Road, Lodhi Colony | 1 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | 70% | 113 | …..
44 | X- Road between Block No. 18 & 14 Lodhi Colony | 0.16 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | 10% | 51 | …..
45 | X- Road between D -1 & C-2 (F-24) Lodhi Colony | 0.16 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | 15% | 51 | …..
46 | X- Road between Block No. C- 2 (176) & C- 2 (177) Lodhi Colony | 0.16 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | 15% | 52 | ….. | Sh. Sheel Rajneesh 8527021144
47 | B.P marg to Coffee House Lodhi Colony | 0.35 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | 15% | 568 | …..
48 | F-1 Lodhi Colony to B.P Flyover, Lodhi Colony | 0.24 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | 5% | 97 | …..
49 | Verdhman Marg from IVth- Avenue Road B.P Marg, Lodhi Colony | 0.35 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | 15% | 969 | …..
50 | Maharani Bagh from Manokamna Mandir to Sunlight Colony | 0.55 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | Nil | 226 | …..
51 | Kushak Nallah to Sewa Nagar Flyover, Sewa Nagar | 0.7 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | 5% | 181 | …..
52 | Kushak Nallah to CPWD Enquiry (Near O Blk.), Sewa Nagar | 0.3 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | 5% | 65 | …..
53 | Hanuman mandir to Sewa Nagar Flyover, Sewa Nagar | 0.46 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | 5% | 226 | …..
54 | Railway Phatak to Subhash Bazar, Sewa Nagar | 0.258 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | Nil | 65 | …..
55 | BRT from Bhairon Road T- Point to Defence Colony Flyover | 3 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | 65% | 355 | …..
56 | Sunder Nagar Peripheral Road, Sunder Nagar | 1.1 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | 85% | …… | …..
57 | Ratan Lal Sahdev Marg, Defence Colony | 0.978 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | 5% | …… | …..
58 | Gang Nath Marg, Safdarjung Flyover to round about near Khushak Nalah | 0.625 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | 5% | …… | …..
South-East Road-2 Division
1 | SA Road | 5.46 | M/s R.P. Infrastructure | 15.04.2018 | 28.06.18 | 55% | 2215 |  | Sh. R.K. Sharma 9818615817
2 | Maharaja Agarsen Marg | 0.5 | M/s R.P. Infrastructure | 15.04.2018 | 28.06.18 | 60% | 190
3 | Baba Fateh Singh Marg | 1 | M/s R.P. Infrastructure | 15.04.2018 | 28.06.18 | 100% | 335
4 | Hans Raj Sethi Marg | 1.7 | M/s R.P. Infrastructure | 15.04.2018 | 28.06.18 | 40% | 329
5 | A Block Double Storey (EPDP to Hans Raj Sethi Marg) | 0.45 | M/s R.P. Infrastructure | 15.04.2018 | 28.06.18 | 20% | 31
6 | Maharaja Agarsen marg | 0.8 | M/s R.P. Infrastructure | 15.04.2018 | 28.06.18 |  | 576
7 | Madanpur Khadar Road | 1.2 | M/s R.P. Infrastructure | 15.04.2018 | 28.06.18 |  | 561
8 | Sarita Vihar Road | 1.1 | M/s R.P. Infrastructure | 15.04.2018 | 28.06.18 | 70% | 432
9 | Road No. 13 A | 2.5 | M/s R.P. Infrastructure | 15.04.2018 | 28.06.18 |  | 1350
10 | Mathura Road | 5.5 | M/s Buland Constructions | 14.04.18 | 27.06.18 | 20% | 2640
11 | Lala Lajpat Rai Marg to Raja Dheer Sen Marg | 0.3 | M/s Buland Constructions | 14.04.18 | 27.06.18 |  | 2700
12 | Guru Nanak Market to lala Lajpat Rai Marg | 0.57 | M/s Buland Constructions | 14.04.18 | 27.06.18
13 | Nandi Vithi Marg | 0.73 | M/s Buland Constructions | 14.04.18 | 27.06.18
14 | Link Road | 0.58 | M/s Buland Constructions | 14.04.18 | 27.06.18
15 | Road from BRT to Hans Raj Gupta Marg | 0.34 | M/s Buland Constructions | 14.04.18 | 27.06.18
16 | Hans Raj Gupta Marg | 2.65 |  | 14.04.18 | 27.06.18
17 | Lala Lajpat Rai Marg | 2.4 |  | 14.04.18 | 27.06.18
18 | Guru Harkishan Public School to Nehru Place | 0.27 | M/s Buland Constructions | 14.04.18 | 27.06.18 |  |  |  | Sh. R.K. Sharma 9818615817
19 | R Block GK-1 signal to Outer Ring Road | 0.58 | M/s Buland Constructions | 14.04.18 | 27.06.18
20 | Outer Ring Road | 2.1 | M/s Buland Constructions | 14.04.18 | 27.06.18
21 | Road from Vipin Chander Pal Marg to Police Station CR Park | 0.37 | M/s Buland Constructions | 14.04.18 | 27.06.18
22 | Savitri Cinema Road | 3.1 | M/s Buland Constructions | 14.04.18 | 27.06.18 | 15%
23 | Surya Sen Marg | 0.75 | M/s Buland Constructions | 14.04.18 | 27.06.18 | 85%
24 | MB Road | 5.25 | M/s R.P. Infrastructure | 15.04.18 | 28.06.18 | 5% | 2893
25 | Guru Ravi Dass Marg | 3.75 | M/s R.P. Infrastructure | 14.04.18 | 27.06.18 | 50% | 2294
26 | DDA Market Road | 0.43 | M/s R.P. Infrastructure | 14.04.18 | 27.06.18 | 85% | 277
27 | KPS Road | 0.64 | M/s R.P. Infrastructure | 14.04.18 | 27.06.18 |  | 225
28 | Suraj Kund Road | 0.6 | M/s R.P. Infrastructure | 15.04.18 | 28.06.18 | 70% | 287
29 | Road No13 | 2.7 | M/s Buland Constructions | 14.04.18 | 27.06.18 | 5% | 1090
30 | EPDP Road | 1.8 | M/s Buland Constructions | 14.04.18 | 27.06.18 |  | 582
31 | Outer Ring Road | 3.2 | M/s Buland Constructions | 14.04.18 | 27.06.18 |  | 758
32 | Gurudwara Road GK-II | 1.7 | M/s Buland Constructions | 14.04.18 | 27.06.18 |  | 467
33 | Vipin Chander Pal Marg | 1.5 | M/s Buland Constructions | 14.04.18 | 27.06.18 |  | 624