## Sheet1
PWD Desilting Report (Preparedness for Monsoon)
DESILTING REPORT UNDER PWD MAINTENANCE SOUTH ZONE UPTO 28.06.2018
As on 28.06.2018
Sl. No. | Name of Road / Drain | Length of Road (Km) | Length of drain (Km) | Contractor | Date of Start of De-Siliting | Date of completion | % Drain cleaned (Lengthwise) | Estimate Qty. of silt (cum) | Qty. of silt lifted and disposed off (MT) | EE in charge / Mobile No. | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1)-South-West Circle
South West Road-1 Division
1 | B.J. Marg | 1.3 | 2 | M/s Shatrughna Construction Co M/s WORKCEE |  | 15.07.2018 | 40% | 560 Cum | 168 MT | Er. S.K. Sinha / 9958469778 | Due to encroachment the work could not be completed
2 | Rao Tula Ram Marg (RTR Marg) | 1.7 | 3.6 |  |  | 15.07.2018 | 80% | 450 Cum | 360 MT |  | Work is progress.
3 | Zonal road No. 2 (Baba Balak Nath Marg) | 1.1 | 2.2 |  |  | 15.07.2018 | 40% | 580 Cum | 232 MT
4 | Zonal Road No. 6 (Hare Krishna Mehto Marg) | 0.7 | 0.5 |  |  | 15.07.2018 | 50% | 310 Cum | 155 MT
5 | Outer Ring Road | 4.8 | 6.3 |  |  | 15.07.2018 | 70% | 1060 Cum | 742 MT
6 | Babu Genu Marg, R.K.Puram | 0.6 | 1.4 |  |  | 15.07.2018 | 60% | 185 Cum | 111 MT
7 | Nelson Mandela Marg | 4.04 | 5.8 |  |  | 15.07.2018 | 75% | 1600 Cum | 1120 MT
8 | Baba Gang Nath marg | 1.17 | 2.3 |  |  | 15.07.2018 | 80% | 670 Cum | 536 MT
9 | Major Som nath marg | 1.6 | 1.6 |  |  | 15.07.2018 | 60% | 80 Cum | 48 MT
10 | Africa Avenue (Road No.9) | 2.2 | 4.2 | M/s WORKCEE & M/s Samridhi Construction |  | 15.07.2018 | 82% | 280 Cum | 224 MT
11 | Kafi Azami Marg | 0.9 | 1.2 |  | 26.03.18 | 15.07.2018 | 80% | 168 Cum | 134.4 MT
12 | Church Road, R.K.Puram | 0.85 | 1.6 |  |  | 15.07.2018 | 40% | 224 Cum | 89.6 MT
13 | Vivekanand Marg | 1.1 | 3.2 |  |  | 15.07.2018 | 40% | 539 Cum | 107.8 MT
14 | Venketeshwar Marg | 1.1 | 1.5 |  | 25.04.2018 | 15.07.2018 | 80% | 245 Cum | 196 MT
15 | Ring Road | 5 | 5 |  |  | 15.07.2018 | 40% | 980 Cum | 392 MT
16 | Kama Koti Marg | 1.75 | 1.6 |  | 20.04.2018 | 15.07.2018 | 30%
17 | Prem nath Dogra marg, R.K.Puram | 0.85 | 1 |  |  | 15.07.2018 | 30%
18 | Tamil Sangam Marg | 1.1 | 1 |  |  | 15.07.2018 | 40% | 168 Cum | 50 MT
19 | A-9 Street Road | 0.65 | 1 |  |  | 15.07.2018 | 40% |  |  |  | Due to encroachment the work could not be completed
20 | Basant Marg-II | 0.5 | 1.4 |  |  | 15.07.2018 | 50%
21 | Paschimi Marg | 1.25 | 1.4 |  |  | 15.07.2018 | 50%
22 | Poorvi Marg | 1.65 | 1.4 |  |  | 15.07.2018 | 40% | 56 Cum | 16.8 MT
23 | Ganga Ram Hospital Road | 1.08 | 2.1 | M/S Sai Tube Well Shri Rajpal Sehgal |  | 15.07.2018 | 60% | 295 Cum | 177 MT | Er. S.K. Sinha / 9958469778 | Work is in Progress.
24 | PUSA Road | 2 | 1.6 |  | 25.03.18 | 15.07.2018 | 60% | 540 Cum | 324 MT
25 | Shankar Road | 1.64 | 2.2 |  | 25.03.18 | 15.07.2018 | 70% | 250 Cum | 175 MT
26 | Dr. K.S. Krishanan Marg | 0.915 | 1.8 |  | 25.03.18 | 15.07.2018 | 70% | 250 Cum | 175 MT
27 | PUSA Institute (IARI) Internal Road | 0.7 | 0.7 |  | 25.03.18 | 15.07.2018 | 70% | 200 | 140 MT
28 | Dev Prakash Shastri marg (Road No. 25) | 4.45 | 8.8 |  |  | 15.07.2018 | 50% | 1200 | 600 MT
29 | Girdhari Lal Goswami Marg (Road No. 89) | 3.65 | 6 |  |  | 15.07.2018 | 60% | 1100 | 660 MT
30 | O.P. Bharti Marg 1 | 0.535 | 3.76 |  |  | 15.07.2018 | 80% | 150 | 120 MT
31 | O.P. Bharti Marg 2 | 0.762 |  |  |  | 15.07.2018 | 80% | 205 | 164 MT
32 | O.P. Bharti Marg 3 | 0.181 |  |  |  | 15.07.2018 | 80% | 50 | 40 MT
33 | O.P. Bharti Marg 4 | 0.42 |  |  |  | 15.07.2018 | 80% | 120 | 96 MT
34 | Guru Ravi Dass Marg | 0.8 | 1.1 |  |  | 15.07.2018 | 45% | 215 | 86 MT
35 | Ganga Mandir Marg | 0.75 | 1.4 |  |  | 15.07.2018 | 40% | 210 | 84 MT
36 | Vishnu Mandir Marg | 0.6 | 1.2 |  | 25.03.18 | 15.07.2018 | 36% | 160 | 48 MT
37 | Saraswati Marg | 0.5 | 1 |  |  | 15.07.2018 | 35% | 150 | 45 MT
38 | Ajmal Khan Road | 0.6 | 1 |  | 25.03.18 | 15.07.2018 | 40% | 165 | 66 MT
39 | Gurudwara Road | 0.5 | 0.8 |  | 25.03.18 | 15.07.2018 | 68% | 135 | 81 MT
40 | Abdul Aziz Road | 0.4 | 0.6 |  | 25.03.18 | 15.07.2018 | 28% | 110 | 22 MT
41 | S.K. Dass Road | 0.3 | 0.5 |  | 25.03.18 | 15.07.2018 | 45% | 80 | 40 MT
42 | Abdul Rehman | 0.2 | 0.4 |  |  | 15.07.2018 | 50% | 55 | 27.5 MT
43 | Padam Singh Road | 0.75 | 1.3 |  | 25.03.18 | 15.07.2018 | 55% | 210 | 105 MT
44 | Arya Samaj Road | 1 | 2 |  | 25.03.18 | 15.07.2018 | 54% | 270 | 135 MT
45 | Mahatma gandhi Marg (Ring Road) | 7.1 | 6.6 | M/s Shatrughna Construction Co & Shri Rajnish Yadav | 25.03.18 | 15.07.2018 | 70% | 312 Cum | 218.4 MT
46 | Road No. 36(Sat Guru Ram Singh Marg) | 3.4 | 6.8 |  | 25.03.18 | 15.07.2018 | 62% | 1200 Cum | 720 MT
47 | MM Road | 6.8 | 7.7 | M/s RichCon Engineering Company | 25.03.18 | 15.07.2018 | 60% | 600 Cum | 360 MT
48 | Vatika Road (DPS Vasant Kunj to MM road) | 0.7 | 1.4 |  | 25.03.18 | 15.07.2018 | 60% | 500 Cum | 300 MT
49 | Munirka marg | 0.9 | 0.8 |  |  | 15.07.2018 | 70% | 100 Cum | 70 MT
50 | Basant marg-I | 0.9 |  |  | 25.03.18 | 15.07.2018 | 60% | 100 Cum | 60 MT
A | Total | 78.443 | 112.76
South West Road-2 Division
1 | A Block Road | 0.2 | 0.4 | ANMOL INFRATECH PRIVATE LIMITED | 2018-03-21 | 15.06.18 | 100% | Work executed by super sucker machine | The drain is being cleaned by super sucker machines hence quanitity cannot be ascertained. | Er. J. P. Vashist M- 9971396164 | 2nd cycle in progress
2 | Pankha Road | 1 | 2.05 |  | 2018-03-21 | 15.06.18 | 100% |  |  |  | ….do…..
3 | Nasir Pur Road | 2.3 | 3.89 |  | 2018-03-21 | 15.06.18 | 100% |  |  |  | ….do…..
4 | Palam Dabri Road | 2.5 | 3.496 |  | 2018-03-21 | 15.06.18 | 100% |  |  |  | ….do…..
5 | Paras Public schol to L-103 Pocket-4 Chankya Puri Binda Pur | 0.24 | 0.48 |  | 2018-03-21 | 15.06.18 | 100% |  |  |  | ….do…..
6 | Peer Baba Road | 0.6 | 1.236 |  | 2018-03-21 | 15.06.18 | 100% |  |  |  | ….do…..
7 | Police Station Road | 0.37 | 0.74 |  | 2018-03-21 | 15.06.18 | 100% |  |  |  | ….do…..
8 | Pt. Vishnu Dutt Marg | 0.75 | 1.497 |  | 2018-03-21 | 15.06.18 | 100% |  |  |  | ….do…..
9 | Sagar Pur Road | 3 | 5.55 |  | 2018-03-21 | 15.06.18 | 100% |  |  |  | ….do…..
10 | Satguru Ram Singh Marg | 0.9 | 1.635 |  | 2018-03-21 | 15.06.18 | 100% |  |  |  | ….do…..
11 | Link Road (Pt. Vishnu Dutt Marg to Satguru Ram Singh Marg) | 0.3 | 0.55 |  | 2018-03-21 | 15.06.18 | 100% |  |  |  | ….do…..
12 | Najafgarh Nagloi Road | 2.6 | 8.35 | Surender Singh | 2018-02-23 | 15.06.18 | 100% |  |  |  | 2nd cycle in progress
13 | Najafgarh Phirni | 2.2 | 4.54 |  | 2018-02-23 | 10.07.2018 | 75% |  |  |  | will be completed by 10.07.2018
14 | Najafgarh Dhansa Road | 16.25 | 5.05 |  | 2018-03-07 | 10.07.2018 | 75% |  |  |  | will be completed by 10.07.2018
15 | Najafgarh Dechaun Road | 4.55 | 5.64 | Ram Charan Bansal | 2018-02-23 | 15.06.18 | 100% |  |  |  | 2nd cycle in progress
16 | Najafgarh Jaroda Road | 7.2 | 2.65 |  | 2018-02-23 | 15.06.18 | 90% |  |  |  | will be completed by 10.07.2018
17 | Najafgarh Kakrola Road | 4 | 13.65 | Surender Singh | 2018-03-07 | 10.07.2018 | 75% |  |  |  | will be completed by 10.07.2018
18 | Laxmi Chand Marg | 11.3 | 10.5 | Surender Singh | 2018-03-07 | 15.06.18 | 90% | Work is being executed by super sucker machine |  |  | will be completed by 10.07.2018
19 | Prithvi Singh Dagar Marg | 11.2 | 7.9 |  | 2018-03-07 | 15.06.18 | 100% |  |  |  | 2nd cycle in progress
20 | Jhatikara Morh to Jhatikara | 8.55 | 1.2 | Ram Charan Bansal | 2018-02-23 | 15.06.18 | 100% |  |  |  | 2nd cycle in progress
21 | Najafgarh Bijwasan Road | 11.25 | 16 |  | 2018-02-23 | 10.07.2018 | 90% |  |  |  | will be completed by 10.07.2018
22 | Bhartal Road | 3.48 | 3.48 | Surender Singh | 2018-03-01 | 15.06.18 | 100% |  |  |  | 2nd cycle in progress
23 | Goyla Deenpur Road | 4.2 | 7.4 |  | 2018-03-01 | 15.06.18 | 100% |  |  |  | 2nd cycle in progress
24 | Kapashera Bijwasan Road | 3.8 | 7.6 | ANMOL INFRATECH PRIVATE LIMITED | 2018-03-21 | 10.07.2018 | 85% |  |  |  | will be completed by 10.07.2018
25 | Link Road | 1.7 | 1.7 |  | 2018-03-21 | 10.07.2018 | 90% |  |  |  | will be completed by 10.07.2018
26 | Old DG Road | 2.5 | 5 |  | 2018-03-21 | 15.06.18 | 100% |  |  |  | 2nd cycle in progress
B | Total | 106.94 | 122.184
2)-South Circle
South Road-1 Division
1 | M.B. Road | 5.25 | 5.25 | M/s Maan Builders | 09.04.2018 | 30.06.2018 | 85% | 4682 | --- | Er. Narender Mahajan (M:9643870385)
|  |  |  | M/s Buland constructions | 15.04.2018 | 30.06.2018 | 85% | 3019 | ---
2 | IGNOU Road | 1.9 | 1.9 | M/s Buland constructions | 15.04.2018 |  | 70% | 2725 | ---
3 | Westend Marg | 0.6 | 0.6 | M/s Buland constructions | 09.04.2018 | 28.06.2018 | 100% |  | ---
4 | Devli Road | 1.05 | 1.05 | M/s Maan Builders | 09.04.2018 | 28.06.2018 | 100% |  | ---
5 | H Block Dakshnipuri | 0.9 | 0.9 |  |  |  | 100% |  | ---
6 | Raja Ram Marg | 0.89 | 0.89 |  |  |  | 100% |  | ---
7 | Durbal Nath Marg | 1.09 | 1.09 |  |  |  | 100% |  | ---
8 | Maharishi Balmiki Marg | 1.8 | 1.8 |  |  |  | 100% |  | ---
9 | Phirni Road | 1 | 1 |  |  |  | 100% |  | ---
10 | Old MB Road | 0.6 | 0.6 | M/s Kleenwel Enviro Engg. Services | 09.04.2018 | 15.06.2018 | 100% |  | ---
11 | 100 Foota Road | 1.4 | 1.4 |  | 09.04.2018 | 30.06.2018 | 45% |  | --- | Er. Narender Mahajan (M:9643870385)
12 | 60 Foota Road | 0.9 | 0.9 |  | 09.04.2018 | 30.06.2018 | 40% |  | ---
13 | SSN Marg | 10.5 | 10.5 | M/s Buland Constructions | 09.04.2018 | 30.06.2018 | 50% | 2162 | ---
14 | Mandi Road | 8 | 8 | M/s Buland Constructions | 09.04.2018 | 30.06.2018 | 50% | 1144 cum | --- | Er. Narender Mahajan (M:9643870385)
15 | Gadaipur Bundh Road | 3 | 3 |  | 09.04.2018 | 30.06.2018 | 51% |  | ---
16 | Mandi Road | 8 | 8 | Sh. Ravi Tanwar | 28.04.2018 | 15.06.2018 | 100% | 2340 cum | --- | Er. Narender Mahajan (M:9643870385)
17 | Gadaipur Bundh Road | 3 | 3 |  |  |  | 100% |  | ---
18 | Dera Bhatti Road | 5.76 | 5.76 |  |  |  | 100% |  | ---
19 | Pankaj Juyal Marg | 1.1 | 1.1 | M/s Buland Constructions | 2018-03-31 | 15.06.2018 | 100% | 6150 | --- | Er. Narender Mahajan
20 | Family Court road | 0.55 | 0.55 |  |  |  | 100% |  | ---
21 | J-Block Road | 1.2 | 1.2 |  |  |  | 100% |  | ---
22 | Asian Market Road | 0.45 | 0.45 |  |  |  | 100% |  | ---
23 | Mandir marg | 1.2 | 1.2 |  |  |  | 100% |  | ---
24 | NBCC Plaza Road | 1.1 | 1.1 |  |  |  | 100% |  | ---
25 | Birla Vidya Niketan Marg | 0.95 | 0.95 |  |  |  | 100% |  | ---
26 | Pramod Mahajan Marg | 0.89 | 0.89 |  |  |  | 100% |  | ---
27 | Main Road Pushp Vihar Sector-1 | 0.75 | 0.75 |  |  |  | 100% |  | ---
28 | Metro Enclave Road | 0.45 | 0.45 |  |  |  | 100% |  | ---
29 | Press Enclave Road | 3.78 | 3.78 | M/s Buland Constructions | 2018-04-06 | 30.06.2018 | 70% | 3135 | --- | Er. Narender Mahajan
30 | Khirki Road | 0.85 | 0.85 |  |  |  | 70% |  | ---
31 | Apeejay School Road | 1.3 | 1.3 |  |  |  | 60% |  | ---
32 | Sheikh Sarai Phase-1 Road-1 | 0.6 | 0.6 |  |  |  | 45% |  | ---
33 | Sheikh Sarai Phase-1 Road-2 | 0.3 | 0.3 |  |  |  | 50% |  | ---
34 | Road in front of Mother International School | 0.54 | 0.54 |  |  |  | 100% |  | ---
35 | Road from H.No. C-11 to C-20 Malviya Nagar | 0.11 | 0.11 |  |  |  | 100% |  | ---
36 | Gurudwara Road Saket | 0.55 | 0.55 | Sh. Babu lal Gupta | 2018-04-06 | 30.06.2018 | 76% | 684 | --- | Er. Narender Mahajan
37 | Pramod Mahajan Marg | 0.89 | 0.89 |  |  |  | 100% |  | ---
38 | M.G. Road | 7.5 | 7.5 | M/s Buland Constructions | 09.04.2018 | 28.06.2018 | 42% | 5265 | --- | Sh. Narender Mahajan Mob.No.- 9933331859
39 | Aya Nagar | 0.6 | 0.6 |  |  |  | 95% |  | ---
40 | Ghitorni Road to CPWD Land | 0.54 | 0.54 |  |  |  | 95% |  | ---
41 | Ghitorni Village Road | 1.04 | 1.04 |  |  |  | 90% |  | ---
42 | MG Road to Ghitorni Village | 0.3 | 0.3 |  |  |  | 51% |  | ---
C | Total | 83.18 | 83.18
South Road-2 Division
43 | August Kranti Marg. | 3.24 | 3.54 | Sh. Yogesh Arora | 22.02.2018 | 30.06.2018 | 90% | 618.75 | --- | Sh. Jagdish Prasad 9560207879
44 | Balbir Saxena Marg | 0.8 | 1.6 |  |  |  | 90% | 192 | ---
45 | Ch. Dilip Singh Marg, P.S. Hauz Khas | 0.6 | 1 |  |  |  | 80% | 360 | ---
46 | Mahinder Singh Jain Marg Road / Gautam Nagar Road | 1.2 | 2.4 |  |  |  | 95% | 480 | ---
47 | P-Block Road from August Kranti Marg via jain Mandir & Dustbin to August Kranti Marg. | 0.34 | 0.6 |  |  |  | 90% | 120 | ---
48 | Sudarshan Cinema Road. | 0.72 | 0.7 |  |  |  | 95% | 75 | ---
49 | Gautam Nagar Road | 0.5 | 0.8 |  |  |  | 80% | 225 | ---
50 | Road form Balbir Sxsena Marg to Ch. Dalip SinghMarg (NIFT Road), Hauz Khas | 0.6 | 1.2 |  |  |  | 95% | 135 | ---
51 | Road form August Kranti marg to Aurobindo Marg (Subash Chopra Road), Hauz Khas | 0.79 | 1.5 |  |  |  | 90% | 99 | ---
52 | Asiad Village peripheral road | 3 | 3 |  |  |  | 95% | 375 | ---
53 | Siri Fort Road | 1.2 | 2.4 |  |  |  | 95% | 288 | ---
54 | Sri Krishna Chaitnya Maha Prabhu Marg | 0.7 | 1.4 |  |  |  | 90% | 80 | ---
55 | Sri Aurobindo Marg | 4.3 | 8.6 | M/s Amit Enterprises | 16.02.2018 | 30.06.2018 | 95% | 2874 | --- | Sh. Jagdish Prasad 9560207879
56 | Ring Road | 2 | 3.6 |  |  |  | 95% | 2998 | ---
57 | Outer Ring Road | 1.5 | 3 |  |  |  | 90% |  | ---
58 | Ch. Harsukh Marg | 2 | 4 |  |  |  | 90% |  | ---
59 | Ch Jhandu Singh Marg | 1.53 | 3.06 |  |  |  | 90% |  | ---
60 | Ch Hukum Chand Marg | 0.6 | 0.9 |  |  |  | 80% |  | ---
61 | Green Park Market Road | 0.8 | 1.2 |  |  |  | 90% |  | ---
62 | Hauz Khas Village Road | 0.9 | 0.08 |  |  |  | 92% |  | ---
63 | N. K. Pandey Marg | 1.17 | 1.58 |  |  |  | 85% |  | ---
64 | Road from B15/7 to BSES (B&C Block Qutub Inst. Area) (Both Sides) | 0.3 | 0.6 | M/s Nagendra & Company, | 14.02.2018 | 30.06.2018 | 80% | 6060 | --- | Sh. Jagdish Prasad 9560207879
65 | Road from B12 to IIM (B&C Block Qutub Inst. Area) (Both Sides) | 0.1 | 0.2 |  |  |  | 80% |  | ---
66 | Satsang Vihar Marg (A-Block Qutub Inst. Area) (Both Sides) | 0.41 | 0.82 |  |  |  | 70% |  | ---
67 | USO Marg (A-Block Qutub Inst. Area) (Both Sides) | 0.2 | 0.4 |  |  |  | 70% |  | ---
68 | Peripherial Road (B&C Block Qutub Inst. Area) (Both Sides) | 1.57 | 3.14 |  |  |  | 80% |  | ---
69 | Saheed Jeet Singh Marg (Both Sides) | 2.1 | 4.2 |  |  |  | 90% |  | ---
70 | Aruna Asaf Ali Marg (Both Sides) | 3.5 | 7 |  |  |  | 90% |  | ---
71 | Anuvart Marg (Both Sides) | 2.5 | 5 |  |  |  | 85% |  | ---
72 | Vedant Deshika Marg (Both Sides) | 0.9 | 1.8 |  |  |  | 90% |  | ---
73 | Qutub Minar Round About (Both Sides) | 1 | 2 |  |  |  | 80% |  | ---
74 | DAV School Road (Vasant Kunj) (Both Sides) | 0.55 | 1.1 |  |  |  | 95% |  | ---
75 | B-1 Telephone Exchange Road Vasant Kunj (Mahipalpur Road to B-5 & B-6 Road) (Both Sides) | 0.6 | 1.2 |  |  |  | 90% |  | ---
76 | B-2 & B-3 Road (Shiv Mandir to B-5 & B-6 Road) (Both Sides) | 0.3 | 0.6 |  |  |  | 90% |  | ---
77 | D-1 & D-2 Road Vasant Kunj (Both Sides) | 0.24 | 0.48 |  |  |  | 80% |  | ---
78 | Sports Complex Road (D-2 Vasant Kunj) (Both Sides) | 0.7 | 1.4 |  |  |  | 95% |  | ---
79 | Outer Ring Road | 3.2 | 6.4 | M/s Nagendra & Company, | 16.02.2018 | 30.06.2018 | 80% | 1000 | --- | Sh. Jagdish Prasad 9560207879
80 | A-1 Block, Panchsheel Enlcave Road | 0.5 | 0.5 |  |  |  | 80% | 50 | ---
81 | B,C & D Block Panchsheel Enclave Road | 0.5 | 0.5 |  |  |  | 80% | 50 | ---
82 | S-Bend Road (Maharishi Dayanand Marg) | 1.8 | 2.9 | Sh. Ram Nihor | 30.03.2018 | 30.06.2018 | 80% | 446 | --- | Sh. Jagdish Prasad 9560207879
83 | Shivalik Road (Basant Kaur Marg) | 1.86 | 3.6 |  |  |  | 85% | 306 | ---
84 | Guru Govind Singh Marg | 1.2 | 1.9 |  |  |  | 80% | 185 | ---
D | Total | 52.52 | 91.9
3)-South East Circle
South East Road-1 Division
1 | S. N. Puri Main Road From Cambridge School To CTC | 1.4 | 2.4 | M/s. Buland Construction | 13.05.2018 | 10.08.2018 | 80% | 161 | Work in progress | Sh. Sheel Rajneesh 8527021144 | Work just started.
2 | S. N. Puri Internal Road Post Office to CPWD Via Jal Board Office | 0.54 | 1.08 | -do- | -do- | -do- | 80% | 72 | -do- |  | do
3 | S.N. Puri Internal Road Opp Police Post | 0.15 | 0.3 | -do- | -do- | -do- | 80% | 20 | -do- |  | do
4 | S. N. Puri Internal Road MCD Store to round about Via Maternity Home | 0.91 | 1.86 | -do- | -do- | -do- | 80% | 125 | -do- |  | do
5 | Theka Road Sri Niwas Puri | 0.25 | 0.5 | -do- | -do- | -do- | 80% | 134 | -do- |  | do
6 | Captain Gaur Marg | 2.15 | 4.3 | -do- | -do- | -do- | - | 288 | -do- |  | do
7 | Banglow Road To Gidwani Marg, Lajpat Nagar-4 | 0.12 | 0.24 | -do- | -do- | -do- | - | 16 | -do- |  | do
8 | Dr. Moti Lal Jotwani Road, Lajpat Nagar-IV | 0.47 | 0.94 | -do- | -do- | -do- | - | 63 | -do- |  | do
9 | Central Road to Back of Ring Road, Lajpat Nagar-IV | 0.35 | 0.7 | -do- | -do- | -do- | - | 47 | -do- |  | do
10 | Kalka Devi Marg | 1.12 | 2.24 | -do- | -do- | -do- | - | 150 | -do- |  | do
11 | Kalka Devi Marg to Banglow Road, Lajpat Nagar-IV | 0.49 | 0.98 | -do- | -do- | -do- | - | 65 | -do- |  | do
12 | Road No. 2 Andrews Ganj | 0.4 | 0.8 | -do- | -do- | -do- | 70% | 54 | -do- |  | do
13 | Road No. 5 Andrews Ganj | 0.13 | 0.26 | -do- | -do- | -do- | 70% | 17 | -do- |  | do
14 | Road No. 7 Andrews Ganj | 0.24 | 0.48 | -do- | -do- | -do- | 70% | 32 | -do- | Sh. Sheel Rajneesh 8527021144 | do
15 | Road No. 3 Andrews Ganj | 0.75 | 1.5 | -do- | -do- | -do- | 70% | 100 | -do- |  | do
16 | Road No. 6 Andrews Ganj | 0.24 | 0.48 | -do- | -do- | -do- | 70% | 32 | -do- |  | do
17 | Garhi Village to National Heart Hospital via Sapna Cinema | 0.41 | 0.82 | -do- | -do- | -do- | - | 55 | -do- |  | do
18 | Raja Dheer Sain Marg | 1.78 | 2.8 | -do- | -do- | -do- | - | 188 | -do- |  | do
19 | C.V. Raman Marg | 2 | 3.5 | M/s. Buland Construction | 13.05.18 | 10.08.18 | 40% | 2830 Mtrs | -do- |  | do
20 | Mata Mandir Road | 0.55 | 0.8 | -do- | -do- | -do- | 50% | 750 Mtrs | -do- |  | do
21 | M.P. Road | 1.35 | 1 | -do- | -do- | -do- | 80% | 250 Mtrs | -do- |  | do
22 | Mathura Road (NH2) | 2.05 | 3 | -do- | -do- | -do- | 60% | 2520 Mtrs | -do- |  | do
23 | Sukhdev Vihar Road | 1 | 1.6 | -do- | -do- | -do- | 25% | 1680 Mtrs | -do- |  | do
24 | MMA Road | 3 | 5 | -do- | -do- | -do- | 35% | 2280 Mtrs | -do- |  | do
25 | Gurudwara Road | 1.35 | 2 | -do- | -do- | -do- | 70% | 580 Mtrs | -do- |  | do
26 | Bhishma Pitamah Road | 2.3 | 4.6 | Sh. Rajnish Yadav | 22.04.18 | 20.07.18 | 85% | 955 | -do- |  | do
27 | Road from B.P.Marg to Round About Defence Colony | 0.16 | 0.32 | -do- | -do- | -do- | 85% | 66 | -do- |  | do
28 | Feroz Gandhi Road Lajpat Nagar | 1.05 | 2.1 | -do- | -do- | -do- | 90% | 438 | -do- |  | do
29 | Shiv Mandir Marg from Zonal Office to Ring Road | 0.85 | 1.7 | -do- | -do- | -do- | 90% | 353 | -do- | Sh. Sheel Rajneesh 8527021144 | do
30 | Vir Savarkar Marg, Lajapat Nagar | 1.05 | 2.1 | -do- | -do- | -do- | 90% | 436 | -do- |  | do
31 | Ring Road AIIMS to Bhairon Road 'T' Jn | 9.65 | 19.3 | -do- | -do- | -do- | 70% | 4005 | -do- |  | do
32 | 2 nd Enty Road | 0.6 | 1.2 | -do- | -do- | -do- | 50% | 249 | -do- |  | do
33 | Bhairon Road | 0.98 | 1.96 | -do- | -do- | -do- | Nil | 400 | -do- |  | hand over to ITP
34 | BRT Road | 6.75 | 13.5 | -do- | -do- | -do- | 50% | 2800 | -do- |  | Work just started.
35 | Mathura Roads from DPS to Ashram Chowk | 2.65 | 1.8 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | 90% | 400 | -do- |  | do
36 | Hospital Road, Bhogal | 0.56 | 0.4 | -do- | -do- | -do- | 50% | 100 | -do- |  | do
37 | East Nizamuddin peripheral Road from Mathura Road to Railway Station, East Nizamuddin | 0.7 | 0.7 | -do- | -do- | -do- | 40% | 150 | -do- |  | do
38 | Rajdoot Hotel to Preet Place, Jangpura | 0.2 | 0.2 | -do- | -do- | -do- | 80% | 50 | -do- |  | do
39 | Preet Place to Nizamuddin Railway Station, Jangpura | 0.7 | 0.7 | -do- | -do- | -do- | 65% | 150 | -do- |  | do
40 | School Road, Jangpura Extn. | 0.38 | 0.38 | -do- | -do- | -do- | 40% | 80 | -do- |  | do
41 | Neela Gumbad to Lodhi Flyover, Nizamuddin Basti | 0.2 | 0.4 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | 50% | 85 | -do- |  | do
42 | Lodhi Road Indian Habitat Centre to Lodhi Flyover | 1.76 | 3.5 | -do- | -do- | -do- | 75% | 740 | -do- |  | do
43 | IVth- Avenue Road, Lodhi Colony | 1.22 | 2.4 | -do- | -do- | -do- | 85% | 510 | -do- |  | do
44 | Vth- Avenue Road, Lodhi Colony | 1 | 2 | -do- | -do- | -do- | 80% | 420 | -do- |  | do
45 | X- Road between Block No. 18 & 14 Lodhi Colony | 0.16 | 0.32 | -do- | -do- | -do- | 75% | 70 | -do- |  | do
46 | X- Road between D -1 & C-2 (F-24) Lodhi Colony | 0.16 | 0.32 | -do- | -do- | -do- | 70% | 70 | -do- |  | do
47 | X- Road between Block No. C- 2 (176) & C- 2 (177) Lodhi Colony | 0.16 | 0.32 | -do- | -do- | -do- | 70% | 70 | -do- | Sh. Sheel Rajneesh 8527021144 | do
48 | B.P marg to Coffee House Lodhi Colony | 0.35 | 0.4 | -do- | -do- | -do- | 75% | 125 | -do- |  | do
49 | F-1 Lodhi Colony to B.P Flyover, Lodhi Colony | 0.24 | 0.2 | -do- | -do- | -do- | 70% | 50 | -do- |  | do
50 | Verdhman Marg from IVth- Avenue Road B.P Marg, Lodhi Colony | 0.35 | 0.5 | -do- | -do- | -do- | 70% | 115 | -do- |  | do
51 | Maharani Bagh from Manokamna Mandir to Sunlight Colony | 0.55 | 0.55 | -do- | -do- | -do- | 50% | 120 | -do- |  | do
52 | Kushak Nallah to Sewa Nagar Flyover, Sewa Nagar | 0.7 | 0.7 | -do- | -do- | -do- | 50% | 150 | -do- |  | do
53 | Kushak Nallah to CPWD Enquiry (Near O Blk.), Sewa Nagar | 0.3 | 0.6 | -do- | -do- | -do- | 20% | 60 | -do- |  | do
54 | Hanuman mandir to Sewa Nagar Flyover, Sewa Nagar | 0.46 | 0.46 | -do- | -do- | -do- | 50% | 100 | -do- |  | do
55 | Railway Phatak to Subhash Bazar, Sewa Nagar | 0.258 | 0.2 | -do- | -do- | -do- | 50% | 20 | -do- |  | do
56 | BRT from Bhairon Road T- Point to Defence Colony Flyover | 3 | 2 | -do- | -do- | -do- | 75% | 550 | -do- |  | do
57 | Sunder Nagar Peripheral Road, Sunder Nagar | 1.1 | 1.1 | -do- | -do- | -do- | 85% | 250 | -do- |  | do
58 | Ratan Lal Sahdev Marg, Defence Colony | 0.978 | 1 | -do- | -do- | -do- | 75% | 240 | -do- |  | do
59 | Gang Nath Marg, Safdarjung Flyover to round about near Khushak Nalah | 0.625 | 0.4 | -do- | -do- | -do- | 15% | 150 | -do- |  | do
E | Total | 65.351 | 107.91
South East Road-2 Division
60 | SA Road | 5.46 | 10.92 | M/s R.P. Infrastructure | 15:04 | 30.06.2018 | 95% | 2215 |  | Er. R.K. Sharma, 9818615817
61 | Maharaja Agarsen Marg | 0.5 | 1 |  | 15:04 | Completed on 28.06.2018 | 100% | 190
62 | Baba Fateh Singh Marg | 1 | 2 |  | 15:04 | Completed on 15.06.2018 | 100% | 335
63 | Hans Raj Sethi Marg | 1.7 | 3.4 |  | 15:04 | 30.06.2018 | 85% | 329
64 | A Block Double Storey (EPDP to Hans Raj Sethi Marg) | 0.45 | 0.9 |  | 15:04 | 30.06.2018 | 80% | 31
65 | Maharaja Agarsen marg | 0.8 | 1.6 |  | 15:04 | 30.06.2018 | 75% | 576
66 | Madanpur Khadar Road | 1.2 | 2.4 |  | 15:04 | 30.06.2018 | 65% | 561
67 | Sarita Vihar Road | 1.1 | 2.2 |  | 15:04 | Completed on 15.06.2018 | 100% | 432
68 | Road No. 13 A | 2.5 | 5 |  | 15:04 | 30.06.2018 | 70% | 1350
69 | Mathura Road | 5.5 | 11 | M/s Buland Constructions | 14:04 | 30.06.2018 | 60% | 2640 |  | Er. R.K. Sharma, 9818615817
70 | Lala Lajpat Rai Marg to Raja Dheer Sen Marg | 0.3 | 0.6 |  | 14:04 | 30.06.2018 | 80% | 2700
71 | Guru Nanak Market to lala Lajpat Rai Marg | 0.57 | 1.14 |  | 14:04 | Completed on 15.06.2018 | 100%
72 | Nandi Vithi Marg | 0.73 | 1.46 |  | 14:04 | Completed on 15.06.2018 | 100%
73 | Link Road | 0.58 | 1.16 |  | 14:04 | Completed on 15.06.2018 | 100%
74 | Road from BRT to Hans Raj Gupta Marg | 0.34 | 0.68 |  | 14:04 | Completed on 20.06.2018 | 100%
75 | Hans Raj Gupta Marg | 2.65 | 5.3 |  | 14:04 | 30.06.2018 | 65%
76 | Lala Lajpat Rai Marg | 2.4 | 4.8 |  | 14:04 | 30.06.2018 | 75%
77 | Guru Harkishan Public School to Nehru Place | 0.27 | 0.54 |  | 14:04 | Completed on 18.06.2018 | 100%
78 | R Block GK-1 signal to Outer Ring Road | 0.58 | 1.16 |  | 14:04 | Completed on 18.06.2018 | 100%
79 | Outer Ring Road | 2.1 | 4.2 |  | 14:04 | 30.06.2018 | 95%
80 | Road from Vipin Chander Pal Marg to Police Station CR Park | 0.37 | 0.74 |  | 14:04 | 27:06 | 75%
81 | Savitri Cinema Road | 3.1 | 6.2 |  | 14:04 | 27:06 | 85%
82 | Surya Sen Marg | 0.75 | 1.5 |  | 14:04 | Completed on 18.06.2018 | 100%
83 | E Block Road GK-III | 0.692 | 1.384 |  | 14:04 | 30.06.2018 | 65%
84 | Lala Lajpat Rai Marg to Raja Dheer Sen Marf Block E & F | 0.3 | 0.6 |  | 14:04 | 30.06.2018 | 80%
85 | M Block Road | 1.3 | 2.6 |  | 14:04 | 30.06.2018 | 80%
86 | MB Road | 5.25 | 10.5 | M/s R.P. Infrastructure | 15:04 | 30.06.2018 | 85% | 2893 |  | Er. R.K. Sharma, 9818615817
87 | Guru Ravi Dass Marg | 3.75 | 7.5 |  | 14:04 | 30.06.2018 | 95% | 2294
88 | DDA Market Road | 0.43 | 0.86 |  | 14:04 | Completed on 25.06.2018 | 100% | 277
89 | KPS Road | 0.64 | 1.28 |  | 14:04 |  | 100% | 225
90 | Suraj Kund Road | 0.6 | 1.2 |  | 15:04 | Completed on 28.06.2018 | 100% | 287
91 | Road No13 | 2.7 | 5.4 | M/s Buland Constructions | 14:04 | 30.06.2018 | 85% | 1090
92 | EPDP Road | 1.8 | 3.6 |  | 14:04 | Completed on 28.06.2018 | 100% | 582
93 | Outer Ring Road | 3.2 | 6.4 |  | 14:04 | 30.06.2018 | 80% | 758
94 | Gurudwara Road GK-II | 1.7 | 3.4 |  | 14:04 | Completed on 28.06.2018 | 100% | 467
95 | Vipin Chander Pal Marg | 1.5 | 3 |  | 14:04 |  | 100% | 624
F | Total | 58.812 | 117.624
| Grand Total (A+B+C+D+E+F) | 445.24 | 635.55