## As on 27.7.18
PWD Desilting Report (Preparedness for Monsoon)
DESILTING UNDER PWD MAINTENANCE OF EAST ZONE AS ON 27.07.2018
Sl. No. | Name of Road / Drain | Length of Road (Km) | Length of Drain (Km) | Contractor | Date of Start of De-silting | Date of completion (Ist Cycle) | % Drain cleaned (Lengthwise) | Estimate Qty. of silt (cum) | Qty. of silt lifted and disposed off (MT) | EE in charge / Mobile No.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Project Circle
SRD-I Divn.
Name of MLA :- Ms. Alka Lamba | [9 empty] | Er.Suresh Pal (Mob. 9871997722) AE Er. Haider Rizwi ( Mob. No. 8384011059)
Name of Constituency & Constituency No.:- Chandni Chowk AC 20
1 | Road No.- 47 | 1.04 | 1.5 | M/s Shiva Costruction Co. | 14.05.2018 | 30.08.2018 | 40% | 760 cum | 450 MT
2 | Boulevard Road | 1.2 | 1.8 |  | 14.05.2018 | 30.08.2018 | 30%
3 | Rajpur Road | 2.565 | 4.5 |  | 14.05.2018 | 30.08.2018 | 25%
4 | Approach Road | 0.25 | 0.35 |  | 14.05.2018 | 30.08.2018 | 30%
5 | Approach Road | 0.215 | 0.27 |  | 14.05.2018 | 30.08.2018 | 30%
6 | Hamilton Road | 0.24 | 0.3 |  | 14.05.2018 | 30.08.2018 | 30%
7 | Gokhle Road | 0.876 | 1.15 |  | 14.05.2018 | 30.08.2018 | 50%
8 | Sarai Foos Road | 0.71 | 1 |  | 14.05.2018 | 30.08.2018 | 45%
9 | Lothain Road | 1.1 | 1.5 |  | 14.05.2018 | 30.08.2018 | 40%
10 | S.P.M. Marg | 1.48 | 2.1 |  | 14.05.2018 | 30.08.2018 | 40%
11 | HC Sen Road | 0.4 | 0.6 |  | 14.05.2018 | 30.08.2018 | 70%
12 | Khari Bawali Road | 0.427 | 0.6 |  | 14.05.2018 | 30.08.2018 | 50%
13 | Esplanade Road | 0.43 | 0.55 |  | 14.05.2018 | 30.08.2018 | 40%
14 | Naya Bazar Road | 0.58 | 0.65 |  | 14.05.2018 | 30.08.2018 | 60%
15 | Zorawar Singh Marg | 1.32 | 1.9 |  | 14.05.2018 | 30.08.2018 | 35%
16 | Mori Gate Road | 0.38 | 0.5 |  | 14.05.2018 | 30.08.2018 | 25% |  |  |  | 1125
17 | Dewan Hall Road | 0.27 | 0.4 |  | 14.05.2018 | 30.08.2018 | 70%
18 | Chandni Chowk Road | 1.29 | 1.85 |  | 14.05.2018 | 30.08.2018 | 50%
19 | N S Marg | 1.4 | 2 |  | 14.05.2018 | 30.08.2018 | 50%
20 | Jama Masjid Road | 1.481 | 2 |  | 14.05.2018 | 30.08.2018 | -
Name of MLA :- Sh. Asim Ahmed Khan
Name of Constituency & Constituency No.:- Matia Mahal AC 21
21 | Barron Road | 0.28 | 0.38 | M/s Shiva Costruction Co. | 14.05.2018 | 30.08.2018 | 65% | 1040 cum | 675 MT | Er.Suresh Pal (Mob. 9871997722)
22 | Thomson Road | 0.75 | 1.4 |  | 14.05.2018 | 30.08.2018 | 50%
23 | Mir Dard Road | 0.55 | 1.1 |  | 14.05.2018 | 30.08.2018 | 80%
24 | DDU Marg | 1.98 | 3 |  | 14.05.2018 | 30.08.2018 | 80%
25 | Mahawat Khan Road | 1.1 | 2 |  | 14.05.2018 | 30.08.2018 | -
26 | Vishnu Dignamber Marg | 0.32 | 0.6 |  | 14.05.2018 | 30.08.2018 | 80%
27 | Ranjit Singh Road | 0.45 | 0.9 |  | 14.05.2018 | 30.08.2018 | 70%
28 | Minto Road | 0.7 | 1.4 |  | 14.05.2018 | 30.08.2018 | 80%
29 | Mata Sundri Road | 1.1 | 2.2 | M/s Shiva Costruction Co. | 14.05.2018 | 30.08.2018 | 70% | -do- | -do- | AE Er. Ram Sagar Mishra (Mob. No. 9891598094)
30 | Turkman Road | 0.6 | 1.2 |  | 14.05.2018 | 30.08.2018 | 30%
31 | JLN Marg | 1.86 | 3.8 |  | 14.05.2018 | 30.08.2018 | 70%
32 | Kotla Road | 1.48 | 3 |  | 14.05.2018 | 30.08.2018 | 70%
33 | N S Marg | 2.22 | 1.6 |  | 14.05.2018 | 30.08.2018 | 30%
34 | Asaf Ali Marg | 1.9 | 3.6 |  | 14.05.2018 | 30.08.2018 | -
35 | Chaman Lal Marg | 0.18 | 0.2 |  | 14.05.2018 | 30.08.2018 | 80%
SRD-II Divn.
Karol Bagh, Constituency
36 | Panchkuiya Road | 1.28 | 0.75 | M/s Kishan Kumar Mishra | 19-06-2018 | 31-07-2018 | 70% | 1142 | 495 MT | Er. G.L.Sharma (Mob. 7836975727)
37 | Nehru Bazar Road | 0.45 | 0.45 |  | 19-06-2018 | 31-07-2018 | 60%
38 | DAV Aram Bagh Road | 0.46 | 0.39 |  | 19-06-2018 | 31-07-2018 | 65%
39 | Basant Road | 0.77 | 0.77 |  | 19-06-2018 | 31-07-2018 | 65%
40 | Main Bazar Road | 0.95 | - |  | 19-06-2018 | 31-07-2018 | 60%
41 | Chitra Gupta Road | 0.68 | 1.36 |  | 19-06-2018 | 31-07-2018 | 70%
42 | C.G.H.S. Dispansary Road | 0.23 | 0.23 |  | 19-06-2018 | 31-07-2018 | 60%
43 | Desh Bandu Gupta Road | 2.2 | 0.45 |  | 19-06-2018 | 31-07-2018 | 55%
44 | New Rohtak Road | 2.2 | 1.5 |  | 19-06-2018 | 31-07-2018 | 70%
45 | Faiz Road | 1.41 | 0.7 |  | 19-06-2018 | 31-07-2018 | 75%
46 | Rani Jhansi Road | 1.71 | 0.5 |  | 19-06-2018 | 31-07-2018 | 45%
47 | Vallabacharya marg | 0.25 | 0.25 |  | 19-06-2018 | 31-07-2018 | 60%
48 | Link Road | 0.65 | 0.15 |  | 19-06-2018 | 31-07-2018 | 20%
| Ballimaran Constituency |  |  | Sh. Ram Charan Bansal
49 | Chelmsford Road | 0.39 | 0.39 |  | 19-06-2018 | 31-07-2018 | 60% | 290 | 95 MT
50 | Sadar Thana Road | 0.5 | 0.4 |  | 19-06-2018 | 31-07-2018 | 60%
51 | Desh Raj Bhatiya Marg | 0.83 | 0.75 |  | 19-06-2018 | 31-07-2018 | 20%
52 | Ram Kumar Marg | 0.45 | 0.45 |  | 19-06-2018 | 31-07-2018 | 10%
53 | Idgah Road | 1.09 | 1 |  | 19-06-2018 | 31-07-2018 | 50%
54 | G.B. Road | 0.5 | 0.4 |  | 19-06-2018 | 31-07-2018 | 40%
55 | S.N. Marg | 0.95 | 0.8 |  | 19-06-2018 | 31-07-2018 | 20%
56 | Qutub Road | 1.85 | 1.7 |  | 19-06-2018 | 31-07-2018 | 50%
Sadar Bazar Constituency
57 | Azad Market Road | 0.79 | 0.75 |  | 19-06-2018 | 31-07-2018 | 60%
58 | Bahadur Garth Road | 0.91 | 0.85 |  | 19-06-2018 | 31-07-2018 | 10%
59 | Pahari Dheeraj Road | 1.2 | 1.1 |  | 19-06-2018 | 31-07-2018 | 20%
60 | Foota Road | 0.25 | 0.25 |  | 19-06-2018 | 31-07-2018 | 20%
61 | New Rohtak Road | 1 | 0.8 |  | 19-06-2018 | 31-07-2018 | 70%
62 | Gali No. 10 | 0.8 | 0.8 |  | 19-06-2018 | 31-07-2018 | 50%
63 | Arya Samaj Road | 0.8 | 1.45 | Sh. Ram Charan Bansal | 19-06-2018 | 31-07-2018 | - | 1670 | 234.47 MT | Er. G.L.Sharma (Mob. 7836975727)
64 | Road No. 3 | 0.5 | 0.45 |  | 19-06-2018 | 31-07-2018 | 60%
65 | Dyanand Saraswati Marg (Road No. 4) | 0.5 | 0.45 |  | 19-06-2018 | 31-07-2018 | -
66 | Guru Nanak Road (Road No. 5) | 0.9 | 1.65 |  | 19-06-2018 | 31-07-2018 | -
67 | Military Road | 1.4 | 1.65 |  | 19-06-2018 | 31-07-2018 | 75%
68 | Pyare Lal Road | 2 | 3.9 |  | 19-06-2018 | 31-07-2018 | 30%
69 | Hardhyan Singh Road | 1.8 | 3.6 |  | 19-06-2018 | 31-07-2018 | 30%
70 | Padam Singh Road | 0.75 | 1.25 |  | 19-06-2018 | 31-07-2018 | -
71 | Tank Road | 1 | 1 |  | 19-06-2018 | 31-07-2018 | -
72 | Guru Ravi Das Marg | 1.2 | 2.4 |  | 19-06-2018 | 31-07-2018 | 10%
73 | Ajmal Khan Road | 1 | 0.9 |  | 19-06-2018 | 31-07-2018 | -
74 | East Park Road | 0.99 | 0.8 |  | 19-06-2018 | 31-07-2018 | -
75 | S.K. Dass Road | 0.7 | 1.4 |  | 19-06-2018 | 31-07-2018 | -
76 | Abdul Rehman Road | 0.52 | 1.04 |  | 19-06-2018 | 31-07-2018 | -
77 | Abdul Aziz Road | 0.45 | 0.7 |  | 19-06-2018 | 31-07-2018 | -
78 | Elahi Bux Road | 0.415 | 0.93 |  | 19-06-2018 | 31-07-2018 | 60%
79 | Gurudwara Road | 0.5 | 0.5 |  | 19-06-2018 | 31-07-2018 | -
80 | Saraswati Marg | 0.5 | 1 |  | 19-06-2018 | 31-07-2018 | -
81 | Gangeshwar Dham Marg | 0.375 | 0.75 |  | 19-06-2018 | 31-07-2018 | -
82 | D.B Gupta Road | 2.2 | 4.1 |  | 19-06-2018 | 31-07-2018 | 60%
83 | Khajoor Road | 0.32 | 0.32 |  | 19-06-2018 | 31-07-2018 | -
84 | Ganga Mandir Marg | 0.75 | 1.5 |  | 19-06-2018 | 31-07-2018 | -
85 | Vishnu Mandir Marg | 0.9 | 1.8 |  | 19-06-2018 | 31-07-2018 | -
C&ND Circle /C&ND Road Divn.
1 | Main Burari Road | 7.1 | 14.2 | M/s Rajat Construction Co. Agmt. No. 144/EE/C&ND-R/M413/2017-18 | 19.03.2018 | 18.10.2018 | 76% | 15042 | 11500 | Sh. Yadvinder Singh 9717754877
2 | BBM Road from Hakikat Nagar, Red Light to Mukherjee Nagar Bandh | 2.4 | 4.8 |  | 19.03.2018 | 18.10.2018 | 70%
3 | 60ft Road from Aggarwal Sweets to Nulife Hospital between BBM Road and Burari Road | 0.35 | 0.7 |  | 19.03.2018 | 18.10.2018 | 45%
4 | Sant Parmanand Colony Road | 0.9 | 1.8 |  | 19.03.2018 | 18.10.2018 | 95%
5 | Burari Road from Kingsway Camp to Road No. 50 | 3.5 | 7 | M/s Rajat Construction Co. Agmt. No. 144/EE/C&ND-R/M413/2017-18 | 19.03.2018 | 18.10.2018 | 85% | -do- | -do- 1. On Gandhi Vihar A&C Block Outram Lane and Parmanand Colony road there is mass encroachment in form of Ramp/Steps/Berms over the drain maintained by PWD, due to the reason drains can be opened partially, creating a lot of difficults for desilting. 2. The houses/ shops/commercial complex waste water lines, sewer lines of there roads are connected to storm water drain maintained by PWD causing over flowing even in dry time. | Sh. Yadvinder Singh 9717754877
6 | Wazirabad Flyover | 1.06 | No Drain |  | ---- | ---- | ----
7 | Munshi Ram Road | 0.5 | 1 |  | 19.03.2018 | 18.10.2018 | 100%
8 | Parmanand School Road | 0.33 | 0.66 |  | 19.03.2018 | 18.10.2018 | 60%
9 | Swaroop Nagar Road | 2.2 | 4.4 |  | 19.03.2018 | 18.10.2018 | 85%
10 | Police Chowki to Mandir Ortram Lane | 0.44 | 0.88 |  | 19.03.2018 | 18.10.2018 | 60%
11 | Tagore Park Main road | 0.9 | 1.8 |  | 19.03.2018 | 18.10.2018 | 65%
12 | Avtar Singh Marg (Nirankari colony) (Nirankari Colony Gate to culvert Burari Road towards Nirankari Sr. Sec. School) | 1.9 | 3.8 |  | 19.03.2018 | 18.10.2018 | 95%
13 | BBM Road to Jahangirpuri Drain | 0.4 | 0.8 |  | 19.03.2018 | 18.10.2018 | 60%
14 | Gandhi Vihar | 0.67 | 1.34 |  | 19.03.2018 | 18.10.2018 | 75%
15 | Road in Tagore Park from H. No. 213 to Gole Chakkar | 0.45 | 0.9 |  | 19.03.2018 | 18.10.2018 | 60%
16 | Road in tagore Park from H. No. 37 to H. No. 64 | 0.16 | 0.32 |  | 19.03.2018 | 18.10.2018 | 60%
17 | Magazine Road | 1.35 | 2.7 |  | 19.03.2018 | 18.10.2018 | 75%
18 | Road No. -46 | 0.3 | 0.3 |  | 19.03.2018 | 18.10.2018 | 70%
19 | Road No. -45 | 2.5 | 5 |  | 19.03.2018 | 18.10.2018 | 95%
20 | Parallel CC Road | 7.24 | ---- |  | Drain is under the jurisdition of I&FC Deptt.
21 | University Road from Mall Road to Petrol Pump Ward-10 | 1.58 | 3.16 | M/s K.P. Singh & Co. Agmt. No. 146/EE/C&ND-R/M413/2017-18 | 19.03.2018 | 18.10.2018 | 40% This road is under Bonta hills. In first rain silt from hills entered in to drain. | 6250 | 5200 | Sh. Yadvinder Singh 9717754877
22 | Khalsa College road from Mall Road to Roop Nagar (Gurutegh Bahadur Road) | 1.3 | 2.6 |  | 19.03.2018 | 18.10.2018 | 50% The outlet is passing through University Campus. (Shri Ram College).Silt/Debris from Sudhir Bose Marg entered in drain.
23 | Chhatra Marg Road from Mall Road to Malka Gunj Chowk | 1.65 | 3.3 |  | 19.03.2018 | 18.10.2018 | 77%
24 | Shiriya Mishra marg from Jai Jawan Tea Stall to Moris Nagar Thana | 0.42 | 0.84 |  | 19.03.2018 | 18.10.2018 | 30%
25 | Sudhir Bose Marg from chouburjja chowk to ACP Office | 1.25 | 2.5 |  | 19.03.2018 | 18.10.2018 | 30%
26 | Mahatma Gandhii Road (Ring Road) | 1.6 | 3.2 |  | 19.03.2018 | 18.10.2018 | 30%
27 | Road No. 48 | 1.92 | 3.84 |  | 19.03.2018 | 18.10.2018 | 30% Some domestic drains are connected with storm water drain
28 | Vijay Nagar main road from Royal Palace to E-11 Vijay Nagar | 0.75 | 1.5 |  | 19.03.2018 | 18.10.2018 | 90% Some domestic drains are connected with storm water drain
29 | Surjit Singh Marg Camp Chowk to Najafgarh Drain | 0.8 | 1.6 |  | 19.03.2018 | 18.10.2018 | 70% Some domestic drains are connected with storm water drain
30 | Bunglow Road from Roop Nagar round about to Hansraj College T-point on Chattra Marg | 0.65 | 1.3 | M/s K.P. Singh & Co. Agmt. No. 146/EE/C&ND-R/M413/2017-18 | 19.03.2018 | 18.10.2018 | 50% Some domestic drains are connected with storm water drain | -do- | -do- | Sh. Yadvinder Singh 9717754877
31 | Mandelia Road from GT Road to Bunglow Road | 0.7 | 1.4 |  | 19.03.2018 | 18.10.2018 | 60% Some domestic drains are connected with storm water drain.Commercial area wendors had semi permanent structure over manholes. For Food aritcles storm water drain is used as sewer line.
32 | Polo Road from Bhama Shah Road to Shani Mandir (Vijay Nagar) | 0.84 | 1.68 |  | 19.03.2018 | 18.10.2018 | 90% Ramps are constructed over manholes and the-bazari shops are over manholes.
33 | Polo Road from Jahanara Marg to shani Mandir Vijay Nagar | 0.3 | 0.6 |  | 19.03.2018 | 18.10.2018 | 90% Ramps are constructed over manholes and the-bazari shops are over manholes.
34 | Kalyan Vihar Road from 25 Kalyan Vihar to 1 No. Priyadarshni Vihar | 0.9 | 1.8 |  | 19.03.2018 | 18.10.2018 | 90% Some domestic drains are connected with storm water drain
35 | Gurmandi Road from Tripolia gate GT Road to H. NO. 264 Kalyan Vihar | 0.425 | 0.85 | M/s K.P. Singh & Co. Agmt. No. 146/EE/C&ND-R/M413/2017-18 | 19.03.2018 | 18.10.2018 | 90% Some domestic drains are connected with storm water drain. Waste of cattles thrown in to and washing of cattle was done on road daily. | -do- | -do- | Sh. Yadvinder Singh 9717754877
36 | Jahanara Road from Bhamashah Marg to vijay Nagar | 0.83 | 1.66 |  | 19.03.2018 | 18.10.2018 | 90%
37 | Satyawati Marg from Police Station Roop Nagar to Shakti Nagar Chowk | 0.52 | 1.04 |  | 19.03.2018 | 18.10.2018 | 30% Some domestic drains are connected with storm water drainCommercial area wendors had semi permanent structure over manholes. For Food aritcles storm water drain is used as sewer line.
38 | Bhama Shah Road from Mall Road to GT Road Nanak Piao Gurudwara | 1.45 | 1.45 |  | 19.03.2018 | 18.10.2018 | 90% Some domestic drains are connected with storm water drain. Commercial area wendors had semi permanent structure over manholes. For Food aritcles storm water drain is used as sewer line.
39 | G.T. Road from Baraf Khana chowk to Clock Tower | 1.2 | 2.4 |  | 19.03.2018 | 18.10.2018 | 90% Commercial area wendors had semi permanent structure over manholes. For Food aritcles storm water drain is used as sewer line. | -do- | -do- | Sh. Yadvinder Singh 9717754877
40 | Roshnara Road from Pulbanash Metro Station to Hans Raj College. | 2.7 | 5.4 |  | 19.03.2018 | 18.10.2018 | 80% Garreges are permitted on road side shopes washing of vehicles are done on footpath.
41 | GT Road | 1.95 | 1.95 |  | 19.03.2018 | 18.10.2018 | 90%
42 | Inderchand Shastri Marg from Shakti Nagar Chowk to Swami Narayan Marg | 0.9 | 1.8 |  | 19.03.2018 | 18.10.2018 | 0% Commercial area wendors had semi permanent structure over manholes. For Food aritcles storm water drain is used as sewer line
43 | Timarpur road from Mall Road crossing to Wazirabad Crossing | 1.9 | 3.8 |  | 19.03.2018 | 18.10.2018 | 90% Some domestic drains are connected with storm water drain.
44 | Lucknow Road from Mall Road to P.S. Timarpur | 1.7 | 3.4 |  | 19.03.2018 | 18.10.2018 | 90% Some domestic drains are connected with storm water drain.
45 | Ring Road By-pass | 2.9 | 5.8 | M/s Satyam Construction Co. Agmt. No. 04/EE/C&ND-R/M413/2018-19 | 15.04.2018 | 20.06.2018 | 95% | 8021.09 | 7150 | Sh. Yadvinder Singh 9717754877
46 | Sachivalya Road | 1.6 | 3.2 |  | 15.04.2018 | 20.06.2018 | 100%
47 | IP Marg | 0.5 | 1 |  | 15.04.2018 | 20.06.2018 | 100%
48 | IG Slip Road | 0.58 | 1.16 |  | 15.04.2018 | 20.06.2018 | 95%
49 | Velodrome Road | 0.57 | 0.57 |  | 15.04.2018 | 20.06.2018 | 100%
50 | Vikas Marg | 0.5 | 1 |  | 15.04.2018 | 20.06.2018 | 100%
51 | Satyagrah Marg | 0.5 | 1 |  | 15.04.2018 | 20.06.2018 | 100%
52 | Azad Bhawan Road | 0.5 | 1 |  | 15.04.2018 | 20.06.2018 | 90%
53 | Ring Road Bhairon Road T-Jn. to Shanti Van Crossing | 3.7 | 8.4 |  | 15.04.2018 | 20.06.2018 | 100%
54 | JLN Marg (Delhi Gate) | 0.56 | 1.12 |  | 15.04.2018 | 20.06.2018 | 100%
55 | Ghata Masjid Road | 0.26 | 0.52 |  | 15.04.2018 | 20.06.2018 | 90%
56 | Bahadur Shah Zafar Marg | 2 | 4 |  | 20.04.2018 | 25.06.2018 | 90%
57 | Ring Road By-pass | 2.65 | 5.3 |  | 20.04.2018 | 25.06.2018 | 95%
58 | Court Road | 1.75 | 3.5 |  | 20.04.2018 | 25.06.2018 | 95%
59 | Club Road | 1.75 | 3.5 |  | 20.04.2018 | 25.06.2018 | 95%
60 | Under Hill Road | 0.69 | 1.38 |  | 20.04.2018 | 25.06.2018 | 95%
61 | Flag Staff Road | 0.43 | 0.85 |  | 20.04.2018 | 25.06.2018 | 100%
62 | Shamnath Marg | 1.3 | 1.3 |  | 20.04.2018 | 25.06.2018 | 90%
63 | Rajniwas Marg | 0.93 | 1.852 |  | 20.04.2018 | 25.06.2018 | 95%
64 | CNG Crematorium Road | 0.25 | 0.5 |  | 20.04.2018 | 25.06.2018 | 95%
65 | Ring Road | 2 | 4 |  | 07.04.2018 | 20.05.2018 | 95%
66 | Mahatma Gandhi Road | 4 | 8 |  | 07.04.2018 | 20.05.2018 | 95%
67 | Nishad Raj Marg | 0.55 | 1.1 |  | 07.04.2018 | 20.05.2018 | 90%
| Total | 93.355 | 165.522
Shahdara Circle /Shahdara Road Divn. (M-211)
1 | Road No 56 | 5.6 | 4 | Sh. Devender Singh Malik | 10.04.2018 | 30.07.2018 | 100% | 2200 | 1977.77 | Er. Prakash Rawat Mobile no- 9446515711
2 | Road No. 71 | 1.6 | 1.6 |  | 10.04.2018 | 30.07.2018 | 90%
3 | Road No. 71 A | 0.6 | 0.6 |  | 10.04.2018 | 30.07.2018 | 60%
4 | Road No. 56 A | 1 | 2 |  | 10.04.2018 | 30.07.2018 | 90%
5 | G.T Road | 6.35 | 6.35 |  | 09.04.2018 | 30.07.2018 | 60% | 2400 | 100
| G.T Road Railway under bridge near Metro Station Shahdara | 0.176 | 0.176 |  | 09.04.2018 | 30.07.2018 | 50%
| G.T Road Railway under bridge near Railway Station Shahdara | 0.214 | 0.214 |  | 09.04.2018 | 30.07.2018 | 50%
6 | Gandhi Nagar Road | 1.5 | 3 |  | 09.04.2018 | 30.07.2018 | 50%
7 | Road No 58 | 2.84 | 5.68 | M/s Sharma Construction Co | 10.06.2018 | 30.07.2018 | 60% | 6300 | 1500
8 | Road No 58 A | 1.6 | 3.2 |  | 10.06.2018 | 30.07.2018 | 40%
9 | Shaheed Bhagat Singh Marg | 1.4 | 2.8 |  | 20.05.2018 | 30.07.2018 | 74%
10 | Peripherial Road | 1.35 | 2.7 |  | 20.05.2018 | 30.07.2018 | 75%
11 | Shrestha Vihar Road | 1.25 | 2.5 |  | 20.05.2018 | 30.07.2018 | 58%
12 | Surajmal Vihar Market Road | 1.2 | 2.4 |  | 20.05.2018 | 30.07.2018 | 54%
13 | Zonal office Road. | 1.03 | 2.06 |  | 20.05.2018 | 30.07.2018 | 90%
14 | Road No 72 Extn. | 1 | 2 |  | 05.04.2018 | 30.07.2018 | 85%
15 | Road No 72 | 0.91 | 1.82 |  | 05.04.2018 | 30.07.2018 | 58%
16 | Shiva Khand Road | 0.9 | 1.8 |  | 20.05.2018 | 30.07.2018 | 54%
17 | Rishabh Vihar Road | 0.65 | 1.3 |  | 20.05.2018 | 30.07.2018 | 74%
18 | Sant Lal Gupta Marg | 0.617 | 1.23 |  | 20.05.2018 | 30.07.2018 | 58%
19 | Link Road (GT Road to Vivek Vihar ITI) | 0.6 | 1.2 |  | 20.05.2018 | 30.07.2018 | 54%
20 | E.S.I. Hospital Road | 0.45 | 0.9 |  | 20.05.2018 | 30.07.2018 | 50%
21 | Road along B-Block Jhilmil | 0.355 | 0.71 |  | 20.05.2018 | 30.07.2018 | 52%
22 | Road from Booster pumping station DJB opp. B-Block to A-Block market | 0.3 | 0.6 |  | 20.05.2018 | 30.07.2018 | 68%
23 | Road along A-Block Jhilmil Colony | 0.188 | 0.376 |  | 20.05.2018 | 30.07.2018 | 58%
24 | Road No. 57 (Jagatpuri Chowk to Telco-xing) | 3 | 1.5 |  | 20.04.18 | 30.07.2018 | 20% | 2250 cum | 350 | (i) Work rescinded vide letter No. 3672 dated 18.07.2018. Balance work tender to be opened on 30.07.2018 Er. Prakash Rawat Mobile no- 9446515711
25 | Road No. 57 (Jagatpuri Chowk to Bihari Colony) | 2.52 | 2.1 |  | 10.05.18 | 30.07.2018 | 20%
26 | Road No. 75B (Karkari more to Road No. 58A) | 2.13 | 4 |  | 20.05.18 | 30.07.2018 | 15%
27 | Vishwas Nagar 60' Road | 1.17 | 2.34 |  | 28.05.18 | 30.07.2018 | 50%
28 | Shahdara Road from Drain No.1 to Dhalao Snatan Dharam School, Bhola Nath Nagar | 0.6 | 0.9 |  | 28.05.18 | 30.07.2018 | 25%
29 | Bhola Nath Nagar (Railway line to Baburam School | 0.6 | 0.6 |  | 28.05.18 | 30.07.2018 | 30%
30 | Shalimar park extension road (Shahdara road to H. N. 4/29830 | 0.2 | 0.4 |  | 28.05.18 | 30.07.2018 | 0%
31 | DCP Office Road ( DCP office to Shahdara road) | 0.112 | 0.2 |  | 28.05.18 | 30.07.2018 | 0%
32 | Road No. 68 (Road No. 69 to Railway Line Nand Nagri) | 2.2 | 4 |  | 20.04.18 | 30.07.2018 | 30% | 4968 cum | 900 | (ii) Work rescinded vide letter No. 3673 dated 18.07.2018. Balance work tender to be opened on 30.07.2018 Er. Prakash Rawat Mobile no- 9446515711
33 | Loni Road G.T. Road to Loni Gole Chakkar | 2.894 | 5.6 |  | 10.05.18 | 30.07.2018 | 45%
34 | Main Road LIG Flats, East of Loni Road from Loni Road to community centre Ashok Nagar. | 0.375 | 0.7 |  | 10.05.18 | 30.07.2018 | 15%
35 | Main Road LIG flats, Loni Road to Govt. S.S. School Ashok Nagar. | 0.275 | 0.5 |  | 10.05.18 | 30.07.2018 | 20%
36 | Mandoli Road | 1.942 | 3.8 |  | 10.05.18 | 30.07.2018 | 0%
37 | Road No. 65 (Keshav Chowk to Road No.66 T) | 1.2 | 2 |  | 10.05.18 | 30.07.2018 | 15%
38 | Babarpur Road (From Road No.66 to G.T. Road) | 2 | 4 |  | 10.05.18 | 30.07.2018 | 65%
39 | Divider Road from Seemapuri road to Road No. 64 (near SDN Hospital) | 2.4 | 4.8 | Vinod Kumar | 21.05.2018 | 30.07.2018 | 60% | 6200 cum | 4300 MT | Er. Prakash Rawat mobile no- 9446515711
40 | Gurudwara Road from DTC bus depot Road No. 70 to GTB Hospital road | 1.75 | 3.5 |  | 16.05.2018 | 30.07.2018 | 85%
41 | Road No. 62 (Road No. 70 to Apsara Border) | 1.2 | 2.4 |  | 01.05.2018 | 30.07.2018 | 40%
42 | Road No. 70 (Seemapuri to Tahir Pur T-Point) | 1.2 | 2.4 |  | 01.05.2018 | 30.07.2018 | 50%
43 | New Seemapuri Road from Road No. 64 (Mother Dairy) to Road No. 62 near maszid | 1.16 | 2.32 |  | 21.05.2018 | 30.07.2018 | 20%
44 | Seemapuri Road from Road No. 62 to 64 | 1.065 | 2.13 |  | 16.04.2018 | 30.07.2018 | 75%
45 | Road from LIC Colony (T-Point to rotary at Telephone Exchange) | 0.935 | 1.87 |  | 21.05.2018 | 30.07.2018 | 55%
46 | Road from T-point, L-pocket to R Block small rotary | 0.86 | 1.72 |  | 16.05.2018 | 30.07.2018 | 45%
47 | GTB Hospital Road (From GT Road to Aggarwal Sweet Dilshad Garden) | 0.6 | 1.2 |  | 10.05.2018 | 30.07.2018 | 30%
48 | R-Block Road (From Divider road Agarwal sweet to GT Road) | 0.5 | 1 |  | 10.05.2018 | 30.07.2018 | 60%
49 | Road from GT Road to Road No. 64 via Telephone exchange | 0.415 | 0.83 |  | 21.05.2018 | 30.07.2018 | 25%
50 | Road infront of Hans Raj Public School (Divider Road to Gurudwara road) | 0.365 | 0.73 |  | 09.04.2018 | 30.07.2018 | 60%
51 | Road from Divider road to Gurudwara road near pummy sweet | 0.36 | 0.72 |  | 09.04.2018 | 30.07.2018 | 70%
52 | Road from Divider Road (Mukherjee Public School to Sant Ram Public School at Gurudwara road) | 0.36 | 0.72 |  | 09.04.2018 | 30.07.2018 | 85%
53 | LIC Road (from Malaria office MCD to GT Road) | 0.33 | 0.66 |  | 09.04.2018 | 30.07.2018 | 95%
54 | Road No. 62 (J & K pocket) to petrol pump GT Road (infront of Red Crosss society). | 0.33 | 0.66 | Vinod Kumar | 10.05.2018 | 30.07.2018 | 55% | -do- | -do- | Er. Prakash Rawat Mobile no- 9446515711
55 | Road from Gurudwara road (T-point of Kalander Colony) to Gauri Shankar Mandir | 0.31 | 0.62 |  | 09.04.2018 | 30.07.2018 | 80%
56 | Road from General Hospital (Road No. 64 to Shahdara Flyover) | 0.26 | 0.52 |  | 21.05.2018 | 30.07.2018 | 0%
57 | CNG Petrol Pump to deer park (Divider road) west side | 0.2 | 0.4 |  | 16.04.2018 | 30.07.2018 | 75%
58 | CNG Petrol Pump to deer park (Divider road) east side | 0.197 | 0.394 |  | 21.05.2018 | 30.07.2018 | 60%
59 | GTB Hospital road from Red light to Agarwal sweet (Divider road) | 0.195 | 0.39 |  | 21.05.2018 | 30.07.2018 | 0%
60 | Road No. 64 (Swami Dayanand Hospital to DLF More (U.P. Border) | 3 | 6 |  | 1.05.2018 | 30.07.2018 | 70% | 5778 cum | 5500MT
61 | Road No. 68 (Road No. 69 to Railway Line Nand Nagri) | 1.4 | 2.8 |  | 1.05.2018 | 30.07.2018 | 80%
62 | Tanga Stand Road from road no. 68 to Wazirabad Road. | 1.25 | 2.5 |  | 1.05.2018 | 30.06.2018 | 100%
63 | Road No. 69 (Road No. 63 to Road No. 64 (T-point)) | 1.2 | 2.4 |  | 1.05.2018 | 30.07.2018 | 80%
64 | From Rajiv Gandhi super hospital speciality hospital to GTB hospital road | 0.95 | 1.9 |  | 1.05.2018 | 30.07.2018 | 80%
65 | GTB Road (From Road No. 64 to Road No. 68) | 0.91 | 1.82 |  | 1.05.2018 | 30.06.2018 | 100%
66 | From Road No. 69 MIG Flat to GTB Hospital Road Via Nutan Vidya Mandir public school | 0.9 | 1.8 |  | 1.05.2018 | 30.06.2018 | 100%
67 | Captain Javed Ali Marg | 0.84 | 1.68 |  | 1.05.2018 | 30.07.2018 | 10%
68 | From Road No. 68 (petrol pump) to E-pocket GTB enclave police booth near Nutan Vidya Mandir public school | 0.375 | 0.75 | Vinod Kumar | 1.05.2018 | 20.06.2018 | 100% | -do- | -do- | Er. Prakash Rawat mobile no- 9446515711
69 | Road along khel parisor from NVM school to Green field public school. | 0.25 | 0.5 |  | 1.05.2018 | 30.07.2018 | 70%
Circle / Divn. :- East-M / East Road (M-212)
Name of MLA :- Sh. Manoj Kumar
Name of Constituency :- Kondli AC (56)
1 | Road from Live stock market to Gali No. 7 Block - C in Ghazipur Dairy Farm. | 0.8 | 1.6 | M/s Shiva Construction Co. | 18.05.2018 | 31.07.2018 | Continuous process to remove the gobar from drain by JCB | 6955.2 | 2100 | Sh. Iqbal Singh 9910925748
2 | NH-24 Ghazipur to Kondli Bridge. | 1.5 | 3 |  | 18.05.2018 | 31.07.2018
3 | Road from NH-24 to Hindon cut near Ghazipur Slaughter House. | 0.5 | 1 |  | 18.05.2018 | 31.07.2018 | - | 11717
4 | Dharamshilla Road | 0.6 | 1 |  | 18.05.2018 | 31.07.2018 | 5%
5 | Saheed Budh Singh Marg | 0.28 | 0.56 |  | 18.05.2018 | 31.07.2018 | 50%
6 | Dallupura Road | 1.25 | 2.5 |  | 18.05.2018 | 31.07.2018
7 | M.P. Road No. 102 | 2.2 | 4.4 |  | 18.05.2018 | 31.07.2018 | 45%
8 | M.P Road No. 108 | 1.33 | 2.66 |  | 18.05.2018 | 31.07.2018 | 2%
9 | M.P Road 109 | 0.81 | 1.62 |  | 18.05.2018 | 31.07.2018 | 40%
10 | Road from Kondli Village up Gharoli Village X-ing. | 0.75 | 1.5 |  | 18.05.2018 | 31.07.2018 | 80%
11 | Road along Shiv Mandir in Gharoli Dairy Farm 'B' Block. | 0.66 | 1.32 |  | 18.05.2018 | 31.07.2018 | 90%
12 | EWS Flats to DDA Market Mayur Vihar Ph.-III X-ing upto Agarwal Sweet Shop. | 0.66 | 1.32 |  | 18.05.2018 | 31.07.2018 | 90%
13 | Main road between A & B Block New Kondli. | 0.35 | 0.7 |  | 18.05.2018 | 31.07.2018 | 40%
14 | Road from High land Apptt. To Soochna Apptt. In Vasundhara Enclave. | 0.4 | 0.8 |  | 18.05.2018 | 31.07.2018
15 | Road from Manav Ashray Apptt. To Hindon Apptt. In Vasundhara Enclave | 0.48 | 0.96 | M/s Shiva Construction Co. | 18.05.2018 | 31.07.2018 |  | -do- | -do- | Sh. Iqbal Singh 9910925748
16 | Road from Dashmesh Public School to Delux Apptt. Via Mahesh Apptt. In Vasundhara Enclave. | 0.75 | 1.5 |  | 18.05.2018 | 31.07.2018 | 35%
17 | Bhagvan Mahavir Swami Marg. | 0.8 | 1.6 |  | 18.05.2018 | 31.07.2018
18 | Sameer Bhan Marg | 0.825 | 1.5 |  | 18.05.2018 | 31.07.2018 | 26%
19 | Road from Cell Apartment to Angel Public School in Vasundhara Enclave. | 0.2 | 0.4 |  | 18.05.2018 | 31.07.2018
20 | Road from Dainik Janyug Apartment to Hindon Apartment (Budh Singh Marg). | 0.5 | 1 |  | 18.05.2018 | 31.07.2018 | 30%
21 | From Kondli Bridge to Porta Cabin MCD Primary School. | 0.85 | 1 |  | 18.05.2018 | 31.07.2018 | 30%
22 | Road between Pocket A-1 & A-2 Mayur Vihar Ph-III (Gurudwara Road) | 0.26 | 0.52 |  | 18.05.2018 | 31.07.2018
23 | Road between Block No. 12 and 13 from Khichripur Chowk to Kalyanvas Road. | 0.75 | 1.5 |  | 18.05.2018 | 31.07.2018 | 80%
24 | Road between Block No. 11-15 from Block-15 to LBS Hospital through Jalebi Chowk, Kalyanpuri. | 0.67 | 1.34 |  | 18.05.2018 | 31.07.2018 | 50%
25 | Road from between Block No. 2 & 3 upto Khichripur Main Road. | 0.3 | 0.3 |  | 18.05.2018 | 31.07.2018
26 | Khichripur road from Kondli Bridge to Mother Dairy. | 1 | 0.7 |  | 18.05.2018 | 31.07.2018 | 70%
Name of MLA :- Sh. Raju Dhingan
Name of Constituency :- Trilokpuri AC (55)
27 | Kotla Road from Trilok Puri Police Station to Khichirpur Bus Stand. | 3 | 6 | M/s Shiva Construction Co. | 18.05.2018 | 31.07.2018 | 55% | 14276 Cum | 4000 MT | Sh. Iqbal Singh 9910925748
28 | East end apartment road. | 0.84 | 1.68 |  | 18.05.2018 | 31.07.2018 | 20%
29 | Road along Ghazipur Drain | 3.6 | 3.6 |  | 18.05.2018 | 31.07.2018 | 55%
30 | Peripherial road from Chilla Chowk to kotla Village. | 1.25 | 1.5 |  | 18.05.2018 | 31.07.2018 | 55%
31 | Road from Block No. 35 to 17 Trilokpuri (Mahrishi Balmiki Marg) | 1.07 | 1.07 |  | 18.05.2018 | 31.07.2018
32 | Road from Block No. 19 to Block No. 13 Trilokpuri | 1.54 | 3.08 |  | 18.05.2018 | 31.07.2018 | 25%
33 | Main road from Block No. 33 to Block No. 19. Trilokpuri | 0.52 | 0.52 |  | 18.05.2018 | 31.07.2018
34 | Road from Block No. 36 to Block No. 31 Trilokpuri. | 0.99 | 1.98 |  | 18.05.2018 | 31.07.2018 | 20%
35 | Ambedkar Marg from Block No. 18 Trilokpuri to Kotla Road. | 0.95 | 1.9 |  | 18.05.2018 | 31.07.2018
36 | Subhash Mkt. from Chand Cinema Turn to Balvikas School | 0.6 | 1.2 |  | 18.05.2018 | 31.07.2018 | 70%
37 | Road from Block No. (1) to (11) of Trilokpuri | 0.98 | 1.25 |  | 18.05.2018 | 31.07.2018 | 30%
38 | Chilla road from Chilla chowk to Chilla Village. | 0.9 | 1.8 |  | 18.05.2018 | 31.07.2018 | 75%
Name of MLA :- Sh. Manish Sisodia
Name of Constituency :- Patparganj (57)
39 | Sadhabhawana Marg (111) | 0.75 | 1.5 | M/s Shiva Construction Co. | 18.05.2018 | 31.07.2018 | 55% | -do- | -do- | Sh. Iqbal Singh 9910925748
40 | Club Avenue Marg (112) | 0.45 | 0.9 |  | 18.05.2018 | 31.07.2018 | 20%
41 | Sehkarita Marg (113) | 0.65 | 1.3 |  | 18.05.2018 | 31.07.2018 | 50%
42 | ASN School to Parwana Apartment to Kala Apartment upto LSC. | 0.8 | 0.8 |  | 18.05.2018 | 31.07.2018
43 | Samachar Apartment Road (Link Road) Samachar Apartment to Glaxo Apartment. | 0.35 | 0.7 |  | 18.05.2018 | 31.07.2018 | 50%
44 | Road from Block No. 1 Khichripur to NH-24. | 0.85 | 1.7 |  | 18.05.2018 | 31.07.2018 | 70%
45 | Khichripur Main Road from NH-24 to Mother Dairy. | 0.8 | 1.6 |  | 18.05.2018 | 31.07.2018 | 50%
46 | Patparganj Main Road from NH-24 to Patparganj Village. | 0.3 | 0.6 |  | 18.05.2018 | 31.07.2018
47 | Road between Pocket E & F Mayur Vihar Ph-II. | 0.6 | 1.2 |  | 18.05.2018 | 31.07.2018
48 | Road from NH-24 to DJB Office,Mayur Vihar Ph2 | 0.9 | 1.5 |  | 18.05.2018 | 31.07.2018
49 | Road from T-point Mayur vihar ph2 to chand Cinema crossing,kalyanvas road | 1.7 | 2.5 |  | 18.05.2018 | 31.07.2018 | 60%
50 | Road infront of LBS Hospital (from Kalyanvas road to main market khichripur road) | 0.5 | 0.75 |  | 18.05.2018 | 31.07.2018
Name of Constituency :- Patparganj (57)
51 | Sai Chowk | 0.67 | 0.67 | M/s Shiva Construction Co. | 23.04.2018 | Ist Cycle to be completed by July 31, 2018 | 5% | 11582 Cum | 2025 M.T | Sh. Iqbal Singh 9910925748
52 | Kailash Apartment. | 0.354 | 0.354 |  | 23.04.2018 |  | -
53 | Bathla Apartment | 0.328 | 0.328 |  | 23.04.2018 |  | 10%
54 | Gagan Vihar. | 0.4 | 0.4 |  | 23.04.2018 |  | 60%
55 | Agarsain Apartment | 0.61 | 0.61 |  | 23.04.2018 |  | -
56 | Mother Dairy Road (Narwana Road) | 2.5 | 2.5 |  | 23.04.2018 |  | 45%
57 | Patparganj Road (Madhuban Chowk) | 2.8 | 2.8 | M/s Shiva Construction Co. | 23.04.2018 | Ist Cycle to be completed by July 31, 2018 | 40% | -do- | -do- | Sh. Iqbal Singh 9910925748
58 | Madhu Vihar Road | 1.6 | 1.6 |  | 23.04.2018 |  | -
59 | Balco Market | 0.63 | 0.63 |  | 23.04.2018 |  | -
60 | Prince Apartment | 0.59 | 0.59 |  | 23.04.2018 |  | -
61 | Oriental Apartment | 0.334 | 0.334 |  | 23.04.2018 |  | -
62 | Narwana Apartment | 0.46 | 0.46 |  | 23.04.2018 |  | 80%
63 | Trilokia Apartment | 0.38 | 0.38 |  | 23.04.2018 |  | 80%
64 | Rama Krishna Apartment | 0.27 | 0.27 |  | 23.04.2018 |  | 80%
65 | Disused canal road (Main Drain with EDMC) | 2.9 | 2.9 |  | 23.04.2018 |  | 70%
66 | New Rajdhani Road | 0.79 | 0.79 |  | 23.04.2018 |  | 60%
67 | Chitra Vihar Road | 0.69 | 0.69 |  | 23.04.2018 |  | 70%
68 | Patparganj Road | 2.89 | 2.89 |  | 23.04.2018 |  | 60%
69 | Vikas Marg (Road No. 75 A & 75 B) | 3.14 | 3.14 |  | 23.04.2018 |  | 40%
70 | Preet Vihar | 1.47 | 1.47 |  | 23.04.2018 |  | 10%
71 | ROB-36 | 1.3 | 1.3 |  | 23.04.2019 |  | 30%
NE Circle/NE Road Divn.
1 | Road No. 66 (Seelampur Red Light on G.T. Road to Moujpur Red Light) | 2.1 | 3 | Sh. Rajneesh 08/EE/CRMD/M-213/2018-19 | 13.05.2018 | 15.08.2018 (Desilted drains again filled up due to regular coming of cow-dung (Gobar), silt and floating materials from EDMC internal drains to PWD drains. Result desilted drain again filled up with silt etc. Will takeup again in Second Cycle.) | 50% | 350 | 210 | Sh. Pratap Singh 9910435151
2 | Main Road Maujpur (Ghonda Chowk to Red Light on Road No.-66) | 0.999 | 3 |  |  |  | 60% | 450 | 324
3 | Road No. 66 (Moujpur Red Light to Gokalpuri Flyover) | 1.5 | 2 |  |  |  | 50% | 400 | 240
4 | Sewadham Road ( Nand Nagri Red Light on Road No. 63 to U.P. Border) | 2.45 | 4.9 |  |  |  | 55% | 735 | 485
5 | Main Brahmpuri Road (Ghonda Chowk to Brahampuri Dhalav) | 1.84 | 3.68 |  |  |  | 60% | 1380 | 994
6 | Road No. 59 ( Part of Wazirabad Road) Loni Gole Chakkar to Khajuri Chowk) | 3.45 | 7 |  |  |  | 70% | 2480 | 2083
7 | Tanki Road (DTC Depot dividing road to Tikona park Subhash Vihar Water Tank) | 0.65 | 1.3 | Sh. Jitender Kumar 05/EE/CRMD/M-213/2018-19 | 20.04.2018 | 15.08.2018 | 60% | 528 | 380 | Sh. Pratap Singh 9910435151
8 | Yamuna Vihar Road (C-1 to C-4) | 1.1 | 2.2 |  |  |  | 60% | 891 | 642
9 | Yamuna Vihar Road C block Service Road (From gokalpuri Flyover to Bhajanpura Petrol Pump) | 1.7 | 1.7 |  |  |  | 65% | 21 | 16
10 | Yamuna Vihar Dividing road (Wazirabad Road Yamuna Vihar Red Light to DTC Depot near H. No. B-5/18, Yamuna Vihar, Delhi) | 0.5 | 1 |  |  |  | 60% | 405 | 292
11 | Main Road Noor –E-Illahi Road (DTC Depot Yamuna Vihar to Ghonda Chowk) | 0.98 | 1.96 |  |  |  | 60% | 720 | 518
12 | Road No. 63 ( Part of Wazirabad Road) Bhopura Border (U.P.) to Loni Flyover near Loni Gole Chakkar | 3.18 | 6.36 |  |  |  | 60% | 2290 | 1649
13 | Loni Road G.T. Road to U.P. Border (Loni gole Chakkar to U.P. Border (Loni)) | 0.5 | 1 |  |  |  | 70% | 75 | 63
14 | Gokulpuri Main Road (Wazirabad Road H. No. A-1 to Gokulpuri H. No. B-22) | 0.246 | 0.5 |  |  |  | 65% | 265 | 207
15 | Bank Colony Road along western Side of Mandoli Jail Complex (Mandoli Bank Colony to Harsh Vihar Colony.) | 0.337 | 0.5 |  |  |  | 60% | 50 | 36
16 | Shastri Park To Khajuri Chowk | 3.75 | 3.75 | Sh. Jitender Kumar 18/EE/CRMD/M-213/2018-19 | 19.06.2018 | 15.08.2018 | 60% | 710 | 511 | Sh. Pratap Singh 9910435151
17 | Gamri Road | 1.05 | 1.05 |  |  |  | 65% | 1800 | 1404
18 | E.A. Road | 4.2 | 3.3 |  |  |  | 60% | 400 | 288
19 | Seelmapur Road from Road No. 66 to Dhalav. | 0.52 | 0.517 |  |  |  | 62% | 580 | 432
20 | G.T. Road Old Yamuna bridge to Y Point | 0.9 | 0.9 |  |  |  | 60% | 620 | 446
21 | Gurudwara Road | 0.3 | 0.3 |  |  |  | 65% | 400 | 312
22 | Zero Pusta to Bharampuri culvert | 0.99 | 0.99 |  |  |  | 65% | 1320 | 1030