## Sheet1
PWD Desilting Report (Preparedness for Monsoon)
DESILTING REPORT UNDER PWD MAINTENANCE SOUTH ZONE
As on 27.07.2018
Sl. No. | Name of Road / Drain | Length of Road (Km) | Length of drain (km) | Contractor | Date of Start of De-Siliting | Date of Completion | Date of completion | % Drain cleaned (Lengthwise) | Target date of completion of 2nd cycle | Estimate Qty. of silt (cum) | Qty. of silt lifted and disposed off (cum) | EE in charge / Mobile No. | Remarks
1 | 2 | 3 |  | 4 | 5 | 6 | 6 | 7 | 9 | 8 | 9 | 10 | 11
1)-South-West Circle
South West Road-1 Division
1 | B.J. Marg | 1.3 | 2 | M/s Shatrughna Construction Co M/s WORKCEE | 26.03.18 | 15.07.2018 | 31.07.2018 | 65% | 0 | 560 | 269 | Er. S.K. Sinha/ 9958469778 | Due to encroachment the work could not be completed. 2nd cycle in progress. It is not possible to desilt drain properly where mixed flow in storm water drain.
2 | Rao Tula Ram Marg (RTR Marg) | 1.7 | 3.6 |  | 26.03.18 | 15.07.2018 | 31.07.2018 | 82% | 0 | 450 | 288
3 | Zonal road No. 2 (Baba Balak Nath Marg) | 1.1 | 2.2 |  | 26.03.18 | 15.07.2018 | 31.07.2018 | 75% | 0 | 580 | 325
4 | Zonal Road No. 6 (Hare Krishna Mehto Marg) | 0.7 | 0.5 |  | 26.03.18 | 15.07.2018 | 31.07.2018 | 78% | 0 | 310 | 174
5 | Outer Ring Road | 4.8 | 6.3 |  | 26.03.18 | 15.07.2018 | 31.07.2018 | 72% | #VALUE! | 1060 | 594
6 | Babu Genu Marg, R.K.Puram | 0.6 | 1.4 |  | 26.03.18 | 15.07.2018 | 31.07.2018 | 90% | 0 | 185 | 133 |  | 2nd cycle in progress. It is not possible to desilt drain properly where mixed flow in storm water drain.
7 | Nelson Mandela Marg | 4.04 | 5.8 |  | 26.03.18 | 15.07.2018 | 31.07.2018 | 85% | 0 | 1600 | 1088
8 | Baba Gang Nath marg | 1.17 | 2.3 |  | 26.03.18 | 15.07.2018 | 31.07.2018 | 85% | 0 | 670 | 456
9 | Major Som nath marg | 1.6 | 1.6 |  | 26.03.18 | 15.07.2018 | 31.07.2018 | 77% | 0 | 80 | 48
10 | Africa Avenue (Road No.9) | 2.2 | 4.2 | M/s WORKCEE & M/s Samridhi Construction | 26.03.18 | 15.07.2018 | 31.07.2018 | 90% | 0 | 280 | 190
11 | Kafi Azami Marg | 0.9 | 1.2 |  | 26.03.18 | 15.07.2018 | 31.07.2018 | 90% | 0 | 168 | 108
12 | Church Road, R.K.Puram | 0.85 | 1.6 |  | 26.03.18 | 15.07.2018 | 31.07.2018 | 70% | 0 | 224 | 125
13 | Vivekanand Marg | 1.1 | 3.2 |  | 26.03.18 | 15.07.2018 | 31.07.2018 | 70% | 0 | 539 | 302
14 | Venketeshwar Marg | 1.1 | 1.5 |  | 25.04.2018 | 15.07.2018 | 31.07.2018 | 80% | 0 | 245 | 157
15 | Ring Road | 5 | 5 |  | 25.04.2018 | 15.07.2018 | 31.07.2018 | 70% | 0 | 980 | 549
16 | Kama Koti Marg | 1.75 | 1.6 |  | 20.04.2018 | 15.07.2018 | 31.07.2018 | 50%
17 | Prem nath Dogra marg, R.K.Puram | 0.85 | 1 |  | 20.04.2018 | 15.07.2018 | 31.07.2018 | 60%
18 | Tamil Sangam Marg | 1.1 | 1 |  | 20.04.2018 | 15.07.2018 | 31.07.2018 | 65% | 0 | 168 | 54 |  | Due to encroachment the work could not be completed. 2nd cycle in progress. It is not possible to desilt drain properly where mixed flow in storm water drain.
19 | A-9 Street Road | 0.65 | 1 |  | 20.04.2018 | 15.07.2018 | 31.07.2018 | 40%
20 | Basant Marg-II | 0.5 | 1.4 |  | 20.04.2018 | 15.07.2018 | 31.07.2018 | 60%
21 | Paschimi Marg | 1.25 | 1.4 |  | 20.04.2018 | 15.07.2018 | 31.07.2018 | 60%
22 | Poorvi Marg | 1.65 | 1.4 |  | 20.04.2018 | 15.07.2018 | 31.07.2018 | 70% | #VALUE! | 56 | 18
23 | Ganga Ram Hospital Road | 1.08 | 2.1 | M/S Sai Tube Well Shri Rajpal Sehgal | 20.04.2018 | 15.07.2018 | 31.07.2018 | 76% | 0 | 295 | 177 | Er. S.K. Sinha/ 9958469778 | 2nd cycle in progress. It is not possible to desilt drain properly where mixed flow in storm water drain.
24 | PUSA Road | 2 | 1.6 |  | 25.03.18 | 15.07.2018 | 31.07.2018 | 76% | 0 | 540 | 324
25 | Shankar Road | 1.64 | 2.2 |  | 25.03.18 | 15.07.2018 | 31.07.2018 | 80% | 0 | 250 | 160
26 | Dr. K.S. Krishanan Marg | 0.915 | 1.8 |  | 25.03.18 | 15.07.2018 | 31.07.2018 | 80% | 0 | 250 | 160
27 | PUSA Institute (IARI) Internal Road | 0.7 | 0.7 |  | 25.03.18 | 15.07.2018 | 31.07.2018 | 80% | 0 | 200 | 128
28 | Dev Prakash Shastri marg (Road No. 25) | 4.45 | 8.8 |  | 25.03.18 | 15.07.2018 | 31.07.2018 | 70% | 0 | 1200 | 672
29 | Girdhari Lal Goswami Marg (Road No. 89) | 3.65 | 6 |  | 25.03.18 | 15.07.2018 | 31.07.2018 | 74% | 0 | 1100 | 616
30 | O.P. Bharti Marg 1 | 0.535 | 3.76 |  | 25.03.18 | 15.07.2018 | 31.07.2018 | 85% | 0 | 150 | 102
31 | O.P. Bharti Marg 2 | 0.762 |  |  | 25.03.18 | 15.07.2018 | 31.07.2018 |  | 0 | 205 | 139
32 | O.P. Bharti Marg 3 | 0.181 |  |  | 25.03.18 | 15.07.2018 | 31.07.2018 |  | 0 | 50 | 34
33 | O.P. Bharti Marg 4 | 0.42 |  |  | 25.03.18 | 15.07.2018 | 31.07.2018 |  | 0 | 120 | 82
34 | Guru Ravi Dass Marg | 0.8 | 1.1 |  | 25.03.18 | 15.07.2018 | 31.07.2018 | 61% | 0 | 215 | 103
35 | Ganga Mandir Marg | 0.75 | 1.4 |  | 25.03.18 | 15.07.2018 | 31.07.2018 | 61% | 0 | 210 | 101
36 | Vishnu Mandir Marg | 0.6 | 1.2 |  | 25.03.18 | 15.07.2018 | 31.07.2018 | 70% | 0 | 160 | 90
37 | Saraswati Marg | 0.5 | 1 |  | 25.03.18 | 15.07.2018 | 31.07.2018 | 70% | 0 | 150 | 84
38 | Ajmal Khan Road | 0.6 | 1 |  | 25.03.18 | 15.07.2018 | 31.07.2018 | 72% | 0 | 165 | 92
39 | Gurudwara Road | 0.5 | 0.8 |  | 25.03.18 | 15.07.2018 | 31.07.2018 | 77% | 0 | 135 | 76
40 | Abdul Aziz Road | 0.4 | 0.6 |  | 25.03.18 | 15.07.2018 | 31.07.2018 | 70% | 0 | 110 | 62
41 | S.K. Dass Road | 0.3 | 0.5 |  | 25.03.18 | 15.07.2018 | 31.07.2018 | 70% | 0 | 80 | 45
42 | Abdul Rehman | 0.2 | 0.4 |  | 25.03.18 | 15.07.2018 | 31.07.2018 | 70% | 0 | 55 | 31
43 | Padam Singh Road | 0.75 | 1.3 |  | 25.03.18 | 15.07.2018 | 31.07.2018 | 75% | 0 | 210 | 118
44 | Arya Samaj Road | 1 | 2 |  | 25.03.18 | 15.07.2018 | 31.07.2018 | 70% | 0 | 270 | 151
45 | Mahatma gandhi Marg (Ring Road) | 7.1 | 6.6 | M/s Shatrughna Construction Co & Shri Rajnish Yadav | 25.03.18 | 15.07.2018 | 31.07.2018 | 70% | 0 | 312 | 175
46 | Road No. 36(Sat Guru Ram Singh Marg) | 3.4 | 6.8 |  | 25.03.18 | 15.07.2018 | 31.07.2018 | 70% | 0 | 1200 | 672
47 | MM Road | 6.8 | 7.7 | M/s RichCon Engineering Company | 25.03.18 | 15.07.2018 | 31.07.2018 | 70% | 0 | 600 | 336
48 | Vatika Road (DPS Vasant Kunj to MM road) | 0.7 | 1.4 |  | 25.03.18 | 15.07.2018 | 31.07.2018 | 70% | 0 | 500 | 280
49 | Munirka marg | 0.9 | 0.8 |  |  | 15.07.2018 | 31.07.2018 | 70% | 0 | 100 | 56
50 | Basant marg-I | 0.9 |  |  | 25.03.18 | 15.07.2018 | 31.07.2018 | 70% | #REF! | 100 | 56
[10 empty] | 17087 | 10000
South West Road-2 Division
51 | A Block Road | 0.2 | 0.4 | ANMOL INFRATECH PRIVATE LIMITED | 2018-03-21 |  | 31.07.2018 | 95% | 15.10.2017 | Work executed by super sucker machine | The drain is being cleaned by super sucker machines hence quanitity cannot be ascertained. | Er. J. P. Vashist M- 9971396164
52 | Pankha Road | 1 | 2.05 |  | 2018-03-21 |  | 31.07.2018 | 90% | 15.10.2017
53 | Nasir Pur Road | 2.3 | 3.89 |  | 2018-03-21 |  | 31.07.2018 | 95% | 15.10.2017
54 | Palam Dabri Road | 2.5 | 3.496 |  | 2018-03-21 |  | 31.07.2018 | 90% | 15.10.2017
55 | Paras Public schol to L-103 Pocket-4 Chankya Puri Binda Pur | 0.24 | 0.48 |  | 2018-03-21 |  | 31.07.2018 | 95% | 15.10.2017
56 | Peer Baba Road | 0.6 | 1.236 |  | 2018-03-21 |  | 31.07.2018 | 90% | 15.10.2017
57 | Police Station Road | 0.37 | 0.74 |  | 2018-03-21 |  | 31.07.2018 | 95% | 15.10.2017
58 | Pt. Vishnu Dutt Marg | 0.75 | 1.497 |  | 2018-03-21 |  | 31.07.2018 | 90% | 15.10.2017
59 | Sagar Pur Road | 3 | 5.55 |  | 2018-03-21 |  | 31.07.2018 | 90% | 15.10.2017
60 | Satguru Ram Singh Marg | 0.9 | 1.635 |  | 2018-03-21 |  | 31.07.2018 | 95% | 15.10.2017 | Work executed by super sucker machine
61 | Link Road (Pt. Vishnu Dutt Marg to Satguru Ram Singh Marg) | 0.3 | 0.55 |  | 2018-03-21 |  | 31.07.2018 | 90% | 15.10.2017
62 | Najafgarh Dhansa Road | 16.25 | 8356 Mtr | Surender Singh | 07.03.2018 |  | 31.07.2018 | 90% | 30.09.2017 |  | The drain is being cleaned by super sucker machines hence quanitity cannot be ascertained.
63 | Najafgarh Kakrola Road | 4 | 4545 Mtr |  | 07.03.2018 |  | 31.07.2018 | 50% | 30.09.2017
64 | Najafgarh Nangloi Road | 2.6 | 5050 Mtr | Surender Singh | 23.02.2018 |  | 31.07.2018 | 75% | 30.09.2017 |  | The drain is being cleaned by super sucker machines hence quanitity cannot be ascertained.
65 | Najafgarh Phirni | 2.2 | 5640 Mtr |  | 23.02.2018 |  | 31.07.2018 | 75% | 30.09.2017
66 | Najafgarh Dichaon Road | 4.55 | 2650 Mtr |  | 26.05.2018 |  | 31.07.2018 | 50%
67 | Najafgarh Jharoda Road | 7.2 | 13650 Mtr |  | 26.05.2018 |  | 31.07.2018 | 75% | 30.09.2017
68 | Laxmi Chand Marg | 11.3 | 10.5 | Surender Singh | 2018-03-07 |  | 31.07.2018 | 90% | 10.10.2017 | Work is being executed by super sucker machine | The drain is being cleaned by super sucker machines hence quanitity cannot be ascertained. | Er. J. P. Vashist M- 9971396164
69 | Prithvi Singh Dagar Marg | 11.2 | 7.9 |  | 2018-03-07 |  | 31.07.2018 | 100% | 10.10.2017
70 | Jhatikara Morh to Jhatikara | 8.55 | 1.2 | Surender Singh | 2018-02-23 |  | 31.07.2018 | 100% | 10.10.2017
71 | Najafgarh Bijwasan Road | 11.25 | 16 |  | 2018-02-23 |  | 31.07.2018 | 73% | 10.10.2017
72 | Bhartal Road | 3.48 | 3.48 | Surender Singh | 2018-03-01 |  | 31.07.2018 | 75% | 10.10.2017 |  | The drain is being cleaned by super sucker machines hence quanitity cannot be ascertained.
73 | Goyla Deenpur Road | 4.2 | 7.4 |  | 2018-03-01 |  | 31.07.2018 | 90% | 10.10.2017
74 | Kapashera Bijwasan Road | 3.8 | 7.6 | ANMOL INFRATECH PRIVATE LIMITED | 2018-03-21 |  | 31.07.2018 | 90% | 10.10.2017
75 | Link Road | 1.7 | 1.7 |  | 2018-03-21 |  | 31.07.2018 | 95% | 10.10.2017
76 | Old DG Road | 2.5 | 5 |  | 2018-03-21 |  | 31.07.2018 | 90% | 10.10.2017
2)-South Circle
South Road-1 Division
1 | M.B. Road | 5.25 | 5.25 | M/s Maan Builders | 09.04.2018 | 31.07.2018 | 31.07.2018 | 90% |  | 4682 | 2809 | Er. Narender Mahajan (M:9643870385)
|  |  |  | M/s Buland constructions | 15.04.2018 | 31.07.2018 | 31.07.2018 | 90% |  | 3019
2 | IGNOU Road | 1.9 | 1.9 | M/s Buland constructions | 15.04.2018 |  |  | 70% |  | 2725 | 1600
3 | Westend Marg | 0.6 | 0.6 | M/s Buland constructions | 09.04.2018 | 31.07.2018 | 31.07.2018 | 80% |  |  | 2000
4 | Devli Road | 1.05 | 1.05 | M/s Maan Builders | 09.04.2018 | 31.07.2018 | 31.07.2018 | 95%
5 | H Block Dakshnipuri | 0.9 | 0.9 |  |  |  |  | 95%
6 | Raja Ram Marg | 0.89 | 0.89 |  |  |  |  | 90%
7 | Durbal Nath Marg | 1.09 | 1.09 |  |  |  |  | 95%
8 | Maharishi Balmiki Marg | 1.8 | 1.8 |  |  |  |  | 90%
9 | Phirni Road | 1 | 1 |  |  |  |  | 95%
10 | Old MB Road | 0.6 | 0.6 | M/s Kleenwel Enviro Engg. Services | 09.04.2018 | 15.06.2018 | 15.06.2018 | 100%
11 | 100 Foota Road | 2.2 | 2.2 |  | 09.04.2018 | 31.07.2018 | 31.07.2018 | 85% |  |  | 125 | Er. Narender Mahajan (M:9643870385)
12 | 60 Foota Road | 1.8 | 1.8 |  | 09.04.2018 | 31.07.2018 | 31.07.2018 | 80% |  |  | 90
13 | SSN Marg | 14 | 14 | M/s Buland Constructions | 09.04.2018 | 31.07.2018 | 31.07.2018 | 85% |  | 2162 | 56
14 | SSN Marg | 1.4 | 1.4 |  |  |  |  | 75%
15 | SSN Marg | 6 | 6 | M/s Kapil Tanwar | 09.04.2018 | 31.07.2018 | 31.07.2018 | 70% |  |  | 960
16 | Mandi Road | 2.83 | 2.83 | M/s Buland Constructions | 09.04.2018` | 31.07.2018 | 31.07.2018 | 50% |  | 1144 cum | 300 | Er. Narender Mahajan (M:9643870385)
17 | Gadaipur Bundh Road | 1 | 1 | M/s Ravi Tanwar | 09.04.2018 | 13.07.2018 | 13.07.2018 | 100% |  |  | 1900
18 | Mandi Road | 3 | 3 | Sh. Ravi Tanwar | 28.04.2018 | 31.07.2018 | 31.07.2018 | 100% |  | 2340 cum |  | Er. Narender Mahajan (M:9643870385)
19 | Bundh Road | 1.9 | 1.9 | M/s Buland constructions |  | 31.07.2018 | 31.07.2018 | 100%
20 | Dera Bhatti Road | 3 | 3 | Sh. Ravi Tanwar |  |  |  | 100%
21 | Pankaj Juyal Marg | 1.1 | 1.1 | M/s Buland Constructions | 2018-03-31 | 31.07.2018 | 31.07.2018 | 95% |  | 6150 | 4600 | Er. Narender Mahajan
22 | Family Court road | 0.55 | 0.55 |  |  |  |  | 90%
23 | J-Block Road | 1.2 | 1.2 |  |  |  |  | 77%
24 | Asian Market Road | 0.45 | 0.45 |  |  |  |  | 90%
25 | Mandir marg | 1.2 | 1.2 |  |  |  |  | 86%
26 | NBCC Plaza Road | 1.1 | 1.1 |  |  |  |  | 95%
27 | Birla Vidya Niketan Marg | 0.95 | 0.95 |  |  |  |  | 90%
28 | Pramod Mahajan Marg | 0.89 | 0.89 |  |  |  |  | 82%
29 | Main Road Pushp Vihar Sector-1 | 0.75 | 0.75 |  |  |  |  | 90%
30 | Metro Enclave Road | 0.45 | 0.45 |  |  |  |  | 90%
31 | Press Enclave Road | 3.78 | 3.78 | M/s Buland Constructions | 2018-04-06 | 31.07.2018 | 31.07.2018 | 82% |  | 3135 | 2217 | Er. Narender Mahajan
32 | Khirki Road | 0.85 | 0.85 |  |  |  |  | 83%
33 | Apeejay School Road | 1.3 | 1.3 |  |  |  |  | 82%
34 | Sheikh Sarai Phase-1 Road-1 | 0.6 | 0.6 |  |  |  |  | 77%
35 | Sheikh Sarai Phase-1 Road-2 | 0.3 | 0.3 |  |  |  |  | 77%
36 | Road in front of Mother International School | 0.54 | 0.54 |  |  |  |  | 86%
37 | Road from H.No. C-11 to C-20 Malviya Nagar | 0.11 | 0.11 |  |  |  |  | 90%
38 | Gurudwara Road Saket | 0.55 | 0.55 | Sh. Babu lal Gupta | 2018-04-06 | 31.07.2018 | 31.07.2018 | 76% |  | 684 | 270 | Er. Narender Mahajan
39 | Pramod Mahajan Marg | 0.89 | 0.89 |  |  |  |  | 90%
40 | M.G. Road | 7.5 | 7.5 | M/s Buland Constructions | 09.04.2018 | 31.07.2018 | 31.07.2018 | 90% |  | 5265 |  | Sh. Narender Mahajan Mob.No.- 9933331859
41 | Aya Nagar | 0.6 | 0.6 |  |  |  |  | 90% |  |  | 240
42 | Ghitorni Road to CPWD Land | 0.54 | 0.54 |  |  |  |  | 75% |  |  | 260
43 | Ghitorni Village Road | 1.04 | 1.04 |  |  |  |  | 80% |  |  | 50
44 | MG Road to Ghitorni Village | 0.3 | 0.3 |  |  |  |  | 30%
[6 empty] | Total | Total |  |  |  | 17477
South Road-2 Division
45 | August Kranti Marg. | 3.24 | 3.54 | Sh. Yogesh Arora | 22.02.2018 | 31.07.2018 | 31.07.2018 | 95% |  | 618.75 | 588 | Sh. Jagdish Prasad 9560207879
46 | Balbir Saxena Marg | 0.8 | 1.6 |  |  |  |  | 95% |  | 192 | 182
47 | Ch. Dilip Singh Marg, P.S. Hauz Khas | 0.6 | 1 |  |  |  |  | 95% |  | 360 | 342
48 | Mahinder Singh Jain Marg Road / Gautam Nagar Road | 1.2 | 2.4 |  |  |  |  | 95% |  | 480 | 456
49 | P-Block Road from August Kranti Marg via jain Mandir & Dustbin to August Kranti Marg. | 0.34 | 0.6 |  |  |  |  | 95% |  | 120 | 114
50 | Sudarshan Cinema Road. | 0.72 | 0.7 |  |  |  |  | 95% |  | 75 | 71
51 | Gautam Nagar Road | 0.5 | 0.8 |  |  |  |  | 85% |  | 225 | 191
52 | Road form Balbir Sxsena Marg to Ch. Dalip SinghMarg (NIFT Road), Hauz Khas | 0.6 | 1.2 |  |  |  |  | 95% |  | 135 | 128
53 | Road form August Kranti marg to Aurobindo Marg (Subash Chopra Road), Hauz Khas | 0.79 | 1.5 |  |  |  |  | 95% |  | 99 | 94
54 | Asiad Village peripheral road | 3 | 3 |  |  |  |  | 95% |  | 375 | 356
55 | Siri Fort Road | 1.2 | 2.4 |  |  |  |  | 95% |  | 288 | 274
56 | Sri Krishna Chaitnya Maha Prabhu Marg | 0.7 | 1.4 |  |  |  |  | 90% |  | 80 | 72
57 | Sri Aurobindo Marg | 4.3 | 8.6 | M/s Amit Enterprises | 16.02.2018 | 31.07.2018 | 31.07.2018 | 95% |  | 2874 | 2730 | Sh. Jagdish Prasad 9560207879
58 | Ring Road | 2 | 3.6 |  |  |  |  | 95% |  | 2998 | 1460
59 | Outer Ring Road | 1.5 | 3 |  |  |  |  | 90% |  |  | 343
60 | Ch. Harsukh Marg | 2 | 4 |  |  |  |  | 90% |  |  | 355
61 | Ch Jhandu Singh Marg | 1.53 | 3.06 |  |  |  |  | 90% |  |  | 185
62 | Ch Hukum Chand Marg | 0.6 | 0.9 |  |  |  |  | 90% |  |  | 140
63 | Green Park Market Road | 0.8 | 1.2 |  |  |  |  | 90% |  |  | 153
64 | Hauz Khas Village Road | 0.9 | 0.08 |  |  |  |  | 95% |  |  | 70
65 | N. K. Pandey Marg | 1.17 | 1.58 |  |  |  |  | 90% |  |  | 80
66 | Road from B15/7 to BSES (B&C Block Qutub Inst. Area) (Both Sides) | 0.3 | 0.6 | M/s Nagendra & Company, | 14.02.2018 | 31.07.2018 | 31.07.2018 | 98% |  | 6060 | 125 | Sh. Jagdish Prasad 9560207879
67 | Road from B12 to IIM (B&C Block Qutub Inst. Area) (Both Sides) | 0.1 | 0.2 |  |  |  |  | 98% |  |  | 42
68 | Satsang Vihar Marg (A-Block Qutub Inst. Area) (Both Sides) | 0.41 | 0.82 |  |  |  |  | 98% |  |  | 160
69 | USO Marg (A-Block Qutub Inst. Area) (Both Sides) | 0.2 | 0.4 |  |  |  |  | 100% |  |  | 82
70 | Peripherial Road (B&C Block Qutub Inst. Area) (Both Sides) | 1.57 | 3.14 |  |  |  |  | 100% |  |  | 636
71 | Saheed Jeet Singh Marg (Both Sides) | 2.1 | 4.2 |  |  |  |  | 98% |  |  | 795
72 | Aruna Asaf Ali Marg (Both Sides) | 3.5 | 7 |  |  |  |  | 98% |  |  | 1376
73 | Anuvart Marg (Both Sides) | 2.5 | 5 |  |  |  |  | 98% |  |  | 1098
74 | Vedant Deshika Marg (Both Sides) | 0.9 | 1.8 |  |  |  |  | 100% |  |  | 430
75 | Qutub Minar Round About (Both Sides) | 1 | 2 |  |  |  |  | 98% |  |  | 382
76 | DAV School Road (Vasant Kunj) (Both Sides) | 0.55 | 1.1 |  |  |  |  | 100% |  |  | 238
77 | B-1 Telephone Exchange Road Vasant Kunj (Mahipalpur Road to B-5 & B-6 Road) (Both Sides) | 0.6 | 1.2 |  |  |  |  | 100% |  |  | 242
78 | B-2 & B-3 Road (Shiv Mandir to B-5 & B-6 Road) (Both Sides) | 0.3 | 0.6 |  |  |  |  | 100% |  |  | 128
79 | D-1 & D-2 Road Vasant Kunj (Both Sides) | 0.24 | 0.48 |  |  |  |  | 98% |  |  | 90
80 | Sports Complex Road (D-2 Vasant Kunj) (Both Sides) | 0.7 | 1.4 |  |  |  |  | 98% |  |  | 305
81 | Outer Ring Road | 3.2 | 6.4 | M/s Nagendra & Company, | 16.02.2018 | 31.07.2018 | 31.07.2018 | 91% |  | 1000 | 910 | Sh. Jagdish Prasad 9560207879
82 | A-1 Block, Panchsheel Enlcave Road | 0.5 | 0.5 |  |  |  |  | 92% |  | 50 | 46
83 | B,C & D Block Panchsheel Enclave Road | 0.5 | 0.5 |  |  |  |  | 95% |  | 50 | 48
84 | S-Bend Road (Maharishi Dayanand Marg) | 1.8 | 2.9 | Sh. Ram Nihor | 30.03.2018 | 31.07.2018 | 31.07.2018 | 95% |  | 446 | 424 | Sh. Jagdish Prasad 9560207879
85 | Shivalik Road (Basant Kaur Marg) | 1.86 | 3.6 |  |  |  |  | 92% |  | 306 | 282
86 | Guru Govind Singh Marg | 1.2 | 1.9 |  |  |  |  | 92% |  | 185 | 170
[6 empty] | Total |  |  | 16393
3)-South-East Circle
South-East Road-1 Division
1 | S. N. Puri Main Road From Cambridge School To CTC | 1.4 | 2.4 | M/s. Buland Construction | 13.05.2018 | 10.08.2018 | 10.08.2018 | 80% | 161 | 161 | - | Sh. Sheel Rajneesh 8527021144 | Work just started.
2 | S. N. Puri Internal Road Post Office to CPWD Via Jal Board Office | 0.54 | 1.08 | -do- | -do- | -do- | -do- | 80% | 72 | 72 | - |  | do
3 | S.N. Puri Internal Road Opp Police Post | 0.15 | 0.3 | -do- | -do- | -do- | -do- | 80% | 20 | 20 | - |  | do
4 | S. N. Puri Internal Road MCD Store to round about Via Maternity Home | 0.91 | 1.86 | -do- | -do- | -do- | -do- | 80% | 125 | 125 | - |  | do
5 | Theka Road Sri Niwas Puri | 0.25 | 0.5 | -do- | -do- | -do- | -do- | 80% | 134 | 134 | - |  | do
6 | Captain Gaur Marg | 2.15 | 4.3 | -do- | -do- | -do- | -do- | 25% | 288 | 288 | 21 cum |  | do
7 | Banglow Road To Gidwani Marg, Lajpat Nagar-4 | 0.12 | 0.24 | -do- | -do- | -do- | -do- | - | 16 | 16 | - |  | do
8 | Dr. Moti Lal Jotwani Road, Lajpat Nagar-IV | 0.47 | 0.94 | -do- | -do- | -do- | -do- | - | 63 | 63 | - |  | do
9 | Central Road to Back of Ring Road, Lajpat Nagar-IV | 0.35 | 0.7 | -do- | -do- | -do- | -do- | - | 47 | 47 | - |  | do
10 | Kalka Devi Marg | 1.12 | 2.24 | -do- | -do- | -do- | -do- | - | 150 | 150 | - | Sh. Sheel Rajneesh 8527021144 | do
11 | Kalka Devi Marg to Banglow Road, Lajpat Nagar-IV | 0.49 | 0.98 | -do- | -do- | -do- | -do- | - | 65 | 65 | - |  | do
12 | Road No. 2 Andrews Ganj | 0.4 | 0.8 | -do- | -do- | -do- | -do- | 70% | 54 | 54 | - |  | do
13 | Road No. 5 Andrews Ganj | 0.13 | 0.26 | -do- | -do- | -do- | -do- | 70% | 17 | 17 | - |  | do
14 | Road No. 7 Andrews Ganj | 0.24 | 0.48 | -do- | -do- | -do- | -do- | 70% | 32 | 32 | - |  | do
15 | Road No. 3 Andrews Ganj | 0.75 | 1.5 | -do- | -do- | -do- | -do- | 70% | 100 | 100 | - |  | do
16 | Road No. 6 Andrews Ganj | 0.24 | 0.48 | -do- | -do- | -do- | -do- | 70% | 32 | 32 | - |  | do
17 | Garhi Village to National Heart Hospital via Sapna Cinema | 0.41 | 0.82 | -do- | -do- | -do- | -do- | - | 55 | 55 | - |  | do
18 | Raja Dheer Sain Marg | 1.78 | 2.8 | -do- | -do- | -do- | -do- | - | 188 | 188 | - |  | do
19 | C.V. Raman Marg | 2 | 3.5 | M/s. Buland Construction | 13.05.18 | 10.08.18 | 10.08.18 | 60% | 2830 Mtrs | 2830 Mtrs | Total Qty. Measured vide1st RA Bill 1641.71 Cum |  | do
20 | Mata Mandir Road | 0.55 | 0.8 | -do- | -do- | -do- | -do- | 60% | 750 Mtrs | 750 Mtrs |  |  | do
21 | M.P. Road | 1.35 | 1 | -do- | -do- | -do- | -do- | 80% | 250 Mtrs | 250 Mtrs |  | Sh. Sheel Rajneesh 8527021144 | do
22 | Mathura Road (NH2) | 2.05 | 3 | -do- | -do- | -do- | -do- | 75% | 2520 Mtrs | 2520 Mtrs |  |  | do
23 | Sukhdev Vihar Road | 1 | 1.6 | -do- | -do- | -do- | -do- | 70% | 1680 Mtrs | 1680 Mtrs |  |  | do
24 | MMA Road | 3 | 5 | -do- | -do- | -do- | -do- | 55% | 2280 Mtrs | 2280 Mtrs |  |  | do
25 | Gurudwara Road | 1.35 | 2 | -do- | -do- | -do- | -do- | 70% | 580 Mtrs | 580 Mtrs |  |  | do
26 | Bhishma Pitamah Road | 2.3 | 4.6 | Sh. Rajnish Yadav | 22.04.18 | 20.07.18 | 20.07.18 | 90% | 955 | 955 | Not readily available |  | do
27 | Road from B.P.Marg to Round About Defence Colony | 0.16 | 0.32 | -do- | -do- | -do- | -do- | 90% | 66 | 66 | --do-- |  | do
28 | Feroz Gandhi Road Lajpat Nagar | 1.05 | 2.1 | -do- | -do- | -do- | -do- | 90% | 438 | 438 | --do-- |  | do
29 | Shiv Mandir Marg from Zonal Office to Ring Road | 0.85 | 1.7 | -do- | -do- | -do- | -do- | 90% | 353 | 353 | --do-- |  | do
30 | Vir Savarkar Marg, Lajapat Nagar | 1.05 | 2.1 | -do- | -do- | -do- | -do- | 90% | 436 | 436 | --do-- |  | do
31 | Ring Road AIIMS to Bhairon Road 'T' Jn | 9.65 | 19.3 | -do- | -do- | -do- | -do- | 75% | 4005 | 4005 | --do-- |  | do
32 | 2 nd Enty Road | 0.6 | 1.2 | -do- | -do- | -do- | -do- | 50% | 249 | 249 | --do-- | Sh. Sheel Rajneesh 8527021144 | do
33 | Bhairon Road | 0.98 | 1.96 | -do- | -do- | -do- | -do- | Nil | 400 | 400 | --do-- |  | hand over to ITP
34 | BRT Road | 6.75 | 13.5 | -do- | -do- | -do- | -do- | 70% | 2800 | 2800 | --do-- |  | Work just started.
35 | Mathura Roads from DPS to Ashram Chowk | 2.65 Km | 1.8 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | 15.07.2018 | 90% | 400 | 400 | 2463 Cum |  | do
36 | Hospital Road, Bhogal | 0.56 Km | 0.4 | -do- | -do- | -do- | -do- | 70% | 100 | 100 |  |  | do
37 | East Nizamuddin peripheral Road from Mathura Road to Railway Station, East Nizamuddin | 0.70 Km | 0.7 | -do- | -do- | -do- | -do- | 70% | 150 | 150 |  |  | do
38 | Rajdoot Hotel to Preet Place, Jangpura | 0.20 Km | 0.2 | -do- | -do- | -do- | -do- | 85% | 50 | 50 |  |  | do
39 | Preet Place to Nizamuddin Railway Station, Jangpura | 0.70 Km | 0.7 | -do- | -do- | -do- | -do- | 80% | 150 | 150 |  |  | do
40 | School Road, Jangpura Extn. | 0.38 Km | 0.38 | -do- | -do- | -do- | -do- | 90% | 80 | 80 |  |  | do
41 | Neela Gumbad to Lodhi Flyover, Nizamuddin Basti | 0.20 Km | 0.4 | Sh. Surender Singh | 15.04.2018 | 15.07.2018 | 15.07.2018 | 75% | 85 | 85 |  |  | do
42 | Lodhi Road Indian Habitat Centre to Lodhi Flyover | 1.76 Km | 3.5 | -do- | -do- | -do- | -do- | 85% | 740 | 740 |  |  | do
43 | IVth- Avenue Road, Lodhi Colony | 1.22 Km | 2.4 | -do- | -do- | -do- | -do- | 85% | 510 | 510 |  |  | do
44 | Vth- Avenue Road, Lodhi Colony | 1.00 Km | 2 | -do- | -do- | -do- | -do- | 85% | 420 | 420 |  |  | do
45 | X- Road between Block No. 18 & 14 Lodhi Colony | 0.16 Km | 0.32 | -do- | -do- | -do- | -do- | 85% | 70 | 70 |  |  | do
46 | X- Road between D -1 & C-2 (F-24) Lodhi Colony | 0.16 Km | 0.32 | -do- | -do- | -do- | -do- | 80% | 70 | 70 |  |  | do
47 | X- Road between Block No. C- 2 (176) & C- 2 (177) Lodhi Colony | 0.16 Km | 0.32 | -do- | -do- | -do- | -do- | 80% | 70 | 70 |  |  | do
48 | B.P marg to Coffee House Lodhi Colony | 0.35 Km | 0.4 | -do- | -do- | -do- | -do- | 85% | 125 | 125 |  |  | do
49 | F-1 Lodhi Colony to B.P Flyover, Lodhi Colony | 0.24 Km | 0.2 | -do- | -do- | -do- | -do- | 80% | 50 | 50 |  |  | do
50 | Verdhman Marg from IVth- Avenue Road B.P Marg, Lodhi Colony | 0.35 Km | 0.5 | -do- | -do- | -do- | -do- | 80% | 115 | 115 |  |  | do
51 | Maharani Bagh from Manokamna Mandir to Sunlight Colony | 0.55 Km | 0.55 | -do- | -do- | -do- | -do- | 65% | 120 | 120 |  |  | do
52 | Kushak Nallah to Sewa Nagar Flyover, Sewa Nagar | 0.70 Km | 0.7 | -do- | -do- | -do- | -do- | 70% | 150 | 150 |  | Sh. Sheel Rajneesh 8527021144 | do
53 | Kushak Nallah to CPWD Enquiry (Near O Blk.), Sewa Nagar | 0.30 Km | 0.6 | -do- | -do- | -do- | -do- | 65% | 60 | 60 |  |  | do
54 | Hanuman mandir to Sewa Nagar Flyover, Sewa Nagar | 0.46 Km | 0.46 | -do- | -do- | -do- | -do- | 65% | 100 | 100 |  |  | do
55 | Railway Phatak to Subhash Bazar, Sewa Nagar | 0.258 Km | 0.2 | -do- | -do- | -do- | -do- | 65% | 20 | 20 |  |  | do
56 | BRT from Bhairon Road T- Point to Defence Colony Flyover | 3.00 Km | 2 | -do- | -do- | -do- | -do- | 80% | 550 | 550 |  |  | Bhairo road T-Point to DPS, Mathura Road is handed over to ITPO Project Division, PWD
57 | Sunder Nagar Peripheral Road, Sunder Nagar | 1.10 Km | 1.1 | -do- | -do- | -do- | -do- | 95% | 250 | 250 |  |  | Work just started.
58 | Ratan Lal Sahdev Marg, Defence Colony | 0.978 Km | 1 | -do- | -do- | -do- | -do- | 80% | 240 | 240 |  |  | do
59 | Gang Nath Marg, Safdarjung Flyover to round about near Khushak Nalah | 0.625 Km | 0.4 | -do- | -do- | -do- | -do- | 70% | 150 | 150 |  |  | do
16146
South-East Road-II Division
60 | SA Road | 5.46 | 10.92 | M/s R.P. Infrastructure | 15:04 | 2018-07-25 | 2018-07-25 | 95% |  | 2215 | 1750 | Er. R.K. Sharma, EE, SER-2 9818615817
61 | Maharaja Agarsen Marg | 0.5 | 1 |  | 15:04 | Completed on 28.06.2018 | Completed on 28.06.2018 | 100% |  | 190 | 122
62 | Baba Fateh Singh Marg | 1 | 2 |  | 15:04 | Completed on 15.06.2018 | Completed on 15.06.2018 | 100% |  | 335 | 502
63 | Hans Raj Sethi Marg | 1.7 | 3.4 |  | 15:04 | 2018-07-25 | 2018-07-25 | 85% |  | 329 | 370
64 | A Block Double Storey (EPDP to Hans Raj Sethi Marg) | 0.45 | 0.9 |  | 15:04 | 2018-07-25 | 2018-07-25 | 80% |  | 31 | 45
65 | Maharaja Agarsen marg | 0.8 | 1.6 |  | 15:04 | 2018-07-25 | 2018-07-25 | 100% |  | 576 | 835
66 | Madanpur Khadar Road | 1.2 | 2.4 |  | 15:04 | 2018-07-25 | 2018-07-25 | 89% |  | 561 | 496
67 | Sarita Vihar Road | 1.1 | 2.2 |  | 15:04 | Completed on 15.06.2018 | Completed on 15.06.2018 | 100% |  | 432 | 1338
68 | Road No. 13 A | 2.5 | 5 |  | 15:04 | 2018-07-25 | 2018-07-25 | 72% |  | 1350 | 975
69 | Mathura Road | 5.5 | 11 | M/s Buland Constructions | 14:04 | 2018-07-25 | 2018-07-25 | 60% |  | 2640 | 1056
70 | Lala Lajpat Rai Marg to Raja Dheer Sen Marg | 0.3 | 0.6 |  | 14:04 | 2018-07-25 | 2018-07-25 | 80% |  | 2700 | 70
71 | Guru Nanak Market to lala Lajpat Rai Marg | 0.57 | 1.14 |  | 14:04 | Completed on 15.06.2018 | Completed on 15.06.2018 | 100% |  |  | 150
72 | Nandi Vithi Marg | 0.73 | 1.46 |  | 14:04 | Completed on 15.06.2018 | Completed on 15.06.2018 | 100% |  |  | 230 | Er. R.K. Sharma, EE, SER-2 9818615817
73 | Link Road | 0.58 | 1.16 |  | 14:04 | Completed on 15.06.2018 | Completed on 15.06.2018 | 100% |  |  | 160
74 | Road from BRT to Hans Raj Gupta Marg | 0.34 | 0.68 |  | 14:04 | Completed on 20.06.2018 | Completed on 20.06.2018 | 100% |  |  | 42
75 | Hans Raj Gupta Marg | 2.65 | 5.3 |  | 14:04 | 2018-07-25 | 2018-07-25 | 65% |  |  | 195
76 | Lala Lajpat Rai Marg | 2.4 | 4.8 |  | 14:04 | 2018-07-25 | 2018-07-25 | 75% |  |  | 170
77 | Guru Harkishan Public School to Nehru Place | 0.27 | 0.54 |  | 14:04 | Completed on 18.06.2018 | Completed on 18.06.2018 | 100% |  |  | 65
78 | R Block GK-1 signal to Outer Ring Road | 0.58 | 1.16 |  | 14:04 | Completed on 18.06.2018 | Completed on 18.06.2018 | 100% |  |  | 110
79 | Outer Ring Road | 2.1 | 4.2 |  | 14:04 | 2018-07-25 | 2018-07-25 | 95% |  |  | 335
80 | Road from Vipin Chander Pal Marg to Police Station CR Park | 0.37 | 0.74 |  | 14:04 | 2018-07-25 | 2018-07-25 | 75% |  |  | 35
81 | Savitri Cinema Road | 3.1 | 6.2 |  | 14:04 | 2018-07-25 | 2018-07-25 | 85% |  |  | 250
82 | Surya Sen Marg | 0.75 | 1.5 |  | 14:04 | Completed on 18.06.2018 | Completed on 18.06.2018 | 100% |  |  | 370
83 | E Block Road GK-III | 0.692 | 1.384 |  | 14:04 | 2018-07-25 | 2018-07-25 | 65% |  |  | 160
84 | Lala Lajpat Rai Marg to Raja Dheer Sen Marf Block E & F | 0.3 | 0.6 |  | 14:04 | 2018-07-25 | 2018-07-25 | 80% |  |  | 40
85 | M Block Road | 1.3 | 2.6 |  | 14:04 | 2018-07-25 | 2018-07-25 | 80% |  |  | 35
86 | MB Road | 5.25 | 10.5 | M/s R.P. Infrastructure | 15:04 | 2018-07-25 | 2018-07-25 | 85% |  | 2893 | 1660
87 | Guru Ravi Dass Marg | 3.75 | 7.5 |  | 14:04 | 2018-07-25 | 2018-07-25 | 95% |  | 2294 | 1560
88 | DDA Market Road | 0.43 | 0.86 |  | 14:04 | Completed on 25.06.2018 | Completed on 25.06.2018 | 100% |  | 277 | 470
89 | KPS Road | 0.64 | 1.28 |  | 14:04 | Completed on 25.06.2018 | Completed on 25.06.2018 | 100% |  | 225 | 250
90 | Suraj Kund Road | 0.6 | 1.2 |  | 15:04 | Completed on 28.06.2018 | Completed on 28.06.2018 | 100% |  | 287 | 280
91 | Road No13 | 2.7 | 5.4 | M/s Buland Constructions | 14:04 | 2018-07-25 | 2018-07-25 | 85% |  | 1090 | 348 | Er. R.K. Sharma, EE, SER-2 9818615817
92 | EPDP Road | 1.8 | 3.6 |  | 14:04 | Completed on 28.06.2018 | Completed on 28.06.2018 | 100% |  | 582 | 160
93 | Outer Ring Road | 3.2 | 6.4 |  | 14:04 | 2018-07-25 | 2018-07-25 | 80% |  | 758 | 230
94 | Gurudwara Road GK-II | 1.7 | 3.4 |  | 14:04 | Completed on 28.06.2018 | Completed on 28.06.2018 | 100% |  | 467 | 285
95 | Vipin Chander Pal Marg | 1.5 | 3 |  | 14:04 | Completed on 28.06.2018 | Completed on 28.06.2018 | 100% |  | 624 | 170
[10 empty] | 20856 | 15319