## Abstract
East Delhi Municipal Corporation Engineering Department
Dt. 15.05.19
Subject :- Progress report regarding Desilting of drains.
S. No. | Zone | Total no. of drains | Total length in km | Total targeted qty. in M.T. | Qty. of silt removed and sent at SLF in M.T. w.e.f 01.10.18 to 09.05.19 (a) | Silt removed in M.T. during this week (10.05.19 to 14.05.19) (b) | Total qty. in M.T. (a + b) | %age progress | Remarks
1 | Shah. South | 108 | 59.87 | 17089 | 8516 | 1589 | 10105 | 59.1316
2 | Shah. North | 114 | 62.86 | 31187 | 12664 | 4172 | 16836 | 53.984 | Timeline for completion 10.06.17
| Total | 222 | 122.73 | 48276 | 21180 | 5761 | 26941 | 55.8062
East Delhi Municipal Corporation Engineering Department
Dt. 03.05.19
S. No. | Zone | Total no. of drains | Total length in km | Total targeted qty. in M.T. | Qty. of silt removed and sent at SLF in M.T. w.e.f 01.10.18 to 09.05.19 (a) | Silt removed in M.T. during this week (b) | Total qty. in M.T. (a + b) | %age progress | Remarks
1 | Shah. South | 108 | 59.87 | 17089 | 8516 | 1589 | 10105 | 59.1316
2 | Shah. North | 114 | 62.86 | 31187 | 13462 | 4172 | 17634 | 56.5428 | Timeline for completion 10.06.17
| Total | 222 | 122.73 | 48276 | 21978 | 5761 | 27739 | 57.4592
2 | Shah. North | 114 | 62.86 | 31187 | 11016 |  |  | 35.3224 | Timeline for completion 10.06.17
| Total | 336 | 185.59 | 79463 | 32994 |  |  | 41.5212
East Delhi Municipal Corporation Engineering Department
Dt. 11.04.19
Subject :-Abstract of Desilting of drains in EDMC.
S. No. | Zone | Total no. of drains | Total length of drains (In KM) | Proposed qty. of silt in M.T. | Total qty. of silt removed as on 31.03.2019 |  |  | %age progress | Remarks
1 | Shah. (South) | 108 | 59.87 | 17089 | 2897 |  |  | 16.9524
2 | Shah. (North) | 114 | 62.86 | 31187 | 875 |  |  | 2.806% | Timeline for completion 10.06.17
| Total | 222 | 122.73 | 48276 | 3772 |  |  | 7.813%

## North & South Compile
East Delhi Municipal Corporation
Subject:- Report regarding Desilting of Drains upto 14th May 2019
Date 15.05.19
S. No. | Name of Drain | Length of Drain | Date of Issue of Desilting Tender | Date of Commencement of Desilting | Excepted Date of Completion of Desilting | Progres of Work (in %) | Quantity of Silt removed (in MT) | Inter Departmental Problem faced (if any)
Shah. North Zone
E.E(M)-I-Sh. North
1 | Nalla in Old Seemapuri G block to Pump house | 1361 | 31.03.2019 | 01.05.2019 | 30.05.2019 | 41.0122 | 235 | _ | 1361 | 1.2 | 2 | 0.3 | 490 | 573
2 | Desilting of nalla from SSBL drain Jalli Kheda Vill. To SDN Hopt. Road in W.No. 241 | 135 | 26.03.2019 | 15.04.2019 | 15.06.2019 | 85.5263 | 65 | _ | 135 | 2.4 | 3 | 0.2 | 65 | 76
3 | SSBL drain from 100Ft. road no.68 to G.T.Road flyover Rd 1081 to 1481 mtr | 400 | 26.03.2019 | 15.04.2019 | 15.06.2019 | 33.7591 | 185 | _ | 400 | 6.5 | 1.8 | 0.18 | 468 | 548
4 | SSBL drain from 100Ft. road no.68 to G.T.Road flyover Rd 1481 to 1946 mtr | 510 | 26.03.2019 | 15.04.2019 | 15.06.2019 | 37.9656 | 265 | _ | 510 | 6.5 | 1.8 | 0.18 | 597 | 698
5 | SSBL drain from 100Ft. road no.68 to G.T.Road flyover Rd 1946 to 2362 mtr. | 397 | 26.03.2019 | 15.04.2019 | 15.06.2019 | 54.4513 | 263 | _ | 397 | 5.2 | 1.9 | 0.2 | 413 | 483
6 | SSBL drain from 100Ft. road no.68 to G.T.Road flyover Rd 2362 to 2702 mtr. | 314 | 26.03.2019 | 15.04.2019 | 15.06.2019 | 45.4545 | 170 | _ | 314 | 5.1 | 2 | 0.2 | 320 | 374
7 | Nallah along DDA park from MCD sotre to Q-Pkt. Drain in Dilshad Garden | 310 | 26.03.2019 | 15.04.2019 | 01.06.2019 | 89.0411 | 65 | _ | 310 | 1 | 1.6 | 0.2 | 62 | 73
8 | Nallah from Tahirpur Sarai to R-Pkt. Dilshad Garden | 150 | 26.03.2019 | 15.04.2019 | 30.05.2019 | 84.9057 | 45 | _ | 150 | 1 | 1.5 | 0.3 | 45 | 53
9 | Nallah from Gali No-8 Jagatpuri extn. Unauthorized colony | 90 | 26.03.2019 | 15.04.2019 | 30.05.2019 | 87.5 | 14 | _ | 90 | 0.75 | 1 | 0.2 | 14 | 16
10 | Nallah along DDA park from P-15/A-4 to MCD Store Dilshad Garden | 330 | 26.03.2019 | 15.04.2019 | 15.06.2019 | 100 | 59 | _ | 330 | 1 | 1.5 | 0.15 | 50 | 59
11 | Nalla in new seemapuri from E-blk to Machli Market | 220 | 25.03.2019 | 26.03.2019 | 15.06.2019 | 31.3725 | 16 | _ | 220 | 1 | 1.5 | 0.2 | 44 | 51
12 | Nalla in Tahirpur village from Shiv mandir to Kali mandir | 240 | 25.03.2019 | 26.03.2019 | 15.06.2019 | 45.7143 | 16 | _ | 240 | 1.25 | 1.4 | 0.1 | 30 | 35
13 | Nalla in E-Block Jhuggi Nalla New Seemapuri | 100 | 25.03.2019 | 26.03.2019 | 04.05.2019 | 100 | 13 | _ | 100 | 0.7 | 1.7 | 0.15 | 11 | 13
14 | Nalla in New seemapuri from Bhopal Pulia to Dhobi Ghat | 110 | 25.03.2019 | 26.03.2019 | 30.05.2019 | 76.1905 | 16 | _ | 110 | 0.8 | 1.5 | 0.2 | 18 | 21
15 | SSBL drain from Wazirabad Road to Ashok Nagar railway phatak (Hanuman Pulia) | 540 | 26.03.2019 | 07.04.2019 | 15.06.2019 | 38.9306 | 415 | _ | 540 | 6.75 | 1.55 | 0.25 | 911 | 1066
16 | Internal nallas in D- block Nand Nagari from D-1/275 to D-1/231 to Upto D-3/355 | 190 | 26.03.2019 | 28.03.2019 | 15.06.2019 | 37.037 | 10 | _ | 190 | 0.6 | 1.3 | 0.2 | 23 | 27
17 | Nalla both side E block pump house nalla in Nand Nagari from E-4/160 to pump house including sump well | 780 | 26.03.2019 | 28.03.2019 | 15.06.2019 | 41.6667 | 65 | _ | 780 | 0.85 | 1.5 | 0.2 | 133 | 156
18 | Both side Nalla of Akhara park E -4 Block Nand Nagari | 700 | 26.03.2019 | 28.03.2019 | 15.06.2019 | 30.5344 | 40 | _ | 700 | 0.8 | 1.6 | 0.2 | 112 | 131
19 | Internal nallas in A-1/30 in A block Nand Nagari from A-2/30 to A-2 Block Nand Nagri | 525 | 26.03.2019 | 28.03.2019 | 15.06.2019 | 43.4783 | 40 | _ | 525 | 0.6 | 1.3 | 0.25 | 79 | 92
20 | Internal nallas in A-1/481 and Ujala Pulia to road No 68 towards cement godown both side | 1200 | 26.03.2019 | 28.03.2019 | 15.06.2019 | 36.3924 | 115 | _ | 1200 | 0.9 | 1.45 | 0.25 | 270 | 316
21 | Nallah from Sr. Sec. School Raja Ravin Verma corner to B-5 Block Market Nand Nagri | 375 | 26.03.2019 | 28.03.2019 | 15.06.2019 | 30.6122 | 30 | _ | 375 | 0.9 | 1.45 | 0.25 | 84 | 98
22 | Nallah from B-5 Block Market Corner to road no-68 | 150 | 26.03.2019 | 28.03.2019 | 15.06.2019 | 78.125 | 25 | _ | 150 | 0.9 | 1.45 | 0.2 | 27 | 32
23 | Nallah H.no-30 E-1 Nand Nagri to H.no-231 E-Block Nand Nagri | 115 | 26.03.2019 | 28.03.2019 | 15.06.2019 | 76.9231 | 20 | _ | 115 | 1.3 | 1.4 | 0.15 | 22 | 26
24 | Nallah from H.no-481 E-2 Nand Nagri to H.no-280 E-2 Block Nand nagri | 115 | 26.03.2019 | 28.03.2019 | 15.06.2019 | 42.8571 | 15 | _ | 115 | 1.3 | 1.4 | 0.2 | 30 | 35
25 | Nalla along Murga Mkt. in G & H block Sunder Nagari from mandir to Upto pumphouse including sump well | 589 | 25.03.2019 | 07.05.2019 | 30.06.2019 | 28.8462 | 45 | _ | 589 | 0.75 | 1.3 | 0.3 | 133 | 156
26 | Nalla in L Block Sunder Nagari from police chowki to L-55 Sunder Nagari | 478 | 25.03.2019 | 07.05.2019 | 30.06.2019 | 55.9748 | 89 | _ | 478 | 0.95 | 1.5 | 0.3 | 136 | 159
27 | nalla in sunder nagari from M.C. Primary school to Sani bazar mandi along F2 sunder nagari | 254 | 25.03.2019 | 07.05.2019 | 30.06.2019 | 62.069 | 18 | _ | 254 | 0.65 | 1.2 | 0.15 | 25 | 29
28 | Desilting of nallah in Bhagirathi Vihar from Brijpuri culvert to Drain No.1 in W.No.261 Shah.North Zone. | 1410 | 31.03.2019 | 05.04.2019 | 15.06.2019 | 59.3023 | 102 | _ | 1410 | 1.04 | 1.5 | 0.1 | 147 | 172
29 | Desilting of nallah in Ambedkar Colony from main road Johripur to Drain no.1 in W.No.261 Shah.North Zone. | 278 | 31.03.2019 | 05.04.2019 | 05.05.2019 | 100 | 46 | _ | 278 | 0.7 | 1.15 | 0.2 | 39 | 46
30 | Desilting of nallah from main road Johari Pur along Johari pur Ext. to block, main road (both side) to Drain no.1 in W.No.261 Shah.North Zone. | 560 | 31.03.2019 | 05.04.2019 | 15.06.2019 | 76.2712 | 45 | _ | 560 | 0.45 | 1.3 | 0.2 | 50 | 59
31 | Desilting of nallah along C-block, main road to Ganga Vihar W.No.261 Shah.North Zone. | 540 | 31.03.2019 | 15.04.2019 | 15.06.2019 | 73.6842 | 70 | _ | 540 | 0.6 | 2 | 0.25 | 81 | 95
32 | Desilting of internal nallah A,B,C & D block to pump house to school block, Ambey Cycle to post office and Kaushik Garment to M.C. Pry. School B-block in Gokulpuri W.No.262 Shah.North Zone. | 380 | 31.03.2019 | 15.04.2019 | 15.06.2019 | 90.1639 | 55 | _ | 380 | 0.55 | 1.1 | 0.25 | 52 | 61
33 | Desilting of nallah from Amar Colony to Loni road flyover in W.No.262 Shah.North Zone. | 285 | 31.03.2019 | 15.04.2019 | 15.06.2019 | 80 | 64 | _ | 285 | 0.95 | 1.5 | 0.25 | 68 | 80
34 | Desilting of nallah C-block, jhuggi area along main road up to Pump house i.e sump well in Gokulpuri W.No.262 Shah.North Zone. | 508 | 31.03.2019 | 15.04.2019 | 15.06.2019 | 71.4286 | 55 | _ | 508 | 0.65 | 1.3 | 0.2 | 66 | 77
35 | Desilting of nallah along main road Ganga Vihar from dhalao to drain no.1 along A,B,D & F block in Ganga Vihar W.No.262 Shah.North Zone. | 600 | 31.03.2019 | 15.04.2019 | 15.06.2019 | 71.4286 | 75 | _ | 600 | 0.6 | 1 | 0.25 | 90 | 105
36 | Desilting of nallah from main road Ganga Vihar to Gokulpur Village W.No.262 Shah.North Zone. | 340 | 31.03.2019 | 15.04.2019 | 15.06.2019 | 72.9167 | 35 | _ | 340 | 0.6 | 1 | 0.2 | 41 | 48
37 | Nalla from Shamshan Ghat to Saboli goan bada kuan (Rathore Cement Store) | 700 | 31.03.2019 | 05.04.2019 | 30.05.2019 | 51.0204 | 50 | _ | 700 | 0.6 | 1.2 | 0.2 | 84 | 98
38 | Nalla along railway line from Saboli Phatak | 620 | 31.03.2019 | 05.04.2019 | 30.05.2019 | 78.5441 | 205 | _ | 620 | 1.2 | 1.3 | 0.3 | 223 | 261
39 | Nalla on both side along Gali No 9 Bank Colony Harsh Vihar dividing road from Jail B/wall to Budh Vihar Chowk | 400 | 31.03.2019 | 05.04.2019 | 06.05.2019 | 96.7213 | 59 |  | 400 | 0.65 | 1.1 | 0.2 | 52 | 61
40 | Nalla from P.W.D P/house Harsh Vihar to Jail Boundary wall | 1370 | 31.03.2019 | 05.04.2019 | 30.05.2019 | 70.8333 | 255 |  | 1370 | 0.9 | 2.1 | 0.25 | 308 | 360
41 | Nalla on both side along bank colony Road from Wazirabad road to Kishan Lal Chowk | 960 | 31.03.2019 | 05.04.2019 | 30.05.2019 | 63.4921 | 80 |  | 960 | 0.75 | 1.2 | 0.15 | 108 | 126
| Total | 19629 |  |  |  |  | 3550 |  | 19629 |  |  |  | 6021 | 7045
E.E-(M)-II-Sh. North
1 | Gokalpur drain | 2000 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 36.8844 | 1015 |  | 2000 | 4.2 | 4.57 | 0.28 | 2352 | 2751.84
2 | Drain Gamri road to Gokalpur drain | 100 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 87.2144 | 25 |  | 100 | 0.7 | 1.35 | 0.35 | 24.5 | 28.665
3 | Gokalpur drain from Ivth pusta to Culvert near M.C. Pry. School | 1984 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 29.4582 | 875 |  | 1984 | 4.57 | 4.57 | 0.28 | 2538.7264 | 2970.3099
4 | DrainGali No. 12 X-Block Brahmpuri to Gokalpur drain | 400 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 83.7942 | 120 |  | 400 | 0.9 | 1.2 | 0.34 | 122.4 | 143.208
5 | Drain from Gokalpur drain to Khaddey wali Masjid | 1000 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 42.735 | 120 |  | 1000 | 0.6 | 1.05 | 0.4 | 240 | 280.8
6 | Drain from Gautam Vihar chowk to Gokalpur drain | 400 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 90.812 | 102 |  | 400 | 0.6 | 1.05 | 0.4 | 96 | 112.32
7 | Drain from Gamri road to Gali No. 1 Khaddey wali masjid (RHS) | 900 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 75.9734 | 96 |  | 900 | 0.6 | 1.05 | 0.2 | 108 | 126.36
8 | Drain from Gamri road to Gali no. 1Brahmpuri (LHS) | 600 | 2019-02-04 | 2019-03-29 | 2019-05-31 | 83.0959 | 70 |  | 600 | 0.6 | 1.05 | 0.2 | 72 | 84.24
9 | Drain from Main market Bhajanpura gali no. 14 to Wazirabad road RHS | 400 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 97.3409 | 41 |  | 400 | 0.6 | 1.2 | 0.15 | 36 | 42.12
10 | Drain from B-1 Block Yamuna Vihar to B-3 Block Yamuna Vihar | 660 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 90.6501 | 105 |  | 660 | 1 | 2 | 0.15 | 99 | 115.83
11 | Drain from B-4 Block Dividing road to S.S. School Yamuna Vihar | 650 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 89.4149 | 102 |  | 650 | 1 | 1.8 | 0.15 | 97.5 | 114.075
12 | Drain from Sachdeva Marriage home to Bhajanpura pump house | 380 | 2019-02-04 | 2019-03-29 | 2019-05-31 | 89.9685 | 54 |  | 380 | 0.9 | 2.15 | 0.15 | 51.3 | 60.021
13 | Drain from dividing road to C-10 Nursery Yamuna Vihar | 535 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 95.8543 | 54 |  | 535 | 0.6 | 1.1 | 0.15 | 48.15 | 56.3355
14 | Drain from Bhagat Singh Pump house to C-12, Yamuna Vihar Shiv Shakti mandir | 692 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 68.6176 | 75 |  | 692 | 0.9 | 2.5 | 0.15 | 93.42 | 109.3014
15 | Drain from Patel road from Patel chowk to Harizan Basti gali no. 1 Pucca road in ward no. 265 | 400 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 94.9668 | 84 |  | 400 | 0.63 | 1.3 | 0.3 | 75.6 | 88.452
16 | Drain Karawal Nagar road from Shiv Vihar chowk | 1000 | 2019-01-31 | 2019-04-10 | 2019-05-31 | 55.7138 | 176 |  | 1000 | 0.9 | 1.5 | 0.3 | 270 | 315.9
17 | Drain Shiv Vihar Tiraha | 175 | 2019-01-31 | 2019-04-10 | 2019-05-31 | 81.4001 | 45 |  | 175 | 0.9 | 2 | 0.3 | 47.25 | 55.2825
18 | Drain 33' road from Karawal Nagar | 690 | 2019-01-31 | 2019-04-10 | 2019-05-31 | 88.0851 | 160 |  | 690 | 0.75 | 1.5 | 0.3 | 155.25 | 181.6425
19 | Drain Industrial area Nall from Karawal Nagar road | 250 | 2019-01-31 | 2019-04-10 | 2019-05-31 | 75.9734 | 40 |  | 250 | 0.6 | 1.2 | 0.3 | 45 | 52.65
20 | Drain Brijpuri road from gali no.1 to shiv Vihar Tiraha | 450 | 2019-01-31 | 2019-04-10 | 2019-05-31 | 91.4495 | 130 |  | 450 | 0.9 | 2 | 0.3 | 121.5 | 142.155
21 | Drain Karawal Nagar road from Shiv Vihar Tiraha to Mukhiya market | 1350 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 76.2079 | 260 |  | 1350 | 0.9 | 1.5 | 0.24 | 291.6 | 341.172
22 | Drain from Karawal Nagar road from Dayalpur 33' feet road | 1100 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 94.9668 | 220 |  | 1100 | 0.6 | 1.5 | 0.3 | 198 | 231.66
23 | Drain Karawal Nagar road from Chand bagh culvert to Sherpur Chowk | 800 | 2019-01-31 | 2019-04-10 | 2019-05-31 | 65.2896 | 220 |  | 800 | 1.5 | 1.5 | 0.24 | 288 | 336.96
24 | Drain 25' road from Sanjay chowk road to Fauzi market | 750 | 2019-01-31 | 2019-04-10 | 2019-05-31 | 67.5319 | 160 |  | 750 | 0.9 | 1.25 | 0.3 | 202.5 | 236.925
25 | Drain Karawal Nagar road from Sherpur chowk to Jodha ram gali no. 1 | 475 | 2019-01-31 | 2019-04-10 | 2019-05-31 | 97.9657 | 245 |  | 475 | 1.5 | 1.5 | 0.3 | 213.75 | 250.0875
26 | Drain from 33' road from 25' road chowk to Gali No. 1 Nehru Vihar | 800 | 2019-01-31 | 2019-04-10 | 2019-05-31 | 81.4001 | 160 |  | 800 | 0.7 | 1.2 | 0.3 | 168 | 196.56
27 | Drain from Gali No. 6 from 25' road to Escape drain in ward no. 267 | 300 | 2019-01-31 | 2019-04-10 | 2019-05-31 | 93.5279 | 130 |  | 300 | 1.2 | 1.5 | 0.33 | 118.8 | 138.996
28 | Drain Gali No. 8 from 25' road to Escape drain | 300 | 2019-01-31 | 2019-04-10 | 2019-05-31 | 80.7217 | 102 |  | 300 | 1.2 | 1.5 | 0.3 | 108 | 126.36
29 | Drain Brijpuri road from escape drain | 600 | 2019-01-31 |  | 2019-05-31 | 47.1342 | 135 |  | 600 | 1.2 | 1.5 | 0.34 | 244.8 | 286.416
30 | Drain Brijpuri road from escape drain to Gali no. 1 Mustafabad | 814 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 44.9167 | 154 |  | 814 | 1.2 | 1.6 | 0.3 | 293.04 | 342.8568
31 | Drain 33' road from Brijpuri road to 25' Chowk | 615 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 69.4879 | 102 |  | 615 | 0.6 | 1.25 | 0.34 | 125.46 | 146.7882
32 | Drain 33' road from Brijpuri road to 25' chowk | 615 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 64.7191 | 95 |  | 615 | 0.6 | 1.25 | 0.34 | 125.46 | 146.7882
| Total | 22185 |  |  |  |  | 5472 |  | 22185 | 34.55 |  |  | 9071.0064 | 10613.0775
E.EM)-III-Sh. North
1 | SSBL drian from Natthu Colony Railway Crossimg to C-3 Nand Nagari | 480 | 09.02.19 | 20.04.19 | 31.05.19 | 100 | 1010 |  | 480 | 6 | 1.8 | 0.3 | 864 | 1010 | 100%
2 | Nalla along East nathu Colony in C-37E | 350 | 2019-02-09 | 16.04.19 | 31.05.19 | 21.5227 | 8 |  | 350 | 0.6 | 1.5 | 0.15 | 31.5 | 37.17 | 20% | 7.434
3 | Hardevparl nalla from Hardevpuri to loni Rd. pump house. | 1400 | 15.02.19 | 01.05.19 | 31.05.19 | 44.2177 | 65 |  | 1400 | 0.9 | 1.5 | 0.1 | 126 | 147 | 5% | 29.4
4 | 52 cusec drain from Mandoli Rd. to loni Rd. | 640 | 09.02.19 | 20.04.19 | 31.05.19 | 79.6178 | 375 |  | 640 | 4.2 | 3.6 | 0.15 | 403.2 | 471 | 70%
5 | Covered drain from Loni road to Mother Dairy kabool Nagar | 250 | 2019-02-09 | 25.04.19 | 31.05.19 | 127.1186 | 45 |  | 250 | 1.2 | 1.2 | 0.1 | 30 | 35.4 | 20%
6 | Covered drain from 1/143 Sri Ram nagar to Shri Ram Nagar pump house internal nalla | 524 | 2019-02-09 | 25.04.19 | 31.05.19 | 74.1256 | 55 |  | 524 | 1.2 | 1.8 | 0.1 | 62.88 | 74.1984 | 20%
7 | Moti Ram road nalla from loni road pump house to mandoli road dhalao | 191 | 2019-02-09 | 25.04.19 | 31.05.19 | 42.663 | 15 |  | 191 | 1.3 | 1.8 | 0.12 | 29.796 | 35.1593 | 20%
8 | Naveen Shahdara Nalla at G.T Road to pump house naveen Shahdara | 900 | By Departmental | 15.04.19 | 31.05.19 | 35.7143 | 45 |  | 900 | 1.2 | 0.6 | 0.1 | 108 | 126 | 25%
9 | Khajoor wala nalla ( Covered drain) Naveen Shah. From gali No.2 West Rohtash Nagar to Naveen Shadara drain. | 341 | By Departmental | 15.04.19 | 31.05.19 | 22.0908 | 10 |  | 341 | 0.75 | 1.5 | 0.15 | 38.3625 | 45.2677 | 20%
10 | Chintamani pond drain from the point near power station to the jali behind Zonal Office | 300 | By Departmental | 15.04.19 | 31.05.19 | 34 | 34 |  | 300 | 1.9 | 2.1 | 0.15 | 85.5 | 100 | 25%
11 | Punchsheel Garden nalla along sarovar marg to the jail opp. Muskan Restaurent on 65 No. road | 30 | By Departmental | 15.04.19 | 31.05.19 | 94.162 | 5 |  | 30 | 1 | 1.43 | 0.15 | 4.5 | 5.31 | 10%
12 | Mochi Mkt. drain from Ravi Dass Mandir to Kabristan Culvert | 225 | By Departmental | 12.04.19 | 31.05.19 | 8.0645 | 5 |  | 225 | 1.58 | 1.6 | 0.15 | 53.325 | 62 | 10%
13 | Kabootar market drain from Mochi mkt. Drain (near kabristan) to masjid | 100 | By Departmental | 12.04.19 | 31.05.19 | 52.9661 | 10 |  | 100 | 0.8 | 1.15 | 0.2 | 16 | 18.88 | 15%
14 | Nalla from Mohanpuri school to gali no.16 Adrash mohalla vijay park | 285 | By Departmental | 22.04.19 | 31.05.19 | 23.1275 | 7 |  | 285 | 0.6 | 1.2 | 0.15 | 25.65 | 30.267 | 10%
15 | Nalla from C-12, Pump House to Priya Panchvati Yamuna Vihar C-11/8. | 510 | By Departmental | 22.04.19 | 31.05.19 | 21.917 | 15 |  | 510 | 0.8 | 1.8 | 0.15 | 58 | 68.44 | 15%
16 | Nalla from Krishna Park A-Block North Ghonda to Gamri pump house | 670 | By Departmental | 22.04.19 | 31.05.19 | 16.3934 | 20 |  | 670 | 1 | 1.8 | 0.15 | 105 | 122 | 10%
17 | Nalla gali no. 16 Vijay park to Road No. 66. | 330 | By Departmental | 22.04.19 | 31.05.19 | 33.7902 | 15 |  | 330 | 0.76 | 2.44 | 0.15 | 37.62 | 44.3916 | 10%
18 | Kardam Marg nalla from Harkishan Public School to Drain No. 1 Kardam Puri. | 350 | By Departmental | 12.04.19 | 31.05.19 | 72.6392 | 27 |  | 350 | 0.6 | 1.2 | 0.15 | 31.5 | 37.17 | 40%
19 | 52 cusec drain from drain No.1 to Babarpur Road | 750 | 2019-02-09 | 26.04.19 | 31.05.19 | 3.5488 | 28 |  | 750 | 6 | 4.5 | 0.15 | 675 | 789 | 50%
20 | Drain from M.I office, New Zafrabad to 52 Cusec drain. | 190 | By Departmental | 26.04.19 | 31.05.19 | 77.4358 | 25 |  | 190 | 1.2 | 1.2 | 0.12 | 27.36 | 32.2848 | 20%
21 | Drain from Gulati Tent House , New Zafrabad to 52 Cusec drain. | 110 | By Departmental | 26.04.19 | 31.05.19 | 87.3138 | 17 |  | 110 | 1 | 1.2 | 0.15 | 16.5 | 19.47 | 20%
22 | Drain opp. BSES office DDA colony New Zafrabad to 52 Cusec drain. | 90 | By Departmental | 26.04.19 | 31.05.19 | 55.7997 | 8 |  | 90 | 0.9 | 1.1 | 0.15 | 12.15 | 14.337 | 10%
23 | Drain from 52 cusec to pt. near H.No. B-64, Sudama Puri Ext. | 90 | By Departmental | 26.04.19 | 31.05.19 | 94.162 | 15 |  | 90 | 1 | 1.2 | 0.15 | 13.5 | 15.93 | 10%
24 | 52 cusec drain from Loni Road to Babarpur Road | 1100 | 09.02.19 | 01.05.19 | 31.05.19 | 8.8083 | 102 |  | 1100 | 6 | 3.6 | 0.15 | 990 | 1158 | 20%
| Total | 10206 |  |  |  |  | 1961 |  | 10206 |  |  |  | 3845.3435 | 4498.6758
E.E(M)-IV-Sh. North
1 | Gokal Pur drain | 280 | 2019-04-04 | 2019-04-14 | 2019-05-30 | 80.3118 | 1230 |  | 280 | 8.5 | 4 | 0.55 | 1309 | 1531.53 | 85%
2 | CPJ & K Block Nalla | 580 | 2019-03-28 | 2019-04-07 | 2019-05-30 | 82.6122 | 370 |  | 580 | 1.2 | 1.3 | 0.55 | 382.8 | 447.876 | 55%
3 | J.J Cluster Nalla | 550 | 2019-03-28 | 2019-04-07 | 2019-05-30 | 67.6448 | 185 |  | 550 | 0.85 | 1.25 | 0.5 | 233.75 | 273.4875 | 55%
4 | Fruit Market Nalla | 320 | 2019-03-28 | 2019-04-07 | 2019-05-30 | 59.989 | 105 |  | 320 | 0.85 | 1.2 | 0.55 | 149.6 | 175.032 | 85%
5 | Gokulpur drain | 750 | 2019-04-15 | 2019-04-25 | 2019-06-15 | 57.6657 | 1556 |  | 750 | 4.1 | 2.5 | 0.75 | 2306.25 | 2698.3125 | 30%
6 | Moni Baba Nalla | 544 | 2019-04-02 | 2019-04-12 | 2019-05-30 | 54.9899 | 105 |  | 544 | 0.75 | 1.5 | 0.4 | 163.2 | 190.944 | 82%
7 | Rajender Parsad Marg drain | 175 | 2019-03-28 | 2019-04-07 | 2019-06-15 | 57.8845 | 40 |  | 175 | 0.75 | 1.5 | 0.45 | 59.0625 | 69.1031 | 0
8 | Vijay Park Nalla | 290 | 2019-03-28 | 2019-04-07 | 2019-05-30 | 82.8912 | 90 |  | 290 | 0.8 | 1.2 | 0.4 | 92.8 | 108.576 | 55%
9 | Gokal Pur drain | 433 | 2019-03-28 | 2019-04-07 | 2019-06-15 | 43.8449 | 479 |  | 415 | 4.5 | 4 | 0.5 | 933.75 | 1092.4875 | 0
10 | Karawal Nagar road Nalla | 540 | 2019-04-02 | 2019-04-12 | 2019-05-30 | 72.2573 | 210 |  | 540 | 1.15 | 1.3 | 0.4 | 248.4 | 290.628 | 65%
11 | Karawal Nagar road Nalla | 675 | 2019-04-02 | 2019-04-12 | 2019-05-30 | 67.5319 | 224 |  | 675 | 1.4 | 1.5 | 0.3 | 283.5 | 331.695 | 65%
12 | Karawal Nagar road Nalla | 1550 | 2019-03-28 | 2019-04-07 | 2019-05-30 | 45.0326 | 294 |  | 1550 | 0.9 | 1.3 | 0.4 | 558 | 652.86 | 60%
13 | C Block Nalla | 470 | 2019-03-28 | 2019-04-07 | 2019-05-30 | 95.2554 | 110 |  | 470 | 0.6 | 1.3 | 0.35 | 98.7 | 115.479 | 75%
14 | Pusta road Nalla | 1200 | 2019-03-28 | 2019-04-07 | 2019-05-30 | 83.4351 | 205 |  | 1200 | 0.5 | 1.25 | 0.35 | 210 | 245.7 | 45%
15 | Karawal Nagar road Nalla | 900 | 2019-03-28 | 2019-04-07 | 2019-05-30 | 94.9668 | 280 |  | 900 | 0.8 | 1.25 | 0.35 | 252 | 294.84 | 70%
16 | Mariginal Bandh Ist pusta Nalla | 1100 | 2019-03-28 | 2019-04-07 | 2019-05-30 | 66.7948 | 245 |  | 1100 | 0.75 | 1.3 | 0.38 | 313.5 | 366.795 | 20%
17 | Mariginal Bandh IInd pusta Nalla | 500 | 2019-03-28 | 2019-04-07 | 2019-05-30 | 86.5082 | 125 |  | 500 | 0.65 | 1.2 | 0.38 | 123.5 | 144.495 | 40%
| Total | 10839 |  |  |  |  | 5853 |  | 10839 |  |  |  | 7717.8125 | 9029.8406
Shah. South Zone
S. No. | Name of Drain | Length of Drain (in Mtr) | Date of issue of desilting tender | Date of Commencement of Desilting | Excepted Date of Completion of Desilting | Progres of Work (in %) | Quantity of Silt removed (in MT) | Inter Departmental Problem faced (if any) |  |  |  |  | Aprox. Volume of silt to be desilted (in Cum) | Aprox. Weight of silt to be desilted (in MT)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | Length of Drain (in Mtr) | Width of Drain (in Mtr) | Depth of drain (in Mtr) | Depth of Silt (in Mtr)
E.E(M)-I-Sh.S
1 | Mahila Colony drain | 400 | Departmental |  | 31.05.19 | 5.9866 | 5 | _ | 400 | 0.9 | 1.3 | 0.2 | 72 | 83.52
2 | Geeta Colony, Katcha Drain | 600 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 600 | 2 | 1.5 | 0.2 | 240 | 278.4
3 | Krishna Nagar drain | 400 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 400 | 1.75 | 1.3 | 0.2 | 140 | 162.4
4 | Radhey puri drain H Block, . | 230 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 230 | 2 | 1.35 | 0.3 | 138 | 160.08
5 | Drain at Krishna nagar , Krishna Nagar | 320 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 320 | 1 | 1.4 | 0.3 | 96 | 111.36
6 | Sumpwell Krishna Nagar | 6.4 | Departmental | - | 31.05.19 | 0 | 0 |  | 6.4 | 2.5 | 1 | 0.55 | 8.8 | 10.208
7 | Hari Singh Gurdwara | 570 | Departmental | - | 31.05.19 | 15.124 | 15 |  | 570 | 0.6 | 1.5 | 0.25 | 85.5 | 99.18
8 | Jagat puri drain | 1215 | 2019-03-26 | 04.04.19 | 31.05.19 | 39.7714 | 150 | _ | 1215 | 2.23 | 3 | 0.12 | 325.134 | 377.1554
9 | Bhagat Singh Nalla | 1460 | 2019-03-26 | 04.04.19 | 31.05.19 | 41.3321 | 105 | _ | 1460 | 1 | 2 | 0.15 | 219 | 254.04
10 | 6-12 Block Nalla (LHS) | 400 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 400 | 0.75 | 1.35 | 0.25 | 75 | 87
11 | 6-12 Block Nalla (RHS) | 400 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 400 | 0.75 | 1.35 | 0.25 | 75 | 87
12 | Geeta Colony drain | 1300 | 2019-04-04 | 13.04.19 | 31.05.19 | 0 | 0 | _ | 1300 | 2.5 | 2.5 | 0.2 | 650 | 754
13 | Sump Well. (Shastri Park) | 2 | Departmental |  | 31.05.19 | 0 | 0 |  | 2 | 5 x 5 | 0.6 | 0.15 | 8 | 9.28
14 | Kailash Nagar drain | 760 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 760 | 1.2 | 2 | 0.2 | 182.4 | 211.584
15 | Fish market drain | 150 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 150 | 1 | 1.5 | 0.25 | 37.5 | 43.5
16 | Sumpwell Kailash Nagar | 5 | Departmental |  | 31.05.19 | 0 | 0 | _ | 5 | 4 | 0.6 | 0.4 | 8 | 9.28
17 | Shastri Park drain | 600 | 2019-03-26 | 04.04.19 | 31.05.19 | 7.3681 | 20 | _ | 600 | 1.3 | 1.8 | 0.3 | 234 | 271.44
18 | East Azad Nagar drain | 520 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 520 | 1.5 | 0.75 | 0.1 | 78 | 90.48
19 | Krishna Nagar drain | 405 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 405 | 1.8 | 2 | 0.1 | 72.9 | 84.564
20 |  | 390 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 390 | 1.8 | 0.75 | 0.15 | 105.3 | 122.148
21 | Shankar Nagar nalla | 540 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 540 | 1.5 | 1.1 | 0.15 | 121.5 | 140.94
22 |  | 120 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 120 | 1.6 | 1.1 | 0.15 | 28.8 | 33.408
23 |  | 270 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 270 | 1.7 | 1.8 | 0.15 | 68.85 | 79.866
24 | Scooter market Drain | 500 | 2019-04-04 | 13.04.19 | 31.05.19 | 36.0153 | 47 | _ | 500 | 1.5 | 0.65 | 0.15 | 112.5 | 130.5
25 | Ajeet Nagar drain | 700 | 2019-04-04 | 13.04.19 | 31.05.19 | 27.0936 | 55 | _ | 700 | 1.25 | 2 | 0.2 | 175 | 203
26 | Raghubar pura drain LHS Lal | 250 | 2019-04-04 | 13.04.19 | 31.05.19 | 30.6513 | 12 | _ | 250 | 0.9 | 1 | 0.15 | 33.75 | 39.15
27 | Raghubar pura drain RHS | 250 | 2019-04-04 | 13.04.19 | 31.05.19 | 25.5428 | 10 | _ | 250 | 0.9 | 1 | 0.15 | 33.75 | 39.15
28 | Kashyap Mohalla drain | 250 | 2019-04-04 | 13.04.19 | 31.05.19 | 79.1826 | 31 | _ | 250 | 0.9 | 1 | 0.15 | 33.75 | 39.15
29 | Ramnagar drain | 300 | 2019-04-04 | 13.04.19 | 31.05.19 | 0 | 0 | _ | 300 | 1.6 | 1 | 0.15 | 72 | 83.52
30 | Raghubarpura Drain (RHS) | 900 | 2019-04-04 | 13.04.19 | 31.05.19 | 0 | 0 | _ | 900 | 1.75 | 1.05 | 0.15 | 236.25 | 274.05
31 | Raghubarpura drain (LHS) | 600 | 2019-04-04 | 13.04.19 | 31.05.19 | 0 | 0 | _ | 600 | 1.65 | 1.05 | 0.15 | 148.5 | 172.26
32 | Nalla along main road Seelampur | 570 | 2019-04-04 | 13.04.19 | 31.05.19 | 0 | 0 |  | 570 | 1.5 | 1.1 | 0.15 | 128.25 | 148.77
| Total | 15383.4 |  |  |  |  | 450 |  | 15383.4 |  |  |  | 4043.434 | 4690.3834
E.E(M)-II-Sh.S
33 | Drain along Gharonda Apptt, | 460 | - | - | 31.05.19 | 72.2573 | 35 | _ | 460 | 0.6 | 1.2 | 0.15 | 41.4 | 48.438
34 | Kasturba drain | 1200 | 31.03.19 | 01.04.19 | 31.05.19 | 62.1939 | 635 | _ | 1200 | 4.1 | 3.75 | 0.15 | 738 | 863.46
|  | 300 | 31.03.19 | 01.04.19 | 31.05.19 |  |  | _ | 300 | 3 | 3.75 | 0.15 | 135 | 157.95
35 | Nakul Gali drain Vishwas Nagar | 483 | 31.03.19 | 01.04.19 | 31.05.19 | 81.269 | 62 | _ | 483 | 0.9 | 1.5 | 0.15 | 65.205 | 76.2898
36 | Gali No.10, drain Vishwas Nagar | 220 | 31.03.19 | 01.04.19 | 31.05.19 | 77.7001 | 30 | _ | 220 | 0.75 | 1.5 | 0.2 | 33 | 38.61
37 | Gali No.3 drain Vishwas Nagar | 402 | 31.03.19 | 01.04.19 | 31.05.19 | 78.7452 | 50 | _ | 402 | 0.9 | 1.5 | 0.15 | 54.27 | 63.4959
38 | 18 Qtr. To New Vishwas Nagar drain | 180 | 31.03.19 | 01.04.19 | 31.05.19 | 87.6289 | 85 | _ | 180 | 0.6 | 1.5 | 0.15 | 16.2 | 18.954
|  | 213 | 31.03.19 | 01.04.19 | 31.05.19 |  |  | _ | 213 | 0.9 | 1.5 | 0.15 | 28.755 | 33.6433
|  | 174 | 31.03.19 | 01.04.19 | 31.05.19 |  |  | _ | 174 | 0.6 | 1.5 | 0.15 | 15.66 | 18.3222
|  | 200 | 31.03.19 | 01.04.19 | 31.05.19 |  |  | _ | 200 | 0.75 | 1.5 | 0.15 | 22.5 | 26.325
39 | Gazipur Village drain | 800 | 26.03.19 | - | 31.05.19 | 106.1254 | 149 | _ | 800 | 0.75 | 1.8 | 0.2 | 120 | 140.4
40 | Arya Nagar drain | 625 | 26.03.19 | 01.04.19 | 31.05.19 | 42.735 | 225 | _ | 625 | 3.6 | 1.8 | 0.2 | 450 | 526.5
41 | Pandav Road Nallah | 450 | 26.03.19 | - | 31.05.19 | 73.0514 | 50 | _ | 450 | 0.65 | 1.2 | 0.2 | 58.5 | 68.445
42 | Satgarh Nallah | 400 | 26.03.19 | 01.04.19 | 31.05.19 | 28.49 | 20 | _ | 400 | 0.75 | 0.1 | 0.2 | 60 | 70.2
43 | Tikona Park Nallah | 225 | 26.03.19 | 01.04.19 | 31.05.19 | 85.4701 | 45 | _ | 225 | 1 | 1.4 | 0.2 | 45 | 52.65
44 | Bhola Nath Nagar Nallah | 1100 | 26.03.19 | - | 31.05.19 | 60.2176 | 155 | _ | 1100 | 1 | 1.5 | 0.2 | 220 | 257.4
45 | Nalla along Railway line | 1000 | 26.03.19 | 01.04.19 | 31.05.19 | 83.5708 | 352 | _ | 1000 | 1.2 | 1.35 | 0.3 | 360 | 421.2
46 | Swami Amardev Nalla | 425 | 26.03.19 | - | 31.05.19 | 50.2765 | 45 | _ | 425 | 1.2 | 1.5 | 0.15 | 76.5 | 89.505
47 | Vishwkarma Nagar Nalla | 900 | 26.03.19 | 01.04.19 | 31.05.19 | 88.6356 | 280 | _ | 900 | 1.5 | 2.1 | 0.2 | 270 | 315.9
48 | Janta Flat Nalla | 852 | 26.03.19 | 01.04.19 | 31.05.19 | 65.5919 | 255 | _ | 852 | 1.95 | 1.8 | 0.2 | 332.28 | 388.7676
49 | Majid Road Nalla | 416 | 26.03.19 | - | 31.05.19 |  | 0 | _ | 416 | 1.15 | 1.5 | 0.2 | 95.68 | 111.9456
| Total | 11025 |  |  |  |  | 2473 | _ | 11025 |  |  |  | 3237.95 | 3788.4015
E.E(M)-III-Sh. South
50 | Nalla from Block No. 19 to 25 Central Road Trilokpuri. | 950 | 28.03.19 | 05.04.19 | 31.05.19 | 88.2353 | 150 | _ | 950 | 0.75 | 1.25 | 0.2 | 142.5 | 170
51 | Drain from Mayur Vihar Pkt-II to Gurudward Chowk. | 600 | 28.03.19 | 05.04.19 | 31.05.19 | 83.6364 | 92 | _ | 600 | 0.85 | 1.4 | 0.2 | 102 | 110
52 | Nalla from Block No. 14 to 13 Central Road Trilokpuri. | 300 | 28.03.19 | 05.04.19 | 31.05.19 | 72.7273 | 40 | _ | 300 | 0.75 | 1.25 | 0.2 | 45 | 55
53 | Sanjay drain in Trilok Puri | 950 | 28.03.19 | 05.04.19 | 31.05.19 | 90.1345 | 1005 | _ | 950 | 5 | 1.65 | 0.2 | 950 | 1115
54 | Block No. 9 to 12 (L.H.S), Trilok Puri | 700 | 28.03.19 | 05.04.19 | 31.05.19 | 80 | 120 | _ | 700 | 0.9 | 1.25 | 0.2 | 126 | 150
55 | Block No. 9 to 12 (R.H.S), Trilok Puri | 700 | 28.03.19 | 05.04.19 | 31.05.19 | 80 | 120 | _ | 700 | 0.9 | 1.25 | 0.2 | 126 | 150
56 | Block No. 15 to 18 (Internal Road). | 550 | 28.03.19 | 05.04.19 | 31.05.19 | 80.9524 | 85 | _ | 550 | 0.8 | 1.3 | 0.2 | 88 | 105
57 | Nalla from Block No. 26 to 30 Central Rd. | 880 | 28.03.19 | 05.04.19 | 31.05.19 | 72.2222 | 130 | _ | 880 | 0.75 | 1.25 | 0.2 | 132 | 180
58 | Nalla from Block No. 26 to 30 Main Rd. | 980 | 28.03.19 | 05.04.19 | 31.05.19 | 81.8182 | 45 | _ | 980 | 0.75 | 1.25 | 0.2 | 147 | 55
59 | Nalla from Block No. 31 to 36 Central Rd. | 1000 | 28.03.19 | 05.04.19 | 31.05.19 | 91.6667 | 165 | _ | 1000 | 0.75 | 1.25 | 0.2 | 150 | 180
60 | DSIDC Market to Chilla drain along Pkt-III, Mayur Vihar Phase-I. | 700 | 28.03.19 | 05.04.19 | 31.05.19 | 84 | 210 | _ | 700 | 1.2 | 1.5 | 0.25 | 210 | 250
61 | Nalla from Chilla Village to Chilla regulator | 800 | 28.03.19 | 05.04.19 | 31.05.19 | 94.7368 | 180 | _ | 800 | 1 | 2.3 | 0.2 | 160 | 190
62 | Nalla from Vashundara Enclave to New Ashok Nagar Metro Station | 1400 | 28.03.19 | 05.04.19 | 31.05.19 | 93.1373 | 950 | _ | 1400 | 2.1 | 3 | 0.3 | 882 | 1020
63 | Drain between D Block Gazipur Dairy Farm & SLF Gazipur | 252 | 28.03.19 | 05.04.19 | 31.05.19 | 100 | 59 | _ | 252 | 1 | 1.6 | 0.2 | 50.4 | 59
64 | Gazipur Out fall Nalla | 400 | 28.03.19 | 05.04.19 | 31.05.19 | 87.2727 | 240 | _ | 400 | 2.9 | 1.6 | 0.2 | 232 | 275
65 | Outfall nalla from New Ashok Nagar to P.S. Toll Tax Noida | 500 | 28.03.19 | 05.04.19 | 31.05.19 | 50.9091 | 28 | _ | 500 | 0.75 | 1.25 | 0.2 | 75 | 55
66 | Drain between C & D Block Gazipur Dairy Farm | 225 | 28.03.19 | 05.04.19 | 31.05.19 | 72.7273 | 40 | _ | 225 | 0.75 | 1.25 | 0.2 | 33.75 | 55
67 | Drain along Animal Hospital Gazipur Dairy Farm (L.H.S) | 780 | 28.03.19 | 05.04.19 | 31.05.19 | 69.2308 | 135 | _ | 1100 | 1 | 2.3 | 0.2 | 220 | 195
68 | Drain of road from Block No. 19 to 21 Kalyan Puri L/R | 1100 | 28.03.19 | 05.04.19 | 31.05.19 | 60 | 15 | _ | 150 | 0.75 | 1.25 | 0.2 | 22.5 | 25
69 | Drain of road from Block No. 11 to 13 Kalyan Puri L/R | 960 | 28.03.19 | 05.04.19 | 31.05.19 | 94.4444 | 17 | _ | 13137 | - | - | - | 3894.15 | 18
70 | Khichri Pur Nalla Block No. 9 to 10 | 150 | 28.03.19 | 05.04.19 | 31.05.19 | 55.5556 | 10 | _ | 70 | 1 | 1.4 | 0.2 | 14 | 18
| Total | 14877 |  |  |  |  | 3836 |  | 70 | - | - | - | 14
E.E(M)-IV-Sh. South
71 | Drain from Sriram chowk to Aggarwal Sweets, C-Block West Vinod Nagar | 480 | 2019-03-09 | 09.03.19 | 30.05.19 | 89.6443 | 90 | _ | 480 | 0.9 | 1.2 | 0.2 | 86.4 | 100.3968 | In progress | Contractual
72 | Drain from Sriram chowk to Jewellary Shop, D-Block West Vinod Nagar | 290 | - | 01.10.18 | 30.05.19 | 69.2425 | 35 | _ | 290 | 0.75 | 1.2 | 0.2 | 43.5 | 50.547 | In progress | Departmental
73 | Drain on Shanti marg from Budha Marg to Narwana Road (Both Sides) | 700 | 2019-03-09 | 09.03.19 | 30.05.19 | 88.7905 | 130 | _ | 700 | 0.9 | 1.2 | 0.2 | 126 | 146.412 | In progress | Contractual
74 | Drain from Sadbhawna Chowk to Taxi Stand on Sadbhawana Road | 420 | 2019-03-09 | 09.03.19 | 30.05.19 | 82.7486 | 105 | _ | 420 | 1.3 | 1.5 | 0.2 | 109.2 | 126.8904 | In progress | Contractual
75 | Drain on Shanti Marg from RCC culvert, Mandawali Road to Budha Marg (Both Sides) | 500 | 2019-03-09 | 09.03.19 | 30.05.19 | 66.9344 | 70 | _ | 500 | 0.9 | 1.2 | 0.2 | 90 | 104.58 | In progress | Contractual
76 | Drain from Budha Marg to Sadbhavna Chowk | 150 | - | 01.05.19 | - | 100.4016 | 35 | _ | 150 | 1 | 1.2 | 0.2 | 30 | 34.86 |  | Departmental
77 | Drain from Harijan Basti Rly. Colony to Pump House, Mayfair Apptt. | 430 | - | 01.10.18 | 30.05.19 | 59.0401 | 59 | _ | 430 | 1 | 1.5 | 0.2 | 86 | 99.932 | In progress | Departmental
78 | Drains from Sriram Chowk to Rly. Colony on both sides of Kalyan Marg | 1500 | 2019-03-09 | 09.03.19 | 30.05.19 | 92.4332 | 290 | _ | 1500 | 0.9 | 1.2 | 0.2 | 270 | 313.74 | In progress | Contractual
79 | Drain from Milenium Park to MC Pry School No.1 via Pandit Mohalla, Mandawali | 500 | 2019-03-09 | 09.03.19 | 30.05.19 | 63.7471 | 50 | _ | 500 | 0.9 | 1.2 | 0.15 | 67.5 | 78.435 | In progress | Contractual
80 | Drain from Railway Colony to Bhim Gali along Sonia Vihar Subzi Mandi | 100 | - | 01.10.18 | 30.05.19 | 53.1225 | 25 | _ | 300 | 0.9 | 1.2 | 0.15 | 40.5 | 47.061 | In progress | Departmental
81 | Drain from Pump House Bus Stand near H. No. A/185 to outfall | 305 | - | 01.10.18 | 30.05.19 | 98.7557 | 63 | _ | 305 | 0.9 | 1.2 | 0.2 | 54.9 | 63.7938 | In progress | Departmental
| Pumphouse outfall nalla | 330 | - | 01.10.18 | 30.05.19 | 95.6206 | 60 | _ | 300 | 0.9 | 1.2 | 0.2 | 54 | 62.748 | In progress | Departmental
82 | Drain in Mayur Vihar-II Pocket B from M.C. Pry School Pocket F to Sanjay Jheel. | 425 | 2019-03-09 | 09.03.19 | 30.05.19 | 65.1958 | 50 | _ | 330 | 1 | 1.2 | 0.2 | 66 | 76.692 | In progress | Departmental
83 | Drain in Mayur Vihar Ph. II from E/560 to Pump House | 400 | - | 01.10.18 | 30.05.19 | 85.0461 | 63 | _ | 425 | 1 | 1.25 | 0.15 | 63.75 | 74.0775 | In progress | Contractual
84 | Drain from G-Block to Gurudwara East Vinod Nagar adjoning NH-9 | 350 | 2019-03-09 | 09.03.19 | 30.05.19 | 80.6799 | 90 | _ | 400 | 1.2 | 1.3 | 0.2 | 96 | 111.552 | In progress | Departmental
85 | Drain from IFS App. To Fine Home App. | 800 | 2019-03-09 | 09.03.19 | 30.05.19 | 68.7273 | 115 | _ | 800 | 0.9 | 1.3 | 0.2 | 144 | 167.328 | In progress | Contractual
86 | Drain from Sahyog App. to Anand Lok Appt. | 395 | - | 01.10.18 | 30.05.19 | 84.7271 | 70 | _ | 395 | 0.9 | 1.3 | 0.2 | 71.1 | 82.6182 | In progress | Contractual
87 | Drain from Ahalcon Intl. School to Police App. Mayur Vihar | 350 | - | 01.10.18 | 30.05.19 | 68.3004 | 50 | _ | 350 | 0.9 | 1.2 | 0.2 | 63 | 73.206 | In progress | Departmental
88 | Drain from Partap Nagar to Aggarwal Sweets in Mayur Vihar Ph. - I | 510 | 2019-03-09 | 09.03.19 | 30.05.19 | 63.2783 | 75 | _ | 510 | 1 | 1.2 | 0.2 | 102 | 118.524 | In progress | Departmental
89 | Drain in P-Block Pandav Nagar. | 330 | 2019-03-09 | 09.03.19 | 30.05.19 | 65.1958 | 30 | _ | 330 | 0.6 | 1.2 | 0.2 | 39.6 | 46.0152 | In progress | Contractual
90 | Acharya Niketan Nalla from Maternity Home to Church. | 500 | - | 01.10.18 | 30.05.19 | 64.5439 | 45 | _ | 500 | 0.6 | 1.2 | 0.2 | 60 | 69.72 | In progress | Contractual
91 | Samaspur Vill. Nalla from E-54 to Police Aptt. | 500 | - | 01.10.18 | 30.05.19 | 66.1989 | 50 | _ | 500 | 0.65 | 1.2 | 0.2 | 65 | 75.53 | In progress | Departmental
92 | Drain along Una Aptt. to Mavila apptt., Mayur Vihar -Ph-I | 260 | - | 01.10.18 | 30.05.19 | 82.7486 | 30 | _ | 260 | 0.6 | 1.2 | 0.2 | 31.2 | 36.2544 | In progress | Departmental
93 | Lalita park Nalla | 450 | - | 01.10.18 | - | 99.9554 | 70.56 | _ | 450 | 0.9 | 1.3 | 0.15 | 60.75 | 70.5915 | Completed | Departmental
94 | Gali No. 12 drain Lalita Park, | 200 | - | 01.10.18 | 30.05.19 | 86.0585 | 30 | _ | 200 | 0.75 | 1.2 | 0.2 | 30 | 34.86 | In progress | Departmental
95 | Ramesh Park Community Centre Nalla | 350 | - | 01.10.18 | 30.05.19 | 94.2546 | 23 | _ | 200 | 0.7 | 1.2 | 0.15 | 21 | 24.402 | In progress | Departmental
96 | Bank Enclave drain opp. H. No. 1 | 300 | - | 01.10.18 | 30.05.19 | 87.8148 | 50 | _ | 350 | 0.7 | 1.3 | 0.2 | 49 | 56.938 | In progress | Departmental
97 | Ramesh Park Police Stn. Drain | 360 | - | 01.10.18 | - | 100.3504 | 32.65 | _ | 200 | 0.7 | 1.25 | 0.2 | 28 | 32.536 | Completed | Depatmental
98 | MB road drain | 1200 | 2019-03-09 | 09.03.19 | 30.05.19 | 99.4454 | 52 | _ | 300 | 1 | 1.2 | 0.15 | 45 | 52.29 | Completed | Departmental
99 | Bank Enclave drain | 200 | 2019-03-09 | 09.03.19 | - | 35.8577 | 30 | _ | 360 | 1 | 1.35 | 0.2 | 72 | 83.664 | In progress | Contractual
100 | Kundan Nagar Nalla (Right Side) | 200 | - | 01.10.18 | - | 99.9235 | 627 | _ | 1200 | 3 | 3 | 0.15 | 540 | 627.48 | Completed | Contractual
101 | PD Vihar drain | 400 | - | 01.10.18 | 30.05.19 | 76.838 | 50 | _ | 400 | 0.7 | 1.2 | 0.2 | 56 | 65.072 | In progress | Departmental
102 | Laxmi Nagar Market Nalla | 1900 | 2019-03-09 | 09.03.19 | 30.05.19 | 85.2592 | 240 | _ | 1900 | 0.85 | 1.2 | 0.15 | 242.25 | 281.4945 | In progress | Departmental
103 | Shakarpur Market Nalla | 795 | 2019-03-09 | 09.03.19 | 30.05.19 | 81.1873 | 120 | _ | 795 | 0.8 | 1.2 | 0.2 | 127.2 | 147.8064 | In progress | Contractual
104 | Drain from Bhim Gali to Budha Marg | 1000 | 2019-03-09 | 09.03.19 | 30.05.19 | 90.8395 | 95 | _ | 600 | 0.75 | 1.2 | 0.2 | 90 | 104.58 | In progress | Contractual
105 | Hanuman Mandir road Pandav Nagar nalla | 555 | 2019-03-09 | 09.03.19 | 30.05.19 | 91.3133 | 106 | _ | 555 | 0.9 | 1.2 | 0.2 | 99.9 | 116.0838 | In progress | Contractual
106 | D Park to 11/3 Pandav Nagar nalla | 340 | 2019-03-09 | 09.03.19 | 30.05.19 | 73.8247 | 35 | _ | 340 | 0.8 | 1.2 | 0.15 | 40.8 | 47.4096 | In progress | Contractual
107 | Drain from DDA Park to S 380 School Block Pandav Nagar | 650 | - | 01.10.18 | 30.05.19 | 88.2651 | 90 | _ | 650 | 0.9 | 1.2 | 0.15 | 87.75 | 101.9655 | In progress | Contractual
108 | C-68/4 to S-101 Pandav Nagar nalla | 125 | - | 01.10.18 | 30.05.19 | 74.4566 | 14.6 | _ | 125 | 0.9 | 1.2 | 0.15 | 16.875 | 19.6087 | In progress | Departemntal
| Total | 19550 |  |  |  |  | 3345.81 | [7 empty] | In progress | Departemntal
20%

## Sheet1 (hidden)
East Delhi Municipal Corporation
Divisin | No. of Drains | Length of Drain (in Mtr) | Silt removed from 01.10.18 to 09.05.19 (In MT) (a) | Silt removed upto 16.02.18 | Silt removed during this week (In MT) (b) | Total qty. in M.T. (a + b)
Shahdara North Zone
EE-M-I-SHN | 41 | 19629 | 2351 |  | 815 | 3166 | S. No. | Div. | Total No. of Drain | Total length of drains (In Mtr.) | Total targeted qty. in M.T. | Qty. of silt removed and sent at SLF in M.T. w.e.f 01.10.18 to 09.05.19 (a) | Silt removed in M.T. during this week (10.05.19 to 14.05.19) (b) | Total qty. in M.T. (a + b) | Progress in %age
EE-M-II-SHN | 32 | 22185 | 5400 |  | 1452.8 | 6852.8 | 1 | M-I | 32 | 15383 | 4690 | 203 | 247 | 450 | 9.5949
EE-M-III-SHN | 24 | 10206 | 682.93 |  | 830.895 | 1513.825 | 2 | M-II | 17 | 11025 | 3788 | 1832 | 641 | 2473 | 65.2851
EE-M-IV-SHN | 17 | 10839 | 4184 |  | 1073.29 | 5257.29 | 3 | M-III | 21 | 14167 | 4582 | 3335 | 501 | 3836 | 83.7189
Total | 114 | 62859 | 12617.93 |  | 4171.985 | 16789.915 | 4 | M-IV | 38 | 19300 | 4028 | 3146 | 200.165 | 3346.165 | 83.0726
Shahdara South Zone | [7 empty] | Total | 108 | 59875 | 17088 | 8516 | 1589.165 | 10105.165 | 59.136
EE-M-I-SHS | 32 | 15383.4 | 203 |  | 247 | 450 | SHAHDARA NORTH ZONE
EE-M-II-SHS | 17 | 11025 | 1832 |  | 641 | 2473 | SILT (IN MT)
EE-M-III-SHS | 22 | 14877 | 3335 |  | 501 | 3836 | M-I | M-II | M-III | M-IV | Total
EE-M-IV-SHS | 39 | 22650 | 3146 |  | 200 | 3346 | 167.13 | 172.675 | 49.405 | 400.27 | 789.48
Total | 110 | 63935.4 | 8516 |  | 1589 | 10105 | 133.485 | 210.785 | 27.53 | 290.19 | 661.99
[7 empty] | 0 | 378.255 | 0 | 155.94 | 534.195
[7 empty] | 129.866 | 326.3 | 41.45 | 16.01 | 513.626
[7 empty] | 130.055 | 102.725 | 39.565 | 253.305 | 525.65
[7 empty] | 163.05 | 436.515 | 191.58 | 366.805 | 1157.95
[7 empty] | 135.295 | 59.05 | 256.01 | 311.6 | 761.955

## MIsc (hidden)
East Delhi Municipal Corporation
Report on Desilting of Drains for the week upto 2nd May 2019
Date 08.05.19
S. No. | Name of Drain | Length of Drain | Date of Issue of Desilting Tender | Date of Commencement of Desilting | Excepted Date of Completion of Desilting | Progres of Work (in %) | Quantity of Silt removed (in MT) | Inter Departmental Problem faced (if any)
Shah. North Zone
E.E(M)-I-Sh. North
1 | Nalla in Old Seemapuri G block to Pump house | 1361 | 31.03.2019 | 01.05.2019 | 30.05.2019 | 41.0122 | 235 | _ | 1361 | 1.2 | 2 | 0.3 | 490 | 573
2 | Desilting of nalla from SSBL drain Jalli Kheda Vill. To SDN Hopt. Road in W.No. 241 | 135 | 26.03.2019 | 15.04.2019 | 15.06.2019 | 85.5263 | 65 | _ | 135 | 2.4 | 3 | 0.2 | 65 | 76
3 | SSBL drain from 100Ft. road no.68 to G.T.Road flyover Rd 1081 to 1481 mtr | 400 | 26.03.2019 | 15.04.2019 | 15.06.2019 | 33.7591 | 185 | _ | 400 | 6.5 | 1.8 | 0.18 | 468 | 548
4 | SSBL drain from 100Ft. road no.68 to G.T.Road flyover Rd 1481 to 1946 mtr | 510 | 26.03.2019 | 15.04.2019 | 15.06.2019 | 37.9656 | 265 | _ | 510 | 6.5 | 1.8 | 0.18 | 597 | 698
5 | SSBL drain from 100Ft. road no.68 to G.T.Road flyover Rd 1946 to 2362 mtr. | 397 | 26.03.2019 | 15.04.2019 | 15.06.2019 | 54.4513 | 263 | _ | 397 | 5.2 | 1.9 | 0.2 | 413 | 483
6 | SSBL drain from 100Ft. road no.68 to G.T.Road flyover Rd 2362 to 2702 mtr. | 314 | 26.03.2019 | 15.04.2019 | 15.06.2019 | 45.4545 | 170 | _ | 314 | 5.1 | 2 | 0.2 | 320 | 374
7 | Nallah along DDA park from MCD sotre to Q-Pkt. Drain in Dilshad Garden | 310 | 26.03.2019 | 15.04.2019 | 01.06.2019 | 89.0411 | 65 | _ | 310 | 1 | 1.6 | 0.2 | 62 | 73
8 | Nallah from Tahirpur Sarai to R-Pkt. Dilshad Garden | 150 | 26.03.2019 | 15.04.2019 | 30.05.2019 | 84.9057 | 45 | _ | 150 | 1 | 1.5 | 0.3 | 45 | 53
9 | Nallah from Gali No-8 Jagatpuri extn. Unauthorized colony | 90 | 26.03.2019 | 15.04.2019 | 30.05.2019 | 87.5 | 14 | _ | 90 | 0.75 | 1 | 0.2 | 14 | 16
10 | Nallah along DDA park from P-15/A-4 to MCD Store Dilshad Garden | 330 | 26.03.2019 | 15.04.2019 | 15.06.2019 | 100 | 59 | _ | 330 | 1 | 1.5 | 0.15 | 50 | 59
11 | Nalla in new seemapuri from E-blk to Machli Market | 220 | 25.03.2019 | 26.03.2019 | 15.06.2019 | 31.3725 | 16 | _ | 220 | 1 | 1.5 | 0.2 | 44 | 51
12 | Nalla in Tahirpur village from Shiv mandir to Kali mandir | 240 | 25.03.2019 | 26.03.2019 | 15.06.2019 | 45.7143 | 16 | _ | 240 | 1.25 | 1.4 | 0.1 | 30 | 35
13 | Nalla in E-Block Jhuggi Nalla New Seemapuri | 100 | 25.03.2019 | 26.03.2019 | 04.05.2019 | 100 | 13 | _ | 100 | 0.7 | 1.7 | 0.15 | 11 | 13
14 | Nalla in New seemapuri from Bhopal Pulia to Dhobi Ghat | 110 | 25.03.2019 | 26.03.2019 | 30.05.2019 | 76.1905 | 16 | _ | 110 | 0.8 | 1.5 | 0.2 | 18 | 21
15 | SSBL drain from Wazirabad Road to Ashok Nagar railway phatak (Hanuman Pulia) | 540 | 26.03.2019 | 07.04.2019 | 15.06.2019 | 38.9306 | 415 | _ | 540 | 6.75 | 1.55 | 0.25 | 911 | 1066
16 | Internal nallas in D- block Nand Nagari from D-1/275 to D-1/231 to Upto D-3/355 | 190 | 26.03.2019 | 28.03.2019 | 15.06.2019 | 37.037 | 10 | _ | 190 | 0.6 | 1.3 | 0.2 | 23 | 27
17 | Nalla both side E block pump house nalla in Nand Nagari from E-4/160 to pump house including sump well | 780 | 26.03.2019 | 28.03.2019 | 15.06.2019 | 41.6667 | 65 | _ | 780 | 0.85 | 1.5 | 0.2 | 133 | 156
18 | Both side Nalla of Akhara park E -4 Block Nand Nagari | 700 | 26.03.2019 | 28.03.2019 | 15.06.2019 | 30.5344 | 40 | _ | 700 | 0.8 | 1.6 | 0.2 | 112 | 131
19 | Internal nallas in A-1/30 in A block Nand Nagari from A-2/30 to A-2 Block Nand Nagri | 525 | 26.03.2019 | 28.03.2019 | 15.06.2019 | 43.4783 | 40 | _ | 525 | 0.6 | 1.3 | 0.25 | 79 | 92
20 | Internal nallas in A-1/481 and Ujala Pulia to road No 68 towards cement godown both side | 1200 | 26.03.2019 | 28.03.2019 | 15.06.2019 | 36.3924 | 115 | _ | 1200 | 0.9 | 1.45 | 0.25 | 270 | 316
21 | Nallah from Sr. Sec. School Raja Ravin Verma corner to B-5 Block Market Nand Nagri | 375 | 26.03.2019 | 28.03.2019 | 15.06.2019 | 30.6122 | 30 | _ | 375 | 0.9 | 1.45 | 0.25 | 84 | 98
22 | Nallah from B-5 Block Market Corner to road no-68 | 150 | 26.03.2019 | 28.03.2019 | 15.06.2019 | 78.125 | 25 | _ | 150 | 0.9 | 1.45 | 0.2 | 27 | 32
23 | Nallah H.no-30 E-1 Nand Nagri to H.no-231 E-Block Nand Nagri | 115 | 26.03.2019 | 28.03.2019 | 15.06.2019 | 76.9231 | 20 | _ | 115 | 1.3 | 1.4 | 0.15 | 22 | 26
24 | Nallah from H.no-481 E-2 Nand Nagri to H.no-280 E-2 Block Nand nagri | 115 | 26.03.2019 | 28.03.2019 | 15.06.2019 | 42.8571 | 15 | _ | 115 | 1.3 | 1.4 | 0.2 | 30 | 35
25 | Nalla along Murga Mkt. in G & H block Sunder Nagari from mandir to Upto pumphouse including sump well | 589 | 25.03.2019 | 07.05.2019 | 30.06.2019 | 28.8462 | 45 | _ | 589 | 0.75 | 1.3 | 0.3 | 133 | 156
26 | Nalla in L Block Sunder Nagari from police chowki to L-55 Sunder Nagari | 478 | 25.03.2019 | 07.05.2019 | 30.06.2019 | 55.9748 | 89 | _ | 478 | 0.95 | 1.5 | 0.3 | 136 | 159
27 | nalla in sunder nagari from M.C. Primary school to Sani bazar mandi along F2 sunder nagari | 254 | 25.03.2019 | 07.05.2019 | 30.06.2019 | 62.069 | 18 | _ | 254 | 0.65 | 1.2 | 0.15 | 25 | 29
28 | Desilting of nallah in Bhagirathi Vihar from Brijpuri culvert to Drain No.1 in W.No.261 Shah.North Zone. | 1410 | 31.03.2019 | 05.04.2019 | 15.06.2019 | 59.3023 | 102 | _ | 1410 | 1.04 | 1.5 | 0.1 | 147 | 172
29 | Desilting of nallah in Ambedkar Colony from main road Johripur to Drain no.1 in W.No.261 Shah.North Zone. | 278 | 31.03.2019 | 05.04.2019 | 05.05.2019 | 100 | 46 | _ | 278 | 0.7 | 1.15 | 0.2 | 39 | 46
30 | Desilting of nallah from main road Johari Pur along Johari pur Ext. to block, main road (both side) to Drain no.1 in W.No.261 Shah.North Zone. | 560 | 31.03.2019 | 05.04.2019 | 15.06.2019 | 76.2712 | 45 | _ | 560 | 0.45 | 1.3 | 0.2 | 50 | 59
31 | Desilting of nallah along C-block, main road to Ganga Vihar W.No.261 Shah.North Zone. | 540 | 31.03.2019 | 15.04.2019 | 15.06.2019 | 73.6842 | 70 | _ | 540 | 0.6 | 2 | 0.25 | 81 | 95
32 | Desilting of internal nallah A,B,C & D block to pump house to school block, Ambey Cycle to post office and Kaushik Garment to M.C. Pry. School B-block in Gokulpuri W.No.262 Shah.North Zone. | 380 | 31.03.2019 | 15.04.2019 | 15.06.2019 | 90.1639 | 55 | _ | 380 | 0.55 | 1.1 | 0.25 | 52 | 61
33 | Desilting of nallah from Amar Colony to Loni road flyover in W.No.262 Shah.North Zone. | 285 | 31.03.2019 | 15.04.2019 | 15.06.2019 | 80 | 64 | _ | 285 | 0.95 | 1.5 | 0.25 | 68 | 80
34 | Desilting of nallah C-block, jhuggi area along main road up to Pump house i.e sump well in Gokulpuri W.No.262 Shah.North Zone. | 508 | 31.03.2019 | 15.04.2019 | 15.06.2019 | 71.4286 | 55 | _ | 508 | 0.65 | 1.3 | 0.2 | 66 | 77
35 | Desilting of nallah along main road Ganga Vihar from dhalao to drain no.1 along A,B,D & F block in Ganga Vihar W.No.262 Shah.North Zone. | 600 | 31.03.2019 | 15.04.2019 | 15.06.2019 | 71.4286 | 75 | _ | 600 | 0.6 | 1 | 0.25 | 90 | 105
36 | Desilting of nallah from main road Ganga Vihar to Gokulpur Village W.No.262 Shah.North Zone. | 340 | 31.03.2019 | 15.04.2019 | 15.06.2019 | 72.9167 | 35 | _ | 340 | 0.6 | 1 | 0.2 | 41 | 48
37 | Nalla from Shamshan Ghat to Saboli goan bada kuan (Rathore Cement Store) | 700 | 31.03.2019 | 05.04.2019 | 30.05.2019 | 51.0204 | 50 | _ | 700 | 0.6 | 1.2 | 0.2 | 84 | 98
38 | Nalla along railway line from Saboli Phatak | 620 | 31.03.2019 | 05.04.2019 | 30.05.2019 | 78.5441 | 205 | _ | 620 | 1.2 | 1.3 | 0.3 | 223 | 261
39 | Nalla on both side along Gali No 9 Bank Colony Harsh Vihar dividing road from Jail B/wall to Budh Vihar Chowk | 400 | 31.03.2019 | 05.04.2019 | 06.05.2019 | 96.7213 | 59 |  | 400 | 0.65 | 1.1 | 0.2 | 52 | 61
40 | Nalla from P.W.D P/house Harsh Vihar to Jail Boundary wall | 1370 | 31.03.2019 | 05.04.2019 | 30.05.2019 | 70.8333 | 255 |  | 1370 | 0.9 | 2.1 | 0.25 | 308 | 360
41 | Nalla on both side along bank colony Road from Wazirabad road to Kishan Lal Chowk | 960 | 31.03.2019 | 05.04.2019 | 30.05.2019 | 63.4921 | 80 |  | 960 | 0.75 | 1.2 | 0.15 | 108 | 126
| Total | 19629 |  |  |  |  | 3550 |  | 19629 |  |  |  | 6021 | 7045
E.E-(M)-II-Sh. North
1 | Gokalpur drain | 2000 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 36.8844 | 1015 |  | 2000 | 4.2 | 4.57 | 0.28 | 2352 | 2751.84
2 | Drain Gamri road to Gokalpur drain | 100 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 87.2144 | 25 |  | 100 | 0.7 | 1.35 | 0.35 | 24.5 | 28.665
3 | Gokalpur drain from Ivth pusta to Culvert near M.C. Pry. School | 1984 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 29.4582 | 875 |  | 1984 | 4.57 | 4.57 | 0.28 | 2538.7264 | 2970.3099
4 | DrainGali No. 12 X-Block Brahmpuri to Gokalpur drain | 400 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 83.7942 | 120 |  | 400 | 0.9 | 1.2 | 0.34 | 122.4 | 143.208
5 | Drain from Gokalpur drain to Khaddey wali Masjid | 1000 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 42.735 | 120 |  | 1000 | 0.6 | 1.05 | 0.4 | 240 | 280.8
6 | Drain from Gautam Vihar chowk to Gokalpur drain | 400 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 90.812 | 102 |  | 400 | 0.6 | 1.05 | 0.4 | 96 | 112.32
7 | Drain from Gamri road to Gali No. 1 Khaddey wali masjid (RHS) | 900 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 75.9734 | 96 |  | 900 | 0.6 | 1.05 | 0.2 | 108 | 126.36
8 | Drain from Gamri road to Gali no. 1Brahmpuri (LHS) | 600 | 2019-02-04 | 2019-03-29 | 2019-05-31 | 83.0959 | 70 |  | 600 | 0.6 | 1.05 | 0.2 | 72 | 84.24
9 | Drain from Main market Bhajanpura gali no. 14 to Wazirabad road RHS | 400 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 97.3409 | 41 |  | 400 | 0.6 | 1.2 | 0.15 | 36 | 42.12
10 | Drain from B-1 Block Yamuna Vihar to B-3 Block Yamuna Vihar | 660 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 90.6501 | 105 |  | 660 | 1 | 2 | 0.15 | 99 | 115.83
11 | Drain from B-4 Block Dividing road to S.S. School Yamuna Vihar | 650 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 89.4149 | 102 |  | 650 | 1 | 1.8 | 0.15 | 97.5 | 114.075
12 | Drain from Sachdeva Marriage home to Bhajanpura pump house | 380 | 2019-02-04 | 2019-03-29 | 2019-05-31 | 89.9685 | 54 |  | 380 | 0.9 | 2.15 | 0.15 | 51.3 | 60.021
13 | Drain from dividing road to C-10 Nursery Yamuna Vihar | 535 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 95.8543 | 54 |  | 535 | 0.6 | 1.1 | 0.15 | 48.15 | 56.3355
14 | Drain from Bhagat Singh Pump house to C-12, Yamuna Vihar Shiv Shakti mandir | 692 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 68.6176 | 75 |  | 692 | 0.9 | 2.5 | 0.15 | 93.42 | 109.3014
15 | Drain from Patel road from Patel chowk to Harizan Basti gali no. 1 Pucca road in ward no. 265 | 400 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 94.9668 | 84 |  | 400 | 0.63 | 1.3 | 0.3 | 75.6 | 88.452
16 | Drain Karawal Nagar road from Shiv Vihar chowk | 1000 | 2019-01-31 | 2019-04-10 | 2019-05-31 | 55.7138 | 176 |  | 1000 | 0.9 | 1.5 | 0.3 | 270 | 315.9
17 | Drain Shiv Vihar Tiraha | 175 | 2019-01-31 | 2019-04-10 | 2019-05-31 | 81.4001 | 45 |  | 175 | 0.9 | 2 | 0.3 | 47.25 | 55.2825
18 | Drain 33' road from Karawal Nagar | 690 | 2019-01-31 | 2019-04-10 | 2019-05-31 | 88.0851 | 160 |  | 690 | 0.75 | 1.5 | 0.3 | 155.25 | 181.6425
19 | Drain Industrial area Nall from Karawal Nagar road | 250 | 2019-01-31 | 2019-04-10 | 2019-05-31 | 75.9734 | 40 |  | 250 | 0.6 | 1.2 | 0.3 | 45 | 52.65
20 | Drain Brijpuri road from gali no.1 to shiv Vihar Tiraha | 450 | 2019-01-31 | 2019-04-10 | 2019-05-31 | 91.4495 | 130 |  | 450 | 0.9 | 2 | 0.3 | 121.5 | 142.155
21 | Drain Karawal Nagar road from Shiv Vihar Tiraha to Mukhiya market | 1350 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 76.2079 | 260 |  | 1350 | 0.9 | 1.5 | 0.24 | 291.6 | 341.172
22 | Drain from Karawal Nagar road from Dayalpur 33' feet road | 1100 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 94.9668 | 220 |  | 1100 | 0.6 | 1.5 | 0.3 | 198 | 231.66
23 | Drain Karawal Nagar road from Chand bagh culvert to Sherpur Chowk | 800 | 2019-01-31 | 2019-04-10 | 2019-05-31 | 65.2896 | 220 |  | 800 | 1.5 | 1.5 | 0.24 | 288 | 336.96
24 | Drain 25' road from Sanjay chowk road to Fauzi market | 750 | 2019-01-31 | 2019-04-10 | 2019-05-31 | 67.5319 | 160 |  | 750 | 0.9 | 1.25 | 0.3 | 202.5 | 236.925
25 | Drain Karawal Nagar road from Sherpur chowk to Jodha ram gali no. 1 | 475 | 2019-01-31 | 2019-04-10 | 2019-05-31 | 97.9657 | 245 |  | 475 | 1.5 | 1.5 | 0.3 | 213.75 | 250.0875
26 | Drain from 33' road from 25' road chowk to Gali No. 1 Nehru Vihar | 800 | 2019-01-31 | 2019-04-10 | 2019-05-31 | 81.4001 | 160 |  | 800 | 0.7 | 1.2 | 0.3 | 168 | 196.56
27 | Drain from Gali No. 6 from 25' road to Escape drain in ward no. 267 | 300 | 2019-01-31 | 2019-04-10 | 2019-05-31 | 93.5279 | 130 |  | 300 | 1.2 | 1.5 | 0.33 | 118.8 | 138.996
28 | Drain Gali No. 8 from 25' road to Escape drain | 300 | 2019-01-31 | 2019-04-10 | 2019-05-31 | 80.7217 | 102 |  | 300 | 1.2 | 1.5 | 0.3 | 108 | 126.36
29 | Drain Brijpuri road from escape drain | 600 | 2019-01-31 |  | 2019-05-31 | 47.1342 | 135 |  | 600 | 1.2 | 1.5 | 0.34 | 244.8 | 286.416
30 | Drain Brijpuri road from escape drain to Gali no. 1 Mustafabad | 814 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 44.9167 | 154 |  | 814 | 1.2 | 1.6 | 0.3 | 293.04 | 342.8568
31 | Drain 33' road from Brijpuri road to 25' Chowk | 615 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 69.4879 | 102 |  | 615 | 0.6 | 1.25 | 0.34 | 125.46 | 146.7882
32 | Drain 33' road from Brijpuri road to 25' chowk | 615 | 2019-01-31 | 2019-03-29 | 2019-05-31 | 64.7191 | 95 |  | 615 | 0.6 | 1.25 | 0.34 | 125.46 | 146.7882
| Total | 22185 |  |  |  |  | 5472 |  | 22185 | 34.55 |  |  | 9071.0064 | 10613.0775
E.EM)-III-Sh. North
1 | SSBL drian from Natthu Colony Railway Crossimg to C-3 Nand Nagari | 480 | 09.02.19 | 20.04.19 | 31.05.19 | 100 | 1010 |  | 480 | 6 | 1.8 | 0.3 | 864 | 1010 | 100%
2 | Nalla along East nathu Colony in C-37E | 350 | 2019-02-09 | 16.04.19 | 31.05.19 | 21.5227 | 8 |  | 350 | 0.6 | 1.5 | 0.15 | 31.5 | 37.17 | 20% | 7.434
3 | Hardevparl nalla from Hardevpuri to loni Rd. pump house. | 1400 | 15.02.19 | 01.05.19 | 31.05.19 | 44.2177 | 65 |  | 1400 | 0.9 | 1.5 | 0.1 | 126 | 147 | 5% | 29.4
4 | 52 cusec drain from Mandoli Rd. to loni Rd. | 640 | 09.02.19 | 20.04.19 | 31.05.19 | 79.6178 | 375 |  | 640 | 4.2 | 3.6 | 0.15 | 403.2 | 471 | 70%
5 | Covered drain from Loni road to Mother Dairy kabool Nagar | 250 | 2019-02-09 | 25.04.19 | 31.05.19 | 127.1186 | 45 |  | 250 | 1.2 | 1.2 | 0.1 | 30 | 35.4 | 20%
6 | Covered drain from 1/143 Sri Ram nagar to Shri Ram Nagar pump house internal nalla | 524 | 2019-02-09 | 25.04.19 | 31.05.19 | 74.1256 | 55 |  | 524 | 1.2 | 1.8 | 0.1 | 62.88 | 74.1984 | 20%
7 | Moti Ram road nalla from loni road pump house to mandoli road dhalao | 191 | 2019-02-09 | 25.04.19 | 31.05.19 | 42.663 | 15 |  | 191 | 1.3 | 1.8 | 0.12 | 29.796 | 35.1593 | 20%
8 | Naveen Shahdara Nalla at G.T Road to pump house naveen Shahdara | 900 | By Departmental | 15.04.19 | 31.05.19 | 35.7143 | 45 |  | 900 | 1.2 | 0.6 | 0.1 | 108 | 126 | 25%
9 | Khajoor wala nalla ( Covered drain) Naveen Shah. From gali No.2 West Rohtash Nagar to Naveen Shadara drain. | 341 | By Departmental | 15.04.19 | 31.05.19 | 22.0908 | 10 |  | 341 | 0.75 | 1.5 | 0.15 | 38.3625 | 45.2677 | 20%
10 | Chintamani pond drain from the point near power station to the jali behind Zonal Office | 300 | By Departmental | 15.04.19 | 31.05.19 | 34 | 34 |  | 300 | 1.9 | 2.1 | 0.15 | 85.5 | 100 | 25%
11 | Punchsheel Garden nalla along sarovar marg to the jail opp. Muskan Restaurent on 65 No. road | 30 | By Departmental | 15.04.19 | 31.05.19 | 94.162 | 5 |  | 30 | 1 | 1.43 | 0.15 | 4.5 | 5.31 | 10%
12 | Mochi Mkt. drain from Ravi Dass Mandir to Kabristan Culvert | 225 | By Departmental | 12.04.19 | 31.05.19 | 8.0645 | 5 |  | 225 | 1.58 | 1.6 | 0.15 | 53.325 | 62 | 10%
13 | Kabootar market drain from Mochi mkt. Drain (near kabristan) to masjid | 100 | By Departmental | 12.04.19 | 31.05.19 | 52.9661 | 10 |  | 100 | 0.8 | 1.15 | 0.2 | 16 | 18.88 | 15%
14 | Nalla from Mohanpuri school to gali no.16 Adrash mohalla vijay park | 285 | By Departmental | 22.04.19 | 31.05.19 | 23.1275 | 7 |  | 285 | 0.6 | 1.2 | 0.15 | 25.65 | 30.267 | 10%
15 | Nalla from C-12, Pump House to Priya Panchvati Yamuna Vihar C-11/8. | 510 | By Departmental | 22.04.19 | 31.05.19 | 21.917 | 15 |  | 510 | 0.8 | 1.8 | 0.15 | 58 | 68.44 | 15%
16 | Nalla from Krishna Park A-Block North Ghonda to Gamri pump house | 670 | By Departmental | 22.04.19 | 31.05.19 | 16.3934 | 20 |  | 670 | 1 | 1.8 | 0.15 | 105 | 122 | 10%
17 | Nalla gali no. 16 Vijay park to Road No. 66. | 330 | By Departmental | 22.04.19 | 31.05.19 | 33.7902 | 15 |  | 330 | 0.76 | 2.44 | 0.15 | 37.62 | 44.3916 | 10%
18 | Kardam Marg nalla from Harkishan Public School to Drain No. 1 Kardam Puri. | 350 | By Departmental | 12.04.19 | 31.05.19 | 72.6392 | 27 |  | 350 | 0.6 | 1.2 | 0.15 | 31.5 | 37.17 | 40%
19 | 52 cusec drain from drain No.1 to Babarpur Road | 750 | 2019-02-09 | 26.04.19 | 31.05.19 | 3.5488 | 28 |  | 750 | 6 | 4.5 | 0.15 | 675 | 789 | 50%
20 | Drain from M.I office, New Zafrabad to 52 Cusec drain. | 190 | By Departmental | 26.04.19 | 31.05.19 | 77.4358 | 25 |  | 190 | 1.2 | 1.2 | 0.12 | 27.36 | 32.2848 | 20%
21 | Drain from Gulati Tent House , New Zafrabad to 52 Cusec drain. | 110 | By Departmental | 26.04.19 | 31.05.19 | 87.3138 | 17 |  | 110 | 1 | 1.2 | 0.15 | 16.5 | 19.47 | 20%
22 | Drain opp. BSES office DDA colony New Zafrabad to 52 Cusec drain. | 90 | By Departmental | 26.04.19 | 31.05.19 | 55.7997 | 8 |  | 90 | 0.9 | 1.1 | 0.15 | 12.15 | 14.337 | 10%
23 | Drain from 52 cusec to pt. near H.No. B-64, Sudama Puri Ext. | 90 | By Departmental | 26.04.19 | 31.05.19 | 94.162 | 15 |  | 90 | 1 | 1.2 | 0.15 | 13.5 | 15.93 | 10%
24 | 52 cusec drain from Loni Road to Babarpur Road | 1100 | 09.02.19 | 01.05.19 | 31.05.19 | 8.8083 | 102 |  | 1100 | 6 | 3.6 | 0.15 | 990 | 1158 | 20%
| Total | 10206 |  |  |  |  | 1961 |  | 10206 |  |  |  | 3845.3435 | 4498.6758
E.E(M)-IV-Sh. North
1 | Gokal Pur drain | 280 | 2019-04-04 | 2019-04-14 | 2019-05-30 | 80.3118 | 1230 |  | 280 | 8.5 | 4 | 0.55 | 1309 | 1531.53 | 85%
2 | CPJ & K Block Nalla | 580 | 2019-03-28 | 2019-04-07 | 2019-05-30 | 82.6122 | 370 |  | 580 | 1.2 | 1.3 | 0.55 | 382.8 | 447.876 | 55%
3 | J.J Cluster Nalla | 550 | 2019-03-28 | 2019-04-07 | 2019-05-30 | 67.6448 | 185 |  | 550 | 0.85 | 1.25 | 0.5 | 233.75 | 273.4875 | 55%
4 | Fruit Market Nalla | 320 | 2019-03-28 | 2019-04-07 | 2019-05-30 | 59.989 | 105 |  | 320 | 0.85 | 1.2 | 0.55 | 149.6 | 175.032 | 85%
5 | Gokulpur drain | 750 | 2019-04-15 | 2019-04-25 | 2019-06-15 | 57.6657 | 1556 |  | 750 | 4.1 | 2.5 | 0.75 | 2306.25 | 2698.3125 | 30%
6 | Moni Baba Nalla | 544 | 2019-04-02 | 2019-04-12 | 2019-05-30 | 54.9899 | 105 |  | 544 | 0.75 | 1.5 | 0.4 | 163.2 | 190.944 | 82%
7 | Rajender Parsad Marg drain | 175 | 2019-03-28 | 2019-04-07 | 2019-06-15 | 57.8845 | 40 |  | 175 | 0.75 | 1.5 | 0.45 | 59.0625 | 69.1031 | 0
8 | Vijay Park Nalla | 290 | 2019-03-28 | 2019-04-07 | 2019-05-30 | 82.8912 | 90 |  | 290 | 0.8 | 1.2 | 0.4 | 92.8 | 108.576 | 55%
9 | Gokal Pur drain | 433 | 2019-03-28 | 2019-04-07 | 2019-06-15 | 43.8449 | 479 |  | 415 | 4.5 | 4 | 0.5 | 933.75 | 1092.4875 | 0
10 | Karawal Nagar road Nalla | 540 | 2019-04-02 | 2019-04-12 | 2019-05-30 | 72.2573 | 210 |  | 540 | 1.15 | 1.3 | 0.4 | 248.4 | 290.628 | 65%
11 | Karawal Nagar road Nalla | 675 | 2019-04-02 | 2019-04-12 | 2019-05-30 | 67.5319 | 224 |  | 675 | 1.4 | 1.5 | 0.3 | 283.5 | 331.695 | 65%
12 | Karawal Nagar road Nalla | 1550 | 2019-03-28 | 2019-04-07 | 2019-05-30 | 45.0326 | 294 |  | 1550 | 0.9 | 1.3 | 0.4 | 558 | 652.86 | 60%
13 | C Block Nalla | 470 | 2019-03-28 | 2019-04-07 | 2019-05-30 | 95.2554 | 110 |  | 470 | 0.6 | 1.3 | 0.35 | 98.7 | 115.479 | 75%
14 | Pusta road Nalla | 1200 | 2019-03-28 | 2019-04-07 | 2019-05-30 | 83.4351 | 205 |  | 1200 | 0.5 | 1.25 | 0.35 | 210 | 245.7 | 45%
15 | Karawal Nagar road Nalla | 900 | 2019-03-28 | 2019-04-07 | 2019-05-30 | 94.9668 | 280 |  | 900 | 0.8 | 1.25 | 0.35 | 252 | 294.84 | 70%
16 | Mariginal Bandh Ist pusta Nalla | 1100 | 2019-03-28 | 2019-04-07 | 2019-05-30 | 66.7948 | 245 |  | 1100 | 0.75 | 1.3 | 0.38 | 313.5 | 366.795 | 20%
17 | Mariginal Bandh IInd pusta Nalla | 500 | 2019-03-28 | 2019-04-07 | 2019-05-30 | 86.5082 | 125 |  | 500 | 0.65 | 1.2 | 0.38 | 123.5 | 144.495 | 40%
| Total | 10839 |  |  |  |  | 5853 |  | 10839 |  |  |  | 7717.8125 | 9029.8406
Shah. South Zone
S. No. | Name of Drain | Length of Drain (in Mtr) | Date of issue of desilting tender | Date of Commencement of Desilting | Excepted Date of Completion of Desilting | Progres of Work (in %) | Quantity of Silt removed (in MT) | Inter Departmental Problem faced (if any) |  |  |  |  | Aprox. Volume of silt to be desilted (in Cum) | Aprox. Weight of silt to be desilted (in MT)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | Length of Drain (in Mtr) | Width of Drain (in Mtr) | Depth of drain (in Mtr) | Depth of Silt (in Mtr)
E.E(M)-I-Sh.S
1 | Mahila Colony drain | 400 | Departmental |  | 31.05.19 | 5.9866 | 5 | _ | 400 | 0.9 | 1.3 | 0.2 | 72 | 83.52
2 | Geeta Colony, Katcha Drain | 600 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 600 | 2 | 1.5 | 0.2 | 240 | 278.4
3 | Krishna Nagar drain | 400 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 400 | 1.75 | 1.3 | 0.2 | 140 | 162.4
4 | Radhey puri drain H Block, . | 230 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 230 | 2 | 1.35 | 0.3 | 138 | 160.08
5 | Drain at Krishna nagar , Krishna Nagar | 320 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 320 | 1 | 1.4 | 0.3 | 96 | 111.36
6 | Sumpwell Krishna Nagar | 6.4 | Departmental | - | 31.05.19 | 0 | 0 |  | 6.4 | 2.5 | 1 | 0.55 | 8.8 | 10.208
7 | Hari Singh Gurdwara | 570 | Departmental | - | 31.05.19 | 15.124 | 15 |  | 570 | 0.6 | 1.5 | 0.25 | 85.5 | 99.18
8 | Jagat puri drain | 1215 | 2019-03-26 | 04.04.19 | 31.05.19 | 39.7714 | 150 | _ | 1215 | 2.23 | 3 | 0.12 | 325.134 | 377.1554
9 | Bhagat Singh Nalla | 1460 | 2019-03-26 | 04.04.19 | 31.05.19 | 41.3321 | 105 | _ | 1460 | 1 | 2 | 0.15 | 219 | 254.04
10 | 6-12 Block Nalla (LHS) | 400 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 400 | 0.75 | 1.35 | 0.25 | 75 | 87
11 | 6-12 Block Nalla (RHS) | 400 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 400 | 0.75 | 1.35 | 0.25 | 75 | 87
12 | Geeta Colony drain | 1300 | 2019-04-04 | 13.04.19 | 31.05.19 | 0 | 0 | _ | 1300 | 2.5 | 2.5 | 0.2 | 650 | 754
13 | Sump Well. (Shastri Park) | 2 | Departmental |  | 31.05.19 | 0 | 0 |  | 2 | 5 x 5 | 0.6 | 0.15 | 8 | 9.28
14 | Kailash Nagar drain | 760 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 760 | 1.2 | 2 | 0.2 | 182.4 | 211.584
15 | Fish market drain | 150 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 150 | 1 | 1.5 | 0.25 | 37.5 | 43.5
16 | Sumpwell Kailash Nagar | 5 | Departmental |  | 31.05.19 | 0 | 0 | _ | 5 | 4 | 0.6 | 0.4 | 8 | 9.28
17 | Shastri Park drain | 600 | 2019-03-26 | 04.04.19 | 31.05.19 | 7.3681 | 20 | _ | 600 | 1.3 | 1.8 | 0.3 | 234 | 271.44
18 | East Azad Nagar drain | 520 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 520 | 1.5 | 0.75 | 0.1 | 78 | 90.48
19 | Krishna Nagar drain | 405 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 405 | 1.8 | 2 | 0.1 | 72.9 | 84.564
20 |  | 390 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 390 | 1.8 | 0.75 | 0.15 | 105.3 | 122.148
21 | Shankar Nagar nalla | 540 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 540 | 1.5 | 1.1 | 0.15 | 121.5 | 140.94
22 |  | 120 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 120 | 1.6 | 1.1 | 0.15 | 28.8 | 33.408
23 |  | 270 | 2019-03-26 | 04.04.19 | 31.05.19 | 0 | 0 | _ | 270 | 1.7 | 1.8 | 0.15 | 68.85 | 79.866
24 | Scooter market Drain | 500 | 2019-04-04 | 13.04.19 | 31.05.19 | 36.0153 | 47 | _ | 500 | 1.5 | 0.65 | 0.15 | 112.5 | 130.5
25 | Ajeet Nagar drain | 700 | 2019-04-04 | 13.04.19 | 31.05.19 | 27.0936 | 55 | _ | 700 | 1.25 | 2 | 0.2 | 175 | 203
26 | Raghubar pura drain LHS Lal | 250 | 2019-04-04 | 13.04.19 | 31.05.19 | 30.6513 | 12 | _ | 250 | 0.9 | 1 | 0.15 | 33.75 | 39.15
27 | Raghubar pura drain RHS | 250 | 2019-04-04 | 13.04.19 | 31.05.19 | 25.5428 | 10 | _ | 250 | 0.9 | 1 | 0.15 | 33.75 | 39.15
28 | Kashyap Mohalla drain | 250 | 2019-04-04 | 13.04.19 | 31.05.19 | 79.1826 | 31 | _ | 250 | 0.9 | 1 | 0.15 | 33.75 | 39.15
29 | Ramnagar drain | 300 | 2019-04-04 | 13.04.19 | 31.05.19 | 0 | 0 | _ | 300 | 1.6 | 1 | 0.15 | 72 | 83.52
30 | Raghubarpura Drain (RHS) | 900 | 2019-04-04 | 13.04.19 | 31.05.19 | 0 | 0 | _ | 900 | 1.75 | 1.05 | 0.15 | 236.25 | 274.05
31 | Raghubarpura drain (LHS) | 600 | 2019-04-04 | 13.04.19 | 31.05.19 | 0 | 0 | _ | 600 | 1.65 | 1.05 | 0.15 | 148.5 | 172.26
32 | Nalla along main road Seelampur | 570 | 2019-04-04 | 13.04.19 | 31.05.19 | 0 | 0 |  | 570 | 1.5 | 1.1 | 0.15 | 128.25 | 148.77
| Total | 15383.4 |  |  |  |  | 450 |  | 15383.4 |  |  |  | 4043.434 | 4690.3834
E.E(M)-II-Sh.S
33 | Drain along Gharonda Apptt, | 460 | - | - | 31.05.19 | 72.2573 | 35 | _ | 460 | 0.6 | 1.2 | 0.15 | 41.4 | 48.438
34 | Kasturba drain | 1200 | 31.03.19 | 01.04.19 | 31.05.19 | 62.1939 | 635 | _ | 1200 | 4.1 | 3.75 | 0.15 | 738 | 863.46
|  | 300 | 31.03.19 | 01.04.19 | 31.05.19 |  |  | _ | 300 | 3 | 3.75 | 0.15 | 135 | 157.95
35 | Nakul Gali drain Vishwas Nagar | 483 | 31.03.19 | 01.04.19 | 31.05.19 | 81.269 | 62 | _ | 483 | 0.9 | 1.5 | 0.15 | 65.205 | 76.2898
36 | Gali No.10, drain Vishwas Nagar | 220 | 31.03.19 | 01.04.19 | 31.05.19 | 77.7001 | 30 | _ | 220 | 0.75 | 1.5 | 0.2 | 33 | 38.61
37 | Gali No.3 drain Vishwas Nagar | 402 | 31.03.19 | 01.04.19 | 31.05.19 | 78.7452 | 50 | _ | 402 | 0.9 | 1.5 | 0.15 | 54.27 | 63.4959
38 | 18 Qtr. To New Vishwas Nagar drain | 180 | 31.03.19 | 01.04.19 | 31.05.19 | 87.6289 | 85 | _ | 180 | 0.6 | 1.5 | 0.15 | 16.2 | 18.954
|  | 213 | 31.03.19 | 01.04.19 | 31.05.19 |  |  | _ | 213 | 0.9 | 1.5 | 0.15 | 28.755 | 33.6433
|  | 174 | 31.03.19 | 01.04.19 | 31.05.19 |  |  | _ | 174 | 0.6 | 1.5 | 0.15 | 15.66 | 18.3222
|  | 200 | 31.03.19 | 01.04.19 | 31.05.19 |  |  | _ | 200 | 0.75 | 1.5 | 0.15 | 22.5 | 26.325
39 | Gazipur Village drain | 800 | 26.03.19 | - | 31.05.19 | 106.1254 | 149 | _ | 800 | 0.75 | 1.8 | 0.2 | 120 | 140.4
40 | Arya Nagar drain | 625 | 26.03.19 | 01.04.19 | 31.05.19 | 42.735 | 225 | _ | 625 | 3.6 | 1.8 | 0.2 | 450 | 526.5
41 | Pandav Road Nallah | 450 | 26.03.19 | - | 31.05.19 | 73.0514 | 50 | _ | 450 | 0.65 | 1.2 | 0.2 | 58.5 | 68.445
42 | Satgarh Nallah | 400 | 26.03.19 | 01.04.19 | 31.05.19 | 28.49 | 20 | _ | 400 | 0.75 | 0.1 | 0.2 | 60 | 70.2
43 | Tikona Park Nallah | 225 | 26.03.19 | 01.04.19 | 31.05.19 | 85.4701 | 45 | _ | 225 | 1 | 1.4 | 0.2 | 45 | 52.65
44 | Bhola Nath Nagar Nallah | 1100 | 26.03.19 | - | 31.05.19 | 60.2176 | 155 | _ | 1100 | 1 | 1.5 | 0.2 | 220 | 257.4
45 | Nalla along Railway line | 1000 | 26.03.19 | 01.04.19 | 31.05.19 | 83.5708 | 352 | _ | 1000 | 1.2 | 1.35 | 0.3 | 360 | 421.2
46 | Swami Amardev Nalla | 425 | 26.03.19 | - | 31.05.19 | 50.2765 | 45 | _ | 425 | 1.2 | 1.5 | 0.15 | 76.5 | 89.505
47 | Vishwkarma Nagar Nalla | 900 | 26.03.19 | 01.04.19 | 31.05.19 | 88.6356 | 280 | _ | 900 | 1.5 | 2.1 | 0.2 | 270 | 315.9
48 | Janta Flat Nalla | 852 | 26.03.19 | 01.04.19 | 31.05.19 | 65.5919 | 255 | _ | 852 | 1.95 | 1.8 | 0.2 | 332.28 | 388.7676
49 | Majid Road Nalla | 416 | 26.03.19 | - | 31.05.19 |  | 0 | _ | 416 | 1.15 | 1.5 | 0.2 | 95.68 | 111.9456
| Total | 11025 |  |  |  |  | 2473 | _ | 11025 |  |  |  | 3237.95 | 3788.4015
E.E(M)-III-Sh. South
50 | Nalla from Block No. 19 to 25 Central Road Trilokpuri. | 950 | 28.03.19 | 05.04.19 | 31.05.19 | 88.2353 | 150 | _ | 950 | 0.75 | 1.25 | 0.2 | 142.5 | 170
51 | Drain from Mayur Vihar Pkt-II to Gurudward Chowk. | 600 | 28.03.19 | 05.04.19 | 31.05.19 | 72.7273 | 80 | _ | 600 | 0.85 | 1.4 | 0.2 | 102 | 110
52 | Nalla from Block No. 14 to 13 Central Road Trilokpuri. | 300 | 28.03.19 | 05.04.19 | 31.05.19 | 54.5455 | 30 | _ | 300 | 0.75 | 1.25 | 0.2 | 45 | 55
53 | Sanjay drain in Trilok Puri | 950 | 28.03.19 | 05.04.19 | 31.05.19 | 85.6502 | 955 | _ | 950 | 5 | 1.65 | 0.2 | 950 | 1115
54 | Block No. 9 to 12 (L.H.S), Trilok Puri | 700 | 28.03.19 | 05.04.19 | 31.05.19 | 80 | 120 | _ | 700 | 0.9 | 1.25 | 0.2 | 126 | 150
55 | Block No. 9 to 12 (R.H.S), Trilok Puri | 700 | 28.03.19 | 05.04.19 | 31.05.19 | 80 | 120 | _ | 700 | 0.9 | 1.25 | 0.2 | 126 | 150
56 | Block No. 15 to 18 (Internal Road). | 550 | 28.03.19 | 05.04.19 | 31.05.19 | 80.9524 | 85 | _ | 550 | 0.8 | 1.3 | 0.2 | 88 | 105
57 | Nalla from Block No. 26 to 30 Central Rd. | 880 | 28.03.19 | 05.04.19 | 31.05.19 | 72.2222 | 130 | _ | 880 | 0.75 | 1.25 | 0.2 | 132 | 180
58 | Nalla from Block No. 26 to 30 Main Rd. | 980 | 28.03.19 | 05.04.19 | 31.05.19 | 81.8182 | 45 | _ | 980 | 0.75 | 1.25 | 0.2 | 147 | 55
59 | Nalla from Block No. 31 to 36 Central Rd. | 1000 | 28.03.19 | 05.04.19 | 31.05.19 | 80.5556 | 145 | _ | 1000 | 0.75 | 1.25 | 0.2 | 150 | 180
60 | DSIDC Market to Chilla drain along Pkt-III, Mayur Vihar Phase-I. | 700 | 28.03.19 | 05.04.19 | 31.05.19 | 76 | 190 | _ | 700 | 1.2 | 1.5 | 0.25 | 210 | 250
61 | Nalla from Chilla Village to Chilla regulator | 800 | 28.03.19 | 05.04.19 | 31.05.19 | 94.7368 | 180 | _ | 800 | 1 | 2.3 | 0.2 | 160 | 190
62 | Nalla from Vashundara Enclave to New Ashok Nagar Metro Station | 1400 | 28.03.19 | 05.04.19 | 31.05.19 | 93.1373 | 950 | _ | 1400 | 2.1 | 3 | 0.3 | 882 | 1020
63 | Drain between D Block Gazipur Dairy Farm & SLF Gazipur | 252 | 28.03.19 | 05.04.19 | 31.05.19 | 100 | 59 | _ | 252 | 1 | 1.6 | 0.2 | 50.4 | 59
64 | Gazipur Out fall Nalla | 400 | 28.03.19 | 05.04.19 | 31.05.19 | 87.2727 | 240 | _ | 400 | 2.9 | 1.6 | 0.2 | 232 | 275
65 | Outfall nalla from New Ashok Nagar to P.S. Toll Tax Noida | 500 | 28.03.19 | 05.04.19 | 31.05.19 | 36.3636 | 20 | _ | 500 | 0.75 | 1.25 | 0.2 | 75 | 55
66 | Drain between C & D Block Gazipur Dairy Farm | 225 | 28.03.19 | 05.04.19 | 31.05.19 | 72.7273 | 40 | _ | 225 | 0.75 | 1.25 | 0.2 | 33.75 | 55
67 | Drain along Animal Hospital Gazipur Dairy Farm (L.H.S) | 390 | 28.03.19 | 05.04.19 | 31.05.19 | 69.2308 | 135 | _ | 1100 | 1 | 2.3 | 0.2 | 220 | 195
68 | Drain along Animal Hospital Gazipur Dairy Farm (R.H.S) | 390 | 28.03.19 | 05.04.19 | 31.05.19 | 70.5882 | 120 | _ | 960 | 0.75 | 1.25 | 0.2 | 144 | 170
69 | Drain of road from Block No. 19 to 21 Kalyan Puri L/R | 1100 | 28.03.19 | 05.04.19 | 31.05.19 | 60 | 15 | _ | 150 | 0.75 | 1.25 | 0.2 | 22.5 | 25
70 | Drain of road from Block No. 11 to 13 Kalyan Puri L/R | 960 | 28.03.19 | 05.04.19 | 31.05.19 | 94.4444 | 17 | _ | 14097 | - | - | - | 4038.15 | 18
71 | Khichri Pur Nalla Block No. 9 to 10 | 150 | 28.03.19 | 05.04.19 | 31.05.19 | 55.5556 | 10 | _ | 70 | 1 | 1.4 | 0.2 | 14 | 18
| Total | 14877 |  |  |  |  | 3836 |  | 70 | - | - | - | 14
E.E(M)-IV-Sh. South
72 | Drain from Sriram chowk to Aggarwal Sweets, C-Block West Vinod Nagar | 480 | 2019-03-09 | 09.03.19 | 15.05.19 | 89.6443 | 90 | _ | 480 | 0.9 | 1.2 | 0.2 | 86.4 | 100.3968
73 | Drain from Sriram chowk to Jewellary Shop, D-Block West Vinod Nagar | 290 | - | 01.10.18 | 15.05.19 | 69.2425 | 35 | _ | 290 | 0.75 | 1.2 | 0.2 | 43.5 | 50.547
74 | Drain on Shanti marg from Budha Marg to Narwana Road (Both Sides) | 700 | 2019-03-09 | 09.03.19 | 15.05.19 | 81.9605 | 120 | _ | 700 | 0.9 | 1.2 | 0.2 | 126 | 146.412
75 | Drain from Sadbhawna Chowk to Taxi Stand on Sadbhawana Road | 420 | 2019-03-09 | 09.03.19 | 15.05.19 | 82.7486 | 105 | _ | 420 | 1.3 | 1.5 | 0.2 | 109.2 | 126.8904
76 | Drain on Shanti Marg from RCC culvert, Mandawali Road to Budha Marg (Both Sides) | 500 | 2019-03-09 | 09.03.19 | 15.05.19 | 66.9344 | 70 | _ | 500 | 0.9 | 1.2 | 0.2 | 90 | 104.58
77 | Drain from Budha Marg to Sadbhavna Chowk | 150 | - | 01.05.19 | 15.05.19 | 100.4016 | 35 | _ | 150 | 1 | 1.2 | 0.2 | 30 | 34.86
78 | Drain from Harijan Basti Rly. Colony to Pump House, Mayfair Apptt. | 430 | - | 01.10.18 | 15.05.19 | 45.0306 | 45 | _ | 430 | 1 | 1.5 | 0.2 | 86 | 99.932
79 | Drains from Sriram Chowk to Rly. Colony on both sides of Kalyan Marg | 1500 | 2019-03-09 | 09.03.19 | 15.05.19 | 92.4332 | 290 | _ | 1500 | 0.9 | 1.2 | 0.2 | 270 | 313.74
80 | Drain from Milenium Park to MC Pry School No.1 via Pandit Mohalla, Mandawali | 500 | 2019-03-09 | 09.03.19 | 15.05.19 | 63.7471 | 50 | _ | 500 | 0.9 | 1.2 | 0.15 | 67.5 | 78.435
81 | Drain from Railway Colony to Bhim Gali along Sonia Vihar Subzi Mandi | 100 | - | 01.10.18 | 15.05.19 | 53.1225 | 25 | _ | 300 | 0.9 | 1.2 | 0.15 | 40.5 | 47.061
82 | Drain from Pump House Bus Stand near H. No. A/185 to outfall | 305 | - | 01.10.18 | 15.05.19 | 98.7557 | 63 | _ | 305 | 0.9 | 1.2 | 0.2 | 54.9 | 63.7938
| Pumphouse outfall nalla | 330 | - | 01.10.18 | 15.05.19 | 95.6206 | 60 | _ | 300 | 0.9 | 1.2 | 0.2 | 54 | 62.748
83 | Drain in Mayur Vihar-II Pocket B from M.C. Pry School Pocket F to Sanjay Jheel. | 425 | 2019-03-09 | 09.03.19 | 15.05.19 | 65.1958 | 50 | _ | 330 | 1 | 1.2 | 0.2 | 66 | 76.692
84 | Drain in Mayur Vihar Ph. II from E/560 to Pump House | 400 | - | 01.10.18 | 15.05.19 | 85.0461 | 63 | _ | 425 | 1 | 1.25 | 0.15 | 63.75 | 74.0775
85 | Drain from G-Block to Gurudwara East Vinod Nagar adjoning NH-9 | 350 | 2019-03-09 | 09.03.19 | 15.05.19 | 80.6799 | 90 | _ | 400 | 1.2 | 1.3 | 0.2 | 96 | 111.552
86 | Drain from IFS App. To Fine Home App. | 800 | 2019-03-09 | 09.03.19 | 15.05.19 | 68.7273 | 115 | _ | 800 | 0.9 | 1.3 | 0.2 | 144 | 167.328
87 | Drain from Sahyog App. to Anand Lok Appt. | 395 | - | 01.10.18 | 15.05.19 | 84.7271 | 70 | _ | 395 | 0.9 | 1.3 | 0.2 | 71.1 | 82.6182
88 | Drain from Ahalcon Intl. School to Police App. Mayur Vihar | 350 | - | 01.10.18 | 15.05.19 | 68.3004 | 50 | _ | 350 | 0.9 | 1.2 | 0.2 | 63 | 73.206
89 | Drain from Partap Nagar to Aggarwal Sweets in Mayur Vihar Ph. - I | 510 | 2019-03-09 | 09.03.19 | 15.05.19 | 63.2783 | 75 | _ | 510 | 1 | 1.2 | 0.2 | 102 | 118.524
90 | Drain in P-Block Pandav Nagar. | 330 | 2019-03-09 | 09.03.19 | 15.05.19 | 65.1958 | 30 | _ | 330 | 0.6 | 1.2 | 0.2 | 39.6 | 46.0152
91 | Acharya Niketan Nalla from Maternity Home to Church. | 500 | - | 01.10.18 | 15.05.19 | 64.5439 | 45 | _ | 500 | 0.6 | 1.2 | 0.2 | 60 | 69.72
92 | Samaspur Vill. Nalla from E-54 to Police Aptt. | 500 | - | 01.10.18 | 15.05.19 | 66.1989 | 50 | _ | 500 | 0.65 | 1.2 | 0.2 | 65 | 75.53
93 | Drain along Una Aptt. to Mavila apptt., Mayur Vihar -Ph-I | 260 | - | 01.10.18 | - | 82.7486 | 30 | _ | 260 | 0.6 | 1.2 | 0.2 | 31.2 | 36.2544
94 | Lalita park Nalla | 450 | - | 01.10.18 | 15.05.19 | 79.3297 | 56 | _ | 450 | 0.9 | 1.3 | 0.15 | 60.75 | 70.5915
95 | Gali No. 12 drain Lalita Park, | 200 | - | 01.10.18 | 15.05.19 | 43.0293 | 15 | _ | 200 | 0.75 | 1.2 | 0.2 | 30 | 34.86
96 | Ramesh Park Community Centre Nalla | 350 | - | 01.10.18 | 15.05.19 | 94.2546 | 23 | _ | 200 | 0.7 | 1.2 | 0.15 | 21 | 24.402
97 | Bank Enclave drain opp. H. No. 1 | 300 | - | 01.10.18 | - | 87.8148 | 50 | _ | 350 | 0.7 | 1.3 | 0.2 | 49 | 56.938
98 | Ramesh Park Police Stn. Drain | 360 | - | 01.10.18 | - | 70.6909 | 23 | _ | 200 | 0.7 | 1.25 | 0.2 | 28 | 32.536
99 | MB road drain | 1200 | 2019-03-09 | 09.03.19 | 15.05.19 | 47.8103 | 25 | _ | 300 | 1 | 1.2 | 0.15 | 45 | 52.29
100 | Bank Enclave drain | 200 | 2019-03-09 | 09.03.19 | - | 35.8577 | 30 | _ | 360 | 1 | 1.35 | 0.2 | 72 | 83.664
101 | Kundan Nagar Nalla (Right Side) | 200 | - | 01.10.18 | 15.05.19 | 4.781 | 30 | _ | 1200 | 3 | 3 | 0.15 | 540 | 627.48
102 | PD Vihar drain | 400 | - | 01.10.18 | 15.05.19 | 76.838 | 50 | _ | 400 | 0.7 | 1.2 | 0.2 | 56 | 65.072
103 | Laxmi Nagar Market Nalla | 1900 | 2019-03-09 | 09.03.19 | 15.05.19 | 85.2592 | 240 | _ | 1900 | 0.85 | 1.2 | 0.15 | 242.25 | 281.4945
104 | Shakarpur Market Nalla | 795 | 2019-03-09 | 09.03.19 | 15.05.19 | 81.1873 | 120 | _ | 795 | 0.8 | 1.2 | 0.2 | 127.2 | 147.8064
105 | Drain from Bhim Gali to Budha Marg | 1000 | 2019-03-09 | 09.03.19 | 15.05.19 | 66.9344 | 70 | _ | 600 | 0.75 | 1.2 | 0.2 | 90 | 104.58
106 | Hanuman Mandir road Pandav Nagar nalla | 555 | 2019-03-09 | 09.03.19 | 15.05.19 | 77.5302 | 90 | _ | 555 | 0.9 | 1.2 | 0.2 | 99.9 | 116.0838
107 | D Park to 11/3 Pandav Nagar nalla | 340 | 2019-03-09 | 09.03.19 | 15.05.19 | 73.8247 | 35 | _ | 340 | 0.8 | 1.2 | 0.15 | 40.8 | 47.4096
108 | Drain from DDA Park to S 380 School Block Pandav Nagar | 650 | - | 01.10.18 | 15.05.19 | 68.6507 | 70 | _ | 650 | 0.9 | 1.2 | 0.15 | 87.75 | 101.9655
109 | C-68/4 to S-101 Pandav Nagar nalla | 125 | - | 01.10.18 | 15.05.19 | 76.4965 | 15 | _ | 125 | 0.9 | 1.2 | 0.15 | 16.875 | 19.6087
110 | NH-24 drain | 3100 | 2019-03-09 | 09.03.19 | 15.05.19 | 0.33167 | 10 | _ | 19300 |  |  |  | 3466.175 | 3015
| Total | 22650 |  |  |  |  | 2608
20%

## Misc abst (hidden)
East Delhi Municipal Corporation
Divisin | No. of Drains | Length of Drain (in Mtr) | Silt removed from 01.10.18 to 09.05.19 (In MT) (a) | Silt removed upto 16.02.18 | Silt removed during this week (In MT) (b) | Total qty. in M.T. (a + b)
Shahdara North Zone
EE-M-I-SHN | 41 | 19629 | 2735 |  | 815 | 3550
EE-M-II-SHN | 32 | 22185 | 4018.8 |  | 1452.8 | 5471.6
EE-M-III-SHN | 24 | 10206 | 1130.52 |  | 830.895 | 1961.415
EE-M-IV-SHN | 17 | 10839 | 4779.9 |  | 1073.29 | 5853.19
Total | 114 | 62859 | 12664.22 |  | 4171.985 | 16836.205
Shahdara South Zone
EE-M-I-SHS | 32 | 15383.4 | 203 |  | 247 | 450
EE-M-II-SHS | 17 | 11025 | 1832 |  | 641 | 2473
EE-M-III-SHS | 22 | 14877 | 3335 |  | 501 | 3836
EE-M-IV-SHS | 38 | 22650 | 3146 |  | 200 | 3346
Total | 109 | 63935.4 | 8516 |  | 1589 | 10105