## Sheet1
East Delhi Municipal Corporation
EE-M-I/SHAHDARA NORTH
Report on Desilting of Drains for the week upto 6th June 2019
Date 6.06.19
E.E(M)-I-Sh. North
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
S. No. | Ward No. | Name of Drain | Length of Drain | Date of Issue of Desilting Tender | Date of Commencement of Desilting | Excepted Date of Completion of Desilting | Progres of Work (in %) | Quantity of Silt removed (in MT) | Inter Departmental Problem faced (if any) | Remarks
1 | 28 E | Nalla in Old Seemapuri G block to Pump house | 1361 | 31.03.2019 | 01.05.2019 | 25.05.2019 | 100% | 580 | _ | Comp. | 573
2 | 35 E | Desilting of nalla from SSBL drain Jalli Kheda Vill. To SDN Hopt. Road in W.No. 241 | 135 | 26.03.2019 | 15.04.2019 | 25.05.2019 | 100% | 78 | _ | Comp. | 76
3 | 35 E | SSBL drain from 100Ft. road no.68 to G.T.Road flyover Rd 1081 to 1481 mtr | 400 | 26.03.2019 | 15.04.2019 | 25.05.2019 | 100% | 560 | _ | Comp. | 548
4 | 35 E | SSBL drain from 100Ft. road no.68 to G.T.Road flyover Rd 1481 to 1946 mtr | 510 | 26.03.2019 | 15.04.2019 | 31.05.2019 | 90% | 480 | _ | In Prg | 698
5 | 35 E | SSBL drain from 100Ft. road no.68 to G.T.Road flyover Rd 1946 to 2362 mtr. | 397 | 26.03.2019 | 15.04.2019 | 31.05.2019 | 80% | 255 | _ | In Prg | 483
6 | 35 E | SSBL drain from 100Ft. road no.68 to G.T.Road flyover Rd 2362 to 2702 mtr. | 314 | 26.03.2019 | 15.04.2019 | 31.05.2019 | 90% | 372 | _ | In Prg | 374
7 | 35 E | Nallah along DDA park from MCD sotre to Q-Pkt. Drain in Dilshad Garden | 310 | 26.03.2019 | 15.04.2019 | 25.05.2019 | 100% | 76 | _ | Comp. | 73
8 | 35 E | Nallah from Tahirpur Sarai to R-Pkt. Dilshad Garden | 150 | 26.03.2019 | 15.04.2019 | 25.05.2019 | 100% | 55 | _ | Comp. | 53
9 | 35 E | Nallah from Gali No-8 Jagatpuri extn. Unauthorized colony | 90 | 26.03.2019 | 15.04.2019 | 25.05.2019 | 100% | 20 | _ | Comp. | 16
10 | 35 E | Nallah along DDA park from P-15/A-4 to MCD Store Dilshad Garden | 330 | 26.03.2019 | 15.04.2019 | 25.05.2019 | 100% | 65 | _ | Comp. | 59
11 | 34 E | Nalla in new seemapuri from E-blk to Machli Market | 220 | 25.03.2019 | 26.03.2019 | 31.05.2019 | 100% | 51 | _ | Comp. | 51
12 | 34 E | Nalla in Tahirpur village from Shiv mandir to Kali mandir | 240 | 25.03.2019 | 26.03.2019 | 25.05.2019 | 100% | 40 | _ | Comp. | 35
13 | 34 E | Nalla in E-Block Jhuggi Nalla New Seemapuri | 100 | 25.03.2019 | 26.03.2019 | 25.05.2019 | 100% | 16 | _ | Comp. | 13
14 | 34 E | Nalla in New seemapuri from Bhopal Pulia to Dhobi Ghat | 110 | 25.03.2019 | 26.03.2019 | 25.05.2019 | 100% | 25 | _ | Comp. | 21
15 | 32 E | SSBL drain from Wazirabad Road to Ashok Nagar railway phatak (Hanuman Pulia) | 540 | 26.03.2019 | 07.04.2019 | 31.05.2019 | 90% | 921 | _ | In Prg | 1066
16 | 32 E | Internal nallas in D- block Nand Nagari from D-1/275 to D-1/231 to Upto D-3/355 | 190 | 26.03.2019 | 28.03.2019 | 25.05.2019 | 100% | 30 | _ | Comp. | 27
17 | 32 E | Nalla both side E block pump house nalla in Nand Nagari from E-4/160 to pump house including sump well | 780 | 26.03.2019 | 28.03.2019 | 31.05.2019 | 100% | 165 | _ | Comp. | 156
18 | 32 E | Both side Nalla of Akhara park E -4 Block Nand Nagari | 700 | 26.03.2019 | 28.03.2019 | 31.05.2019 | 95% | 128 | _ | In Prg | 131
19 | 32 E | Internal nallas in A-1/30 in A block Nand Nagari from A-2/30 to A-2 Block Nand Nagri | 525 | 26.03.2019 | 28.03.2019 | 25.05.2019 | 100% | 95 | _ | Comp. | 92
20 | 32 E | Internal nallas in A-1/481 and Ujala Pulia to road No 68 towards cement godown both side | 1200 | 26.03.2019 | 28.03.2019 | 31.05.2019 | 90% | 280 | _ | In Prg | 316
21 | 32 E | Nallah from Sr. Sec. School Raja Ravin Verma corner to B-5 Block Market Nand Nagri | 375 | 26.03.2019 | 28.03.2019 | 31.05.2019 | 90% | 90 | _ | In Prg | 98
22 | 32 E | Nallah from B-5 Block Market Corner to road no-68 | 150 | 26.03.2019 | 28.03.2019 | 25.05.2019 | 100% | 38 | _ | Comp. | 32
23 | 32 E | Nallah H.no-30 E-1 Nand Nagri to H.no-231 E-Block Nand Nagri | 115 | 26.03.2019 | 28.03.2019 | 31.05.2019 | 100% | 30 | _ | Comp. | 26
24 | 32 E | Nallah from H.no-481 E-2 Nand Nagri to H.no-280 E-2 Block Nand nagri | 115 | 26.03.2019 | 28.03.2019 | 25.05.2019 | 100% | 40 | _ | Comp. | 35
25 | 33 E | Nalla along Murga Mkt. in G & H block Sunder Nagari from mandir to Upto pumphouse including sump well | 589 | 25.03.2019 | 07.05.2019 | 31.05.2019 | 25% | 55 | _ | In Prg | 156
26 | 33 E | Nalla in L Block Sunder Nagari from police chowki to L-55 Sunder Nagari | 478 | 25.03.2019 | 07.05.2019 | 31.05.2019 | 70% | 120 | _ | In Prg | 159
27 | 33 E | nalla in sunder nagari from M.C. Primary school to Sani bazar mandi along F2 sunder nagari | 254 | 25.03.2019 | 07.05.2019 | 31.05.2019 | 50% | 20 | _ | In Prg | 29
28 | 52 E | Desilting of nallah in Bhagirathi Vihar from Brijpuri culvert to Drain No.1 in W.No.261 Shah.North Zone. | 1410 | 31.03.2019 | 05.04.2019 | 25.05.2019 | 100% | 180 | _ | Comp. | 172
29 | 52 E | Desilting of nallah in Ambedkar Colony from main road Johripur to Drain no.1 in W.No.261 Shah.North Zone. | 278 | 31.03.2019 | 05.04.2019 | 25.05.2019 | 100% | 50 | _ | Comp. | 46
30 | 52 E | Desilting of nallah from main road Johari Pur along Johari pur Ext. to block, main road (both side) to Drain no.1 in W.No.261 Shah.North Zone. | 560 | 31.03.2019 | 05.04.2019 | 25.05.2019 | 100% | 65 | _ | Comp. | 59
31 | 53 E | Desilting of nallah along C-block, main road to Ganga Vihar W.No.261 Shah.North Zone. | 540 | 31.03.2019 | 15.04.2019 | 25.05.2019 | 100% | 105 | _ | Comp. | 95
32 | 53 E | Desilting of internal nallah A,B,C & D block to pump house to school block, Ambey Cycle to post office and Kaushik Garment to M.C. Pry. School B-block in Gokulpuri W.No.262 Shah.North Zone. | 380 | 31.03.2019 | 15.04.2019 | 25.05.2019 | 100% | 65 | _ | Comp. | 61
33 | 53 E | Desilting of nallah from Amar Colony to Loni road flyover in W.No.262 Shah.North Zone. | 285 | 31.03.2019 | 15.04.2019 | 31.05.2019 | 70% | 55 | _ | In Prg | 80
34 | 53 E | Desilting of nallah C-block, jhuggi area along main road up to Pump house i.e sump well in Gokulpuri W.No.262 Shah.North Zone. | 508 | 31.03.2019 | 15.04.2019 | 25.05.2019 | 100% | 85 | _ | Comp. | 77
35 | 53 E | Desilting of nallah along main road Ganga Vihar from dhalao to drain no.1 along A,B,D & F block in Ganga Vihar W.No.262 Shah.North Zone. | 600 | 31.03.2019 | 15.04.2019 | 25.05.2019 | 100% | 110 | _ | Comp. | 105
36 | 53 E | Desilting of nallah from main road Ganga Vihar to Gokulpur Village W.No.262 Shah.North Zone. | 340 | 31.03.2019 | 15.04.2019 | 25.05.2019 | 100% | 55 | _ | Comp. | 48
37 | 54 E | Nalla from Shamshan Ghat to Saboli goan bada kuan (Rathore Cement Store) | 700 | 31.03.2019 | 05.04.2019 | 25.05.2019 | 100% | 105 | _ | Comp. | 98
38 | 54 E | Nalla along railway line from Saboli Phatak | 620 | 31.03.2019 | 05.04.2019 | 25.05.2019 | 100% | 270 | _ | Comp. | 261
39 | 55 E | Nalla on both side along Gali No 9 Bank Colony Harsh Vihar dividing road from Jail B/wall to Budh Vihar Chowk | 400 | 31.03.2019 | 05.04.2019 | 25.05.2019 | 100% | 70 | _ | Comp. | 61
40 | 55 E | Nalla from P.W.D P/house Harsh Vihar to Jail Boundary wall | 1370 | 31.03.2019 | 05.04.2019 | 25.05.2019 | 100% | 365 | _ | Comp. | 360
41 | 55 E | Nalla on both side along bank colony Road from Wazirabad road to Kishan Lal Chowk | 960 | 31.03.2019 | 05.04.2019 | 25.05.2019 | 100% | 130 | _ | Comp. | 126
|  | Total | 19629 |  |  |  |  | 6395
-6395
|  | Total No. of Drain =41 | [5 empty] | EE-[M. Shah. (N)]-I
Completed=30
In Prg. =11