## Sheet (hidden)
East Delhi Municipal Corporation
ACTION PLAN FOR DESILTING OF DRAINS/ NALLAH FOR THE PERIOD 01.10.2017 to 27.06.18
Dt. 03.08.18
S. No. | Sl. Of drainage Master Plan | Ward No. | Name of Drain | Length of Drain (in Mtr) | Name of contractors/ agency | Name and designation of the Engineer in charge | Date of start | Target date fixed for completion |  |  |  | Aprox. Volume of silt to be desilted (in Cum) | Estimated quantity of th silt to be removed | Silt removed till date (In MT) | Departmental/ Private
E.E(M)-IV-Shahdara South
1 |  | 9 | Drain on Shanti Marg from RCC culvert, Mandawali Road to Budha Marg (Both Sides) | 500 | EDMC | Sh. Mula Singh, Executive Engineer, 9717787761 | 01.10.17 | 31.05.18 | 0.9 | 1.2 | 0.2 | 90 | 104.58 | 106 | One time completed. Floating material being removed regularly.
2 |  | 9 | Drain from Budha Marg to Sadbhavna Chowk | 150 | EDMC |  | 01.10.17 | 31.05.18 | 1 | 1.2 | 0.2 | 30 | 34.86 | 30 | --do--
3 |  | 9 | Drain from Harijan Basti Rly. Colony to Pump House, Mayfair Apptt. | 430 | EDMC |  | 01.10.17 | 31.05.18 | 1 | 1.5 | 0.2 | 86 | 99.932 | 100 | --do--
4 |  | 9 | Drains from Sriram Chowk to Rly. Colony on both sides of Kalyan Marg | 1500 | EDMC |  | 01.10.17 | 2018-06-25 | 0.9 | 1.2 | 0.2 | 270 | 313.74 | 230 | --do--
5 |  | 9 | Drain from Milenium Park to MC Pry School No.1 via Pandit Mohalla, Mandawali | 500 | EDMC |  | 01.10.17 | 31.05.18 | 0.9 | 1.2 | 0.2 | 67.5 | 78.435 | 50 | --do--
6 |  | 10 | Drain from Sriram chowk to Aggarwal Sweets, C-Block West Vinod Nagar | 480 | EDMC |  | 01.10.17 | 31.05.18 | 0.9 | 1.2 | 0.2 | 86.4 | 100.3968 | 95 | --do--
7 |  | 10 | Drain from Sriram chowk to Jewellary Shop, D-Block West Vinod Nagar | 290 | EDMC |  | 01.10.17 | 31.05.18 | 0.75 | 1.2 | 0.2 | 43.5 | 50.547 | 55 | --do--
8 |  | 10 | Drain on Shanti marg from Budha Marg to Narwana Road (Both Sides) | 700 | EDMC |  | 01.10.17 | 31.05.18 | 0.9 | 1.2 | 0.2 | 126 | 146.412 | 145 | --do--
9 |  | 10 | Drain from Sadbhawna Chowk to Taxi Stand on Sadbhawana Road | 420 | EDMC |  | 01.10.17 | 31.05.18 | 1.3 | 1.5 | 0.2 | 109.2 | 126.8904 | 130 | --do--
10 |  | 11 | Drain from Pump House Bus Stand near H. No. A/185 to outfall | 305 | EDMC |  | 01.10.17 | 31.05.18 | 0.9 | 1.2 | 0.2 | 54.9 | 63.7938 | 70 | --do--
|  |  |  | 300 | EDMC |  | 01.10.17 | 31.05.18 | 0.9 | 1.2 | 0.2 | 54 | 62.748 | 63 | --do--
11 |  | 11 | Pumphouse outfall nalla | 330 | EDMC |  | 01.10.17 | 31.05.18 | 1 | 1.2 | 0.2 | 66 | 76.692 | 74 | --do--
12 |  | 11 | Drain in Mayur Vihar-II Pocket B from M.C. Pry School Pocket F to Sanjay Jheel. | 425 | EDMC | Sh. Mula Singh, Executive Engineer, 9717787761 | 01.10.17 | 31.05.18 | 1 | 1.25 | 0.2 | 63.75 | 74.0775 | 82 | --do--
13 |  | 11 | Drain in Mayur Vihar Ph. II from E/560 to Pump House | 400 | EDMC |  | 01.10.17 | 31.05.18 | 1.2 | 1.3 | 0.2 | 96 | 111.552 | 110 | --do--
14 |  | 12 | Drain from IFS App. To Fine Home App. | 800 | EDMC |  | 01.10.17 | 31.05.18 | 0.9 | 1.3 | 0.2 | 144 | 167.328 | 165 | --do--
15 |  | 12 | Drain from Sahyog App. to Anand Lok Appt. | 395 | EDMC |  | 01.10.17 | 31.05.18 | 0.9 | 1.3 | 0.2 | 71.1 | 82.6182 | 80 | --do--
16 |  | 12 | Drain from Ahalcon Intl. School to Police App. Mayur Vihar | 350 | EDMC |  | 01.10.17 | 31.05.18 | 0.9 | 1.2 | 0.2 | 63 | 73.206 | 72 | --do--
17 |  | 12 | Drain from Partap Nagar to Aggarwal Sweets in Mayur Vihar Ph. - I | 510 | EDMC |  | 01.10.17 | 31.05.18 | 1 | 1.2 | 0.2 | 102 | 118.524 | 120 | --do--
18 |  | 12 | Drain in P-Block Pandav Nagar. | 330 | EDMC |  | 01.10.17 | 31.05.18 | 0.6 | 1.2 | 0.2 | 39.6 | 46.0152 | 45 | --do--
19 |  | 12 | Acharya Niketan Nalla from Maternity Home to Church. | 500 | EDMC |  | 01.10.17 | 31.05.18 | 0.6 | 1.2 | 0.2 | 60 | 69.72 | 70 | --do--
20 |  | 12 | Samaspur Vill. Nalla from E-54 to Police Aptt. | 500 | EDMC |  | 01.10.17 | 31.05.18 | 0.65 | 1.2 | 0.2 | 65 | 75.53 | 65 | --do--
21 |  | 12 | Drain along Una Aptt. to Mavila apptt., Mayur Vihar -Ph-I | 260 | EDMC |  | 01.10.17 | 31.05.18 | 0.6 | 1.2 | 0.2 | 31.2 | 36.2544 | 35 | --do--
22 |  | 13 | Lalita park Nalla | 450 | EDMC |  | 01.10.17 | 31.05.18 | 0.9 | 1.3 | 0.2 | 60.75 | 70.5915 | 71 | --do--
23 |  | 13 | Gali No. 12 drain Lalita Park, | 200 | EDMC |  | 01.10.17 | 31.05.18 | 0.7 | 1.2 | 0.2 | 21 | 24.402 | 23 | --do--
24 |  | 13 | Ramesh Park Community Centre Nalla | 350 | EDMC |  | 01.10.17 | 31.05.18 | 0.7 | 1.3 | 0.2 | 49 | 56.938 | 40 | --do--
25 |  | 13 | Bank Enclave drain | 200 | EDMC |  | 01.10.17 | 31.05.18 | 0.7 | 1.25 | 0.2 | 28 | 32.536 | 33 | --do--
26 |  | 13 | Ramesh Park Police Stn. Drain | 360 | EDMC | Sh. Mula Singh, Executive Engineer, 9717787761 | 01.10.17 | 31.05.18 | 1 | 1.35 | 0.2 | 72 | 83.664 | 65 | --do--
27 |  | 13 | MB road drain | 1200 | EDMC |  | 01.10.17 | 31.05.18 | 3 | 3 | 0.2 | 540 | 627.48 | 625 | --do--
28 |  | 14 | Bank Enclave drain opp. H. No. 1 | 300 | EDMC |  | 01.10.17 | 31.05.18 | 1 | 1.2 | 0.2 | 45 | 52.29 | 50 | --do--
29 |  | 14 | Kundan Nagar Nalla (Right Side) | 200 | EDMC |  | 01.10.17 | 31.05.18 | 0.75 | 1.2 | 0.2 | 30 | 34.86 | 30 | --do--
30 |  | 14 | PD Vihar drain | 400 | EDMC |  | 01.10.17 | 31.05.18 | 0.7 | 1.2 | 0.2 | 56 | 65.072 | 62 | --do--
31 |  | 14 | Laxmi Nagar Market Nalla | 1900 | EDMC |  | 01.10.17 | 31.05.18 | 0.85 | 1.2 | 0.2 | 242.25 | 281.4945 | 350 | --do--
32 |  | 15 | Shakarpur Market Nalla | 795 | EDMC |  | 01.10.17 | 31.05.18 | 0.8 | 1.2 | 0.2 | 127.2 | 148 | 135 | --do--
33 |  | 15 | Drain from DDA Park to S 380 School Block Pandav Nagar | 650 | EDMC |  | 01.10.17 | 31.05.18 | 0.9 | 1.2 | 0.2 | 87.75 | 101.9655 | 100 | --do--
34 |  | 16 | Drain from JE Store 218 to Budha Marg | 600 | EDMC |  | 01.10.17 | 31.05.18 | 0.75 | 1.2 | 0.2 | 90 | 104.58 | 100 | --do--
35 |  | 16 | Hanuman Mandir road Pandav Nagar nalla | 555 | EDMC |  | 01.10.17 | 31.05.18 | 0.9 | 1.2 | 0.2 | 99.9 | 116.0838 | 115 | --do--
36 |  | 16 | D Park to 11/3 Pandav Nagar nalla | 340 | EDMC |  | 01.10.17 | 31.05.18 | 0.8 | 1.2 | 0.2 | 40.8 | 47.4096 | 45 | --do--
37 |  | 16 | C-68/4 to S-101 Pandav Nagar nalla | 125 | EDMC |  | 01.10.17 | 31.05.18 | 0.9 | 1.2 | 0.2 | 16.875 | 19.6087 | 20 | --do--
38 |  | 16 | Drain from Railway Colony to JE (M)-218 Store along Sonia Vihar Subzi Mandi | 300 | EDMC |  | 01.10.17 | 31.05.18 | 0.9 | 1.2 | 0.2 | 40.5 | 47.061 | 45 | Under construction
|  |  | Total | 19300 |  |  |  |  | 35.05 | 48.75 | 7.6 | 3425.675 | 3980.8279 | 3901
|  |  | Note:- Total silt semt to SLF (Singrola/ Gazipur) - | 5312 MT

## Action Plan 2018-19
EAST DELHI MUNICIPAL CORPORATION
OFFICE OF THE EXECUTIVE ENGINEER (M)-III
SHAHDARA SOUTH ZONE
SCHOOL BLOCK, SHAKARPUR, DELHI-92
As on 10.06.19
Status of De-silting for the Year 2018-19
S.No. | Division | Ward No. | Name of Drain | Location |  | Nature of drain |  | Section of drain (in mtrs) |  |  | Depth (silt) Mtr. (Av.) | Aprox. Volume of silt to be desilted (in cum) | Aprox. Qty. of silt to be desilted (in MT) | Proposed Qunatity of Silt to be removed from (In MT) |  |  | Achivement upto (In MT) | Silt removed in % | Status | Departmental/ Private | Remarks
[6 empty] | Open | Covered | Length Mtr. (Av.) | Width Mtr. (Av.) | Depth
|  |  |  | From | To | [8 empty] | 01.10.18 to 31.12.18 | 01.01.19 to 31.03.19 | 01.04.19 to 31.05.19
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 5 | 6 | 20 | 7
1 | EE-M-III-Shah.(S) | 001E | Nalla from Block No. 19 to 25 Central Road Trilokpuri. | Sriram chowk | Aggarwal Sweets, C-Block West Vinod Nagar |  | 480 | 480 | 0.9 | 1.2 | 0.2 | 86.4 | 100.3968 | 33 | 33 | 34 | 100 | 100% | Completed | Contractual
2 | EE-M-III-Shah.(S) |  | Drain from Mayur Vihar Pkt-II to Gurudward Chowk. | Sriram chowk | Jewellary Shop, D-Block West Vinod Nagar | 290 |  | 290 | 0.75 | 1.2 | 0.2 | 43.5 | 50.547 | 10 | 24 | 17 | 50 | 100% | Completed | Departmental
3 | EE-M-III-Shah.(S) |  | Nalla from Block No. 14 to 13 Central Road Trilokpuri. | Budha Marg | Narwana Road (Both Sides) |  | 700 | 700 | 0.9 | 1.2 | 0.2 | 126 | 146.412 | 49 | 49 | 48 | 130 | 100% | Completed | Contractual
4 | EE-M-III-Shah.(S) | 002E | Sanjay drain in Trilok Puri | Sadbhawna Chowk | Taxi Stand on Sadbhawana Road |  | 420 | 420 | 1.3 | 1.5 | 0.2 | 109.2 | 126.8904 | 42 | 40 | 45 | 115 | 95% | In progress | Contractual
5 | EE-M-III-Shah.(S) |  | Block No. 9 to 12 (L.H.S), Trilok Puri | RCC culvert, Mandawali Road | Budha Marg (Both Sides) |  | 500 | 500 | 0.9 | 1.2 | 0.2 | 90 | 104.58 | 35 | 40 | 30 | 90 | 100% | Completed | Contractual
6 | EE-M-III-Shah.(S) |  | Block No. 9 to 12 (R.H.S), Trilok Puri | Budha Marg | Sadbhavna Chowk |  | 150 | 150 | 1 | 1.2 | 0.2 | 30 | 34.86 | 12 | 12 | 11 | 30 | 100% | Completed | Departmental
7 | EE-M-III-Shah.(S) |  | Block No. 15 to 18 (Internal Road). | Harijan Basti Rly. Colony | Pump House, Mayfair Apptt. |  | 430 | 430 | 1 | 1.5 | 0.2 | 86 | 99.932 | 33 | 30 | 37 | 80 | 100% | Completed | Departmental
8 | EE-M-III-Shah.(S) | 003E | Nalla from Block No. 26 to 30 Central Rd. | Sriram Chowk | Rly. Colony |  | 1500 | 1500 | 0.9 | 1.2 | 0.2 | 270 | 313.74 | 105 | 100 | 109 | 300 | 100% | Completed | Contractual
9 | EE-M-III-Shah.(S) |  | Nalla from Block No. 26 to 30 Main Rd. | Milenium Park | MC Pry School No 1 |  | 500 | 500 | 0.9 | 1.2 | 0.15 | 67.5 | 78.435 | 26 | 22 | 20 | 65 | 100% | Completed | Contractual
10 | EE-M-III-Shah.(S) |  | Nalla from Block No. 31 to 36 Central Rd. | Railway Colony | Bhim Gali |  | 100 | 100 | 0.9 | 1.2 | 0.15 | 40.5 | 47.061 | 10 | 26 | 13 | 45 | 100% | Completed | Departmental
11 | EE-M-III-Shah.(S) |  | DSIDC Market to Chilla drain along Pkt-III, Mayur Vihar Phase-I. | Bus Stand | outfall | 305 |  | 305 | 0.9 | 1.2 | 0.2 | 54.9 | 63.7938 | 21 | 21 | 20 | 60 | 100% | Completed | Departmental
12 | EE-M-III-Shah.(S) |  | Nalla from Chilla Village to Chilla regulator | Near A/185 | Bus Stand |  | 300 | 300 | 0.9 | 1.2 | 0.2 | 54 | 62.748 | 22 | 21 | 20 | 60 | 100% | Completed | Departmental
13 | EE-M-III-Shah.(S) | 004E | Nalla from Vashundara Enclave to New Ashok Nagar Metro Station | Pocket-C | outfall |  | 330 | 330 | 1 | 1.2 | 0.2 | 66 | 76.692 | 26 | 26 | 25 | 75 | 95% | In progress | Departmental
14 | EE-M-III-Shah.(S) | 005E | Drain between D Block Gazipur Dairy Farm & SLF Gazipur | M.C. Pry School pkt- F | Sanjay Jheel. |  | 425 | 425 | 1 | 1.25 | 0.15 | 63.75 | 74.0775 | 25 | 19 | 30 | 60 | 100% | Completed | Contractual
15 | EE-M-III-Shah.(S) |  | Gazipur Out fall Nalla | E/560 | Pump House, Sanjay Jheel | 400 |  | 400 | 1.2 | 1.3 | 0.2 | 96 | 111.552 | 37 | 37 | 38 | 110 | 100% | Completed | Departmental
16 | EE-M-III-Shah.(S) |  | Outfall nalla from New Ashok Nagar to P.S. Toll Tax Noida | G-Bloc | Gurudwara East Vinod Nagar adjoning NH-9 | 350 |  | 350 | 1.2 | 1.3 | 0.25 | 105 | 120 | 30 | 35 | 55 | 110 | 100% | Completed | Contractual
17 | EE-M-III-Shah.(S) |  | Drain between C & D Block Gazipur Dairy Farm | IFS App | Fine Home App. |  | 800 | 800 | 0.9 | 1.3 | 0.2 | 144 | 167.328 | 57 | 50 | 60 | 150 | 100% | Completed | Contractual
18 | EE-M-III-Shah.(S) | 008E | Drain of road from Block No. 19 to 21 Kalyan Puri L/R | Sahyog App | Anand Lok Appt. |  | 395 | 395 | 0.9 | 1.3 | 0.2 | 71.1 | 82.6182 | 28 | 28 | 27 | 80 | 100% | Completed | Departmental
19 | EE-M-III-Shah.(S) |  | Drain of road from Block No. 11 to 13 Kalyan Puri L/R | Ahalcon Intl. School | Police App. |  | 350 | 350 | 0.9 | 1.2 | 0.2 | 63 | 73.206 | 24 | 24 | 23 | 70 | 100% | Completed | Departmental
20 | EE-M-III-Shah.(S) |  | Khichri Pur Nalla Block No. 9 to 10 | Partap Nagar | Aggarwal Sweets |  | 510 | 510 | 1 | 1.2 | 0.2 | 102 | 118.524 | 40 | 40 | 39 | 115 | 100% | Completed | Contractual
21 | EE-M-III-Shah.(S) | 007E | F-Block, H. No. 130 to Sulabh Sauchalay, Kondli | E-54 | Police Aptt. |  | 500 | 500 | 0.65 | 1.2 | 0.2 | 65 | 75.53 | 25 | 25 | 26 | 75 | 100% | Completed | Departmental

## Action Plan 2018-19 (2) (hidden)
EAST DELHI MUNICIPAL CORPORATION
OFFICE OF THE EXECUTIVE ENGINEER (M)-IV
SHAHDARA SOUTH ZONE
SCHOOL BLOCK, SHAKARPUR, DELHI-92
Annexuer-II
De-silting Action Plan for the Year 2018-19
As on 02.05.19
S.No. | Ward No. | Name of Drain | Length Mtr. (Av.) | Date of issue of desilting tender | Date of commancement of desilting | Excepted date of completion of desilting | Progres of work | Achivement upto (In MT) | Inter-departmental problems faced (If any)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 217 | Drain from Sriram chowk to Aggarwal Sweets, C-Block West Vinod Nagar | 480 | 2019-03-09 | 2019-03-09 | 2019-05-15 | 90 | 90 | -
2 | 217 | Drain from Sriram chowk to Jewellary Shop, D-Block West Vinod Nagar | 290 | - | 2018-10-01 | 2019-05-15 | 70 | 35 | -
3 | 217 | Drain on Shanti marg from Budha Marg to Narwana Road (Both Sides) | 700 | 2019-03-09 | 2019-03-09 | 2019-05-15 | 85 | 120 | -
4 | 217 | Drain from Sadbhawna Chowk to Taxi Stand on Sadbhawana Road | 420 | 2019-03-09 | 2019-03-09 | 2019-05-15 | 85 | 105 | -
5 | 218 | Drain on Shanti Marg from RCC culvert, Mandawali Road to Budha Marg (Both Sides) | 500 | 2019-03-09 | 2019-03-09 | 2019-05-15 | 70 | 70 | -
6 | 218 | Drain from Budha Marg to Sadbhavna Chowk | 150 | - | 2019-05-01 | 43605 | 0 | 35 | -
7 | 218 | Drain from Harijan Basti Rly. Colony to Pump House, Mayfair Apptt. | 430 | - | 2018-10-01 | 2019-05-15 | 50 | 45 | -
8 | 218 | Drains from Sriram Chowk to Rly. Colony on both sides of Kalyan Marg | 1500 | 2019-03-09 | 2019-03-09 | 2019-05-15 | 95 | 290 | -
9 | 218 | Drain from Milenium Park to MC Pry School No.1 via Pandit Mohalla, Mandawali | 500 | 2019-03-09 | 2019-03-09 | 2019-05-15 | 65 | 50 | -
10 | 218 | Drain from Railway Colony to Bhim Gali along Sonia Vihar Subzi Mandi | 100 | - | 2018-10-01 | 2019-05-15 | 55 | 25 | -
11 | 219 | Drain from Pump House Bus Stand near H. No. A/185 to outfall | 305 | - | 2018-10-01 | 2019-05-15 | 55 | 35 | -
|  |  | 300 | - | 2018-10-01 | 2019-05-15 | 65 | 40 | -
12 | 219 | Pumphouse outfall nalla | 330 | - | 2018-10-01 | 2019-05-15 | 85 | 65 | -
13 | 219 | Drain in Mayur Vihar-II Pocket B from M.C. Pry School Pocket F to Sanjay Jheel. | 425 | 2019-03-09 | 2019-03-09 | 2019-05-15 | 70 | 50 | -
14 | 219 | Drain in Mayur Vihar Ph. II from E/560 to Pump House | 400 | - | 2018-10-01 | 2019-05-15 | 70 | 75 | -
15 | 219 | Drain from G-Block to Gurudwara East Vinod Nagar adjoning NH-9 | 350 | 2019-03-09 | 2019-03-09 | 2019-05-15 | 75 | 90 | -
16 | 220 | Drain from IFS App. To Fine Home App. | 800 | 2019-03-09 | 2019-03-09 | 2019-05-15 | 70 | 115 | -
17 | 220 | Drain from Sahyog App. to Anand Lok Appt. | 395 | - | 2018-10-01 | 2019-05-15 | 85 | 70 | -
18 | 220 | Drain from Ahalcon Intl. School to Police App. Mayur Vihar | 350 | - | 2018-10-01 | 2019-05-15 | 70 | 50 | -
19 | 220 | Drain from Partap Nagar to Aggarwal Sweets in Mayur Vihar Ph. - I | 510 | 2019-03-09 | 2019-03-09 | 2019-05-15 | 65 | 75 | -
20 | 220 | Drain in P-Block Pandav Nagar. | 330 | 2019-03-09 | 2019-03-09 | 2019-05-15 | 65 | 30 | -
21 | 220 | Acharya Niketan Nalla from Maternity Home to Church. | 500 | - | 2018-10-01 | 2019-05-15 | 65 | 45 | -
22 | 220 | Samaspur Vill. Nalla from E-54 to Police Aptt. | 500 | - | 2018-10-01 | 2019-05-15 | 70 | 50 | -
23 | 220 | Drain along Una Aptt. to Mavila apptt., Mayur Vihar -Ph-I | 260 | - | 2018-10-01 | - | 100 | 30 | -
24 | 221 | Lalita park Nalla | 450 | - | 2018-10-01 | 2019-05-15 | 80 | 56 | -
25 | 221 | Gali No. 12 drain Lalita Park, | 200 | - | 2018-10-01 | 2019-05-15 | 60 | 15 | -
26 | 221 | Ramesh Park Community Centre Nalla | 350 | - | 2018-10-01 | 2019-05-15 | 55 | 30 | -
27 | 221 | Bank Enclave drain opp. H. No. 1 | 300 | - | 2018-10-01 | - | 100 | 50 | -
28 | 221 | Ramesh Park Police Stn. Drain | 360 | - | 2018-10-01 | - | 100 | 85 | -
29 | 221 | MB road drain | 1200 | 2019-03-09 | 2019-03-09 | 2019-05-15 | 65 | 405 | -
30 | 222 | Bank Enclave drain | 200 | 2019-03-09 | 2019-03-09 | - | 100 | 30 | -
31 | 222 | Kundan Nagar Nalla (Right Side) | 200 | - | 2018-10-01 | 2019-05-15 | 85 | 30 | -
32 | 222 | PD Vihar drain | 400 | - | 2018-10-01 | 2019-05-15 | 80 | 50 | -
33 | 222 | Laxmi Nagar Market Nalla | 1900 | 2019-03-09 | 2019-03-09 | 2019-05-15 | 85 | 240 | -
34 | 223 | Shakarpur Market Nalla | 795 | 2019-03-09 | 2019-03-09 | 2019-05-15 | 80 | 120 | -
35 | 224 | Drain from Bhim Gali to Budha Marg | 1000 | 2019-03-09 | 2019-03-09 | 2019-05-15 | 70 | 70 | -
36 | 224 | Hanuman Mandir road Pandav Nagar nalla | 555 | 2019-03-09 | 2019-03-09 | 2019-05-15 | 80 | 90 | -
37 | 224 | D Park to 11/3 Pandav Nagar nalla | 340 | 2019-03-09 | 2019-03-09 | 2019-05-15 | 75 | 35 | -
38 | 224 | Drain from DDA Park to S 380 School Block Pandav Nagar | 650 | - | 2018-10-01 | 2019-05-15 | 70 | 70 | -
39 | 224 | C-68/4 to S-101 Pandav Nagar nalla | 125 | - | 2018-10-01 | 2019-05-15 | 75 | 15 | -
40 | 217 | NH-24 drain | 3100 | 2019-03-09 | 2019-03-09 | 2019-05-15 | 30 | - | NHAI has stopped the work
|  | Total | 19810 |  |  |  |  | 3076