## Abstract
Date : 19.06.2019
Abstract of Desilting of Drain of All Zones
East Zone
Sl. No. | Name of Division | Total No. of Roads | 0-25% Progress (No. of Roads) | 26-50% Progress (No. of Roads) | 51-75% Progress (No. of Roads) | 76-90% Progress (No. of Roads) | More than 90% (No. of Roads)
I | Shahadra Road | 65 | 4 | 6 | 23 | 22 | 10
% age |  | 44.775 | 0.5 | 2.25 | 14.375 | 18.15 | 9.5
Average %age overall |  | 68.8846
To,
The Superintending Engineer (C&ND)
PWD, GNCTD
New Delhi-110002
No. 23(Report)/SE/Shah. Circle/PWD/ |  |  |  | Date :
Executive Engineer (P) Shahdara Circle, PWD
Copy to:
1 | The Pr. Chief Engineer (East) M, PWD, GNCTD, New Delhi-110002
2 | EE, Shahdara Road Divn., PWD New Delhi w.r.t. Email dated 12.06.2019
Executive Engineer (P)

## 19.06.2019
Annexure-II
Report on Desilting of Drains for the week upto 19th June 2019
S.No | Name of Drains | Length of Drain (Km) | Date of issue of Desilting Tender | Date of Commencement of Desilting | Date of Completion of Desilting (Ist Cycle) | Progress of Work% | Length of drain cleaned % progress | Quantity of Silt removed | Inter Departmental problems faced (if any)
1 | Road No 56 | 4 | 2019-03-08 | 19.05.2019 | 22.06.2019 | 94% | 3.76 | 1100.64 MT | NIL
2 | Road No. 71 | 1.6 | 2019-03-08 | 19.05.2019 | 22.06.2019 | 90% | 1.44 |  | NIL
3 | Road No. 71 A | 0.6 | 2019-03-08 | 25.05.2019 | 22.06.2019 | 80% | 0.48 |  | NIL
4 | Road No. 56 A | 2 | 2019-03-08 | 30.05.2019 | 22.06.2019 | 75% | 1.5 |  | NIL
5 | G.T Road | 6.35 | 2019-02-22 | 30.05.2019 | 22.06.2019 | 90% |  | 2587.43 MT | EDMC Toilet 01 No.
a | Dharampura T point to Seelam Pur | 1.15 | 2019-02-22 | 17.05.2019 | 22.06.2019 | 90% | 1.035 |  | NIL
b | Seelampur to Shyam lal College | 0.95 | 2019-02-22 | 19.05.2019 | 22.06.2019 | 94% | 0.893 |  | NIL
c | Shyam lal College to Shahdara Metro station | 0.8 | 2019-02-22 | 19.05.2019 | 22.06.2019 | 96% | 0.768 |  | NIL
d | Shahdara Metro Station to Mansarover park | 1.65 | 2019-02-22 | 25.05.2019 | 22.06.2019 | 94% | 1.551 |  | NIL
e | Mansariver park to Chintamani Chowk | 1.15 | 2019-02-22 | 01.06.2019 | 22.06.2019 | 85% | 0.9775 |  | NIL
f | Chintamani Chowk to apsara border | 0.65 | 2019-02-22 | 10.06.2019 | 20.06.2019 | 65% | 0.4225 |  | NIL
6 | G.T Road Railway under bridge near Metro Station Shahdara | 0.176 | 2019-02-22 | 20.06.2019 | 25.06.2019 | 85% | 0.1496 |  | EDMC Toilet 01 No.
7 | G.T Road Railway under bridge near Railway Station Shahdara | 0.214 | 2019-02-22 | 20.06.2019 | 25.06.2019 | 90% | 0.1926 |  | NIL
8 | Gandhi Nagar Road | 3 | 2019-02-22 | 25.05.2019 | 20.06.2019 | 85% | 2.55 |  | NIL
9 | Road along A-Block Jhilmil Colony | 0.376 | 2019-02-28 | 30.05.2019 | 22.06.2019 | 89% | 0.33464 | 8135 MT
10 | Road along B-Block Jhilmil | 0.71 | 2019-02-28 | 03.06.2019 | 22.06.2019 | 89% | 0.6319
11 | E.S.I. Hospital Road | 0.9 | 2019-02-28 | 05.06.2019 | 22.06.2019 | 81% | 0.729
12 | Peripherial Road | 2.7 | 2019-02-28 | 09.06.2019 | 22.06.2019 | 80% | 2.16
13 | Sant Lal Gupta Marg | 1.23 | 2019-02-28 | 16.06.2019 | 20.06.2019 | 72% | 0.8856 |  | EDMC Toilet 01 No.
14 | Link Road (GT Road to Vivek Vihar ITI) | 0.3 | 2019-02-28 | 18.04.2019 | 22.06.2019 | 88% | 0.264 |  | EDMC Toilet 01 No.
15 | RUB 58-64 to Shivam Enclave | 0.82 | 2019-02-28 | 22.05.2019 | 22.06.2019 | 95% | 0.779
16 | Shaheed Bhagat Singh Marg | 2.8 | 2019-02-28 | 15.05.2019 | 22.06.2019 | 92% | 2.576 |  | EDMC Toilet 04 No.
17 | Shiva Khand Road | 1.8 | 2019-02-28 | 10.05.2019 | 22.06.2019 | 92% | 1.656 |  | EDMC Toilet 02 No.
18 | Road No 72 Extn. | 2 | 2019-02-22 | 09.06.2019 | 22.06.2019 | 82% | 1.64 | 150 MT | NIL
19 | Road No 72 | 1.82 | 2019-02-22 | 17.06.2019 | 21/06.2019 | 75% | 1.365 |  | EDMC Toilet 03 No.
20 | Zonal office Road. | 2.06 | 2019-02-22 | 26.05.2019 | 22.06.2019 | 88% | 1.8128 |  | EDMC Toilet 03 No.
21 | Surajmal Vihar Marg | 2.4 | 2019-06-11 | 12.06.2019 | 22.06.2019 | 82% | 1.968 |  | NIL
22 | Rishabh Vihar Road | 1.3 | 2019-06-11 | 13.06.2019 | 22.06.2019 | 70% | 0.91 |  | EDMC Toilet 02 No.
23 | Shrestha Vihar Road | 2.5 | 2019-06-11 | 13.06.2019 | 22.06.2019 | 60% | 1.5 |  | EDMC Toilet 02 No.
24 | Road from Booster pumping station DJB opp. B-Block to A- Block market | 1.2 | 2019-06-11 | 18.06.2019 | 21.06.2019 | 88% | 1.056
25 | Road No 58 | 5.68 | 2019-06-11 | 18.06.2019 | 23.06.2019 | 70% | 3.976 |  | EDMC Toilet 01 No.
26 | Road No 58 A | 3.2 | 2019-06-11 | 18.06.2019 | 25.06.2019 | 70% | 2.24 |  | EDMC Toilet 01 No.
27 | Road No. 57 (Jagatpuri Chowk to Telco-xing) | 1.5 | 2019-06-11 | 11.06.2019 | 2019-06-20 | 65% | 0.975 | 0 M.T | NIL
28 | Road No. 57 (Jagatpuri Chowk to Bihari Colony) | 2.1 | 2019-06-11 | 11.06.2019 | 22.06.2019 | 75% | 1.575 |  | NIL
29 | Road No. 75B (Karkari more to Road No. 58A) | 4 | 2019-06-11 | 11.06.2019 | 2019-06-20 | 55% | 2.2 |  | NIL
30 | Vishwas Nagar 60' Road | 2.34 | 2019-06-11 | 15.06.2019 | 2019-06-25 | 60% | 1.404 |  | NIL
31 | Shahdara Road from Drain No.1 to Dhalao Snatan Dharam School, Bhola Nath Nagar | 0.9 | 2019-06-11 | 12.06.2019 | 22.06.2019 | 60% | 0.54 |  | EDMC Toilet 01 No.
32 | Bhola Nath Nagar (Railway line to Baburam School | 0.6 | 2019-06-11 | 13.06.2019 | 22.06.2019 | 65% | 0.39 |  | NIL
33 | Shalimar park extension road (Shahdara road to H. N. 4/29830 | 0.4 | 2019-06-11 | 14.06.2019 | 22.06.2019 | 65% | 0.26 |  | NIL
34 | DCP Office Road ( DCP office to Shahdara road) | 0.2 | 2019-06-11 | 15.06.2019 | 22.06.2019 | 80% | 0.16 |  | NIL
35 | Divider Road from Seemapuri road to Road No. 64 (near SDN Hospital) | 4.8 | 2019-03-08 | 18.05.2019 | 25.06.2016 | 95% | 4.56 | 3875.14 .00 M.T | NIL
36 | Gurudwara Road from DTC bus depot Road No. 70 to GTB Hospital road | 3.5 | 2019-03-08 | 18.05.2019 | 25.06.2016 | 95% | 3.325 |  | EDMC Toilet 02 No.
37 | Road No. 62 (Road No. 70 to Apsara Border) | 2.4 | 2019-03-08 | 18.05.2019 | 25.06.2016 | 95% | 2.28 |  | NIL
38 | Road No. 70 (Seemapuri to Tahir Pur T-Point) | 2.4 | 2019-03-08 | 18.05.2019 | 22.06.2019 | 80% | 1.92 |  | NIL
39 | New Seemapuri Road from Road No. 64 (Mother Dairy) to Road No. 62 near maszid | 2.32 | 2019-03-08 | 27.05.2019 | 22.06.2019 | 75% | 1.74 |  | NIL
40 | Seemapuri Road from Road No. 62 to 64 | 2.13 | 2019-03-08 | 18.05.2019 | 22.06.2019 | 75% | 1.5975 |  | NIL
41 | Road from LIC Colony (T-Point to rotary at Telephone Exchange) | 1.87 | 2019-03-08 | 20.05.2019 | 22.06.2019 | 92% | 1.7204 |  | NIL
42 | Road from T-point, L-pocket to R Block small rotary | 1.72 | 2019-03-08 | 28.05.2019 | 22.06.2019 | 50% | 0.86 | - Do - | NIL
43 | GTB Hospital Road (From GT Road to Aggarwal Sweet Dilshad Garden) | 1.2 | 2019-03-08 | 08.06.2019 | 20.06.2019 | 75% | 0.9 |  | EDMC Toilet 01 No.
44 | R-Block Road (From Divider road Agarwal sweet to GT Road) | 1 | 2019-03-08 | 25.05.2019 | 22.06.2019 | 50% | 0.5 |  | NIL
45 | Road from GT Road to Road No. 64 via Telephone exchange | 0.83 | 2019-03-08 | 25.05.2019 | 22.06.2019 | 95% | 0.7885 |  | NIL
46 | Road infront of Hans Raj Public School (Divider Road to Gurudwara road) | 0.73 | 2019-03-08 | 25.05.2019 | 22.06.2019 | 15% | 0.1095 |  | NIL
47 | Road from Divider road to Gurudwara road near pummy sweet | 0.72 | 2019-03-08 | 01.06.2019 | 22.06.2019 | 20% | 0.144 |  | NIL
48 | Road from Divider Road (Mukherjee Public School to Sant Ram Public School at Gurudwara road) | 0.72 | 2019-03-08 | 10.06.2019 | 22.06.2019 | 15% | 0.108 |  | NIL
49 | LIC Road (from Malaria office MCD to GT Road) | 0.66 | 2019-03-08 | 10.06.2019 | 22.06.2019 | 90% | 0.594 |  | NIL
50 | Road No. 62 (J & K pocket) to petrol pump GT Road (infront of Red Crosss society). | 0.66 | 2019-03-08 | 25.05.2019 | 22.06.2019 | 60% | 0.396 |  | NIL
51 | Road from Gurudwara road (T-point of Kalander Colony) to Gauri Shankar Mandir | 0.62 | 2019-03-08 | 05.06.2019 | 22.06.2019 | 50% | 0.31 |  | NIL
52 | Road from General Hospital (Road No. 64 to Shahdara Flyover) | 0.52 | 2019-03-08 | 05.06.2019 | 22.06.2019 | 40% | 0.208 |  | NIL
53 | CNG Petrol Pump to deer park (Divider road) west side | 0.4 | 2019-03-08 | 05.06.2019 | 22.06.2019 | 10% | 0.04 |  | NIL
54 | CNG Petrol Pump to deer park (Divider road) east side | 0.39 | 2019-03-08 | 11.06.2019 | 22.06.2019 | 60% | 0.234 |  | NIL
55 | GTB Hospital road from Red light to Agarwal sweet (Divider road) | 0.39 | 2019-03-08 | 15.06.2019 | 20.06.2019 | 30% | 0.117 |  | NIL
56 | Road No. 64 (Swami Dayanand Hospital to DLF More (U.P. Border) | 6 | 2019-03-08 | 25.05.2019 | 22.06.2019 | 85% | 5.1 | 6497.25 M.T | NIL
57 | Road No. 68 (Road No. 69 to Railway Line Nand Nagri) | 2.8 | 2019-03-08 | 28.05.2019 | 22.06.2019 | 90% | 2.52 |  | EDMC Toilet 02 No.
58 | Tanga Stand Road from road no. 68 to Wazirabad Road. | 2.5 | 2019-03-08 | 20.05.2019 | 22.06.2019 | 95% | 2.375 |  | NIL
59 | Road No. 69 (Road No. 63 to Road No. 64 (T-point) | 2.4 | 2019-03-08 | 30.05.2019 | 22.06.2019 | 90% | 2.16 |  | NIL
60 | From Rajiv Gandhi super hospital speciality hospital to GTB hospital road | 1.9 | 2019-03-08 | 07.06.2019 | 22.06.2019 | 80% | 1.52 |  | NIL
61 | GTB Road (From Road No. 64 to Road No. 68) | 1.82 | 2019-03-08 | 05.06.2019 | 22.06.2019 | 65% | 1.183 |  | NIL
62 | From Road No. 69 MIG Flat to GTB Hospital Road Via Nutan Vidya Mandir public school | 1.8 | 2019-03-08 | 08.06.2019 | 22.06.2019 | 75% | 1.35 |  | EDMC Toilet 01 No.
63 | Captain Javed Ali Marg | 1.68 | 2019-03-08 | 11.06.2019 | 22.06.2019 | 50% | 0.84 |  | NIL
64 | From Road No. 68 (petrol pump) to E-pocket GTB enclave police booth near Nutan Vidya Mandir public school | 0.75 | 2019-03-08 | 15.06.2019 | 22.06.2019 | 65% | 0.4875 |  | NIL
65 | Road along khel parisor from NVM school to Green field public school. | 0.5 | 2019-03-08 | 15.06.2019 | 20.06.2019 | 65% | 0.325 |  | NIL
| Total | 122.256 |  |  |  |  | 90.0195
[6 empty] | %age | 73.632