## Status Desilting
East Delhi Municipal Corporation
Engineering Department
Status of Desilting of Drain / Nalla having Depth / Widht above 4 feet
Date 04.05.2020
Divisin | No. of Drains | Length of Drain (in Mtr) | Desilting Status |  |  | Aprox. Weight of silt to be desilted (in MT) | Silt removed from 01.10.19 to 21.04.2020 (In MT) | Silt removed from 22.04.2020 to 03.05.2020 (In MT) | Silt removed from 01.10.19 to 03.05.2020 (In MT) | Remark
|  |  | Number of Drain where Desilting Completed (in Nos) | Number of Drain where Desilting in Progress (in Nos) | Number of Drain where Desilting yet to be start (in Nos)
Shahdara South Zone
EE-M-I-SHS | 32 | 15383.4 | 0 | 1 | 31 | 3748 | 0 | 0 | 0
EE-M-II-SHS | 17 | 11025 | 0 | 8 | 9 | 3476.3449 | 43.09 | 0 | 43.09
EE-M-III-SHS | 21 | 14167 | 0 | 6 | 15 | 4771.593 | 0 | 0 | 0
EE-M-IV-SHS | 39 | 19810 | 0 | 22 | 17 | 4027.6953 | 340 | 1103.905 | 1443.905 | Silt / Floating Matrial through Super Sucker at SLF Ghazipur
Total | 109 | 60385.4 | 0 | 37 | 72 | 16023.6333 | 383.09 | 1103.905 | 1486.995
Shahdara North Zone
EE-M-I-SHN | 41 | 19929 | 0 | 5 | 36 | 8619 | 480.47 | 0 | 480.47
EE-M-II-SHN | 32 | 22300 | 0 | 2 | 30 | 10890.2622 | 0 | 0 | 0
EE-M-III-SHN | 24 | 10206 | 0 | 6 | 18 | 4537.5053 | 0 | 187.83 | 187.83
EE-M-IV-SHN | 17 | 10857 | 0 | 6 | 11 | 9589.3434 | 120.485 | 58.725 | 179.21
Total | 114 | 63292 | 0 | 19 | 95 | 33636.1109 | 600.955 | 246.555 | 847.51
Grand Total | 223 | 123677.4 | 0 | 56 | 167 | 49659.7442 | 984.045 | 1350.46 | 2334.505