## Status Desilting
East Delhi Municipal Corporation
Engineering Department
Status of Desilting of Drain / Nalla having Depth / Widht above 4 feet
Date 28.05.2020
Divisin | No. of Drains | Length of Drain (in Mtr) | Desilting Status |  |  | Aprox. Weight of silt to be desilted (in MT) | Silt removed from 01.10.19 to 21.05.2020 (In MT) | Silt removed from dt.22.05.20 to 27.05.2020 (In MT) | Silt removed from 01.10.19 to 27.05.2020 (In MT) | Progress in Percentage % | Remark
|  |  | Number of Drain where Desilting Completed (in Nos) | Number of Drain where Desilting in Progress (in Nos) | Number of Drain where Desilting yet to be start (in Nos)
Shahdara South Zone
EE-M-I-SHS | 32 | 15383.4 | 6 | 21 | 5 | 3748 | 1669.714 | 417.975 | 2087.689 | 55.7%
EE-M-II-SHS | 17 | 11025 | 4 | 13 | 0 | 3476.3449 | 1986.48 | 352.465 | 2338.945 | 67.28%
EE-M-III-SHS | 21 | 14167 | 6 | 16 | 0 | 4771.593 | 2629.543 | 517.68 | 3147.223 | 65.96%
EE-M-IV-SHS | 39 | 19810 | 16 | 23 | 0 | 4027.6953 | 3631.34 | 136.935 | 3768.275 | 93.56% | Silt / Floating Matrial through Super Sucker at SLF Ghazipur
Total | 109 | 60385.4 | 32 | 73 | 5 | 16023.6333 | 9917.077 | 1425.055 | 11342.132 | 70.78%
Shahdara North Zone
EE-M-I-SHN | 41 | 19929 | 17 | 24 | 0 | 8619 | 3970.494 | 1008.205 | 4978.699 | 57.76%
EE-M-II-SHN | 32 | 22300 | 10 | 22 | 0 | 10890.2622 | 2343.425 | 1604.369 | 3947.794 | 36.25%
EE-M-III-SHN | 24 | 10206 | 11 | 11 | 2 | 4537.5053 | 1942.895 | 374.05 | 2316.945 | 51.06%
EE-M-IV-SHN | 17 | 10857 | 3 | 14 | 0 | 9589.3434 | 2545.055 | 961.648 | 3506.703 | 36.57%
Total | 114 | 63292 | 41 | 71 | 2 | 33636.1109 | 10801.869 | 3948.272 | 14750.141 | 43.85%
Grand Total | 223 | 123677.4 | 73 | 144 | 7 | 49659.7442 | 20718.946 | 5373.327 | 26092.273 | 52.54%