## Abstract
East Delhi Municipal Corporation
ACTION PLAN FOR DESILTING OF DRAINS/ NALLAH HAVING DEPTH / WIDTH ABOVE 4 FEET FOR THE PERIOD 01.10.2020 TO 31.05.2021 under EDMC area.
S. No. | Zone | Division | No. of Drains | Length of Drain (in Mtr) | Aprox. Weight of silt to be desilted from 01.10.2020 TO 31.05.2021 (in MT)
1 | Shahdara South Zone | M-I | 28 | 15133 | 3620
2 |  | M-II | 17 | 11025 | 3579
3 |  | M-III | 21 | 14167 | 4210
4 |  | M-IV | 39 | 19810 | 4028
Total |  |  | 105 | 60135 | 15437
1 | Shahdara North Zone | M-I | 41 | 19929 | 8391
2 |  | M-II | 32 | 22300 | 9971
3 |  | M-III | 24 | 7836 | 2897
4 |  | M-IV | 17 | 10857 | 9390
Total |  |  | 114 | 60922 | 30649
Grand Total |  |  | 219 | 121057 | 46397

## Detail of Desilting
East Delhi Municipal Corporation
Engineering Department
ACTION PLAN FOR DESILTING OF DRAINS/ NALLAH FOR THE PERIOD 01.10.2020 TO 31.05.2021
S. No. | Ward No. | Name of Drain | R.D. |  | Section of drain (in mtrs) | [5 empty] | Aprox. Volume of silt to be desilted (in Cum) | Aprox. Weight of silt to be desilted (in MT) | Target of Silt to be removed from 01.10.20 to 31.12.20 (In MT) | Target of Silt to be removed from 01.01.21 to 31.03.21 (In MT) | Target of Silt to be removed from 01.04.21 to 31.05.21 (In MT)
[5 empty] | Length Mtr. (Av.) |  | Length of Drain (in Mtr) | Width of Drain (in Mtr) | Depth of drain (in Mtr) | Depth of Silt (in Mtr)
|  |  | From | To | Open (length in mtr.) | Covered (length in mtr.)
EE-M-I Shahdara South Zone
1 | 21 | Mahila Colony drain | Geeta Colony Nalla | Jheel Chowk | 0 | 400 | 400 | 0.9 | 1.3 | 0.2 | 72 | 83.52 | 9 | 17 | 58
2 | 21 | Geeta Colony, Katcha Drain | Budh Bazar | Raja Ram Kohli Marg | 600 | 0 | 600 | 2 | 1.5 | 0.16 | 192 | 222.72 | 27 | 56 | 140
3 | 21 | Krishna Nagar drain | Delhi Darbar | Mandir Marg. | 0 | 400 | 400 | 1.75 | 1.3 | 0.16 | 112 | 129.92 | 20 | 30 | 80
4 | 21 | Radhey puri drain H Block, . | Radhey Puri wali pulia | Drain No. 1 | 0 | 230 | 230 | 2 | 1.35 | 0.24 | 110.4 | 128.064 | 20 | 30 | 78
5 | 21 | Drain at Krishna nagar , Krishna Nagar | Vijay Chowk | Lajpat Rai Chowk Nalla | 0 | 320 | 320 | 1 | 1.4 | 0.24 | 76.8 | 89.088 | 15 | 25 | 49
6 | 21 | Sumpwell Krishna Nagar | Krishna Nagar Pump House | Krishna Nagar Pump House | 0 | 6.4 | 6.4 | 2.5 | 1 | 0.55 | 8.8 | 10.208 | 1 | 2 | 7
7 | 22 | Hari Singh Gurdwara | Jagat Puri Drain | Bala Sweets Ram Nagar | 0 | 570 | 570 | 0.6 | 1.5 | 0.2 | 68.4 | 79.344 | 10 | 20 | 49
8 | 22 | Jagat puri drain | Old Anarkali road | Disuse Canal | 0 | 1215 | 1215 | 2.23 | 3 | 0.12 | 325.134 | 377.1554 | 70 | 100 | 207
9 | 23 | Bhagat Singh Nalla | Satnam Park | Disuse Canal. | 0 | 1460 | 1460 | 1 | 2 | 0.12 | 175.2 | 203.232 | 30 | 50 | 123
10 | 24 | 6-12 Block Nalla (LHS) | Geeta Colony nalla | 13 Block Geeta Colony Chowk. | 0 | 400 | 400 | 0.75 | 1.35 | 0.2 | 60 | 69.6 | 9 | 17 | 44
11 | 24 | 6-12 Block Nalla (RHS) | Geeta Colony nalla | 13 Block Geeta Colony Chowk. | 0 | 400 | 400 | 0.75 | 1.35 | 0.2 | 60 | 69.6 | 9 | 17 | 44
12 | 24 | Geeta Colony drain | from Raja Ram kohli Marg | Shastri Nagar Culvert. (Upto SDM Pusta Drain) | 1300 | 0 | 1300 | 2.5 | 2.5 | 0.16 | 520 | 603.2 | 75 | 151 | 377
13 | 25 | Sump Well. (Shastri Park) | Shastri Park Pump House | Shastri Park Pump House | 0 | 2 | 2 | 5 x 5 | 0.6 | 0.15 | 8 | 9.28 | 1 | 2 | 6
14 | 25 | Kailash Nagar drain | Pumphouse | Gali No. 19 Ajeet Nagar | 0 | 760 | 760 | 1.2 | 2 | 0.16 | 145.92 | 169.2672 | 30 | 50 | 89
15 | 25 | Fish market drain | Pump house Kailas Nagar | Gali Masjid wali, Kailas Nagar | 0 | 150 | 150 | 1 | 1.5 | 0.25 | 37.5 | 43.5 | 8 | 14 | 22
16 | 25 | Sumpwell Kailash Nagar | Kailash Nagar Pump House | Kailash Nagar Pump House | 0 | 5 | 5 | 4 | 0.6 | 0.4 | 8 | 9.28 | 1 | 2 | 6
17 | 25 | Shastri Park drain | Slip road Shastri Park | GT Road Pump House | 0 | 600 | 600 | 1.3 | 1.8 | 0.24 | 187.2 | 217.152 | 27 | 54 | 136
18 | 26 | East Azad Nagar drain (opposite Brijraj sweet side to hanuman mandir ) | Hanuman Mandir Gali No. 4 East Azad Nagar | Road No. 57 | 0 | 520 | 520 | 1.5 | 0.75 | 0.1 | 78 | 90.48 | 9 | 18 | 63
19 | 26 | East Azad Nagar Drain Brij raj sweet side | Mulla wali pulia Gali NO. 11 West Azad Nagar | Road No. 57 | 0 | 795 | 795 | 1.5 | 1.8 | 0.1 | 119.25 | 138.33 | 21 | 42 | 75
20 | 26 | Shankar Nagar nalla | Mulla wali pulia | Drain No. 1 | 0 | 540 | 540 | 1.5 | 1.1 | 0.1 | 81 | 93.96 | 14 | 28 | 52
21 | 26 |  |  |  | 0 | 120 | 120 | 1.6 | 1.1 | 0.1 | 19.2 | 22.272 | 3 | 7 | 12
22 | 26 |  |  |  | 0 | 270 | 270 | 1.7 | 1.8 | 0.1 | 45.9 | 53.244 | 8 | 16 | 29
23 | 27 | Scooter market Drain | Rajgarh colony gali No.17 | Chand Mohalla Dhalao | 500 | _ | 500 | 1.5 | 0.65 | 0.1 | 75 | 87 | 15 | 25 | 47
24 | 27 | Ajeet Nagar drain | Gali No. 19 Ajeet Nagar | Drain No.1 | 0 | 700 | 700 | 1.25 | 2 | 0.15 | 131.25 | 152.25 | 20 | 41 | 91
25 | 27 | Raghubar pura drain LHS Lal | Gali No. 1 Shankar Nagar Extension | Lal Batti Chowk subhash mohalla | 0 | 1000 | 1000 | 0.9 | 1 | 0.15 | 135 | 156.6 | 23.49 | 46.98 | 86.13
26 | 27 | Raghubar pura drain RHS | Toll Ram Gaur Marg Raj Garh Colony Extn | Lal Batti Chowk subhash mohalla | 0 | 1000 | 1000 | 0.9 | 1 | 0.15 | 135 | 156.6 | 23.49 | 46.98 | 86.13
27 | 27 | Ramnagar drain | Budh Bazar culvert | Jain Chowk Ram Nagar | _ | 300 | 300 | 1.6 | 1 | 0.1 | 48 | 55.68 | 8 | 17 | 31
28 | 27 | Nalla along main road Seelampur (Both Side) | Gurduwara Road | E-82 near Community Center Seelampur | 570 | _ | 570 | 1.5 | 1.1 | 0.1 | 85.5 | 99.18 | 16 | 30 | 53
[7 empty] | 15133.4 |  |  |  |  | 3619.7266 | 522.98 | 954.96 | 2140.26
EE-M-II Shahdara South Zone
29 | 18E | Drain along Gharonda Apptt, | Vivek Apptt | Gharonda Apttt | - | 460 | 460 | 0.6 | 1.2 | 0.15 | 41.4 | 48.438 | 8 | 20 | 20
30 | 17E | Kasturba drain | Shivam Enclave | Gali No.1 Vishwas Nagar | - | 1200 | 1200 | 4.1 | 3.75 | 0.15 | 738 | 863.46 | 10 | 162 | 691
|  |  | Gali No.1 Vishwas Nagar | drain No.1 | - | 300 | 300 | 3 | 3.75 | 0.15 | 135 | 157.95 | 10 | 30 | 118
31 |  | Nakul Gali drain Vishwas Nagar | 60ft road | Kasturba Nagar drain | - | 483 | 483 | 0.9 | 1.5 | 0.15 | 65.205 | 76.2898 | 10 | 20 | 46
32 |  | Gali No.10, drain Vishwas Nagar | 60ft road | Kasturba Nagar drain | - | 220 | 220 | 0.75 | 1.5 | 0.2 | 33 | 38.61 | 10 | 15 | 14
33 |  | Gali No.3 drain Vishwas Nagar | 60ft road | Kasturba Nagar drain | - | 402 | 402 | 0.9 | 1.5 | 0.15 | 54.27 | 63.4959 | 6 | 30 | 27
34 |  | 18 Qtr. To New Vishwas Nagar drain | Pandav road | 60 ft road Vishwas Nagar | 180 | - | 180 | 0.6 | 1.5 | 0.15 | 16.2 | 18.954 | 5 | 5 | 9
|  |  | Pandav road | 60 ft road Vishwas Nagar | - | 213 | 213 | 0.9 | 1.5 | 0.15 | 28.755 | 33.6433 | 8 | 9 | 17
|  |  | 60ft road | Kasturba Nagar drain | 174 | - | 174 | 0.6 | 1.5 | 0.15 | 15.66 | 18.3222 | 5 | 4 | 9
|  |  | 60ft road | Kasturba Nagar drain | - | 200 | 200 | 0.75 | 1.5 | 0.15 | 22.5 | 26.325 | 7 | 6 | 13
35 | 19E | Gazipur Village drain | Ambedkar Park | NH 24 | 800 | - | 800 | 0.75 | 1.8 | 0.2 | 120 | 140.4 | 5 | 35 | 100
36 | 20E | Arya Nagar drain | Arya Nagar Village | drain No.1 | 625 | - | 625 | 3.6 | 1.8 | 0.15 | 337.5 | 394.875 | 10 | 90 | 295
37 | 31E | Pandav Road Nallah | Swarn Cinema | LIC road | 450 | - | 450 | 0.65 | 1.2 | 0.15 | 43.875 | 51.3337 | 5 | 15 | 31
38 |  | Satgarh Nallah | Drain NO.1 | Gali No.15 Bhola Nath Nagar | 400 | - | 400 | 0.75 | 0.1 | 0.2 | 60 | 70.2 | 5 | 20 | 45
39 |  | Tikona Park Nallah | Pandav road | Jwala Nagar chowk | - | 225 | 225 | 1 | 1.4 | 0.2 | 45 | 52.65 | 10 | 10 | 33
40 |  | Bhola Nath Nagar Nallah | drain No.1 | JE Store | - | 1100 | 1100 | 1 | 1.5 | 0.25 | 275 | 321.75 | 10 | 40 | 272
41 | 30E | Nalla along Railway line | Rub Vivek Vihar Ph-II | Shahdara Rly Station | 1000 | - | 1000 | 1.2 | 1.35 | 0.3 | 360 | 421.2 | 5 | 100 | 316
42 |  | Swami Amardev Nalla | Indra Park | Kasturba Nagar Chowk | - | 425 | 425 | 1.2 | 1.5 | 0.15 | 76.5 | 89.505 | 5 | 30 | 55
43 | 29E | Vishwkarma Nagar Nalla | H.No.1 P. Khand | Udiya Mandir | 900 | - | 900 | 1.5 | 2.1 | 0.2 | 270 | 315.9 | 5 | 100 | 211
44 |  | Janta Flat Nalla | RUB Vivek Vihar | drain No.2 | 852 | - | 852 | 1.95 | 1.8 | 0.15 | 249.21 | 291.5757 | 9 | 100 | 183
45 |  | Majid Road Nalla | round about R-Block | GT Road | 416 | - | 416 | 1.15 | 1.5 | 0.15 | 71.76 | 83.9592 | 10 | 14 | 60
[7 empty] | 11025 |  |  |  |  | 3578.8369 | 158 | 855 | 2565
EE-M-III Shahdara South Zone
46 | 001E | Nalla from Block No. 19 to 25 Central Road Trilokpuri. | Block No. 19 | Block No. 25 central road | 300 | 650 | 950 | 0.75 | 1.25 | 0.15 | 106.875 | 125.0437 | 12.5044 | 31.2609 | 81.2784
47 | 001E | Drain from Mayur Vihar Pkt-II to Gurudward Chowk. | Mayur Vihar Pkt-II | Gurudward Chowk. |  | 600 | 600 | 0.85 | 1.4 | 0.15 | 76.5 | 89.505 | 8.9505 | 22.3762 | 58.1782
48 | 001E | Nalla from Block No. 14 to 13 Central Road Trilokpuri. | Block No. 14 | 13 Central Road Trilokpuri. |  | 300 | 300 | 0.75 | 1.25 | 0.15 | 33.75 | 39.4875 | 3.9487 | 9.8719 | 25.6669
49 | 002E | Sanjay drain in Trilok Puri | Kotla road | Gazipur road | 950 |  | 950 | 5 | 1.65 | 0.2 | 950 | 1111.5 | 111.15 | 277.875 | 722.475
50 | 002E | Block No. 9 to 12 (L.H.S), Trilok Puri | Block No. 9 | 12 (L.H.S), Trilok Puri |  | 700 | 700 | 0.9 | 1.25 | 0.15 | 94.5 | 110.565 | 11.0565 | 27.6412 | 71.8672
51 | 002E | Block No. 9 to 12 (R.H.S), Trilok Puri | Block No. 9 | 12 (R.H.S), Trilok Puri |  | 700 | 700 | 0.9 | 1.25 | 0.15 | 94.5 | 110.565 | 11.0565 | 27.6412 | 71.8672
52 | 002E | Block No. 15 to 18 (Internal Road). | Block No. 15 | 18 (Internal Road). |  | 550 | 550 | 0.8 | 1.3 | 0.15 | 66 | 77.22 | 7.722 | 19.305 | 50.193
53 | 003E | Nalla from Block No. 26 to 30 Central Rd. | Block No. 26 | 30 Central Rd. |  | 880 | 880 | 0.75 | 1.25 | 0.15 | 99 | 115.83 | 11.583 | 28.9575 | 75.2895
54 | 003E | Nalla from Block No. 26 to 30 Main Rd. | Block No. 26 | 30 Main Rd. |  | 980 | 980 | 0.75 | 1.25 | 0.15 | 110.25 | 128.9925 | 12.8992 | 32.2481 | 83.8451
55 | 003E | Nalla from Block No. 31 to 36 Central Rd. | Block No. 31 | 36 Central Rd. |  | 1000 | 1000 | 0.75 | 1.25 | 0.15 | 112.5 | 131.625 | 13.1625 | 32.9062 | 85.5563
56 | 003E | DSIDC Market to Chilla drain along Pkt-III, Mayur Vihar Phase-I. | DSIDC Market | Chilla drain along Pkt-III, Mayur Vihar Phase-I. | 495 | 205 | 700 | 1.2 | 1.5 | 0.15 | 126 | 147.42 | 14.742 | 36.855 | 95.823
57 | 003E | Nalla from Chilla Village to Chilla regulator | Nalla from Chilla Village | Chilla regulator | 500 | 300 | 800 | 1 | 2.3 | 0.15 | 120 | 140.4 | 14.04 | 35.1 | 91.26
58 | 004E | Nalla from Vashundara Enclave to New Ashok Nagar Metro Station | Nalla from Vashundara Enclave | New Ashok Nagar Metro Station |  | 1400 | 1400 | 2.1 | 3 | 0.3 | 882 | 1031.94 | 103.194 | 257.985 | 670.761
59 | 005E | Drain between D Block Gazipur Dairy Farm & SLF Gazipur | Drain between D Block Gazipur Dairy Farm | SLF Gazipur | 252 |  | 252 | 1 | 1.6 | 0.2 | 50.4 | 58.968 | 5.8968 | 14.742 | 38.3292
60 | 005E | Gazipur Out fall Nalla | B-65 Gazipur Dairy Farm | E-9 Gazipur Dairy Farm | 400 |  | 400 | 2.9 | 1.6 | 0.2 | 232 | 271.44 | 27.144 | 67.86 | 176.436
61 | 005E | Outfall nalla from New Ashok Nagar to P.S. Toll Tax Noida | Outfall nalla from New Ashok Nagar | P.S. Toll Tax Noida |  | 500 | 500 | 0.75 | 1.25 | 0.2 | 75 | 87.75 | 8.775 | 21.9375 | 57.0375
62 | 005E | Drain between C & D Block Gazipur Dairy Farm | D-1 Gazipur Dairy Farm | D-25Gazipur Dairy Farm | 225 |  | 225 | 1.3 | 1.75 | 0.2 | 58.5 | 68.445 | 6.8445 | 17.1112 | 44.4892
63 | 008E | Drain of road from Block No. 19 to 21 Kalyan Puri L/R | Block No. 19 | Block No. 21 Kalyan Puri L/R |  | 1100 | 1100 | 1 | 2.3 | 0.15 | 165 | 193.05 | 19.305 | 48.2625 | 125.4825
64 | 008E | Drain of road from Block No. 11 to 13 Kalyan Puri L/R | Block No. 11 | Block No. 13 Kalyan Puri L/R |  | 960 | 960 | 0.75 | 1.25 | 0.15 | 108 | 126.36 | 12.636 | 31.59 | 82.134
65 | 008E | Khichri Pur Nalla Block No. 9 to 10 | Block No.3 | Block No. 10 | 150 |  | 150 | 0.75 | 1.25 | 0.2 | 22.5 | 26.325 | 2.6325 | 6 | 17.1113
66 | 007E | F-Block, H. No. 130 to Sulabh Sauchalay, Kondli {Drain in Unauthorised colony] | H. No. 130 | Sulabh Sauchalay, Kondli |  |  | 70 | 1 | 1.4 | 0.2 | 14 | 18 | 3 | 5 | 10
[7 empty] | 14167 |  |  |  |  | 4210.4317 | 422.2432 | 1052.5267 | 2735.0806
EE-M-IV Shahdara South Zone
67 | 10-E | Drain from Sriram chowk to Aggarwal Sweets, C-Block West Vinod Nagar | Sriram chowk | Aggarwal Sweets, C-Block West Vinod Nagar |  | 480 | 480 | 0.9 | 1.2 | 0.2 | 86.4 | 95.04 | 19.008 | 38.016 | 38.016
68 | 10-E | Drain from Sriram chowk to Jewellary Shop, D-Block West Vinod Nagar | Sriram chowk | Jewellary Shop, D-Block West Vinod Nagar | 290 |  | 290 | 0.75 | 1.2 | 0.2 | 43.5 | 47.85 | 9.57 | 19.14 | 19.14
69 | 10-E | Drain on Shanti marg from Budha Marg to Narwana Road (Both Sides) | Budha Marg | Narwana Road (Both Sides) |  | 700 | 700 | 0.9 | 1.2 | 0.15 | 94.5 | 103.95 | 20.79 | 41.58 | 41.58
70 | 10-E | Drain from Sadbhawna Chowk to Taxi Stand on Sadbhawana Road | Sadbhawna Chowk | Taxi Stand on Sadbhawana Road |  | 420 | 420 | 1.3 | 1.5 | 0.2 | 109.2 | 120.12 | 24.024 | 48.048 | 48.048
71 | 09-E | Drain on Shanti Marg from RCC culvert, Mandawali Road to Budha Marg (Both Sides) | RCC culvert, Mandawali Road | Budha Marg (Both Sides) |  | 500 | 500 | 0.9 | 1.2 | 0.2 | 90 | 99 | 19.8 | 39.6 | 39.6
72 | 09-E | Drain from Budha Marg to Sadbhavna Chowk | Budha Marg | Sadbhavna Chowk |  | 150 | 150 | 1 | 1.2 | 0.3 | 45 | 49.5 | 9.9 | 19.8 | 19.8
73 | 09-E | Drain from Harijan Basti Rly. Colony to Pump House, Mayfair Apptt. | Harijan Basti Rly. Colony | Pump House, Mayfair Apptt. |  | 430 | 430 | 1 | 1.5 | 0.2 | 86 | 94.6 | 18.92 | 37.84 | 37.84
74 | 09-E | Drains from Sriram Chowk to Rly. Colony on both sides of Kalyan Marg | Sriram Chowk | Rly. Colony |  | 1500 | 1500 | 0.9 | 1.2 | 0.2 | 270 | 297 | 59.4 | 118.8 | 118.8
75 | 09-E | Drain from Milenium Park to MC Pry School No.1 via Pandit Mohalla, Mandawali | Milenium Park | MC Pry School No 1 |  | 500 | 500 | 0.9 | 1.2 | 0.2 | 90 | 99 | 19.8 | 39.6 | 39.6
76 | 09-E | Drain from Railway Colony to Bhim Gali along Sonia Vihar Subzi Mandi | Railway Colony | Bhim Gali |  | 100 | 100 | 0.9 | 1.2 | 0.3 | 27 | 29.7 | 5.94 | 11.88 | 11.88
77 | 11-E | Drain from Pump House Bus Stand near H. No. A/185 to outfall | Bus Stand | outfall | 305 |  | 305 | 0.9 | 1.2 | 0.2 | 54.9 | 60.39 | 12.078 | 24.156 | 24.156
|  |  | Near A/185 | Bus Stand |  | 300 | 300 | 0.9 | 1.2 | 0.2 | 54 | 59.4 | 11.88 | 23.76 | 23.76
78 | 11-E | Pumphouse outfall nalla | Pocket-C | outfall |  | 330 | 330 | 1 | 1.2 | 0.2 | 66 | 72.6 | 14.52 | 29.04 | 29.04
79 |  | Drain in Mayur Vihar-II Pocket B from M.C. Pry School Pocket F to Sanjay Jheel. | M.C. Pry School pkt- F | Sanjay Jheel. |  | 425 | 425 | 1 | 1.25 | 0.2 | 85 | 93.5 | 18.7 | 37.4 | 37.4
80 | 11-E | Drain in Mayur Vihar Ph. II from E/560 to Pump House | E/560 | Pump House, Sanjay Jheel | 400 |  | 400 | 1.2 | 1.3 | 0.2 | 96 | 105.6 | 21.12 | 42.24 | 42.24
81 |  | Drain from G-Block to Gurudwara East Vinod Nagar adjoning NH-9 | G-Bloc | Gurudwara East Vinod Nagar adjoning NH-9 | 350 |  | 350 | 1.2 | 1.3 | 0.3 | 126 | 138.6 | 27.72 | 55.44 | 55.44
82 | 12-E | Drain from IFS App. To Fine Home App. | IFS App | Fine Home App. |  | 800 | 800 | 0.9 | 1.3 | 0.2 | 144 | 158.4 | 31.68 | 63.36 | 63.36
83 | 12-E | Drain from Sahyog App. to Anand Lok Appt. | Sahyog App | Anand Lok Appt. |  | 395 | 395 | 0.9 | 1.3 | 0.15 | 53.325 | 58.6575 | 11.7315 | 23.463 | 23.463
84 | 12-E | Drain from Ahalcon Intl. School to Police App. Mayur Vihar | Ahalcon Intl. School | Police App. |  | 350 | 350 | 0.9 | 1.2 | 0.15 | 47.25 | 51.975 | 10.395 | 20.79 | 20.79
85 | 12-E | Drain from Partap Nagar to Aggarwal Sweets in Mayur Vihar Ph. - I | Partap Nagar | Aggarwal Sweets |  | 510 | 510 | 1 | 1.2 | 0.2 | 102 | 112.2 | 22.44 | 44.88 | 44.88
86 | 12-E | Drain in P-Block Pandav Nagar. | Kabristhan | Alhcon Public School |  | 330 | 330 | 0.6 | 1.2 | 0.2 | 39.6 | 43.56 | 8.712 | 17.424 | 17.424
87 | 12-E | Acharya Niketan Nalla from Maternity Home to Church. | Maternity Home | Church, Acharya Niketan | 500 |  | 500 | 0.6 | 1.2 | 0.2 | 60 | 66 | 13.2 | 26.4 | 26.4
88 | 12-E | Samaspur Vill. Nalla from E-54 to Police Aptt. | E-54 | Police Aptt. |  | 500 | 500 | 0.65 | 1.2 | 0.2 | 65 | 71.5 | 14.3 | 28.6 | 28.6
89 | 12-E | Drain along Una Aptt. to Mavila apptt., Mayur Vihar -Ph-I | Akash Darshan | Mavila apptt., Mayur Vihar -Ph-I |  | 260 | 260 | 0.6 | 1.2 | 0.2 | 31.2 | 34.32 | 6.864 | 13.728 | 13.728
90 | 13-E | Lalita park Nalla | Lalita Park Gurudwara | M.B. Road drain |  | 450 | 450 | 0.9 | 1.3 | 0.15 | 60.75 | 66.825 | 13.365 | 26.73 | 26.73
91 | 13-E | Gali No. 12 drain Lalita Park, | Main road J&K Block | M.B. Road drain |  | 200 | 200 | 0.7 | 1.2 | 0.2 | 28 | 30.8 | 6.16 | 12.32 | 12.32
92 | 13-E | Ramesh Park Community Centre Nalla | Gali No. 06, Ramesh Park | M.B. Road drain |  | 350 | 350 | 0.7 | 1.3 | 0.15 | 36.75 | 40.425 | 8.085 | 16.17 | 16.17
93 | 13-E | Bank Enclave drain opp. H. No. 1 | Krishan Kunj Road | Disuse Canal |  | 300 | 300 | 1 | 1.2 | 0.15 | 45 | 49.5 | 9.9 | 19.8 | 19.8
94 | 13-E | Ramesh Park Police Stn. Drain | Gali No. 10, Ramesh Park | M.B. Road drain |  | 360 | 360 | 1 | 1.35 | 0.2 | 72 | 79.2 | 15.84 | 31.68 | 31.68
95 | 13-E | MB road drain | Lalita park opp. Masjid | Sump well behind SDM Office |  | 1200 | 1200 | 3 | 3 | 0.15 | 540 | 594 | 118.8 | 237.6 | 237.6
96 | 14-E | Bank Enclave drain | Main road Kishan Kunj | upto Opp., H.No. 09 |  | 200 | 200 | 0.7 | 1.25 | 0.2 | 28 | 30.8 | 6.16 | 12.32 | 12.32
97 | 14-E | Kundan Nagar Nalla (Right Side) | Main road Bank Enclave | Disuse Canal |  | 200 | 200 | 0.75 | 1.2 | 0.2 | 30 | 33 | 6.6 | 13.2 | 13.2
98 | 14-E | PD Vihar drain | Kishan Kunj road | Disuse Canal |  | 400 | 400 | 0.7 | 1.2 | 0.2 | 56 | 61.6 | 12.32 | 24.64 | 24.64
99 | 14-E | Laxmi Nagar Market Nalla | Vijay Chowk | Disuse Canal |  | 1900 | 1900 | 0.85 | 1.2 | 0.15 | 242.25 | 266.475 | 53.295 | 106.59 | 106.59
100 | 15-E | Shakarpur Market Nalla | New Patparganj road | Vikas Marg |  | 795 | 795 | 0.8 | 1.2 | 0.2 | 127.2 | 139.92 | 27.984 | 55.968 | 55.968
101 | 15-E | Drain from DDA Park to S 380 School Block Pandav Nagar | DDA Park | S 380 School Block Pandav Nagar |  | 650 | 650 | 0.9 | 1.2 | 0.2 | 117 | 128.7 | 25.74 | 51.48 | 51.48
102 | 16-E | Drain from Bhim Gali to Budha Marg | Bhim Gali | Budha Marg |  | 1000 | 1000 | 0.9 | 1.2 | 0.2 | 180 | 198 | 39.6 | 79.2 | 79.2
103 | 16-E | Hanuman Mandir road Pandav Nagar nalla | Ganesh Chowk | Shahdara drain |  | 555 | 555 | 0.9 | 1.2 | 0.2 | 99.9 | 109.89 | 21.978 | 43.956 | 43.956
104 | 16-E | D Park to 11/3 Pandav Nagar nalla | D Park | 11/3 Pandav Nagar |  | 340 | 340 | 0.8 | 1.2 | 0.2 | 54.4 | 59.84 | 11.968 | 23.936 | 23.936
105 | 16-E | C-68/4 to S-101 Pandav Nagar nalla | C-68/4 | S-101 Pandav Nagar nalla |  | 125 | 125 | 0.9 | 1.2 | 0.2 | 22.5 | 24.75 | 4.95 | 9.9 | 9.9
[7 empty] | 19810 |  |  |  |  | 4027.6953 | 808 | 1610 | 1610
EE-M-I Shahdara North Zone
106 | 28 E | Nalla in Old Seemapuri G block to Pump house | Nalla in Old Seemapuri G block | Pump house | 400 | 961 | 1361 | 1.2 | 2 | 0.25 | 408 | 477 | 47.7 | 159 | 270.3
107 | 35 E | Desilting of nalla from SSBL drain Jalli Kheda Vill. To SDN Hopt. Road in W.No. 241 | Nalla from SSBL drain Jalli Kheda Village | SDN Hopt. Road | - | 135 | 135 | 2.4 | 3 | 0.25 | 81 | 95 | 9.5 | 31.6667 | 53.8333
108 | 35 E | SSBL drain from 100Ft. road no.68 to G.T.Road flyover Rd 1081 to 1481 mtr | G.T.Road flyover Rd 1081 | to 1481 mtr | 400 | - | 400 | 6.5 | 1.8 | 0.3 | 780 | 913 | 91.3 | 304.3333 | 517.3667
109 | 35 E | SSBL drain from 100Ft. road no.68 to G.T.Road flyover Rd 1481 to 1946 mtr | G.T.Road flyover Rd 1481 | 1946 mtr | 510 | - | 510 | 6.5 | 1.8 | 0.25 | 829 | 970 | 97 | 323.3333 | 549.6667
110 | 35 E | SSBL drain from 100Ft. road no.68 to G.T.Road flyover Rd 1946 to 2362 mtr. | G.T.Road flyover Rd 1946 | 2362 mtr. | 397 | - | 397 | 5.2 | 1.9 | 0.3 | 619 | 724 | 72.4 | 241.3333 | 410.2667
111 | 35 E | SSBL drain from 100Ft. road no.68 to G.T.Road flyover Rd 2362 to 2702 mtr. | G.T.Road flyover Rd 2362 mtr. | 2702 mtr. | 314 | - | 314 | 5.1 | 2 | 0.25 | 400 | 468 | 46.8 | 156 | 265.2
112 | 35 E | Nallah along DDA park from MCD sotre to Q-Pkt. Drain in Dilshad Garden | MCD sotre | Q-Pkt. Drain in Dilshad Garden | - | 310 | 310 | 1 | 1.6 | 0.25 | 78 | 91 | 9.1 | 30.3333 | 51.5667
113 | 35 E | Nallah from Tahirpur Sarai to R-Pkt. Dilshad Garden | Tahirpur Sarai | R-Pkt. Dilshad Garden | - | 150 | 150 | 1 | 1.5 | 0.3 | 45 | 53 | 5.3 | 17.6667 | 30.0333
114 | 35 E | Nallah from Gali No-8 Jagatpuri extn. Unauthorized colony | Gali No-8 Jagatpuri extn. Unauthorized colony |  | 90 | - | 90 | 0.75 | 1 | 0.25 | 17 | 20 | 2 | 6.6667 | 11.3333
115 | 35 E | Nallah along DDA park from P-15/A-4 to MCD Store Dilshad Garden | P-15/A-4 | MCD Store Dilshad Garden | 110 | 220 | 330 | 1 | 1.5 | 0.2 | 66 | 77 | 7.7 | 25.6667 | 43.6333
116 | 34 E | Nalla in new seemapuri from E-blk to Machli Market | E-Block Machli Market | Idgha Seemapuri | 220 | - | 220 | 1 | 1.5 | 0.2 | 44 | 51 | 5.1 | 17 | 28.9
117 | 34 E | Nalla in Tahirpur village from Shiv mandir to Kali mandir | Shiv mandir | Kali mandir | 100 | 140 | 240 | 1.25 | 1.4 | 0.1 | 30 | 35 | 3.5 | 11.6667 | 19.8333
118 | 34 E | Nalla in E-Block Jhuggi Nalla New Seemapuri | Park | PWD Pump house | 100 |  | 100 | 0.7 | 1.7 | 0.15 | 11 | 13 | 1.3 | 4.3333 | 7.3667
119 | 34 E | Nalla in New seemapuri from Bhopal Pulia to Dhobi Ghat | Bhopal Pulia | Dhobi Ghat | 110 |  | 110 | 0.8 | 1.5 | 0.2 | 18 | 21 | 2.1 | 7 | 11.9
120 | 32 E | SSBL drain from Wazirabad Road to Ashok Nagar railway phatak (Hanuman Pulia) | Wazirabad Road | Ashok Nagar railway phatak (Hanuman Pulia) | 540 |  | 540 | 6.75 | 1.55 | 0.3 | 1094 | 1280 | 128 | 426.6667 | 725.3333
121 | 32 E | Internal nallas in D- block Nand Nagari from D-1/275 to D-1/231 to Upto D-3/355 | D-1/275 to D-1/231 | Upto D-3/355 | 890 | - | 190 | 0.6 | 1.3 | 0.25 | 29 | 34 | 3.4 | 11.3333 | 19.2667
122 | 32 E | Nalla both side E block pump house nalla in Nand Nagari from E-4/160 to pump house including sump well | E-4/160 | Pump house including sump well | 780 | - | 780 | 0.85 | 1.5 | 0.25 | 166 | 194 | 19.4 | 64.6667 | 109.9333
123 | 32 E | Both side Nalla of Akhara park E -4 Block Nand Nagari | E -4 Block Nand Nagari | Akhara park | 700 | - | 700 | 0.8 | 1.6 | 0.25 | 140 | 164 | 16.4 | 54.6667 | 92.9333
124 | 32 E | Internal nallas in A-1/30 in A block Nand Nagari from A-2/30 to A-2 Block Nand Nagri | A-1/30 | A-2/3 Block Nand Nagri | 405 | 120 | 525 | 0.6 | 1.3 | 0.25 | 79 | 92 | 9.2 | 30.6667 | 52.1333
125 | 32 E | Internal nallas in A-1/481 and Ujala Pulia to road No 68 towards cement godown both side | A-1/481 and Ujala Pulia | Road No 68 towards cement godown both side | 360 | 840 | 1200 | 0.9 | 1.45 | 0.25 | 270 | 316 | 31.6 | 105.3333 | 179.0667
126 | 32 E | Nallah from Sr. Sec. School Raja Ravin Verma corner to B-5 Block Market Nand Nagri | Sr. Sec. School Raja Ravin Cerma corner | B-5 Block Market Nand Nagri |  | 375 | 375 | 0.9 | 1.45 | 0.2 | 68 | 80 | 8 | 26.6667 | 45.3333
127 | 32 E | Nallah from B-5 Block Market Corner to road no-68 | B-5 Block Market Corner | Road no-68 | 150 | - | 150 | 0.9 | 1.45 | 0.2 | 27 | 32 | 3.2 | 10.6667 | 18.1333
128 | 32 E | Nallah H.no-30 E-1 Nand Nagri to H.no-231 E-Block Nand Nagri | H.no-30 E-1 Nand Nagri | H.no-231 E-Block Nand Nagri | - | 115 | 115 | 1.3 | 1.4 | 0.2 | 30 | 35 | 3.5 | 11.6667 | 19.8333
129 | 32 E | Nallah from H.no-481 E-2 Nand Nagri to H.no-280 E-2 Block Nand nagri | H.no-481 E-2 Nand Nagri | H.no-280 E-2 Block Nand nagri | - | 115 | 115 | 1.3 | 1.4 | 0.2 | 30 | 35 | 3.5 | 11.6667 | 19.8333
130 | 33 E | Nalla along Murga Mkt. in G & H block Sunder Nagari from mandir to Upto pumphouse including sump well | Mandir | Upto pumphouse including sump well | Partly opened | Partly covered | 589 | 0.75 | 1.3 | 0.25 | 110 | 129 | 12.9 | 43 | 73.1
131 | 33 E | Nalla in L Block Sunder Nagari from police chowki to L-55 Sunder Nagari | Police chowki | L-55 Sunder Nagri | 478 | - | 478 | 0.95 | 1.5 | 0.25 | 114 | 133 | 13.3 | 44.3333 | 75.3667
132 | 33 E | nalla in sunder nagari from M.C. Primary school to Sani bazar mandi along F2 sunder nagari | M.C. Primary school | Sani bazar mandi along F2 sunder nagari | - | 254 | 254 | 0.65 | 1.2 | 0.15 | 25 | 29 | 2.9 | 9.6667 | 16.4333
133 | 52 E | Desilting of nallah in Bhagirathi Vihar from Brijpuri culvert to Drain No.1 in | Brijpuri culvert | Drain No.1 | 1410 | - | 1410 | 1.04 | 1.5 | 0.15 | 220 | 257 | 25.7 | 85.6667 | 145.6333
134 | 52 E | Desilting of nallah in Ambedkar Colony from main road Johripur to Drain no.1 in . | Main road Johripur | Drain no.1 | 278 | - | 278 | 0.7 | 1.15 | 0.25 | 49 | 57 | 5.7 | 19 | 32.3
135 | 52 E | Desilting of nallah from main road Johari Pur along Johari pur Ext. to block, main road (both side) to Drain no.1 in | Main road Johari Pur along Johari pur Ext. to block, main road (both side) | Drain no.1 | 560 | - | 560 | 0.45 | 1.3 | 0.25 | 63 | 74 | 7.4 | 24.6667 | 41.9333
136 | 53 E | Desilting of nallah along C-block, main road to Ganga Vihar | C-block, main road | Ganga Vihar | 540 | - | 540 | 0.6 | 2 | 0.25 | 81 | 95 | 9.5 | 31.6667 | 53.8333
137 | 53 E | internal nallah A,B,C & D block to pump house to school block, Ambey Cycle to post office and Kaushik Garment to M.C. Pry. School B-block in Gokulpuri | Internal nallah A,B,C & D block to pump house | School block, Ambey Cycle to post office and Kaushik Garment to M.C. Pry. School B-block in Gokulpuri W.No.262 Shah.North Zone. | 380 | - | 380 | 0.55 | 1.1 | 0.25 | 52 | 61 | 6.1 | 20.3333 | 34.5667
138 | 53 E | nallah from Amar Colony to Loni road flyover | Amar Colony | Loni road flyover | 285 | - | 285 | 0.95 | 1.5 | 0.25 | 68 | 80 | 8 | 26.6667 | 45.3333
139 | 53 E | nallah C-block, jhuggi area along main road up to Pump house i.e sump well in Gokulpuri | Ganesh Medical store | Pump house | 508 | - | 508 | 0.65 | 1.3 | 0.2 | 66 | 77 | 7.7 | 25.6667 | 43.6333
140 | 53 E | nallah along main road Ganga Vihar from dhalao to drain no.1 along A,B,D & F block in Ganga Vihar | Dhalao | drain no.1 along A,B,D & F block in Ganga Vihar | 600 | - | 600 | 0.6 | 1 | 0.2 | 72 | 84 | 8.4 | 28 | 47.6
141 | 53 E | nallah from main road Ganga Vihar to Gokulpur Village W.No.262 Shah.North Zone. | main road Ganga Vihar | Gokulpur Village | 340 | - | 340 | 0.6 | 1 | 0.2 | 41 | 48 | 4.8 | 16 | 27.2
142 | 54 E | Nalla from Shamshan Ghat to Saboli goan bada kuan (Rathore Cement Store) | Shamshan Ghat | Saboli goan bada kuan (Rathore Cement Store) upto phanne khan more | 1000 | - | 1000 | 0.6 | 1.2 | 0.25 | 150 | 176 | 17.6 | 58.6667 | 99.7333
143 | 54 E | Nalla along railway line from Saboli Phatak | Saboli Phatak | Wazirabad Road | 620 | - | 620 | 1.2 | 1.3 | 0.25 | 186 | 218 | 21.8 | 72.6667 | 123.5333
144 | 55 E | Nalla on both side along Gali No 9 Bank Colony Harsh Vihar dividing road from Jail B/wall to Budh Vihar Chowk | Jail B/wall | Budh Vihar Chowk | 400 | - | 400 | 0.65 | 1.1 | 0.2 | 52 | 61 | 6.1 | 20.3333 | 34.5667
145 | 55 E | Nalla from P.W.D P/house Harsh Vihar to Jail Boundary wall | P.W.D P/house Harsh Vihar | Jail Boundary wall | - | 1370 | 1370 | 0.9 | 2.1 | 0.2 | 247 | 289 | 28.9 | 96.3333 | 163.7667
146 | 55 E | Nalla on both side along bank colony Road from Wazirabad road to Kishan Lal Chowk | Wazirabad road | Kishan Lal Chowk | 960 | - | 960 | 0.75 | 1.2 | 0.3 | 216 | 253 | 25.3 | 84.3333 | 143.3667
[7 empty] | 19929 |  |  |  |  | 8391 | 839.1 | 2797 | 4754.9
EE-M-II Shahdara North Zone
147 | 44-E | Gokalpur drain | Wazirabad road(GOKALPUR DRAIN) | Culvert near lal Mandir | 2000 | - | 2000 | 4.2 | 4.57 | 0.24 | 2016 | 2358.72 | 200 | 250 | 1908.72
148 | 44-E | Drain Gamri road to Gokalpur drain | Gamri road | Gokalpur drain | 100 | - | 100 | 0.7 | 1.35 | 0.34 | 23.8 | 27.846 | 10 | 5 | 13
149 | 47-E | Gokalpur drain from Ivth pusta to Culvert near M.C. Pry. School | Ivth pusta (GOKALPUR DRAIN) | Culvert near MC Pry. School | 1984 | - | 1984 | 4.57 | 4.57 | 0.24 | 2176.0512 | 2545.9799 | 400 | 450 | 1695.9799
150 | 47-E | DrainGali No. 12 X-Block Brahmpuri to Gokalpur drain | Gali No. 12 X-Block Brahmpuri | Goaklpur drain | - | 400 | 400 | 0.9 | 1.2 | 0.34 | 122.4 | 143.208 | 20 | 28.208 | 95
151 | 47-E | Drain from Gokalpur drain to Khaddey wali Masjid | Gokalpur drain | khaddey wali masjid | - | 1000 | 1000 | 0.6 | 1.05 | 0.34 | 204 | 238.68 | 20 | 13.68 | 205
152 | 47-E | Drain from Gautam Vihar chowk to Gokalpur drain | Gautam Vihar chowk | Gokalpur drain | - | 400 | 400 | 0.6 | 1.05 | 0.36 | 86.4 | 101.088 | 10 | 11.088 | 80
153 | 46-E | Drain from Gamri road to Gali No. 1 Khaddey wali masjid (RHS) | Gamri road to | Gali No.1 Khadey wali masjic (RHS) | - | 900 | 900 | 0.6 | 1.05 | 0.2 | 108 | 126.36 | 10 | 31.36 | 85
154 | 46-E | Drain from Gamri road to Gali no. 1Brahmpuri (LHS) | Gamri road to | Gali No.1Brahmpuri (LHS) | - | 600 | 600 | 0.6 | 1.05 | 0.2 | 72 | 84.24 | 12 | 7.24 | 65
155 | 45-E | Drain from Main market Bhajanpura gali no. 14 to Wazirabad road RHS | Main Mkt. Bhajanpura gali no. 14 | Wazirabad road RHS | - | 400 | 400 | 0.6 | 1.2 | 0.15 | 36 | 42.12 | 5 | 7.12 | 30
156 | 45-E | Drain from B-1 Block Yamuna Vihar to B-3 Block Yamuna Vihar | B-1 Yamuna Vihar | B-3 yamuna Vihar RHS | - | 660 | 660 | 1 | 2 | 0.15 | 99 | 115.83 | 10 | 25.83 | 80
157 | 45-E | Drain from B-4 Block Dividing road to S.S. School Yamuna Vihar | B-4 Dividing road | S.S. School Yamuna vihar | - | 650 | 650 | 1 | 1.8 | 0.15 | 97.5 | 114.075 | 15 | 24.075 | 75
158 | 45-E | Drain from Sachdeva Marriage home to Bhajanpura pump house | Sachdeva Marriage home | Bhajanpura Pump house | - | 380 | 380 | 0.9 | 2.15 | 0.15 | 51.3 | 60.021 | 10 | 10.021 | 40
159 | 45-E | Drain from dividing road to C-10 Nursery Yamuna Vihar | Dividing road | C-10 Nursery Yamuna Vihar | - | 535 | 535 | 0.6 | 1.1 | 0.15 | 48.15 | 56.3355 | 10 | 6.3355 | 40
160 | 45-E | Drain from Bhagat Singh Pump house to C-12, Yamuna Vihar Shiv Shakti mandir | Bhagat Singh Pump house | C-12 Yamuna Vihar shiv Shakti mandir | - | 692 | 692 | 0.9 | 2.5 | 0.15 | 93.42 | 109.3014 | 15 | 14.3014 | 80
161 | 56-E | Drain from Patel road from Patel chowk to Harizan Basti gali no. 1 Pucca road in ward no. 265 | Patel road from Patel chowk | Harizan Basti gali no. 1 Pucca road in ward no. 265 | - | 400 | 400 | 0.63 | 1.3 | 0.3 | 75.6 | 88.452 | 10 | 18.452 | 60
162 | 56-E | Drain Karawal Nagar road from Shiv Vihar Tiraha | Karawal Nagar road from Shiv Vihar Tiraha | Karawal Nagar RHS in ward no. 265 | 1000 | - | 1000 | 0.9 | 1.5 | 0.3 | 270 | 315.9 | 40 | 25.9 | 250
163 | 56-E | Drain Shiv Vihar Tiraha | Shiv Vihar Tiraha from Karawal nagar | Flood drain in ward no. 265 | 175 | - | 175 | 0.9 | 2 | 0.3 | 47.25 | 55.2825 | 5 | 10.2825 | 40
164 | 57-E | Drain 33' road from Karawal Nagar | 33' road from Karawal Nagar road | Hanuman Chowk LHS | 690 | - | 690 | 0.75 | 1.5 | 0.3 | 155.25 | 181.6425 | 10 | 21.6425 | 150
165 | 57-E | Drain Industrial area Nalla from Karawal Nagar road | Industrial area Nall from Karawal Nagar road | Upto Mukhiya market one side | 250 | - | 250 | 0.6 | 1.2 | 0.3 | 45 | 52.65 | 5 | 7.65 | 40
166 | 57-E | Drain Brijpuri road from gali no.1 to shiv Vihar Tiraha | Brijpuri road from gali no.1 | Shiv Vihar Tiraha Baboo Nagar LHS | - | 450 | 450 | 0.9 | 2 | 0.3 | 121.5 | 142.155 | 15 | 17.155 | 110
167 | 57-E | Drain Karawal Nagar road from Shiv Vihar Tiraha to Mukhiya market | Karawal Nagar road from Shiv Vihar Tiraha | Mukhiya market one side LHS | 1350 | - | 1350 | 0.9 | 1.5 | 0.3 | 364.5 | 426.465 | 12 | 94.465 | 320
168 | 57-E | Drain from Karawal Nagar road from Dayalpur 33' feet road | Karawal Nagar road from Dayalpur 33' feet road | Karawal Nagar upto firni road RHS | 1100 | - | 1100 | 0.6 | 1.5 | 0.3 | 198 | 231.66 | 40 | 11.66 | 180
169 | 59-E | Drain Karawal Nagar road from Chand bagh culvert to Sherpur Chowk | Karawal Nagar road from Chand bagh culvert | Sherpur chowk RHS in ward no. 267 | - | 800 | 800 | 1.5 | 1.5 | 0.3 | 360 | 421.2 | 20 | 40 | 361
170 | 59-E | Drain 25' road from Sanjay chowk road to Fauzi market | 25' road from Sanjay chowk road | Fauzi market in ward no. 267 | 750 | - | 750 | 0.9 | 1.25 | 0.3 | 202.5 | 236.925 | 20 | 11.925 | 205
171 | 59-E | Drain Karawal Nagar road from Sherpur chowk up to 33 feet road | Karawal Nagar road from Sherpur chowk | Upto 33 feet road | - | 590 | 590 | 1.5 | 1.5 | 0.3 | 265.5 | 310.635 | 24 | 76.635 | 210
172 | 59-E | Drain from 33' road from 25' road chowk to Gali No. 1 Nehru Vihar | 33' road from 25' road chowk | Gali No. 1 Nehru Vihar | 800 | - | 800 | 0.7 | 1.2 | 0.3 | 168 | 196.56 | 10 | 40 | 147
173 | 59-E | Drain from Gali No. 6 from 25' road to Escape drain in ward no. 267 | Gali No. 6 from 25' road | Escape drain in ward no. 267 | - | 300 | 300 | 1.2 | 1.5 | 0.25 | 90 | 105.3 | 10 | 30 | 65.3
174 | 59-E | Drain Gali No. 8 from 25' road to Escape drain | Gali No. 8 from 25' road | Escape drain in ward no. 267 | - | 300 | 300 | 1.2 | 1.5 | 0.25 | 90 | 105.3 | 20 | 15 | 70.3
175 | 58-E | Drain Brijpuri road from escape drain | Brijpuri road from escape drain | Escape drain in ward no. 268 | 600 | - | 600 | 1.2 | 1.5 | 0.34 | 244.8 | 286.416 | 24 | 20.416 | 242
176 | 58-E | Drain Brijpuri road from escape drain to Gali no. 1 Mustafabad | Brijpuri road from escape drain | Gali No. 1 Mustafabad in ward no. 268 | 814 | - | 814 | 1.2 | 1.6 | 0.34 | 332.112 | 388.571 | 35 | 3.571 | 350
177 | 58-E | Drain 33' road from Brijpuri road to 25' Chowk | 33' road from Brijpuri road | 25' chowk LHS ward no. 268 | 615 | - | 615 | 0.6 | 1.25 | 0.34 | 125.46 | 146.7882 | 10 | 16.7882 | 120
178 | 58-E | Drain 33' road from Brijpuri road to 25' chowk | 33' road from Brijpuri road | 25' chowk RHS in ward no. 268 | 615 | - | 615 | 0.6 | 1.25 | 0.36 | 132.84 | 155.4228 | 15 | 20.4228 | 120
[7 empty] | 22300 |  |  |  |  | 9971.1298 | 1072 | 1366.2239 | 7533.2999
EE-M-III Shahdara North Zone
179 | 36E | Hardevparl nalla from Hardevpuri to LIG Flats. | Hardevpuri | LIG Flats. | 740 | - | 740 | 0.9 | 1.5 | 0.1 | 66.6 | 78.588 | 13.32 | 38 | 27.268
180 | 37E | SSBL drian from Natthu Colony Railway Crossimg to Hanuman Phatak | Natthu Colony Railway Crossimg | Hanuman Phatak | 577 | - | 577 | 6 | 1.8 | 0.35 | 1211.7 | 1429.806 | 242.34 | 363.51 | 823.956
181 | 37E | Nalla along East nathu Colony in C-37E | Nathu Colony railway line | Gali no. 15 Nathu Colony | 400 | 0 | 400 | 0.6 | 1.5 | 0.15 | 36 | 42.48 | 7.2 | 10.8 | 24.48
182 | 38E | 52 cusec drain from Mandoli Rd. to loni Rd. | Mandoli Rd. | loni Rd. | 30 | - | 30 | 4.2 | 3.6 | 0.4 | 50.4 | 59.472 | 10.08 | 15.12 | 34.272
183 | 38E | Covered drain from Loni road to Mother Dairy kabool Nagar | Loni road | Mother Dairy kabool Nagar | - | 270 | 270 | 0.6 | 1.2 | 0.1 | 16.2 | 19.116 | 3.24 | 4.86 | 11.016
184 | 38E | Covered drain from 1/143 Sri Ram nagar to Shri Ram Nagar pump house internal nalla | 1/143 Sri Ram nagar | Shri Ram Nagar pump house internal nalla | - | 400 | 400 | 1.2 | 1.8 | 0.1 | 48 | 56.64 | 9.6 | 14.4 | 32.64
185 | 38E | Moti Ram road nalla from loni road pump house to mandoli road dhalao | loni road pump house | mandoli road dhalao | - | 190 | 190 | 1.3 | 1.8 | 0.12 | 29.64 | 34.9752 | 5.928 | 8.892 | 20.1552
186 | 39E | Chintamani pond drain from the point near power station to the jali behind Zonal Office | The point near power station | the jali behind Zonal Office | 460 | - | 460 | 1.9 | 2.1 | 0.15 | 131.1 | 154.698 | 26.22 | 39.33 | 89.148
187 | 39E | Mochi Mkt. drain from Ravi Dass Mandir to Kabristan Culvert | Ravi Dass Mandir | Drain No.1 | - | 310 | 310 | 1.5 | 1.6 | 0.15 | 69.75 | 82.305 | 13.95 | 20.925 | 47.43
188 | 39E | Naveen Shahdara Nalla at G.T Road to pump house naveen Shahdara | G.T Road | pump house naveen Shahdara | - | 700 | 700 | 1.2 | 0.6 | 0.1 | 84 | 99.12 | 16.8 | 25.2 | 57.12
189 | 39E | Khajoor wala nalla ( Covered drain) Naveen Shah. From gali No.2 West Rohtash Nagar to Naveen Shadara drain. | gali No.2 West Rohtash Nagar | Naveen Shadara drain. | - | 675 | 675 | 0.75 | 1.5 | 0.15 | 75.9375 | 89.6062 | 15.1875 | 22.7812 | 51.6375
190 | 39E | Punchsheel Garden nalla along sarovar marg to the jail opp. Muskan Restaurent on 65 No. road | H.No.1/11670 Naveen Shahdara | the jail opp. Muskan Restaurent on 65' road | 130 | - | 130 | 1 | 1.43 | 0.15 | 19.5 | 23.01 | 2 | 2 | 19.01
191 | 39E | Kabootar market drain from Mochi mkt. Drain (near kabristan) to masjid | Mochi mkt. Drain (near kabristan) | Police booth. | 155 | - | 155 | 0.8 | 1.15 | 0.2 | 24.8 | 29.264 | 5 | 8 | 16.264
192 | 48E | Nalla from C-12, Pump House to Priya Panchvati Yamuna Vihar C-11/8. | C-12, Pump House | Priya Panchvati Yamuna Vihar C-11/8. | - | 490 | 490 | 0.65 | 1.8 | 0.15 | 58 | 68.44 | 12 | 17 | 39.44
193 | 48E | Nalla from Mohanpuri school to gali no.16 vijay park main road | Mohanpuri school | gali no.16 vijay park main road | 335 | - | 335 | 0.6 | 1.2 | 0.15 | 30.15 | 35.577 | 7 | 10 | 18.577
194 | 48E | Nalla from Shivaji road to Gamri pump house, North Ghonda | Shivaji road | Gamri pump house | 380 | - | 380 | 1 | 1.8 | 0.15 | 105 | 123.9 | 21 | 31.5 | 71.4
195 | 48E | Nalla from gali no. 16 Vijay park to Road No. 66. | gali no. 16, Vijay park | Road no. 66 | 344 | - | 344 | 0.76 | 2.44 | 0.15 | 39.216 | 46.2749 | 8 | 11 | 27.2749
196 | 49E | Kardam Marg nalla from Ambedakar Chowk to Drain No. 1, Kardam Puri. | Ambedakar Chowk | Drain No. 1, Kardampuri | 340 | - | 340 | 0.6 | 1.2 | 0.2 | 40.8 | 48.144 | 6 | 9 | 33.144
197 | 50E | 52 cusec drain from Loni Road to Babarpur Road | Loni road | Babarpur culvert | 100 | - | 100 | 6 | 3.6 | 0.3 | 180 | 212.4 | 36 | 54 | 122.4
198 | 51E | 52 cusec drain from drain No.1 to Babarpur Road | Babarpur culvert | Drain No. 1 | 40 | - | 40 | 6 | 4.5 | 0.3 | 72 | 84.96 | 14.4 | 16.992 | 53.568
199 | 51E | Drain from M.I office, New Zafrabad to 52 Cusec drain. | M.I office, New Zafrabad . | 52 Cusec drain | 285 | - | 285 | 0.7 | 1.2 | 0.12 | 23.94 | 28.2492 | 5 | 8 | 15.2492
200 | 51E | Drain from Gulati Tent House , New Zafrabad to 52 Cusec drain. | Gulati Tent House , New Zafrabad | 52 Cusec drain. | 180 | - | 180 | 0.5 | 1.2 | 0.15 | 13.5 | 15.93 | 3 | 5 | 7.93
201 | 51E | Drain opp. BSES office DDA colony New Zafrabad to 52 Cusec drain. | opp. BSES office DDA colony New Zafrabad | 52 Cusec drain. | 180 | - | 180 | 0.7 | 1.1 | 0.15 | 18.9 | 22.302 | 2 | 4 | 16.302
202 | 51E | Drain from 52 cusec to pt. near H.No. B-64, Sudama Puri Ext. | 52 cusec | pt. near H.No. B-64, Sudama Puri Ext. | 125 | - | 125 | 0.55 | 1.2 | 0.15 | 10.3125 | 12.1687 | 3 | 4 | 5.1687
[7 empty] | 7836 |  |  |  |  | 2897.4263 | 488.2655 | 744.3102 | 1664.8505
EE-M-IV Shahdara North Zone
203 | 41E | Gokal Pur drain | Brahmpuri Culvert | Jafrabad culvert | 280 | 0 | 280 | 8.5 | 4 | 0.55 | 1309 | 1531.53 | 100 | 100 | 1331.53
204 | 42E | CPJ & K Block Nalla | E-16 B/72 | G.T Road Nalla | 58 | 522 | 580 | 1.2 | 1.3 | 0.5 | 348 | 407.16 | 120 | 180 | 107.16
205 | 42E | J.J Cluster Nalla | H.No E-13A510 | Gokal pur drain | 0 | 550 | 550 | 0.85 | 1.25 | 0.45 | 210.375 | 246.1387 | 50 | 100 | 96.1387
206 | 42E | Fruit Market Nalla | Main road seelampur | Chauhan bangar culvert both side | 0 | 320 | 320 | 0.85 | 1.2 | 0.45 | 122.4 | 143.208 | 40 | 50 | 53.208
207 | 43E | Gokulpur drain | R- Block, Braham Puri Culvert | S- block, Brahampuri Culvert | 750 | 0 | 750 | 4.1 | 2.5 | 0.75 | 2306.25 | 2698.3125 | 600 | 800 | 1298.3125
208 | 43E | Moni Baba Nalla | Gali No. 1 Brahampuri | Gali No. 12 Brahmpuri | 109 | 435 | 544 | 0.75 | 1.5 | 0.45 | 183.6 | 214.812 | 0 | 61 | 153.812
209 | 40E | Rajender Parsad Marg drain | Gokalpur drain | near chand Masjid Gali No. 6 Jafrabad | 0 | 175 | 175 | 0.75 | 1.5 | 0.5 | 65.625 | 76.7812 | 15.4 | 46.02 | 15.3612
210 | 40E | Vijay Park Nalla | Red Light Vijay Park | Gali No. 16 Adarsh Mohalla | 0 | 290 | 290 | 0.8 | 1.2 | 0.45 | 104.4 | 122.148 | 0 | 62 | 60.148
211 | 40E | Gokal Pur drain (325+108=433) | Jafrabad culvert | Road No. 66 at zero point | 433 | 0 | 433 | 4.15 | 4 | 0.6 | 1078.17 | 1261.4589 | 250 | 200 | 811.4589
212 | 63E | Karawal Nagar road Nalla | Wazirabad road | Chand Bag both side | 120 | 420 | 540 | 1.2 | 1.3 | 0.35 | 226.8 | 265.356 | 30 | 70 | 165.356
213 | 63E | Karawal Nagar road Nalla | Chand Bag Culvert | Sherpur Chowk L.H.S | 175 | 500 | 675 | 1.4 | 1.5 | 0.35 | 330.75 | 386.9775 | 80 | 80 | 226.9775
214 | 62 | Karawal Nagar road Nalla | Sherpur Chowk | Gali No. 6 Sadatpur Extn. LHS | 1000 | 550 | 1550 | 1.2 | 1.3 | 0.4 | 744 | 870.48 | 80 | 80 | 710.48
215 | 62 | C Block Nalla | Tukhmirpur pur road | C Block Dayalpur | 470 | 0 | 470 | 0.6 | 1.3 | 0.65 | 183.3 | 214.461 | 30 | 40 | 144.461
216 | 61E | Pusta road Nalla | 28 ft road | Mariginal Bandh both side | 1200 | 0 | 1200 | 0.5 | 1.25 | 0.3 | 180 | 210.6 | 60 | 100 | 50.6
217 | 61E | Karawal Nagar road Nalla | Sadatpur gali No 6 | Mukhia market Chowk L.H.S. | 900 | 0 | 900 | 0.8 | 1.25 | 0.4 | 288 | 336.96 | 40 | 80 | 216.96
218 | 60E | Mariginal Bandh Ist pusta Nalla | Mariginal Bandh | Sabhapur Village Ist pusta both side | 1100 | 0 | 1100 | 0.75 | 1.3 | 0.3 | 247.5 | 289.575 | 30 | 80 | 179.575
219 | 60E | Mariginal Bandh IInd pusta Nalla | Mariginal Bandh | Sabhapur Village IInd pusta and near dispanceray one side | 500 | 0 | 500 | 0.65 | 1.2 | 0.3 | 97.5 | 114.075 | 10 | 74.07 | 30
[7 empty] | 10857 |  |  |  |  | 9390.0339 | 1535.4 | 2203.09 | 5651.5389